## Guidelines
This file contains three specific planning tools to complete the supplementary information required when submitting a proposal for Readiness Programme support (including for NAP/adaptation planning):
- Budget plan and accompany Budget notes - Procurement plan - Implementation plan
The following considerations are important when completing the budget:
1. Before preparing the Readiness and budget, procurement, and implementation plans, please read the full guidance contained in the Readiness Programme Guidebook, specifically Part III Section 5
2. You can select the appropriate budget categories from the dropdown list in the budget plan:
3. To insert additional rows, right click on the row number below where you wish to insert the new row and choose INSERT.
4. Additional budget categories may be added by manually typing them on the Budget Category sheet. :
5. The Budget Notes sheet should be used to record explanations, further details or cost breakdowns for individual lines
Project Management Cost:
Project management costs (PMC) are the direct administrative costs incurred to execute a project. They should cover only incremental costs incurred due to the GCF contribution. In most cases, these costs are directly related to the support of a dedicated project management unit which manages the day to day execution related activities of the project.
General Principles for PMC costs:
1. The percentage of PMC financed by GCF should not be more than the percentage share of the overall budget financed by GCF
2. PMC budget thresholds: Up to 7.5 per cent of total activity budget.
> PMC exceeding 7.5 per cent for the readiness (including NAPs) proposals, and PPF proposals, up to $ 3 million will require detailed documentation
and justification supporting the entire PMC budget.
> The PMC should be shown as a separate component in the project budget. A detailed breakdown of PMC should be provided by budget category.
> Indicative list of eligible project management costs:
> Project staffing and consultants: Project manager, Project Assistant, Procurement personnel, Finance personnel & Support/admin. Personnel
> Other direct costs: Office equipment, Mission related travel cost of the PMU, Project management systems and information technology,
Office supplies, Audit cost
Contingency :
1. Select the appropriate % of Contingency Budget from the dropdown list :
2. Contingency budget for unforeseen costs arising during the project implementation should not be included in the outcome budget separately.
3. Contingency budget must be used for any unforeseen programme (output level) cost that is unrelated to implementation/service fee.
4. Any use of contingency must be reported to and agreed by the GCF Secretariat in writing in advance provided with justifications that are acceptable to the GCF
5. If by the end of the grant implementation period, you have not spent Contingency, you may not increase the scope of the project or make any other expenditures using the Contingency.
If you are unsure about how to complete the budget template, please send your query to: countries@gcfund.org
Readiness Grant Budget Preparation Guidelines

## Budget Category
Budget Categories
Audio Visual & Printing
Audit Fee
Consultant - Individual - International
Consultant - Individual - Local
Professional Services – Companies/Firm
IT Equipment
Office Supplies
Travel - International
Travel – Local
Workshop/Training
Indicate additional budget categories
Choose percentage
0
1%
2%
3%
4%
5%

## 5.1 Budget Plan
5.1 Budget Plan
Please add rows for Outcomes, Outputs and Cost Categories as required. Additional budget categories may be added by manually typing them on the Budget Category sheet.
Outcomes / Outputs |  | Detailed Budget (in US$) | [5 empty] | Total Budget (per outcome) | Expenditure Plan | [5 empty] | Budget notes
|  | Budget Categories choose from the drop-down list | Unit | # of Unit | Unit Cost | Total Budget (per budget category) | Total Budget (per sub-outcome) |  | 6m | 12m | 18m | 24m | 30m | 36m
Example: Outcome 1.1 Country NDAs or focal points and the network/ systems that enable them to fulfil their roles, responsibilities and policy requirements are operational and effective | Example: Output 1.1.1 NDA operational manual developed and validated | Consultant - Individual - International | W/Day | 30 | 500 | 15000 | 53000 | 53000 | [6 empty] | A
|  | Consultant - Individual - Local | W/Day | 20 | 300 | 6000
|  | IT Equipment | Laptop | 3 | 1500 | 4500
|  | Consultant - Individual - International | W/Day | 30 | 600 | 18000
|  | Travel – Local | Trip | 15 | 300 | 4500
|  | Travel - International | Trip | 10 | 500 | 5000
| 1.1.2 Output |  |  |  |  | 0 | 0
0
| 1.1.3 Output |  |  |  |  | 0 | 0
0
Outcome 2.2 | 2.2.1 Output |  |  |  |  | 0 | 0 | 0
0
| 2.2.1 Output |  |  |  |  | 0 | 0
0
Outcome 4.1 | 4.1.1 Output |  |  |  |  | 0 | 0 | 0
0
| 4.1.2 Output |  |  |  |  | 0 | 0
0
Total Outcome Budget | [7 empty] | 53000 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1
Project Management Cost (PMC) Up to 7.5% of Total Activity Budget |  | Consultant - Individual - Local | Month | 5 | 300 | 1500 | Actual amount and % of PMC requested: | Maximum PMC that can be requested:
|  | Audit Fee | Lumpsum | 5 | 500 | 2475
[6 empty] | 0 | do not change the formula | do not change the formula
[6 empty] | 0 | 3975 | 3975
[6 empty] | 0 | 7.5% | 7.5%
FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Breakdown (per budget category) |  | Total (per budget category)
Audio Visual & Printing |  | 0
Audit Fee |  | 2475 |  |  |  | FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Consultant - Individual - International |  | 33000
Consultant - Individual - Local |  | 7500 |  |  |  | Total Outcome Budget | [6 empty] | 53000
Professional Services – Companies/Firm |  | 0 |  |  |  | Project Management Cost (PMC) |  | 7.5% | requested |  |  |  | 3975
IT Equipment |  | 4500 |  |  |  | Contingency | 1% |  | requested |  |  |  | 530
Office Supplies |  | 0
Travel - International |  | 5000
Travel – Local |  | 4500 |  |  |  | Sub-Total (Total Outcome Budget + Contingency + PMC) | [6 empty] | 57505
Workshop/Training |  | 0
0 |  | 0 |  |  |  | Delivery Partner Fee (DP) - Up to 8.5% of the Sub-Total | [6 empty] | 4887.925
0 |  | 0
0 |  | 0
0 |  | 0 |  |  |  | Total Project Budget (Total Activity Budget + Contingency + PMC + DP) | [5 empty] | 62393
0 |  | 0
Total Outcome Budget + PMC |  | 56975
0

## Budget Notes
Budget Note | Detailed Description
A | Example - One national consultant (climate change sepcialist) for 30 working days @ $500 per day for activity 1.1.1, 1.1.2

## 5.2 Procurement Plan
5.2 Procurement Plan
For goods, services, and consultancies to be procured, please list the items, descriptions in relation to the activities in Section 3, estimated cost, procurement method, relevant threshold, and the estimated dates. Please include the procurement plan for at least the first tranche of disbursement requested below and provide a full procurement plan for the entire duration of the implementation period if available at this stage.
Item | Item Description | Estimated Cost (US$) | Procurement Method | Thresholds (Min-Max monetary value for which indicated procurement method must be used) | Estimated Start Date | Projected Contracting Date
Goods and Non-Consulting Services
Example - Office Equipment | #of laptop, # of printer | 5000 | e.g. Open tender | $5,000 - $10,000
e.g. Shopping
e.g. Direct Procurement
Sub-Total (US$) |  | 5000
Consultancy Services
Example - International Consultant | Climate Change Specialist | 40000 | Open tender | $20,000 - $50,000
Example - Local Consultant | Project Coordinator | 25000 | Open tender | $20,000 - $50,001
Sub-Total (US$) |  | 65000

## 5.3 Implementation Plan
5.3 Implementation Plan
Please list all the deliverables (e.g. D.1.1.1a) per activity (e.g. A1.1.1) with the identifierand mark the planned duration as show in the example. Please also indicate milestones for any deliverables to be completed during the implementation period of the activity in question.
Make sure the identifier number of each activity and deliverable matches with the proposal as this table does not require its name or description. Please refrain from adding descriptions.
For more guidance on how to fill out this tables, please see Part III Section 5 of the Readiness Guidebook
|  |  | Planned duration | [6 empty] | Milestone (deliverable) | [7 empty] | Target completion date
Activities & Deliverables |  | Estimated Timeline
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Reporting
EXAMPLE | bar: Estimated Timeline M6 to Estimated Timeline M12
A1.1.1 | D1.1.1
A1.1.2 | D1.1.2a
D1.1.2b
D1.1.2c
A1.1.3 | D1.1.3
A1.1.4 | D1.1.4
A1.1.5 | D1.1.5
A1.1.6 | D1.1.6
A1.1.7 | D1.1.7a
D1.1.7b
D1.1.7c
D1.3.1
A1.3.2 | D1.3.2a
D1.3.2b
A1.3.3 | D1.3.3a
D1.3.3b
A1.3.4 | D1.3.4
A1.3.5 | D1.3.5
A2.1.1 | D2.1.1
A2.1.2 | D2.1.2
A2.1.3 | D2.1.3a
D2.1.3b
A2.2.1 | D2.2.1
A2.4.1 | D2.4.1a
D2.4.1b
A4.1.1 | D4.1.1
A4.1.2 | D4.1.2