# aLogical Framework specific for the project

| Expected Result | Indicator | Means of Verification (MoV) | Baseline | Target |  | Assumptions |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Mid-term (if applicable) | Final |  |
| Fund-level impacts |  |  |  |  |  |  |
|  | Number of direct and indirect beneficiaries; Number of beneficiaries relative to total population. | SCOPE- WFP data management platform ZimSTAT- National Agency of Statistics and Demographics | 2,000 HH (10,000 Beneficiaries) | 6,000 HH (30,000 Beneficiaries) | Direct beneficiaries 50,000; (indirect beneficiaries 52,000) (1% of total population) | Participants are interested and motivated to participate to project activities. |
| A1.0 Increased resilience and enhanced livelihoods of the most vulnerable people, communities and regions | Number of males and females benefitting from the adoption of diversified, climate-resilient livelihood options | Quantitative Surveys: % change in number of HH productive assets. Differentiated by women- and men-headed HHs | Baseline | 20% increase in men and women HHH | 35% increase in men and women HHH | Communities are interested and willing to participate in identification, planning implementation and maintenance of project activities. Communities are interested and willing to participate in identification, planning implementation and maintenance of project activities. |
|  |  | % of HH who purchase insurance in cash. Differentiated by women- and men- headed HHs (from year 2 in each community) | 0% | 10% | 20% |  |
|  |  | % change Resilience Capacity Index | Baseline | Men and women HHH increase average RCI by 5% | Men and women HHH increase average RCI by 10% |  |
|  |  | Livelihood Coping Strategy Index (LCSI) | 25% HH recurring to emergency CS | 15% HH recurring to emergency CS | 10% HH recurring to emergency CS |  |
| A2.0 Increased resilience of health and well-being, and food and water security | Number of food secure households in areas/periods at risk of climate change impacts (reduced food gap) | Quantitative Surveys: Food Consumption Score (FCS) disaggregated by sex of household head | 40% HH with acceptable FCS | 50% HH with acceptable FCS | 80% HH with acceptable FCS |  |
|  |  | Consumption based reduced Coping Strategy Index (rCSI) | Average rCSI of 15 | Average rCSI of 10 | Average rCSI of 7 |  |
|  |  | Food Expenditure Share (FES) | 50%HH with very high FES | 35%HH with very high FES | 15%HH with very high FES |  |
|  |  | Dietary Diversity Score | 50% HH with low DDS | 40% HH with low DDS | 20% HH with low DDS |  |
| A3.0 Increased resilience of infrastructure and the built environment to climate change threats | Number and type of physical assets strengthened or constructed to help communities withstand impacts from climate variability and change | WFP and Partners Records | 20 assets Currently we cannot specify the types of assets, but they will be inserted after completion. | 50 assets Currently we cannot specify the types of assets, but they will be inserted after completion. | 90 assets Currently we cannot specify the types of assets, but they will be inserted after completion. | Farmers voluntarily participate to assets creation and complete the construction of assets |

| Project outcomes | Outcomes that contribute to Fund-level impacts |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A5.0 Strengthened institutional and regulatory systems for climate-responsive planning and development | Institutional and regulatory systems that improve incentives for climate resilience and their effective implementation | Quantitative surveys: # of local institutions and companies that offer at least one insurance and/or other risk transfer mechanisms and financial service to targeted people | 1 local institutions | 1 local institutions |  |  | 2 local institutions | National, local and district governments recognize and prioritize climate risks as a threat to development gains |
|  |  | # of Zimbabwe Meteorological Services Department (MSD) staff reporting improved capacity in generating relevant tailored climate information. | 0 | 15 |  |  | 30 |  |
|  |  | # of government and development actors plans that include the development or implementation of risk management programmes in targeted districts | 1 government/developme nt actor plans | 5 government/development actor plans |  |  | 22 government/development actor plans |  |
| A6.0 Increased generation and use of climate information in decision-making | Use of climate information products/services in decision-making in climate-sensitive sectors | Quantitative surveys: % households within the targeted communities using agro climatic advice to make DRR, agro and/or livelihood related decisions | 0 HHs | 50% HHs |  |  | 85% HHs | Local organizations are willing to invest to provide climate services to the required standards and number of people Beneficiaries are interested in climate services |
|  |  | #seasonal forecast and trigger mechanism established | 0 forecast/trigger mechanism | 0 forecast/trigger mechanism |  |  | 1 forecast/trigger mechanism |  |
|  |  | #early action plans established | 0 early action plans | 1 early action plans |  |  | 2 early action plans |  |
| A7.0 Strengthened adaptive capacity and reduced exposure to climate risks | Use by vulnerable households, communities and public-sector services of Fund-supported tools, instruments, strategies and activities to respond to climate change and variability | Quantitative surveys: % of Household income derived from climate sensitive sources. Differentiated by women- and men- headed HHs | 100% HH income | 80% HH income |  |  | 65% HH income | Beneficiaries participate to village level discussions Beneficiaries integrate adaptation measures in their activities |
|  |  | % participating households practicing improved agro-ecological farming methods/conservation agriculture | 30% participating HHs | 60% participating HHs |  |  | 100% participating HHs |  |
|  |  | % of pay-out/savings/credit used for investment on productive activities (agriculture/livestock/IGA) | 0% payouts/savings/credit | 20% payouts/savings/credit |  |  | 50% payouts/savings/credit |  |
| A8.0 Strengthened awareness of climate threats and risk-reduction processes | Number of males and females made aware of climate threats and related appropriate responses | Survey | 170 males 330 females | 2,040 males 3,960 women |  |  | 3,400 males 6,600 women | Communities are interested and willing to participate in awareness sessions. |
| Project/programme outputs | Outputs that contribute to outcomes |  |  |  |  |  |  |  |
| 1.1. Strengthen national capacity and systems to develop, interpret, deliver tailored climate and weather data and effectively prepare for and manage climate shocks | #new AWS/rain gauges installed #government staff trained at national level, disaggregate by sex # climate vulnerability assessments #seasonal forecast & trigger mechanism # SOPS developed and applied # capacity building plans developed & applied | WFP and Partners Records | 1 AWS/ 4 rain gauges installed 0 govt staff trained 0 climate vulnerability assessments 0 seasonal forecast & trigger mechanism 0SOPs 0 capacity building plans developed & applied |  | 11 AWS/20 rain gauges installed 30 govt staff trained 1 climate & food security analysis 1 prototype seasonal forecast & trigger mechanism 1 SOPs 0 capacity building plans developed & applied |  | 11 AWS/20 rain gauges installed 50 govt staff trained 1 climate & food security analysis & 1 documentation of indigenous knowledge systems on climate/weather 1 functional seasonal forecast & trigger mechanism 2 SOPs 1 capacity building plans developed & applied | Stakeholders have an adequate understanding of climate issues and are interested in implementation |
| 1.2. Strengthen access to reliable climate and weather information by vulnerable communities to support improved decision making for food security and livelihoods | # HH trained in climate services % HHs within the targeted communities that receive seasonal climate services with agro climatic advice, disaggregated by source (e.g.. farm intermediaries, radio advisories, and SMS) Number of intermediaries trained in how to access, interpret and communicate climate information to households, to support household decision-making related to food security, livelihoods, and DRR Number and type of climate services dissemination channels established | WFP and Partners Records | 0HHs 0HHs 0 intermediaries 0 channels |  | 6,000HHs 60% HHs 40 intermediaries At least 1 channel (PICSA) |  | 10,000HHs 100% HHs 70 intermediaries At least 2 channels (PICSA and ICTs) | Farmers sign up to receive climate information and participate to training on advisory services. |
| 2.1. Risk reduction through the creation of climate adaptation assets | Number of people benefitting from DRR community-based assets (# beneficiaries) Number & types of assets built restored or maintained by targeted households and communities Number of people trained in asset management | WFP and Partners Records | 20,4000 people (10,000 Direct, 10,400 indirect) 20 assets (not possible to specify the type at this stage) 2,000 people |  | 61,200 people (30,000 direct + 31,200 indirect) 50 assets (not possible to specify the type at this stage) 6,000 people |  | 102,000 people (50,000 direct + 52,000 indirect 90 assets (not possible to specify the type at this stage) 10,000 people | Farmers voluntarily participate to assets creation and complete the construction of assets |
| 2.2. Risk transfer through the provision of weather index insurance (WII) | # of farmers covered by a programme-subsidized insurance policy (men/women) #Farmers paying premiums fully in cash/transitioned Total sum insured by gender (subsidised only) Total subsidized premiums paid by gender Maximum cash contribution percentage by participants towards insurance premiums Proportion of participants paying for insurance in cash (partial) by gender # of insurance policies fully subsidised # of insurance policies partially paid in cash # of insurance policies fully paid in cash | Insurance Company Records | 1,320 women 680 men 0 Farmers 132,000 USD (women) 68,000 USD (men) 19,181 USD (women) 9,881 USD (men) 25% 25% total 17% women, 8% men 1,500 fully subsidised 500 partial cash 0 full cash |  | 6,660 women 3,400 men 500 Farmers (330 women, 170 men) 660,000 USD (women) 340,000 USD (men) 80,561 USD (women) 41,501 USD (men) 75% 60% total 40% women, 20% men 4,000 fully subsidised 6,000 partial cash 0 full cash purchases |  | 5,280 women 2,720 men 2,000 Farmers (1320 women, 680 men) 800,000 USD (women) 528,000 USD (men) 30,690 USD (women) 15,810 USD (men) 100% 100% total 66% women, 34% men 0 fully subsidised 8,000 partial cash 2,000 full cash purchases | Farmers understand the importance of insuring the risk deriving from climate variability |
| 3.1 Strengthening the Investment Capacity of small-holder farmers to sustain climate-resilient practices | # HH trained in VSL groups, disaggregated by sex # HH trained in insurance, disaggregated by sex # HH trained in access to market and business skills, disaggregated by sex # HH trained in post-harvest management, disaggregated by sex %Targeted HH (male and female headed) who are member of an informal savings scheme (VSL) No. of new groups & participants by gender (incl. total to date). Total savings contribution in groups by gender Average per capita savings contributions by gender Total number of active borrowers, distributed by gender Average loan size % Targeted male and female headed HH accessing formal credit | WFP and Partners Records | 2,000 (65% women) 1,320 women 680 men 2,000 (65% women) 2,000 (65% women) 12% of FHHs 12% of MHHs 20 groups 720USD women, 180 USD men 15 USD 0 borrowers 0USD 0 FHHs 0 MHHs |  | 6,600 FHHs 3,400 MHHs 6,660 women 3,400 men 6,600 FHHs 3,400 MHHs 6,600 FHHs 3,400 MHHs 30% of FHHs 30% of MHHs 100 groups 14,400 USD women, 3,600 USD men 15USD 1,200 borrowers 15USD 20% of FHHs 20% of MHHs |  | 6,600 FHHs 3,400 MHHs 5,280 women 2,720 men 6,600 FHHs 3,400 MHHs 6,600 FHHs 3,400 MHHs 60% of FHHs 60% of MHHs 500 groups 72,000 USD women. 18,000 USD men 15USD 2,000 borrowers 25USD 20% of FHHs 20%of MHHs | Farmers understand the importance of formal and informal credit and saving schemes. |
| Activities |  | Description |  |  |  | Inputs |  |  |
| 1.1.1 Strengthen the capacity of MSD to provide high quality climate services |  | Improve observation, data collection, analysis and visualization capacity. |  |  |  | Trainers, technical experts and procurement of software |  |  |
| 1.1.2. Conduct climate and food security analysis |  | National assessment to understand the impacts of climate change on food security and nutrition as well as drought and flood-mitigation strategies of multiple stakeholders. |  |  |  | Trainers, technical experts, workshops |  |  |
| 1.1.3. Development of seasonal forecast and trigger system |  | Build the capacity of national stakeholders to define their own thresholds and triggers that will correspond to and inform their integrated developed action plans. |  |  |  | Trainers, technical experts and procurement of software |  |  |
| 1.1.4. Identify key local actors and their existing food security monitoring systems and socioeconomic indicators (i.e. vulnerability analysis) in order to translate climate forecasts into local context-specific anticipatory action |  | Scoping study of the relevant local actors and the existing systems in place, such as Standard Operating Procedures, to monitor food security, anticipate and communicate crises, and coordinate and implement response action. |  |  |  | Trainers, technical experts, workshops |  |  |
| 1.1.5. Develop a capacity building plan for key users |  | Develop appropriate guidance material and we will ensure that produced information can be adapted to local contexts. |  |  |  | Trainers, technical experts, workshops |  |  |
| 1.2.1. Strengthen capacities and systems for co-production of tailored climate services, including translation and tailoring of key messages to ease understanding and use by local communities |  | Support MSD, Agritex and other key stakeholders in the co-production process and in establishing feedback mechanisms from end-users to inform tailoring of climate services |  |  |  | Trainers, technical experts, district/community awareness sessions and trainings |  |  |
| 1.2.2. Strengthen capacities at district and local levels to support dissemination and use of tailored climate services to ensure vulnerable communities have access to information needed for climate resilient practices |  | Train Agritex, cooperating partners at District level, and lead farmers to access, understand and use climate and weather information through the Participatory Climate Services for Agriculture (PICSA) methodology. |  |  |  | Trainers, technical experts, district/community awareness sessions and trainings |  |  |
| 1.2.3. Strengthen dissemination channels to ensure communication of climate services, including using a range of ICTs in partnerships with key national stakeholders |  | Dissemination channels will be further developed and, whenever possible, existing structures will be strengthened such as preparation meetings for the seasonal outlook workshops that are delivered in each districts. Establishment of feedback mechanisms will be essential to enable MSD to refine and further tailor information to needs. |  |  |  | Climate information & relevant ICTs |  |  |
| 2.1.1 Build and/or rehabilitate assets that reduce the impact of climate shocks and help food insecure communities adapt to climate change |  | Construction of community water harvesting, small weir dams, area closure, tree planting to address droughts and erratic rainfall and reduce soil degradation, livestock fences, forage preservation, small warehouses at community and/or household level) to address high post-harvest losses of grains, and poor storage conditions that prohibit grains storage for either food security purposes or to allow sale later, when market prices are higher Trainings on natural resource management and asset management |  |  |  | Construction material, equipment, tree seedlings, engineering and agricultural extension officers, trainers, technical experts, district/community awareness sessions and trainings |  |  |
| 2.2.1. Develop and test the design and implementation of the index for the micro-insurance component. |  | Design of rainfall deficit index based on satellite database |  |  |  | Field analysis (topographic, demographic, socio-economic) for new intervention area Satellite and rain fall index are developed for all areas covered |  |  |
| 2.2.2. Enrol participants and deliver insurance policies |  | Farmers who completed the asset creation activities linked to insurance or paid in cash receive insurance vouchers. |  |  |  | Participants’ record keeping; distributions of insurance coupons; signature of insurance contracts |  |  |
| 2.2.3. Deliver insurance pay-out (if triggered). |  | WFP in collaboration with IRI and local insurance partners assessed rainfall season performance and index results to determine the existence of a payout and its amount. |  |  |  | Monitoring of season; Assessment field mission; elaboration of the end of season report. |  |  |
| 3.1.1. Training of farmers on financial literacy, numeracy and income generating activities (IGAs) |  | Train farmers to provide them with the ability to save, use their savings as buffer or to invest in income generating activities (IGAs), but also build a sustainability path transitioning them to the commercial insurance market. Strengthen existing (or form new) VSLs as an important part of community resilience building through financial literacy training, which spans borrowing, savings, and the role of insurance. |  |  |  | Trainers, technical experts, district/community awareness sessions and trainings |  |  |
| 3.1.2. Training on post-harvest handling and commodity quality |  | Train farmers on the best post-harvest practices and appropriate technology for the selected commodities, including drought tolerant crops. |  |  |  | Trainers, technical experts, district/community awareness sessions and trainings |  |  |
| 3.1.3. Training on group marketing |  | Train farmers on basic marketing and business skills- including records keeping, pricing, contracts, negotiations. training on group formation- and on group dynamics, leadership, governance, organizational management and linking the farmers to other structured trading platforms. |  |  |  | Trainers, technical experts, district/community awareness sessions and trainings |  |  |

The Livelihoods-based Coping Strategies Index (LCSI) is used to better understand longer-term household coping capacities. The LCSI therefore provides a measure of the different types of livelihood-related coping strategies that households may engage in in order to ensure their food needs are met and ensure their survival. It ranks these coping mechanisms by how costly it may be to their livelihoods and ability to cope with shocks in the future. Strategies are classified into three broad groups namely: 1.Stress strategies: such as borrowing money or spending savings, are those which indicate a reduced ability to deal with future shocks due to a current reduction in resources or increase in debts; 2.Crisis strategies: such as selling productive assets, directly reduce future productivity, including human capital formation; 3.Emergency strategies:  such as selling one's land, affect future productivity, but are more difficult to reverse or more dramatic in nature.

The household Food Consumption Score (FCS) is used as a proxy for household food security and is the core indicator for consumption recommended by WFP. It is a measure of dietary diversity, food frequency and the relative nutritional importance of the food consumed. FCS is calculated using a weighted frequency of consumption of different food groups consumed by a household during the 7 days before the survey.

The rCSI (Reduced Coping Strategy Index) is used to compare the hardship faced by households by measuring the frequency and severity of the food consumption behaviors they engage in when faced with shortages of food. It considers food consumption based coping mechanisms such as relying on less preferred, less expensive food, borrowing food or relying on help from friends and relatives; reducing the number of meals eaten per day and or the portions size; and reduction in the quantities consumed by adults/ mothers for young children. The higher the CSI the more stressed the household in its attempts to secure enough food for consumption.

The Food Expenditure Share (FES) is based on the premise that the greater the importance of food within a household’s overall budget (relative to other consumed items/services) the more economically vulnerable the household. The FES is constructed by dividing the total food expenditures by the total household expenditures. The FES is then categorized per group considering that households spending more than 75% of their income in food are severely food insecure, if the FES is between 75% and 65% households are considered Moderately food insecure and if FES is between 50% and 65% households are considered Marginally food insecure.

The household Diet Diversity Score (DDS) provides an estimation of the quality of diet by measuring the number of different food groups (out of 7 total) consumed over a given period (7 days).