## Implementation plan
Implementation Schedule for Project 1: "Implementation of the Lao PDR Emission Reductions Programme through improved governance and sustainable forest landscape management"
Timeline
| Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4
| Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16
Output 1: Enabling environment for REDD+ implementation
Activity 1.1. REDD+ Funding Window & Sustainable Finance | Year 1 Q3: Experts mobilized for restructuring and building standard compliance system and procedures; Assessment of VDFs in target villages; Year 1 Q4: Ongoing capacity building for FFRDF and EPF; Year 2 Q8: REDD+ Funding Window is operational according to developed SOPs; Year 4 Q13: Assessment of new financing instruments initiated
Activity 1.2: Mainstreaming REDD+ into the NDC and socio-economic development plans (SEDPs) | Year 1 Q4: Province and district -level workshops implemented; Year 2 Q5: REDD+ mainsteamed into SEDPs 2021-2025
Activity 1.3. Strengthening the regulatory framework | Year 1 Q3: Experts for policy revision mobilized; Year 1 Q4: Revisions to the regulatory frameowrk initiated; Year 2 Q7: Meetings with Government officials to facilitate cross-sectoral coordination; Year 3 Q9: 1st revisions of regulations of village forest management (commercial use) completed; Year 4 Q13: Revision of PMO 15: Lifting the ban on logging in production forest
Activity 1.4. Law enforcement and monitoring | Year 1 Q3: Equipment procured; Experts for revising SOPs and systems mobilized; Coordination, exchange and reporting channels clarified; Year 1 Q4: Training for POFI and DOFI staff begins, 28 workshops held; Dissemination of regulations and guidelines on permitted and prohibited clearing and utilization of forest; Year 2 Q5: Ongoing trainings for enhanced law enforcement;; Year 2 Q8: Training for POFI and DOFI staff, 28 workshops held; Year 3 Q12: Training for POFI and DOFI staff, 28 workshops held; Year 4 Q16: 4x Standard Operating Procedures (SOPs) for protection, production, conservation, unclassified forest approved and applied correctly
Activity 1.5. Land use planning and improved tenure security | Year 1 Q3: Revision of LUP guidelines initiated; FLR experts mobilized; Vehicles and equipment procured; Year 2 Q6: FLR mainstreamed into LUP guideline; Government staff trained on new guideline, and monitoring and evaluation of LUPs; Year 2 Q7: 50 participatory land use planning (PLUP) established & implemented; Year 3 Q10: Technical asssistance for PLUP implementation provided; Year 4 Q13: 130 PLUP established & implemented
Activity 1.6. Implementation of the MRV system | Year 1 Q3: Development of 4th NFI and the National Forest-Type Map for 2020/21 initiated; Year 1 Q4: Assessment of leakage effects initiated; Year 2 Q5: Provide support for national and international reporting requirements and procedures; Year 2 Q6: Calculation of emission factors and removal factors for forest and non-forest land-use classes; Year 2 Q7: Finalization of 4th National Forest Inventory and National Forest Type Map; Reporting requirements fulfilled; Year 2 Q8: Forest-Types Maps for 2021 completed
Activity 1.7 Knowledge management, FPIC, safeguards and gender | Year 1 Q1: Implementation of ESMP, GAP, and knowledge managementstrategy initiated; ongoing; Year 1 Q2: Ongoing capacity building and training of project staff and associated experts; Year 1 Q4: FPIC agreements for all districts concluded; Year 4 Q16: Provision of all documentation on proper implementation of ESS
Output 2: Market solutions for agricultural drivers of deforestation
Activity 2.1. Local incentives for good agricultural practices and agroforestry | Year 1 Q2: Development of trainings, training trainers, and training government staff on FFS initiated; Vehicles procured; Year 1 Q3: Capacity building operationalized (co-financed with matching grants); Year 1 Q4: 1st installment of performance based payments transferred to 100 villages; Year 2 Q5: Exchanges between kumban and districts begin Match-making support for private sector and villages begins; Year 2 Q6: 2nd installment of performance-based payments transferred to 100 villages; Year 2 Q8: Village-level investments commence; Year 3 Q9: Exchange workshops to share lessons learned initiated each year; Year 4 Q13: Exchange workshops to share lessons learned
Activity 2.2. Catalyzing private sector investment in value chains | Year 1 Q2: In-depth value chain studies initiated; Year 1 Q3: 6 provincial value chain reports elaborated; MSP on value chain development operational; Year 1 Q4: 1st installment of matching grants made; Year 2 Q5: Business development support to farmers initiated; Year 2 Q6: 2nd installment of matching grants made; Year 4 Q16: Green credit line capitalised with international and national finance amounting to Euro 5 million
Activity 2.3. ADB Sustainable Rural Infrastructure Watershed Management Project | Year 1 Q1: Upgrades to rural irrigation infrastructure, and market studies begin; Year 1 Q2: Nutrition-sensitive agriculture in PRI communities supported; Year 4 Q16: 1,000 women using appropriate technologies to produce high-value crops and livestock; 11 market assessments conducted for dry season and upland crops
Output 3: Climate change mitigation action through forestry
Activity 3.1. Village Forest Management | Year 1 Q3: Equipment and vehicles procured; FPIC awareness raising events initiated (ongoing); Year 1 Q4: Development of VFMPs initiated; District level consultation and training events; Year 2 Q7: Implementation of approved VFMPs begins (simultaneously with development of VFMPs); Year 3 Q9: 100,000 ha of village forest managed under approved VFMPs; Year 4 Q16: 200,000 ha of village forest managed under approved VFMPs
Activity 3.2. Sustainable management of production forests | Year 1 Q3: Equipment and vehicles procured; Trainings for government staff initiated; Year 1 Q4: Management planning initiated, incl. village-level consultations; Year 2 Q8: Forest management plans prepared and approved by village forest committees in production forests; Year 3 Q9: Implementation of management plans initiated; Year 4 Q16: 12,000 ha of production forest sustainably managed
Activity 3.3. National protected area management | Year 1 Q3: Vehicles and equipment procured; Development of 4 new NPA management plans begins; Year 2 Q5: Negotiation of village conservation contracts initiated; Year 2 Q7: Implementation of management plans begins; Year 4 Q16: 21,000 ha of protection forest managed under approved management plans
Output 4: Project management, coordination, monitoring and evaluation
Project management, coordination, monitoring, evaluation, knowledge management and safeguards management | Year 1 Q1: Recruitment of Project Staff; Project launch workshop; Year 1 Q2: Inception Workshop and Report; Year 1 Q4: Procurement of Office supplies; Year 2 Q5: Annual Performance Report; Year 3 Q9: Annual Performance Report; mid term evaluation; Year 4 Q13: Annual Performance Report; Year 4 Q14: Project Completion Report; Year 4 Q15: Project Closure Workshop; Year 4 Q16: Final Evaluation

## Forestry 1 ha model (hidden)
GCF project 1 ha models - forestry
| Discount rate | #REF!
Without Project Scenario (BAU) Unsustainable forest management & harvesting (complete degradation over 5 years) (For activity 3.1 and 3.2) follwed by shifting cultivation
| Inputs at establishment (year 0) | Quantity | Unit | Price per unit | Unit | Total
| Chainsaw (every 5 years) | 1 | Unit | 50 | USD | 50 | USD
| Axe (every 5 years) | 3 | Units | 2.5 | USD | 7.5 | USD
| Labor inputs | 40 | days | 3 | USD | 120 | USD
| Sum of establishment costs |  |  |  |  | 177.5 | USD
| Inputs at management (from year 1 onwards) | Quantity | Unit | Price per unit | Unit
| Chainsaw (every 5 years) |  | Unit | 50 | USD | 0 | USD
| Axe (every 5 years) |  | Units | 2.5 | USD | 0 | USD
| Labor inputs | 40 | days | 3 | USD | 120 | USD
| Sum of establishment costs |  |  |  |  | 120 | USD
Yields/Prices
| Revenues from sale of firewood | 6 | m³/ha/year | 12 | USD | 72 | USD
| Revenues from sale of construction timber | 3 | m³/ha/year | 24 | USD | 72 | USD
| Revenues from sale of large diameter timber | 1 | m³/ha/year | 45 | USD | 45 | USD
| Sum of revenues |  |  |  |  | 189 | USD
Costs, Revenues and Cashflows
| Costs |  | Unit | Year
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Establishment Cost |  | USD/ha | 57.5 |  |  |  |  | 15.75 | 6.75 | 6.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.75 | 6.75 | 6.75 | 0 | 0 | 0 | 0 | 0 | 0 | 15.75 | 6.75 | 6.75 | 0 | 0 | 0
| Labor Cost |  | USD/ha | 120 | 120 | 120 | 120 | 120 | 540 | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 510 | 510 | 0 | 0 | 0
| Total cost |  | USD/ha | 177.5 | 120 | 120 | 120 | 120 | 555.75 | 516.75 | 516.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555.75 | 516.75 | 516.75 | 0 | 0 | 0 | 0 | 0 | 0 | 555.75 | 516.75 | 516.75 | 0 | 0 | 0
| Revenues |  | Unit
| Total revenues |  | USD/ha | 189 | 189 | 189 | 189 | 189 | 455 | 455 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 455 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 455 | 455 | 0 | 0 | 0
Cashflows
| Annual Cashflow |  | USD/ha | 11.5 | 69 | 69 | 69 | 69 | -100.75 | -61.75 | -61.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -425.75 | -61.75 | -61.75 | 0 | 0 | 0 | 0 | 0 | 0 | -425.75 | -61.75 | -61.75 | 0 | 0 | 0 | -34.5083
| Cummulative Cashflow |  | USD/ha | 11.5 | 80.5 | 149.5 | 218.5 | 287.5 | 186.75 | 125 | 63.25 | 63.25 | 63.25 | 63.25 | 63.25 | 63.25 | 63.25 | 63.25 | -362.5 | -424.25 | -486 | -486 | -486 | -486 | -486 | -486 | -486 | -911.75 | -973.5 | -1035.25 | -1035.25 | -1035.25 | -1035.25
| NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  |  | NPV 20yrs | #REF!
|  |  |  | NPV 30yrs | #REF!
| IRR |  |  | Year 1: IRR 10yrs; Year 2: -7.049%
|  |  |  | IRR 20yrs | 11.49%
|  |  |  | IRR 30yrs | 13.36%
Without Project Scenario - Unsustainable use of native forest NTFP (Activity 3.3) (assume annual producitivty reduction by 10%)
| Inputs at establishment (year 0) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit; Year 3: Total
| Tools & Equipment | 1 | Unit | Year 1: 57.5; Year 2: USD; Year 3: 57.5; Year 4: USD
|  |  | Units | Year 2: USD; Year 3: 0; Year 4: USD
| Labor inputs | 20 | days | Year 1: 3; Year 2: USD; Year 3: 60; Year 4: USD
| Sum of establishment costs |  |  | Year 3: 117.5; Year 4: USD
| Inputs at management (from year 1 onwards) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit
| Chainsaw (every 5 years) |  | Unit | Year 2: USD; Year 3: 0; Year 4: USD
| Axe (every 5 years) |  | Units | Year 2: USD; Year 3: 0; Year 4: USD
| Labor inputs | 25 | days | Year 1: 3; Year 2: USD; Year 3: 75; Year 4: USD
| Sum of establishment costs |  |  | Year 3: 75; Year 4: USD
Yields/Prices
| Revenues from sale of timber products | 1 | m³/ha/year | Year 1: 24; Year 2: USD; Year 3: 24; Year 4: USD
| Revenues from sale NTFPs | 20 | kg/ha/year | Year 1: 1.5; Year 2: USD; Year 3: 30; Year 4: USD
| Revenues from sale of bamboo | 70 | stems/ha/year | Year 1: 1; Year 2: USD; Year 3: 70; Year 4: USD
| Sum of revenues |  |  | Year 3: 124; Year 4: USD
Costs, Revenues and Cashflows
| Costs |  | Unit | Year 1: Year
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Establishment Cost |  | USD/ha | 50 |  |  |  |  | 50 |  |  |  |  | 15.75 | 6.75 | 6.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.75 | 6.75 | 6.75 | 0 | 0 | 0 | 0 | 0 | 0 | 15.75
| Labor Cost |  | USD/ha | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 540 | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 510 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | AVG cost
| Total cost |  | USD/ha | 110 | 60 | 60 | 60 | 60 | 110 | 60 | 60 | 60 | 60 | 555.75 | 516.75 | 516.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555.75 | 516.75 | 516.75 | 0 | 0 | 0 | 0 | 0 | 0 | 555.75 | 147.8083
| Revenues |  | Unit
[5 empty] | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15%
| Total revenues |  | USD/ha | 124 | 105.4 | 89.59 | 76.1515 | 64.7288 | 55.0195 | 46.7665 | 39.7516 | 33.7888 | 28.7205 | 455 | 455 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 455 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 106.6306
Cashflows
| Annual Cashflow |  | USD/ha | 14 | 45.4 | 29.59 | 16.1515 | 4.7288 | -54.9805 | -13.2335 | -20.2484 | -26.2112 | -31.2795 | -100.75 | -61.75 | -61.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -425.75 | -61.75 | -61.75 | 0 | 0 | 0 | 0 | 0 | 0 | -425.75 | -41.1778
| Cummulative Cashflow |  | USD/ha | 14 | 59.4 | 88.99 | 105.1415 | 109.8703 | 54.8897 | 41.6563 | 21.4078 | -4.8033 | -36.0828 | -136.8328 | -198.5828 | -260.3328 | -260.3328 | -260.3328 | -260.3328 | -260.3328 | -260.3328 | -260.3328 | -260.3328 | -686.0828 | -747.8328 | -809.5828 | -809.5828 | -809.5828 | -809.5828 | -809.5828 | -809.5828 | -809.5828 | -1235.3328
| NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  |  | NPV 20yrs | #REF!
|  |  |  | NPV 30yrs | #REF!
| IRR |  |  | Year 1: IRR 10yrs; Year 2: 5.661%
|  |  |  | IRR 20yrs | 18.21%
|  |  |  | IRR 30yrs | 21.17%
Model 1 | With Project Scenario - Sustainable Natural Forest Management & NTFP utilization (Activity 3.3 and 3.1)
| Inputs at establishment (year 0) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit; Year 3: Total
| Tools & Equipment | 1 | Unit | Year 1: 50; Year 2: USD; Year 3: 50; Year 4: USD
|  |  | Units | Year 2: USD; Year 3: 0; Year 4: USD
| Labor inputs | 20 | days | Year 1: 3; Year 2: USD; Year 3: 60; Year 4: USD
| Sum of establishment costs |  |  | Year 3: 110; Year 4: USD
| Inputs at management (from year 1 onwards) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit
| Chainsaw (every 5 years) |  | Unit | Year 2: USD; Year 3: 0; Year 4: USD
| Axe (every 5 years) |  | Units | Year 2: USD; Year 3: 0; Year 4: USD
| Labor inputs | 20 | days | Year 1: 3; Year 2: USD; Year 3: 60; Year 4: USD
| Sum of establishment costs |  |  | Year 3: 60; Year 4: USD
Yields/Prices
| Revenues from sale of timber products | 1 | m³/ha/year | Year 1: 24; Year 2: USD; Year 3: 24; Year 4: USD
| Revenues from sale NTFPs | 10 | kg/ha/year | Year 1: 1.5; Year 2: USD; Year 3: 15; Year 4: USD
| Revenues from sale of bamboo | 50 | stems/ha/year | Year 1: 1; Year 2: USD; Year 3: 50; Year 4: USD
| Sum of revenues |  |  | Year 3: 89; Year 4: USD
Costs, Revenues and Cashflows
| Costs |  | Unit | Year 1: Year
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Establishment Cost |  | USD/ha | Year 1: 50; Year 6: 50; Year 11: 50; Year 16: 50; Year 21: 50; Year 26: 50
| Labor Cost |  | USD/ha | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | AVG cost
| Total cost |  | USD/ha | 110 | 60 | 60 | 60 | 60 | 110 | 60 | 60 | 60 | 60 | 110 | 60 | 60 | 60 | 60 | 110 | 60 | 60 | 60 | 60 | 110 | 60 | 60 | 60 | 60 | 110 | 60 | 60 | 60 | 60 | 70
| Revenues |  | Unit
| Total revenues |  | USD/ha | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89 | 89
Cashflows
| Annual Cashflow |  | USD/ha | -21 | 29 | 29 | 29 | 29 | -21 | 29 | 29 | 29 | 29 | -21 | 29 | 29 | 29 | 29 | -21 | 29 | 29 | 29 | 29 | -21 | 29 | 29 | 29 | 29 | -21 | 29 | 29 | 29 | 29 | 19
| Cummulative Cashflow |  | USD/ha | -21 | 8 | 37 | 66 | 95 | 74 | 103 | 132 | 161 | 190 | 169 | 198 | 227 | 256 | 285 | 264 | 293 | 322 | 351 | 380 | 359 | 388 | 417 | 446 | 475 | 454 | 483 | 512 | 541 | 570
| NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  |  | NPV 20yrs | #REF!
|  |  |  | NPV 30yrs | #REF!
| IRR |  |  | Year 1: IRR 10yrs; Year 2: 133.4%
|  |  |  | IRR 20yrs | 133.4%
|  |  |  | IRR 30yrs | 133.4%
Model 2 | With Project Scenario - Natural Forest assistend natural regeneration (Activity 3.1)
| Inputs and prices at establishment (year 1) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit; Year 3: Costs
| Equipment every 5 years | 1 | Units | Year 1: 60; Year 2: USD; Year 3: 60
| Tools | 8 | Units | Year 1: 2; Year 2: USD; Year 3: 16
| Labour input (clearing, planting, maintenance) | 50 | days | Year 1: 3; Year 2: USD; Year 3: 150
| Protection contracts |  | lumpsum | Year 1: 30; Year 2: USD; Year 3: 0
| Total cost establishment |  |  | Year 3: 226
| Inputs and prices at management (from year 2 to year 6) | Quantity | Unit | Year 1: Price per unit; Year 3: Costs
| Labour input/yr/ha (maintenance) | 20 | days | Year 1: 3; Year 2: USD; Year 3: 60
| Transport | 1 | lumpsum | Year 1: 30; Year 2: USD; Year 3: 30
| Total costs management |  |  | Year 3: 90
| Yields and revenues | Quantity | Unit | Year 1: Price per unit; Year 3: Revenues
| Product 1: Round wood (Yields /ha/yr) | 1 | m3/year | Year 1: 55; Year 2: USD; Year 3: 55
| Yield start after establishment: | 5 | Year
| Product 2: Fire wood (Yields /ha/yr) | 5 | 0.75m3 | Year 1: 12; Year 2: USD; Year 3: 60
| Yield start after establishment: | 1 | Year
| NTFP collection |  |  | Year 3: 44.5
Costs, Revenues and Cashflows
| Costs |  | Unit | Year 1: Year
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Establishment Cost |  | USD/ha | 76 |  |  |  |  | 90 | 30 | 30 | 30 | 30 | 90 | 30 | 30 | 30 | 30 | 90 | 30 | 30 | 30 | 30 | 90 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
| Labor Cost |  | USD/ha | 150 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | AVG cost
| Total cost |  | USD/ha | 226 | 60 | 60 | 60 | 60 | 150 | 90 | 90 | 90 | 90 | 150 | 90 | 90 | 90 | 90 | 150 | 90 | 90 | 90 | 90 | 150 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 98.5333
| Revenues |  | Unit
| Total revenues |  | USD/ha | 44.5 | 104.5 | 104.5 | 104.5 | 104.5 | 115 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 159.5 | 146.85
Cashflows
| Annual Cashflow |  | USD/ha | -181.5 | 44.5 | 44.5 | 44.5 | 44.5 | -35 | 69.5 | 69.5 | 69.5 | 69.5 | 9.5 | 69.5 | 69.5 | 69.5 | 69.5 | 9.5 | 69.5 | 69.5 | 69.5 | 69.5 | 9.5 | 69.5 | 69.5 | 69.5 | 69.5 | 69.5 | 69.5 | 69.5 | 69.5 | 69.5 | 48.3167
| Cummulative Cashflow |  | USD/ha | -181.5 | -137 | -92.5 | -48 | -3.5 | -38.5 | 31 | 100.5 | 170 | 239.5 | 249 | 318.5 | 388 | 457.5 | 527 | 536.5 | 606 | 675.5 | 745 | 814.5 | 824 | 893.5 | 963 | 1032.5 | 1102 | 1171.5 | 1241 | 1310.5 | 1380 | 1449.5
| NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  |  | NPV 20yrs | #REF!
|  |  |  | NPV 30yrs | #REF!
| IRR |  |  | Year 1: IRR 10yrs; Year 2: 18.7%
|  |  |  | IRR 20yrs | 23.76%
|  |  |  | IRR 30yrs | 24.19%
Model 3 | With Project Scenario (BAU) Sustainable forest management & harvesting (For activity 3.2)
| Inputs at establishment (year 0) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit; Year 3: Total
| Equipment every 5 years | 1 | Unit | Year 1: 50; Year 2: USD; Year 3: 50; Year 4: USD
|  |  | Units | Year 2: USD; Year 3: 0; Year 4: USD
| Labor inputs | 30 | days | Year 1: 3; Year 2: USD; Year 3: 90; Year 4: USD
| Sum of establishment costs |  |  | Year 3: 140; Year 4: USD
| Inputs at management (from year 1 onwards) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit
| Chainsaw (every 5 years) |  | Unit | Year 2: USD; Year 3: 0; Year 4: USD
| Transport cost forest to road | 1 | Units | Year 1: 30; Year 2: USD; Year 3: 30; Year 4: USD
| Labor inputs harvesting and transport | 25 | days | Year 1: 3; Year 2: USD; Year 3: 75; Year 4: USD
| Sum of establishment costs |  |  | Year 3: 75; Year 4: USD
Yields/Prices
| Revenues from sale of firewood | 6 | m³/ha/year | Year 1: 12; Year 2: USD; Year 3: 72; Year 4: USD
| Revenues from sale of construction timber | 1.5 | m³/ha/year | Year 1: 30; Year 2: USD; Year 3: 45; Year 4: USD
| Revenues from sale of large diameter timber | 1 | m³/ha/year | Year 1: 60; Year 2: USD; Year 3: 60; Year 4: USD
| Sum of revenues |  |  | Year 3: 177; Year 4: USD
Costs, Revenues and Cashflows
| Costs |  | Unit | Year 1: Year
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Establishment Cost |  | USD/ha | 80 | 30 | 30 | 30 | 30 | 80 | 30 | 30 | 30 | 30 | 80 | 30 | 30 | 30 | 30 | 80 | 30 | 30 | 30 | 30 | 80 | 30 | 30 | 30 | 30 | 80 | 30 | 30 | 30 | 30
| Labor Cost |  | USD/ha | 90 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
| Total cost |  | USD/ha | 170 | 150 | 150 | 150 | 150 | 200 | 150 | 150 | 150 | 150 | 200 | 150 | 150 | 150 | 150 | 200 | 150 | 150 | 150 | 150 | 200 | 150 | 150 | 150 | 150 | 200 | 150 | 150 | 150 | 150
| Revenues |  | Unit
| Total revenues |  | USD/ha | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177 | 177
Cashflows
| Annual Cashflow |  | USD/ha | 7 | 27 | 27 | 27 | 27 | -23 | 27 | 27 | 27 | 27 | -23 | 27 | 27 | 27 | 27 | -23 | 27 | 27 | 27 | 27 | -23 | 27 | 27 | 27 | 27 | -23 | 27 | 27 | 27 | 27 | 18
| Cummulative Cashflow |  | USD/ha | 7 | 34 | 61 | 88 | 115 | 92 | 119 | 146 | 173 | 200 | 177 | 204 | 231 | 258 | 285 | 262 | 289 | 316 | 343 | 370 | 347 | 374 | 401 | 428 | 455 | 432 | 459 | 486 | 513 | 540
| NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  |  | NPV 20yrs | #REF!
|  |  |  | NPV 30yrs | #REF!
| IRR |  |  | Year 1: IRR 10yrs; Year 2: #NUM!
|  |  |  | IRR 20yrs | #NUM!
|  |  |  | IRR 30yrs | #NUM!
Model 4 | With Project Scenario - Fast growing forest plantations (Activity 3.4)
| Inputs at establishment (year 0) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit; Year 3: Total
| Seedlings (Eucalyptus) | 1100 | ssedlings | Year 1: 0.16; Year 2: USD; Year 3: 176; Year 4: USD
| Fertilizer and other inputs | 1 | Lumsum | Year 1: 200; Year 2: USD; Year 3: 200; Year 4: USD
| Urea |  | units | Year 1: 0.22; Year 2: USD; Year 3: 0; Year 4: USD
| sacks |  | Units | Year 1: 0.2; Year 2: USD; Year 3: 0; Year 4: USD
| Sum of Investments/Materials |  |  | Year 3: 376; Year 4: USD
| Labor cost | 100 | days | Year 1: 3; Year 2: USD; Year 3: 300; Year 4: USD
| SUM FOR ESTABLISHMENT COSTS |  |  | Year 3: 676; Year 4: USD
Yields/Prices
| Revenues from harvest/Sale of Products |  | kg/ha/year | Year 2: USD; Year 3: 0; Year 4: USD
| Inputs at management (from year 1 onwards) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit
| Replacement seedlings | 200 | Units | Year 1: 0.16; Year 2: USD; Year 3: 32; Year 4: USD
| Fertilizer | 200 | kg | Year 1: 0.2; Year 2: USD; Year 3: 40; Year 4: USD
|  |  | liters | Year 2: USD; Year 3: 0; Year 4: USD
|  |  | Units | Year 2: USD; Year 3: 0; Year 4: USD
| Sum Investments/Materials |  |  | Year 3: 72; Year 4: USD
| Labor cost (year 2-3) | 60 | days/yr | Year 1: 3; Year 2: USD; Year 3: 180; Year 4: USD
| Labour cost annual year 4-7 | 20 | Days/yr | Year 1: 3; Year 2: USD; Year 3: 60
| Labor harvesting | 100 | Days/ha | Year 1: 3; Year 2: USD; Year 3: 300; Year 4: USD
| SUM OF ANNUAL COSTS |  |  | Year 3: 252; Year 4: USD
Yields/Prices
| Revenues from harvest/Sale of Products | 175 | m3/ha/year | Year 1: 25; Year 2: USD/m³; Year 3: 4375; Year 4: USD
Costs, Revenues and Cashflows
| Costs |  | Unit | Year 1: Year
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Establishment Cost |  | USD/ha | 376 | 72 | [6 empty] | 376 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 376 | 72 | 0 | 0 | 0 | 0
| Labor Cost |  | USD/ha | 300 | 180 | 180 | 60 | 60 | 60 | 60 | 300 | 300 | 180 | 180 | 60 | 60 | 60 | 60 | 300 | 300 | 180 | 180 | 60 | 60 | 60 | 60 | 300 | 300 | 180 | 180 | 60 | 60 | 60 | AVG cost
| Total cost |  | USD/ha | 676 | 252 | 180 | 60 | 60 | 60 | 60 | 300 | 676 | 252 | 180 | 60 | 60 | 60 | 60 | 300 | 676 | 252 | 180 | 60 | 60 | 60 | 60 | 300 | 676 | 252 | 180 | 60 | 60 | 60 | 207.7333
1648
| Revenues |  | Unit
| Total revenues |  | USD/ha | Year 8: 4375; Year 16: 4375; Year 24: 4375; Year 30: 4375 | 4375
Cashflows
| Annual Cashflow |  | USD/ha | -676 | -252 | -180 | -60 | -60 | -60 | -60 | 4075 | -676 | -252 | -180 | -60 | -60 | -60 | -60 | 4075 | -676 | -252 | -180 | -60 | -60 | -60 | -60 | 4075 | -676 | -252 | -180 | -60 | -60 | 4315 | 375.6
| Cummulative Cashflow |  | USD/ha | -676 | -928 | -1108 | -1168 | -1228 | -1288 | -1348 | 2727 | 2051 | 1799 | 1619 | 1559 | 1499 | 1439 | 1379 | 5454 | 4778 | 4526 | 4346 | 4286 | 4226 | 4166 | 4106 | 8181 | 7505 | 7253 | 7073 | 7013 | 6953 | 11268
| NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  |  | NPV 20yrs | #REF!
|  |  |  | NPV 30yrs | #REF!
| IRR |  |  | Year 1: IRR 10yrs; Year 2: 16.3%
|  |  |  | IRR 20yrs | 19.49%
|  |  |  | IRR 30yrs | 20.42%
Note on J31: Eduard Merger: Shifitng culitvation starts
Note on O78: Eduard Merger: Assume complete degradaiton not continuation of use and shifitng cultivation land use

## Agriculture 1 model (hidden)
Discount rate | #REF!
GCF project 1 ha models - Agriculture
without project scenario (BAU) | [9 empty] | with project scenario (PAM)
shifting cultivation (upland rice) - 3 yeas cultivation, 7 years fallow (For activity 2.,3.4) | [9 empty] | Introduction of multi-year rotation crops during fallow periods (e.g. 10 year fallow with sapan)
Inputs at establishment (year 0) | Quantity | Unit | Price per unit | Unit | Total |  |  |  |  | Inputs at establishment (upland rice) | Quantity | Unit | Price per unit | Unit | Total
Seeds | 45 | kg | 0.1 | USD | 4.5 | USD |  |  |  | Seedlings | 45 | kg | 0.1 | USD | 4.5 | USD
Fertilizer |  | kg |  | USD | 0 | USD |  |  |  | Fertilizer | 50 | kg | 0.25 | USD | 12.5 | USD
Herbicides/Insecticides |  | liters |  | USD | 0 | USD |  |  |  | Herbicides/Insecticides |  | liters |  | USD | 0 | USD
Tools | 6 | Units | 1.875 | USD | 11.25 | USD |  |  |  | Tools | 6 | Units | 0.38 | USD | 2.28 | USD
Sum of Investments/Materials |  |  |  |  | 15.75 | USD |  |  |  | Sum of Investments/Materials |  |  |  |  | 19.28 | USD
Labor cost | 180 | days | 3 | USD | 540 | USD |  |  |  | Labor inputs | 160 | days | 3 | USD | 480 | USD
SUM FOR ESTABLISHMENT COSTS |  |  |  |  | 555.75 | USD |  |  |  | SUM FOR ESTABLISHMENT COSTS |  |  |  |  | 499.28 | USD
Yields/Prices | [9 empty] | Yields/Prices
Revenues from harvest/Sale of Products | 1000 | kg/ha/year | 0.13 | USD | 130 | USD |  |  |  | Revenues from harvest/Sale of Products | 1000 | kg/ha/year | 0.13 | USD | 130 | USD
Inputs at management (from year 1 onwards) | Quantity | Unit | Price per unit | Unit | [5 empty] | Cashcrop inputs (yr 3 - yr 10) e.g. sapan | Quantity | Unit | Price per unit | Unit | Total
Seeds | 45 | Units | 0.1 | USD | 4.5 | USD |  |  |  | Seeds | 2 | Units | 1.5 | USD | 3 | USD
Fertilizer |  | kg |  | USD | 0 | USD |  |  |  | Fertilizer | 50 | kg | 0.25 | USD | 12.5 | USD
Herbicides/Insecticides |  | liters |  | USD | 0 | USD |  |  |  | Herbicides/Insecticides |  | liters |  | USD | 0 | USD
Tools | 6 | Units | 0.375 | USD | 2.25 | USD |  |  |  | Tools | 6 | Units | 0.38 | USD | 2.28 | USD
Sum Investments/Materials |  |  |  |  | 6.75 | USD |  |  |  | Sum Investments/Materials |  |  |  |  | 17.78 | USD
Labor cost | 170 | days/yr | 3 | USD | 510 | USD |  |  |  | Labor cost | 135 | days/yr | 3 | USD | 405 | USD
SUM OF ANNUAL COSTS |  |  |  |  | 516.75 | USD |  |  |  | SUM OF ANNUAL COSTS |  |  |  |  | 422.78 | USD
Yields/Prices | [9 empty] | Yields/Prices
Revenues from harvest/Sale of Products | 1300 | kg/ha/year | 0.35 | USD | 455 | USD |  |  |  | Revenues from harvest/Sale of Products | 2000 | kg/ha/year | 0.35 | USD | 700 | USD
Data based on Keneke mission in Nov 2018
Sequential Cropping: Upland rice with sesame/ginger yr1 and soybean/peanut yr 2&3 and jobs tear yr4 - 4 yr rotations
[10 empty] | Inputs at establishment | Quantity | Unit | Price per unit | Unit | Total |  |  | Yea 2 & 3 (soybean & peanut) | Quantity | Unit | Price per unit | Unit | Total
[10 empty] | Seedlings (rice) | 45 | kg | 0.1 | USD | 4.5 | USD |  | Seedlings | 45 | kg | 1.5 | USD | 67.5 | USD
[10 empty] | Fertilizer |  | kg |  | USD | 0 | USD |  | Fertilizer | 10 | kg | 1.25 | USD | 12.5 | USD
[10 empty] | Herbicides/Insecticides |  | liters |  | USD | 0 | USD |  | Herbicides/Insecticides |  | liters |  | USD | 0 | USD
[10 empty] | Tools | 5 | Units | 7 | USD | 35 | USD |  | Tools |  | Units |  | USD | 0 | USD
[10 empty] | Sum of Investments/Materials |  |  |  |  | 39.5 | USD |  | Sum of Investments/Materials |  |  |  |  | 80 | USD
[10 empty] | Labor inputs | 185 | days | 3 | USD | 555 | USD |  | Labor inputs | 140 | days | 3 | USD | 420 | USD
[10 empty] | SUM FOR ESTABLISHMENT COSTS |  |  |  |  | 594.5 | USD |  | SUM FOR ESTABLISHMENT COSTS |  |  |  |  | 500 | USD
[10 empty] | Yields/Prices | [7 empty] | Yields/Prices
[10 empty] | Revenues from harvest/Sale of Products | 1600 | kg/ha/year | 0.13 | USD | 208 | USD |  | Revenues from soybean | 1600 |  | 0.3125 | USD | 500 | USD
[18 empty] | Revenues from peanut | 650 | kg/ha/year | 0.5625 | USD | 365.625 | USD
[10 empty] | Yea 1 inputs (sesame & ginger) | Quantity | Unit | Price per unit | Unit
[10 empty] | Seedlings (sesame, ginger) | 60 | Units | 0.1875 | USD | 11.25 | USD |  | Year 4 (job's tear) | Quantity | Unit | Price per unit | Unit | Total
[10 empty] | Fertilizer | 3 | kg | 1.25 | USD | 3.75 | USD |  | Fertilizer |  | Units |  | USD | 0 | USD
[10 empty] | Herbicides/Insecticides | 5 | liters | 0.75 | USD | 3.75 | USD |  | Seedlings | 60 | kg | 0.25 | USD | 15 | USD
[10 empty] | Tools |  | Units |  | USD | 0 | USD |  | Herbicides/Insecticides |  | liters |  | USD | 0 | USD
[10 empty] | Sum Investments/Materials |  |  |  |  | 18.75 | USD |  | Tools |  | Units |  | USD | 0 | USD
[10 empty] | Labor cost | 170 | days/yr | 3 | USD | 510 | USD |  | Sum Investments/Materials |  |  |  |  | 15 | USD
[10 empty] | SUM OF ANNUAL COSTS |  |  |  |  | 528.75 | USD |  | Labor cost | 150 | days/yr | 3 | USD | 450 | USD
[18 empty] | SUM OF ANNUAL COSTS |  |  |  |  | 465 | USD
Yields/Prices
[15 empty] | 0 | USD |  | Yields/Prices
|  |  | Average calculation for in-kind villager leverage of finance | [6 empty] | Revenues from sesame | 400 | kg/ha/year | 1.125 | USD | 450 | USD |  | Revenues from harvest/Sale of Products | 1500 | kg/ha/year | 0.125 | USD | 187.5 | USD
|  |  | 602.35 | [6 empty] | Revenues from Ginger | 2800 | kg/ha/year | 0.1875 | USD | 525 | USD
Costs, Revenues and Cashflows
BAU - shifting cultivation (upland rice) - 3 yeas cultivation, 7 years fallow
Costs |  | Unit | Year
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Establishment Cost |  | USD/ha | Year 1: 15.75; Year 2: 6.75; Year 3: 6.75; Year 11: 15.75; Year 12: 6.75; Year 13: 6.75; Year 20: 15.75; Year 21: 6.75; Year 22: 6.75; Year 30: 15.75
Labor Cost |  | USD/ha | Year 1: 540; Year 2: 510; Year 3: 510; Year 11: 540; Year 12: 510; Year 13: 510; Year 20: 540; Year 21: 510; Year 22: 510; Year 30: 540
Total cost |  | USD/ha | 555.75 | 516.75 | 516.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555.75 | 516.75 | 516.75 | 0 | 0 | 0 | 0 | 0 | 0 | 555.75 | 516.75 | 516.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555.75
Revenues |  | Unit
Total revenues |  | USD/ha | Year 1: 455; Year 2: 455; Year 3: 455; Year 11: 130; Year 12: 455; Year 13: 455; Year 20: 130; Year 21: 455; Year 22: 455; Year 30: 455
Cashflows
Annual Cashflow |  | USD/ha | -100.75 | -61.75 | -61.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -425.75 | -61.75 | -61.75 | 0 | 0 | 0 | 0 | 0 | 0 | -425.75 | -61.75 | -61.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -100.75 | -47.45
Cummulative Cashflow |  | USD/ha | -100.75 | -162.5 | -224.25 | -224.25 | -224.25 | -224.25 | -224.25 | -224.25 | -224.25 | -224.25 | -650 | -711.75 | -773.5 | -773.5 | -773.5 | -773.5 | -773.5 | -773.5 | -773.5 | -1199.25 | -1261 | -1322.75 | -1322.75 | -1322.75 | -1322.75 | -1322.75 | -1322.75 | -1322.75 | -1322.75 | -1423.5
NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  | NPV 20yrs | #REF!
|  |  | NPV 30yrs | #REF!
IRR |  |  | Year 1: IRR 10yrs; Year 2: #NUM!
|  |  | IRR 20yrs | #NUM!
|  |  | IRR 30yrs | #NUM!
PAM - Sequential Cropping: Upland rice with sesame/ginger yr1 and soybean/peanut yr 2&3 and jobs tear yr4 - 4 yr rotations
Costs |  | Unit | Year 1: Year
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Establishment Cost |  | USD/ha | 39.5 | 18.75 | 80 | 15 | 39.5 | 18.75 | 80 | 15 | 39.5 | 18.75 | 80 | 15 | 39.5 | 18.75 | 80 | 15 | 39.5 | 18.75 | 80 | 15 | 39.5 | 18.75 | 80 | 15 | 39.5 | 18.75 | 80 | 15 | 39.5 | 18.75
Labor Cost |  | USD/ha | 555 | 510 | 420 | 450 | 555 | 510 | 420 | 450 | 555 | 510 | 420 | 450 | 555 | 510 | 420 | 450 | 555 | 510 | 420 | 450 | 555 | 510 | 420 | 450 | 555 | 510 | 420 | 450 | 555 | 510 | AVG cost
Total cost |  | USD/ha | 594.5 | 528.75 | 500 | 465 | 594.5 | 528.75 | 500 | 465 | 594.5 | 528.75 | 500 | 465 | 594.5 | 528.75 | 500 | 465 | 594.5 | 528.75 | 500 | 465 | 594.5 | 528.75 | 500 | 465 | 594.5 | 528.75 | 500 | 465 | 594.5 | 528.75 | 524.7
Revenues |  | Unit
Total revenues |  | USD/ha | 208 | 975 | 865.625 | 187.5 | 208 | 975 | 865.625 | 187.5 | 208 | 975 | 865.625 | 187.5 | 208 | 975 | 865.625 | 187.5 | 208 | 975 | 865.625 | 187.5 | 208 | 975 | 865.625 | 187.5 | 208 | 975 | 865.625 | 187.5 | 208 | 975 | 561.1958
Cashflows
Annual Cashflow |  | USD/ha | -386.5 | 446.25 | 365.625 | -277.5 | -386.5 | 446.25 | 365.625 | -277.5 | -386.5 | 446.25 | 365.625 | -277.5 | -386.5 | 446.25 | 365.625 | -277.5 | -386.5 | 446.25 | 365.625 | -277.5 | -386.5 | 446.25 | 365.625 | -277.5 | -386.5 | 446.25 | 365.625 | -277.5 | -386.5 | 446.25 | 36.4958
Cummulative Cashflow |  | USD/ha | -386.5 | 59.75 | 425.375 | 147.875 | -238.625 | 207.625 | 573.25 | 295.75 | -90.75 | 355.5 | 721.125 | 443.625 | 57.125 | 503.375 | 869 | 591.5 | 205 | 651.25 | 1016.875 | 739.375 | 352.875 | 799.125 | 1164.75 | 887.25 | 500.75 | 947 | 1312.625 | 1035.125 | 648.625 | 1094.875
NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  | NPV 20yrs | #REF!
|  |  | NPV 30yrs | #REF!
IRR |  |  | Year 1: IRR 10yrs; Year 2: 45.33%
|  |  | IRR 20yrs | 46.58%
|  |  | IRR 30yrs | 46.58%
Cashcrops
Unsustainable maize cultivation |  |  | Year 8: Intercropping (mix of corn and cashcrop, e.g. soybean/peanut)
Inputs at establishment (year 0) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit; Year 3: Total; Year 8: Inputs at establishment (year 0); Year 9: Quantity; Year 10: Unit; Year 11: Price per unit; Year 12: Unit; Year 13: Total
Seeds | 35 | kg | Year 1: 3; Year 2: USD; Year 3: 105; Year 4: USD; Year 8: Planting corn; Year 9: 15; Year 10: kg; Year 11: 3; Year 12: USD; Year 13: 45; Year 14: USD
Fertilizer | 150 | kg | Year 1: 0.63; Year 2: USD; Year 3: 94.5; Year 4: USD; Year 8: Planting soybean; Year 9: 40; Year 10: kg; Year 11: 1.5; Year 12: USD; Year 13: 60; Year 14: USD
Herbicides/Insecticides | 3 | liters | Year 1: 0.16; Year 2: USD; Year 3: 0.48; Year 4: USD; Year 8: Herbicides/Insecticides; Year 10: liters; Year 12: USD; Year 13: 0; Year 14: USD
Tools | 1 | Units | Year 1: 10; Year 2: USD; Year 3: 10; Year 4: USD; Year 8: Tools; Year 9: 5; Year 10: Units; Year 11: 7.5; Year 12: USD; Year 13: 37.5; Year 14: USD
Sum of Investments/Materials |  |  | Year 3: 209.98; Year 4: USD; Year 8: Sum of Investments/Materials; Year 13: 142.5; Year 14: USD
Labor cost | 160 | days | Year 1: 3; Year 2: USD; Year 3: 480; Year 4: USD; Year 8: Labor inputs; Year 9: 201; Year 10: days; Year 11: 3; Year 12: USD; Year 13: 603; Year 14: USD
SUM FOR ESTABLISHMENT COSTS |  |  | Year 3: 689.98; Year 4: USD; Year 8: Sum of establishment costs; Year 13: 745.5; Year 14: USD
Yields/Prices |  |  | Year 8: Yields/Prices
Revenues from harvest/Sale of Products | 5500 | kg/ha/year | Year 1: 0.1625; Year 2: USD; Year 3: 893.75; Year 4: USD; Year 8: Revenues from harvest/Sale of Products; Year 10: kg/ha/year; Year 12: USD; Year 13: 0; Year 14: USD
Inputs at management (from year 1 onwards) | Quantity | Unit | Year 1: Price per unit; Year 2: Unit; Year 8: Inputs at management (from year 1 onwards); Year 9: Quantity; Year 10: Unit; Year 11: Price per unit; Year 12: Unit
Seeds | 40 | kg | Year 1: 3; Year 2: USD; Year 3: 120; Year 4: USD; Year 8: Planting corn; Year 9: 15; Year 10: Units; Year 11: 3; Year 12: USD; Year 13: 45; Year 14: USD
Fertilizer | 150 | kg | Year 1: 0.63; Year 2: USD; Year 3: 94.5; Year 4: USD; Year 8: Planting soybean; Year 9: 40; Year 10: kg; Year 11: 1.5; Year 12: USD; Year 13: 60; Year 14: USD
Herbicides/Insecticides | 3 | liters | Year 1: 0.16; Year 2: USD; Year 3: 0.48; Year 4: USD; Year 8: Herbicides/Insecticides; Year 10: liters; Year 12: USD; Year 13: 0; Year 14: USD
Tools | 1 | Units | Year 1: 10; Year 2: USD; Year 3: 10; Year 4: USD; Year 8: Tools; Year 9: 3; Year 10: Units; Year 11: 5; Year 12: USD; Year 13: 15; Year 14: USD
Sum Investments/Materials |  |  | Year 3: 224.98; Year 4: USD; Year 8: Sum Investments/Materials; Year 13: 120; Year 14: USD
Labor cost | 140 | days/yr | Year 1: 3; Year 2: USD; Year 3: 420; Year 4: USD; Year 8: Labor inputs; Year 9: 180; Year 10: days/yr; Year 11: 3; Year 12: USD; Year 13: 540; Year 14: USD
SUM OF ANNUAL COSTS |  |  | Year 3: 644.98; Year 4: USD; Year 8: Sum of annual costs; Year 13: 660; Year 14: USD
Yields/Prices |  |  | Year 8: Yields/Prices
Revenues from harvest/Sale of Products | 4700 | kg/ha/year | Year 1: 0.16; Year 2: USD; Year 3: 752; Year 4: USD; Year 8: Revenues from corn; Year 9: 3500; Year 10: kg/ha/year; Year 11: 0.1625; Year 12: USD; Year 13: 568.75; Year 14: USD
[10 empty] | Revenues from cashcrop | 1200 | kg/ha/year | 0.3125 | USD | 375 | USD
Seuqential cropping with cashcrops (soybean, peanut..) - 2yr roation
[10 empty] | Inputs at establishment (year 0) | Quantity | Unit | Price per unit | Unit | Total
[10 empty] | Planting corn | 35 | kg | 3 | USD | 105 | USD
[10 empty] | Planting soybean |  | kg |  | USD | 0 | USD
[10 empty] | Herbicides/Insecticides |  | liters |  | USD | 0 | USD
[10 empty] | Tools | 5 | Units | 7.5 | USD | 37.5 | USD
[10 empty] | Sum of Investments/Materials |  |  |  |  | 142.5 | USD
[10 empty] | Labor inputs | 166 | days | 3 | USD | 498 | USD
[10 empty] | Sum of establishment costs |  |  |  |  | 640.5 | USD
Yields/Prices
[10 empty] | Revenues from harvest/Sale of Products | 4100 | kg/ha/year | 0.16 | USD | 656 | USD
[10 empty] | Inputs at management (from year 1 onwards) | Quantity | Unit | Price per unit | Unit
[10 empty] | Planting corn |  | Units |  | USD | 0 | USD
[10 empty] | Planting cashcrops | 45 | kg | 1.5 | USD | 67.5 | USD
[10 empty] | Herbicides/Insecticides |  | liters |  | USD | 0 | USD
[10 empty] | Tools | 3 | Units | 5 | USD | 15 | USD
[10 empty] | Sum Investments/Materials |  |  |  |  | 82.5 | USD
[10 empty] | Labor inputs | 171 | days/yr | 3 | USD | 513 | USD
[10 empty] | Sum of annual costs |  |  |  |  | 595.5 | USD
Yields/Prices
[10 empty] | Revenues from corn |  | kg/ha/year |  | USD |  | USD
[10 empty] | Revenues from cashcrop | 2000 | kg/ha/year | 0.5 | USD | 1000 | USD
BAU - Unsustainable maize cultivation
Costs |  | Unit | Year 1: Year
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Establishment Cost |  | USD/ha | 209.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98 | 224.98
Labor Cost |  | USD/ha | 480 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420 | 420
Total cost |  | USD/ha | 689.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98 | 644.98
Revenues |  | Unit
Total revenues |  | USD/ha | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752 | 752
Cashflows
Annual Cashflow |  | USD/ha | 62.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 107.02 | 105.52
Cummulative Cashflow |  | USD/ha | 62.02 | 169.04 | 276.06 | 383.08 | 490.1 | 597.12 | 704.14 | 811.16 | 918.18 | 1025.2 | 1132.22 | 1239.24 | 1346.26 | 1453.28 | 1560.3 | 1667.32 | 1774.34 | 1881.36 | 1988.38 | 2095.4 | 2202.42 | 2309.44 | 2416.46 | 2523.48 | 2630.5 | 2737.52 | 2844.54 | 2951.56 | 3058.58 | 3165.6
NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  | NPV 20yrs | #REF!
|  |  | NPV 30yrs | #REF!
IRR |  |  | Year 1: IRR 10yrs; Year 2: #NUM!
|  |  | IRR 20yrs | #NUM!
|  |  | IRR 30yrs | #NUM!
PAM - Intercropping (mix of corn and cashcrop, e.g. soybean/peanut)
Costs |  | Unit | Year 1: Year
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Establishment Cost |  | USD/ha | 142.5 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
Labor Cost |  | USD/ha | 603 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | AVG cost
Total cost |  | USD/ha | 745.5 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 660 | 662.85
Revenues |  | Unit
Total revenues |  | USD/ha | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75 | 943.75
Cashflows
Annual Cashflow |  | USD/ha | 198.25 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 283.75 | 280.9
Cummulative Cashflow |  | USD/ha | 198.25 | 482 | 765.75 | 1049.5 | 1333.25 | 1617 | 1900.75 | 2184.5 | 2468.25 | 2752 | 3035.75 | 3319.5 | 3603.25 | 3887 | 4170.75 | 4454.5 | 4738.25 | 5022 | 5305.75 | 5589.5 | 5873.25 | 6157 | 6440.75 | 6724.5 | 7008.25 | 7292 | 7575.75 | 7859.5 | 8143.25 | 8427
NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  | NPV 20yrs | #REF!
|  |  | NPV 30yrs | #REF!
IRR |  |  | Year 1: IRR 10yrs; Year 2: #NUM!
|  |  | IRR 20yrs | #NUM!
|  |  | IRR 30yrs | #NUM!
PAM - Seuqential cropping with cashcrops (soybean, peanut..) - 2yr roation
Costs |  | Unit | Year 1: Year
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Establishment Cost |  | USD/ha | 142.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5 | 82.5 | 142.5
Labor Cost |  | USD/ha | 498 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | 513 | 498 | AVG cost
Total cost |  | USD/ha | 640.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 595.5 | 640.5 | 619.5
Revenues |  | Unit
Total revenues |  | USD/ha | 656 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 1000 | 656 | 816.5333
Cashflows
Annual Cashflow |  | USD/ha | 15.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 404.5 | 15.5 | 197.0333
Cummulative Cashflow |  | USD/ha | 15.5 | 31 | 435.5 | 451 | 855.5 | 871 | 1275.5 | 1291 | 1695.5 | 1711 | 2115.5 | 2131 | 2535.5 | 2551 | 2955.5 | 2971 | 3375.5 | 3391 | 3795.5 | 3811 | 4215.5 | 4231 | 4635.5 | 4651 | 5055.5 | 5071 | 5475.5 | 5491 | 5895.5 | 5911
NPV |  |  | Year 1: NPV 10yrs; Year 2: #REF!
|  |  | NPV 20yrs | #REF!
|  |  | NPV 30yrs | #REF!
IRR |  |  | Year 1: IRR 10yrs; Year 2: #NUM!
|  |  | IRR 20yrs | #NUM!
|  |  | IRR 30yrs | #NUM!