## Instructions
The following considerations are important when populating the budget:
Title Lists
Before filling out the “Detailed Budget Plan” Sheet, please populate the title data in the “Title List” Sheet.
Fill out the actual names of the Components; Outputs; and List of Funding Sources. An indicative list of Budget Categories has already been provided.
Please use this list as much as possible, however if list does not adequately address, kindly add onto the list where appropriate.
The information captured in the “Title List” will feed into the drop down lists in the “Detailed Budget Plan” Sheet.
Detailed Budget Plan
The detailed breakdown of the project budget is populated in this sheet.
The Component; Output; Funding Source; and Budget Categories fields are to be populated from drop-down lists.
The data for the drop-down lists is based on the data entered in the “Title List” Sheet.
Please insert/delete rows/columns under the Component; Output; Activity; Funding Source and Budget Categories as appropriate.
Please provide the assumptions and basis of how unit cost and quantities are arrived under the Budget Notes field.
If the space provided is not enough, insert an appropriate reference and enter the detailed comments in the "Detailed budget Notes" Sheet
Detailed Budget Notes
Detailed comments on the assumptions/estimates underlying the Unit Cost/ Quantities and justifications should be provided in this sheet. Please provide as much details as possible.
Project Management Cost
Please include the Project management costs (PMC) under this component and provide details of PMC.
Project management costs (PMC) are the direct administrative costs incurred to execute a project. They should cover only incremental costs incurred due
to the GCF contribution. In most cases, these costs are directly related to the support of a dedicated project management unit (PMU) which manages
the day to day execution related activities of the project.
General Principles for PMC costs:
1. The percentage of PMC financed by GCF should not be more than the percentage share of the overall budget financed by GCF.
2. PMC budget thresholds:
> PMC exceeding 5 per cent (5%) for a funding proposal exceeding USD 3 million will require detailed documentation supporting the entire PMC budget.
> PMC exceeding 7.5 per cent (7.5%) for the proposals up to USD 3 million will require detailed documentation and justification supporting the entire PMC budget.
3. Indicative list of eligible project management costs:
> Project staffing and consultants: Project manager, Project Assistant, Procurement personnel, Finance personnel & Support/admin personnel.
> Other direct costs: Office equipment, Mission related travel cost of the PMU, Project management systems and information technology,
Office supplies, Audit cost, etc.
Please note that the examples provided are simplified for illustrative purposes only.
Thus, please regard the examples as a guidance, not binding examples.
Simplified Approval Process - Budget Preparation Guidelines

## Dashboard (hidden)
Annex 3 - Budget Plan
Brief Project/ Programme Information
Project/ Programme Title: | [7 empty] | Values
Country(ies) | [6 empty] | Component | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total Budget
Accredited Entity | [6 empty] | Component 1 | 70000 | 250000 | 350000 | 100000 | 180000 | 950000
Budget Currency | USD/GBP/JPY/EUR | [5 empty] | Component 2 | 40000 | 30000 | 30000 | 50000 | 50000 | 200000
Date of Submission | [6 empty] | Component 3 | 20000 | 30000 | 40000 | 60000 | 50000 | 200000
[7 empty] | Project Management Cost | 30000 | 40000 | 40000 | 30000 | 10000 | 150000
[7 empty] | (blank) | [5 empty] | 0
[7 empty] | Grand Total | 160000 | 350000 | 460000 | 240000 | 290000 | 1500000
Output | (All) |  |  |  |  | Component | (All)
Sum of Total Cost | Funding Source |  |  |  |  | Sum of Total Cost | Funding Source
Component | GCF | Grand Total |  |  |  | Budget Categories | GCF | Grand Total
Component 1 | 150000 | 150000 |  |  |  | Consultant - Individual - International | 150000 | 150000
Grand Total | 150000 | 150000 |  |  |  | Grand Total | 150000 | 150000
Sum of Total Cost | Column Labels
Row Labels | Co-Financer 1 | Co-Financer 2 | GCF | (blank) | Grand Total
Output 1.1 |  |  | 800000 |  | 800000
Output 1.2 | 200000 |  |  |  | 200000
Output 2.1 |  | 200000 | 150000 |  | 350000
PMC |  |  | 150000 |  | 150000
(blank) |  |  |  | 0 | 0
Grand Total | 200000 | 200000 | 1100000 | 0 | 1500000
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Detailed Budget Plan
Project Name: Building resilience of urban populations with ecosystem-based solutions in Lao PDR
Budget: 11,500,000
[5 empty] | Detailed Budget |  |  |  | Annual Budget | [5 empty] | **Budget Notes
3 Jul 2019
Component | Output | Activity | Funding Source | Budget Categories | Unit | # of Unit | Unit Cost | Total Cost | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total Budget |  |  | prev version of the budget
Component 1. Technical and institutional capacity building to plan, design, implement and maintain integrated urban Ecosystems-based Adaptation (EbA) interventions for the reduction of climate change-induced flooding | Output 1.1 Strengthening of institutional capacity for integrated flood risk management and implementation of urban ecosystems-based adaptation and males and females with increased awareness of climate threats | Activity 1.1.1 Build the capacity of national and local representatives for using urban EbA to manage climate change-induced flooding. | GCF | Consultant - Individual - International | Days | 60 | 700 | 42000 | 14000 | 7000 | 7000 | 7000 | 7000 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Days | 60 | 700 | 42000 | 14000 | 7000 | 7000 | 7000 | 7000 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Salary | 1 | 18000 | 18000 | 3600 | 3600 | 3600 | 3600 | 3600 | 18000 | A1 | TRUE | 18000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Salary | 1 | 10000 | 10000 | 2000 | 2000 | 2000 | 2000 | 2000 | 10000 | A2 | TRUE | 10000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 1 | 50000 | 50000 | 50000 |  |  |  |  | 50000 | A4 |  | 50000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Salary | 5 | 3000 | 15000 | 3000 | 3000 | 3000 | 3000 | 3000 | 15000 | A2 | TRUE | 15000 | TRUE | 0
|  |  | MONRE | Consultant - Individual - Local | Salary | 5 | 3000 | 15000 | 3000 | 3000 | 3000 | 3000 | 3000 | 15000 | A2 | TRUE | 15000 | TRUE | 0
|  |  | MONRE | Materials & Goods | Training materials | 4 | 1000 | 4000 | 2000 |  | 2000 |  |  | 4000 | A3 | TRUE | 4000 | TRUE | 0
|  |  | MONRE | Materials & Goods | Training material | 4 | 1000 | 4000 | 2000 |  | 2000 |  |  | 4000 | A3 | TRUE | 4000 | TRUE | 0
|  |  | GCF | Travel | Flights | 5 | 1500 | 7500 | 4500 | 0 | 3000 |  |  | 7500 | A5 | TRUE | 7500 | TRUE | 0
|  |  | GCF | Travel | Flights | 5 | 1500 | 7500 | 4500 | 0 | 3000 |  |  | 7500 | A5 | TRUE | 7500 | TRUE | 0
|  |  | GCF | Workshop/Training | Workshops | 16 | 3750 | 60000 | 15000 | 15000 | 15000 | 15000 | 0 | 60000 | A6 | TRUE | 60000 | TRUE | 0
|  |  | GCF | Workshop/Training | Workshops | 16 | 3750 | 60000 | 15000 | 15000 | 15000 | 15000 | 0 | 60000 | A6 | TRUE | 60000 | TRUE | 0
|  |  | GCF | Workshop/Training | Exchange trip | 1 | 52800 | 52800 |  | 52800 |  |  |  | 52800 | A6 | TRUE | 52800 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 32968.2046 | 6593.6409 | 6593.6409 | 6593.6409 | 6593.6409 | 6593.6409 | 32968.2046 | A8 | TRUE | 32968.2046 | TRUE | 0
|  | Activity 1.1.2 Establish a national knowledge hub that produces and disseminates information on urban EbA interventions locally, regionally and internationally. | GCF | Consultant - Individual - International | Days | 60 | 700 | 42000 | 14000 | 7000 | 7000 | 7000 | 7000 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Days | 40 | 700 | 28000 | 7000 | 7000 | 7000 | 7000 |  | 28000 | A1 | TRUE | 28000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Salary | 5 | 45000 | 225000 | 45000 | 45000 | 45000 | 45000 | 45000 | 225000 | A1 | TRUE | 225000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 300 | 200 | 60000 | 12000 | 12000 | 12000 | 12000 | 12000 | 60000 | A2 | TRUE | 60000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 90 | 200 | 18000 | 18000 |  |  |  |  | 18000 | A2 | TRUE | 18000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 60 | 300 | 18000 | 18000 |  |  |  |  | 18000 | A2 | TRUE | 18000 | TRUE | 0
|  |  | GCF | Materials & Goods | Equipment | 1 | 50000 | 50000 | 50000 |  |  |  |  | 50000 | A3 | TRUE | 50000 | TRUE | 0
|  |  | MONRE | Materials & Goods | Equipment | 1 | 5000 | 5000 | 5000 |  |  |  |  | 5000 | A3 | TRUE | 5000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Knowledge fund | 1 | 500000 | 500000 | 100000 | 100000 | 100000 | 100000 | 100000 | 500000 | A4 | TRUE | 500000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Days | 400 | 300 | 120000 | 24000 | 24000 | 24000 | 24000 | 24000 | 120000 | A4 | TRUE | 120000 | TRUE | 0
|  |  | GCF | Travel | DSA | 40 | 194 | 7760 | 1940 | 1940 | 1940 | 1940 |  | 7760 | A5 | TRUE | 7760 | TRUE | 0
|  |  | GCF | Travel | DSA | 60 | 194 | 11640 | 3880 | 1940 | 1940 | 1940 | 1940 | 11640 | A5 | TRUE | 11640 | TRUE | 0
|  |  | GCF | Travel | Flights | 2 | 1500 | 3000 | 1500 |  |  |  | 1500 | 3000 | A5 | TRUE | 3000 | TRUE | 0
|  |  | GCF | Travel | DSA | 300 | 30 | 9000 | 1800 | 1800 | 1800 | 1800 | 1800 | 9000 | A5 | TRUE | 9000 | TRUE | 0
|  |  | GCF | Travel | DSA | 90 | 30 | 2700 | 540 | 540 | 540 | 540 | 540 | 2700 | A5 | TRUE | 2700 | TRUE | 0
|  |  | GCF | Travel | DSA | 60 | 30 | 1800 | 1800 |  |  |  |  | 1800 | A5 | TRUE | 1800 | TRUE | 0
|  |  | MONRE | Workshop/Training | Meeting | 1 | 1000 | 1000 | 1000 |  |  |  |  | 1000 | A6 | TRUE | 1000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 110835.3131 | 22167.0626 | 22167.0626 | 22167.0626 | 22167.0626 | 22167.0626 | 110835.3131 | A8 | TRUE | 110835.3131 | TRUE | 0
|  | Activity 1.1.3 Conduct awareness-raising campaigns in each of the four target cities for communities and the private sector on urban EbA and flood management. | GCF | Consultant - Individual - Local | Days | 80 | 300 | 24000 | 24000 |  |  |  |  | 24000 | A2 | TRUE | 24000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 300 | 300 | 90000 | 18000 | 18000 | 18000 | 18000 | 18000 | 90000 | A2 | TRUE | 90000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Months | 30 | 2500 | 75000 | 15000 | 15000 | 15000 | 15000 | 15000 | 75000 | A2 | TRUE | 75000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Salary | 1 | 18000 | 18000 | 3600 | 3600 | 3600 | 3600 | 3600 | 18000 | A1 | TRUE | 18000 | TRUE | 0
|  |  | MONRE | Materials & Goods | Campaign materials | 4 | 50000 | 200000 | 200000 |  |  |  |  | 200000 | A3 | TRUE | 200000 | TRUE | 0
|  |  | GCF | Travel | DSA | 80 | 30 | 2400 | 2400 |  |  |  |  | 2400 | A5 | TRUE | 2400 | TRUE | 0
|  |  | GCF | Travel | DSA | 300 | 30 | 9000 | 1800 | 1800 | 1800 | 1800 | 1800 | 9000 | A5 | TRUE | 9000 | TRUE | 0
|  |  | GCF | Workshop/Training | Meetings | 40 | 3750 | 150000 | 30000 | 30000 | 30000 | 30000 | 30000 | 150000 | A6 | TRUE | 150000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 57121.0372 | 11424.2074 | 11424.2074 | 11424.2074 | 11424.2074 | 11424.2074 | 57121.0372 | A8 | TRUE | 57121.0372 | TRUE | 0
| Subtotal for Output 1.1. | [6 empty] | 2260024.5549 | 773044.911 | 418204.911 | 375404.911 | 365404.911 | 327964.911 | 2260024.5549 |  | TRUE | 2260024.5549 | TRUE | 0
| Output 1.2 Integrated Climate-resilient Flood Management Strategies and urban EbA guidelines developed for Vientiane, Paksan, Savannakhet and Pakse, and effective Flood Risk Management Committees as coordination mechanisms | Activity 1.2.1 Conduct economic valuation of urban ecosystem services. | GCF | Professional Services – Companies/Firm | Contract | 1 | 1000000 | 1000000 |  | 600000 | 400000 |  |  | 1000000 | A4 | TRUE | 1000000 | TRUE | 0
|  |  | MONRE | Materials & Goods | Equipment | 1 | 7500 | 7500 |  | 7500 |  |  |  | 7500 | A3 | TRUE | 7500 | TRUE | 0
|  |  | GCF | Workshop/Training | Workshops | 1 | 20000 | 20000 |  |  | 20000 |  |  | 20000 | A6 | TRUE | 20000 | TRUE | 0
|  |  | GCF | Workshop/Training | Workshops | 1 | 30000 | 30000 |  | 30000 |  |  |  | 30000 | A6 | TRUE | 30000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 113460.2278 | 22692.0456 | 22692.0456 | 22692.0456 | 22692.0456 | 22692.0456 | 113460.2278 | A8 | TRUE | 113460.2278 | TRUE | 0
|  | Activity 1.2.2 Conduct hydrological assessments and climate risk assessments to inform climate change adaptation solutions for flood management in Vientiane, Paksan, Savannakhet and Pakse. | GCF | Consultant - Individual - Local | Days | 80 | 300 | 24000 | 21000 | 3000 |  |  |  | 24000 | A2 | TRUE | 24000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 320 | 300 | 96000 | 90000 | 6000 |  |  |  | 96000 | A2 | TRUE | 96000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 4 | 350000 | 1400000 | 280000 | 280000 | 280000 | 280000 | 280000 | 1400000 | A4
|  |  | GCF | Professional Services – Companies/Firm | Contract | 4 | 100000 | 400000 | 80000 | 80000 | 80000 | 80000 | 80000 | 400000 | A4
|  |  | GCF | Materials & Goods | Software licenses | 5 | 12000 | 60000 | 60000 |  |  |  |  | 60000 | A3 | TRUE | 60000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 1 | 67580 | 67580 | 67580 |  |  |  |  | 67580 | A4 | TRUE | 67580 | TRUE | 0
|  |  | GCF | Travel | DSA | 80 | 30 | 2400 | 2100 | 300 |  |  |  | 2400 | A5 | TRUE | 2400 | TRUE | 0
|  |  | GCF | Travel | DSA | 320 | 30 | 9600 | 9000 | 600 |  |  |  | 9600 | A5 | TRUE | 9600 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 27133.4976 | 5426.6995 | 5426.6995 | 5426.6995 | 5426.6995 | 5426.6995 | 27133.4976 | A8 | TRUE | 27133.4976 | TRUE | 0
|  | Activity 1.2.3 Develop the ICFMS and mainstream climate change and urban EbA into relevant policies, guidelines and plans. | GCF | Consultant - Individual - International | Salary | 1 | 18000 | 18000 | 3600 | 3600 | 3600 | 3600 | 3600 | 18000 | A1 | TRUE | 18000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Days | 320 | 700 | 224000 | 105000 | 105000 |  |  | 14000 | 224000 | A1 |  | 224000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 480 | 300 | 144000 | 60000 | 60000 |  |  | 24000 | 144000 | A2 |  | 144000 | TRUE | 0
|  |  | GCF | Travel | DSA | 320 | 194 | 62080 | 62080 |  |  |  |  | 62080 | A5 |  | 62080 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Salary | 1 | 10000 | 10000 | 2000 | 2000 | 2000 | 2000 | 2000 | 10000 | A2 | TRUE | 10000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Salary | 5 | 1500 | 7500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7500 | A2 | TRUE | 7500 | TRUE | 0
|  |  | MONRE | Consultant - Individual - Local | Salary | 5 | 1500 | 7500 | 1500 | 1500 | 1500 | 1500 | 1500 | 7500 | A2 | TRUE | 7500 | TRUE | 0
|  |  | MONRE | Workshop/Training | Workshops | 8 | 3750 | 30000 | 30000 |  |  |  |  | 30000 | A6 | TRUE | 30000 | TRUE | 0
|  |  | MONRE | Workshop/Training | Meetings | 4 | 3750 | 15000 | 15000 |  |  |  |  | 15000 | A6 | TRUE | 15000 | TRUE | 0
|  |  | MONRE | Workshop/Training | Meetings | 1 | 3750 | 3750 | 3750 |  |  |  |  | 3750 | A6 | TRUE | 3750 | TRUE | 0
|  |  | MONRE | Workshop/Training | Meetings | 4 | 3750 | 15000 | 7500 | 7500 |  |  |  | 15000 | A6 | TRUE | 15000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 191617.7652 | 38323.553 | 38323.553 | 38323.553 | 38323.553 | 38323.553 | 191617.7652 | A8 | TRUE | 191617.7652 | TRUE | 0
|  | Activity 1.2.4 Develop national urban EbA guidelines for Laos. | GCF | Consultant - Individual - International | Days | 60 | 700 | 42000 | 14000 | 14000 |  |  | 14000 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Days | 80 | 700 | 56000 | 56000 |  |  |  |  | 56000 | A1
|  |  | GCF | Consultant - Individual - International | Days | 60 | 700 | 42000 | 14000 | 14000 |  |  | 14000 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 120 | 300 | 36000 | 15000 | 15000 |  |  | 6000 | 36000 | A2 | TRUE | 36000 | TRUE | 0
|  |  | MONRE | Workshop/Training | Annual PSC meetings | 5 | 5000 | 25000 | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | A6 | TRUE | 25000 | TRUE | 0
|  |  | GCF | Travel | DSA | 60 | 194 | 11640 | 11640 |  |  |  |  | 11640 | A5 | TRUE | 11640 | TRUE | 0
|  |  | GCF | Travel | DSA | 60 | 194 | 11640 | 3880 | 3880 |  |  | 3880 | 11640 | A5 | TRUE | 11640 | TRUE | 0
|  |  | GCF | Travel | DSA | 480 | 30 | 14400 | 4800 | 4800 |  |  | 4800 | 14400 | A5 | TRUE | 14400 | TRUE | 0
|  |  | GCF | Travel | DSA | 80 | 194 | 15520 | 15520 |  |  |  |  | 15520 | A5
|  |  | GCF | Travel | DSA | 120 | 30 | 3600 | 1500 | 1500 |  |  | 600 | 3600 | A5 | TRUE | 3600 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 61940.7504 | 12388.1501 | 12388.1501 | 12388.1501 | 12388.1501 | 12388.1501 | 61940.7504 | A8 |  | 61940.7504 | TRUE | 0
| Subtotal for Output 1.2. | [6 empty] | 4305862.241 | 1121780.4482 | 1325510.4482 | 872430.4482 | 452430.4482 | 533710.4482 | 4305862.241 |  | TRUE | 4305862.241 | TRUE | 0
GCF Subtotal for Component 1 |  |  | GCF |  |  |  |  | 5638060 | 1500060 | 1600200 | 1115320 | 689320 | 733160 |  |  |  | 0 | TRUE | 0
MONRE Subtotal for Component 1 |  |  | MONRE |  |  |  |  | 927826.796 | [8 empty] | 0 | TRUE | 0
Subtotal for Component 1 | [7 empty] | 6565886.796 | 1894825.3592 | 1743715.3592 | 1247835.3592 | 817835.3592 | 861675.3592 | 6565886.796 |  | TRUE | 6565886.796 | TRUE | 0
Component 2. Rehabilitation and protection of ecosystem in response to climate variability and change | Output 2.1 Area of wetland restored contributing to flood reduction and sustainable management of the Nong Peung wetland in Paksan | Activity 2.1.1 Develop a wetland management plan for Nong Peung wetland in Paksan. | GCF | Materials & Goods | Monitoring equipment | 1 | 30000 | 30000 | 30000 |  |  |  |  | 30000 | A3 | TRUE | 30000 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Days | 35 | 700 | 24500 |  | 24500 |  |  |  | 24500 | A1
|  |  | GCF | Consultant - Individual - International | Salary | 1 | 42000 | 42000 | 8400 | 8400 | 8400 | 8400 | 8400 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 80 | 300 | 24000 |  | 24000 |  |  |  | 24000 | A2
|  |  | GCF | Consultant - Individual - Local | Salary | 1 | 10000 | 10000 | 2000 | 2000 | 2000 | 2000 | 2000 | 10000 | A2 | TRUE | 10000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 1 | 65000 | 65000 | 13000 | 13000 | 13000 | 13000 | 13000 | 65000 | A4 | TRUE | 65000 | TRUE | 0
|  |  | MONRE | Workshop/Training | Workshops | 16 | 3750 | 60000 | 60000 |  |  |  |  | 60000 | A6 | TRUE | 60000 | TRUE | 0
|  |  | MONRE | Workshop/Training | Meeting | 2 | 3750 | 7500 | 7500 |  |  |  |  | 7500 | A6 | TRUE | 7500 | TRUE | 0
|  |  | MONRE | Workshop/Training | Workshops | 4 | 3750 | 15000 | 15000 |  |  |  |  | 15000 | A6 |  | 15000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 33346.0636 | 6669.2127 | 6669.2127 | 6669.2127 | 6669.2127 | 6669.2127 | 33346.0636 | A8 | TRUE | 33346.0636 | TRUE | 0
|  | Activity 2.1.2 Rehabilitate the Nong Peung wetland. | GCF | Professional Services – Companies/Firm | Contract | 1 | 50000 | 50000 | 50000 |  |  |  |  | 50000 | A4 |  | 50000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 1 | 800000 | 800000 |  | 200000 | 200000 | 200000 | 200000 | 800000 | A4 | TRUE | 800000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 1 | 170000 | 170000 | 34000 | 34000 | 34000 | 34000 | 34000 | 170000 | A4
|  |  | GCF | Workshop/Training | Workshops | 20 | 3750 | 75000 | 15000 | 15000 | 15000 | 15000 | 15000 | 75000 | A6 | TRUE | 75000 | TRUE | 0
|  |  | GCF | Travel | DSA | 35 | 194 | 6790 |  | 6790 |  |  |  | 6790 | A5 | TRUE | 6790 | TRUE | 0
|  |  | GCF | Travel | DSA | 80 | 30 | 2400 |  | 2400 |  |  |  | 2400 | A5 | TRUE | 2400 | TRUE | 0
|  |  | GCF | O&M | O&M | 3 | 8000 | 24000 | 0 | 0 | 8000 | 8000 | 8000 | 24000 | A7 | TRUE | 24000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 96142.0217 | 19228.4043 | 19228.4043 | 19228.4043 | 19228.4043 | 19228.4043 | 96142.0217 | A8 | TRUE | 96142.0217 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | MTE contract | 1 | 95450 | 95450 | 19090 | 19090 | 19090 | 19090 | 19090 | 95450 | A1 | TRUE | 95450 | TRUE | 0
| Subtotal Output 2.1. | [6 empty] | 1631128.0853 | 279887.6171 | 375077.6171 | 325387.6171 | 325387.6171 | 325387.6171 | 1631128.0853 |  | TRUE | 1521128.0853 | TRUE | -110000
| Output 2.2 Area of urban streams restored contributing to flood reduction and sustainable management of urban streams in Savannakhet and Pakse | Activity 2.2.1 Restore natural urban streams in Savannakhet and Pakse. | GCF | Consultant - Individual - International | Salary | 1 | 42000 | 42000 | 8400 | 8400 | 8400 | 8400 | 8400 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Materials & Goods | Vehicle | 1 | 60000 | 60000 | 60000 |  |  |  |  | 60000 | A3 | TRUE | 60000 | TRUE | 0
|  |  | MONRE | Materials & Goods | Vehicle maintenance | 5 | 2000 | 10000 | 2000 | 2000 | 2000 | 2000 | 2000 | 10000 | A3 | TRUE | 10000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 1 | 860000 | 860000 | 172000 | 172000 | 172000 | 172000 | 172000 | 860000 | A4 | TRUE | 860000 | TRUE | 0
|  |  | GCF | Travel | DSA | 60 | 194 | 11640 | 3880 | 1940 | 1940 | 1940 | 1940 | 11640 | A5 | TRUE | 11640 | TRUE | 0
|  |  | GCF | Travel | DSA | 60 | 30 | 1800 | 600 | 300 | 300 | 300 | 300 | 1800 | A5 | TRUE | 1800 | TRUE | 0
|  |  | GCF | Workshop/Training | Workshops | 20 | 3750 | 75000 | 15000 | 15000 | 15000 | 15000 | 15000 | 75000 | A6 | TRUE | 75000 | TRUE | 0
|  |  | GCF | O&M | O&M | 3 | 8600 | 25800 | 0 | 0 | 8600 | 8600 | 8600 | 25800 | A7 | TRUE | 25800 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 132274.796 | 26454.9592 | 26454.9592 | 26454.9592 | 26454.9592 | 26454.9592 | 132274.796 | A8 | TRUE | 132274.796 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | TE contract | 1 | 120750 | 120750 | 24150 | 24150 | 24150 | 24150 | 24150 | 120750 | A1 | TRUE | 120750 | TRUE | 0
|  | Activity 2.2.2 Develop management models for continued monitoring and management of drainage and streams. | GCF | Workshop/Training | Meetings | 5 | 3750 | 18750 | 18750 |  |  |  |  | 18750 | A6 | TRUE | 18750 | TRUE | 0
|  |  | GCF | Workshop/Training | Workshops | 10 | 3750 | 37500 | 7500 | 7500 | 7500 | 7500 | 7500 | 37500 | A6 | TRUE | 37500 | TRUE | 0
|  |  | GCF | Consultant - Individual - International | Days | 60 | 700 | 42000 | 14000 | 7000 | 7000 | 7000 | 7000 | 42000 | A1
|  |  | GCF | Consultant - Individual - International | Salary | 1 | 42000 | 42000 | 8400 | 8400 | 8400 | 8400 | 8400 | 42000 | A1 | TRUE | 42000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 60 | 300 | 18000 | 6000 | 3000 | 3000 | 3000 | 3000 | 18000 | A2
|  |  | GCF | Consultant - Individual - Local | Salary | 1 | 10000 | 10000 | 2000 | 2000 | 2000 | 2000 | 2000 | 10000 | A2 | TRUE | 10000 | TRUE | 0
|  |  | GCF | Materials & Goods | Monitoring equipment | 2 | 30000 | 60000 | 60000 |  |  |  |  | 60000 | A3
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 12385.9392 | 2477.1878 | 2477.1878 | 2477.1878 | 2477.1878 | 2477.1878 | 12385.9392 | A8 | TRUE | 12385.9392 | TRUE | 0
| Subtotal Output 2.2. | [6 empty] | 1579900.7352 | 431612.147 | 280622.147 | 289222.147 | 289222.147 | 289222.147 | 1579900.7352 |  | TRUE | 1689900.7352 | TRUE | 110000
| Output 2.3 Area of permeable paving solutions installed in public areas contributing to flood reduction in Vientiane, Paksan, Savannakhet and Pakse | Activity 2.3.1 Design permeable paving solutions for public areas in Vientiane, Paksan, Savannakhet and Pakse. | GCF | Consultant - Individual - International | Days | 40 | 700 | 28000 | 14000 | 10500 | 3500 |  |  | 28000 | A1 | TRUE | 28000 | TRUE | 0
|  |  | GCF | Consultant - Individual - Local | Days | 60 | 300 | 18000 | 6000 | 6000 | 6000 |  |  | 18000 | A2 | TRUE | 18000 | TRUE | 0
|  |  | GCF | Professional Services – Companies/Firm | Contract | 1 | 20000 | 20000 | 20000 |  |  |  |  | 20000 | A4 | TRUE | 20000 | TRUE | 0
|  |  | GCF | Travel | DSA | 40 | 194 | 7760 | 3880 | 2910 | 970 |  |  | 7760 | A5 | TRUE | 7760 | TRUE | 0
|  |  | GCF | Travel | DSA | 60 | 30 | 1800 | 600 | 600 | 600 |  |  | 1800 | A5 | TRUE | 1800 | TRUE | 0
|  |  | GCF | Workshop/Training | Workshops | 24 | 3750 | 90000 | 30000 | 30000 | 30000 |  |  | 90000 | A6 | TRUE | 90000 | TRUE | 0
|  |  | MONRE | Workshop/Training | Workshops | 4 | 3750 | 15000 | 0 | 0 | 15000 | 0 | 0 | 15000 | A6 | TRUE | 15000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 18145.2753 | 3629.0551 | 3629.0551 | 3629.0551 | 3629.0551 | 3629.0551 | 18145.2753 | A8 | TRUE | 18145.2753 | TRUE | 0
|  | Activity 2.3.2 Install permeable paving in public areas in Vientiane, Paksan, Savannakhet and Pakse. | GCF | Professional Services – Companies/Firm | Contract | 1 | 900000 | 900000 | 180000 | 180000 | 180000 | 180000 | 180000 | 900000 | A4 | TRUE | 900000 | TRUE | 0
|  |  | GCF | O&M | O&M | 3 | 9000 | 27000 | 0 | 0 | 9000 | 9000 | 9000 | 27000 | A7 | TRUE | 27000 | TRUE | 0
|  |  | MONRE | MONRE staff time contribution to activity |  |  |  | 97379.1082 | 19475.8216 | 19475.8216 | 19475.8216 | 19475.8216 | 19475.8216 | 97379.1082 | A8 | TRUE | 97379.1082 | TRUE | 0
| Subtotal Output 2.3. | [6 empty] | 1223084.3835 | 277584.8767 | 253114.8767 | 268174.8767 | 212104.8767 | 212104.8767 | 1223084.3835 |  | TRUE | 1223084.3835 | TRUE | 0
GCF Subtotal for Component 2 |  |  | GCF |  |  |  |  | 3936940 | 826650 | 828880 | 787850 | 746780 | 746780 |  |  |  | 0 | TRUE | 0
MONRE Subtotal for Component 2 |  |  | MONRE |  |  |  |  | 497173.204 | [8 empty] | 0 | TRUE | 0
Subtotal for Component 2 | [7 empty] | 4434113.204 | 989084.6408 | 908814.6408 | 882784.6408 | 826714.6408 | 826714.6408 | 4434113.204 |  | TRUE | 4434113.204 | TRUE | 0
Project Management Cost | PMC | Procurement and Financial Officer | GCF | PMC staff and personnel | Annual salary | 5 | 25000 | 125000 | 25000 | 25000 | 25000 | 25000 | 25000 | 125000 | PMU1 | GCF | 125000 | TRUE | 0
| PMC | Administrative Officer | GCF | PMC staff and personnel | Annual salary | 5 | 20000 | 100000 | 20000 | 20000 | 20000 | 20000 | 20000 | 100000 | PMU2 | GCF | 100000 | TRUE | 0
| PMC | Project Manager | GCF | PMC staff and personnel | Project Manager | 5 | 40000 | 200000 | 40000 | 40000 | 40000 | 40000 | 40000 | 200000 | PMU3 | GCF | 200000 | TRUE | 0
| PMC | The Project Director (PD) will be a senior MONRE staff member who will dedicate a proportion (20%) of their time to project director responsibilities. The cost to the project for the PD's time will be US$50,000 across 5 years. MONRE will cover this amount of the Project Director's time as part of MONRE's co-financing. | MONRE |  | 20% of Project Director's salary | 5 | 10000 | 50000 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | PMU4 | MONRE | 50000 | TRUE | 0
| PMC | Office space for five years in the PoNRE departments for use by focal points. This cost includes computers, photocopying, overheads etc. | MONRE | PMC staff and personnel | Office space | 5 | 5000 | 25000 | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | PMU5 | MONRE | 25000 | TRUE | 0
| Subtotal PMC | [6 empty] | 500000 | 100000 | 100000 | 100000 | 100000 | 100000 | 500000 |  | 0 | 500000 | TRUE | 0
Project Management Cost allocation
Subtotal | GCF | [6 empty] | 425000 | 85000 | 85000 | 85000 | 85000 | 85000
Subtotal | MONRE | [6 empty] | 75000 | 15000 | 15000 | 15000 | 15000 | 15000
Total PMC | [7 empty] | 500000
Subtotal GCF | [7 empty] | 10000000 | 2411710 | 2514080 | 1988170 | 1521100 | 1564940
Subtotal MONRE | [7 empty] | 1500000
Sum of GCF and MONRE contributions | [7 empty] | 11500000
Project total | [7 empty] | 11500000 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | 2) | GCF PMC | 425000 |  | 1) | GCF PMC | 425000
**Please provide the assumptions and basis of how unit cost and quantities are arrived. Please insert an appropriate reference as illustrated and enter the detailed comments in the "Detailed budget Notes" Sheet | [12 empty] | Total PMC | 500000 | 85% |  | GCF grant minus PMC | 9575000 | 4.439%
[7 empty] | C1 total | 6565886.796 | 59.69% |  |  |  | GCF contributions | 10000000
[7 empty] | C2 total | 4434113.204 | 40.31% |  |  |  | Total project cost | 11500000 | 86.96% |  |  | 500000
[7 empty] | Sum of components | 11000000 |  |  | 0 | [6 empty] | 11500000 | 4.348%
575000
[7 empty] | Output 1.1 | 2260024.5549 | 33.76% |  | 0
[12 empty] | A 1.1.1 | 420768.2046 | 387800 | 32968.2046
[12 empty] | A 1.1.2 | 1213735.3131 | 1102900 | 110835.3131
[12 empty] | A 1.1.3 | 625521.0372 | 568400 | 57121.0372
2260024.5549
[7 empty] | Output 1.2 | 4305862.241 | 66.24% |  | 0 |  |  |  | 0
[12 empty] | A 1.2.1 | 1170960.2278 | 1057500 | 113460.2278
[12 empty] | A 1.2.2 | 299133 | 2059580 | -1760447
[12 empty] | A 1.2.3 | 728447.7652 | 536830 | 191617.7652
[12 empty] | A 1.2.4 | 319740.7504 | 257800 | 61940.7504
2518281.7434
[7 empty] | Output 2.1 | 1631128.0853 | 33.23% |  | 0 |  |  |  | 0
[12 empty] | A 2.1.1 | 311346.0636 | 263000 | 48346.0636
[12 empty] | A 2.1.2 | 1319782.0217 | 1223640 | 96142.0217
1631128.0853
[7 empty] | Output 2.2 | 1579900.7352 | 37.12% |  | 0 |  |  |  | 0
[12 empty] | A 2.2.1 | 1339264.796 | 1206990 | 132274.796
[12 empty] | A 2.2.2 | 240635.9392 | 168250 | 72385.9392
1579900.7352
0
[7 empty] | Output 2.3 | 1223084.3835 | 29.65% |  | 0 |  |  |  | 0
[12 empty] | A 2.3.1 | 198705.2753 | 180560 | 18145.2753
[7 empty] | Sum of outputs | 11000000 |  |  | 0 | A 2.3.2 | 1024379.1082 | 927000 | 97379.1082
1223084.3835
-727830.4976
[13 empty] | 11000000 |  | -227580.4976
budget notes
[15 empty] | main budget table | calculated | written BN
[14 empty] | A1 | 1233700 | 1233700 | 1233700
[14 empty] | A2 | 730000 | 730000 | 730000
[14 empty] | A3 | 490500 | 490500 | 490500
[14 empty] | A4 | 6402580 | 6402580 | 6402580

## Detailed Budget Notes
Note
Consultant | To detail unit cost and duration of consultant(s) work and position
Equipment | Include machinery specification, equipment name, quantity, and unit cost in budget notes and how the unit cost is arrived.
Workshop | Include the number of workshops anticipated, number of people attending, number of days, target group, cost per work workshop, venue cost, etc.
Travel | Breakdown travel cost information by number of people and cost per person and separating DSA where applicable. Also please provide the reason why international travel is needed.
Professional Services | Please provide the details of the professional services needed, purpose of the services, and also the basis of the cost estimates.
Materials & Goods | Include material and goods specification, name, quantity, and unit cost in budget notes, and how the unit cost is arrived.
Office Supplies | Include office supplies' name, quantity, and unit cost in budget notes, and how the unit cost is arrived.
PMU | PMC percentage applies on the sub-total of components/activities.
Detailed Budget Notes | (important - prepared in conjunction with Budget Plan)
A1 | International consultants to support the implementation of the project
| Activity number and item description | Unit | Quantity | Unit cost (USD) | Total
| 1.1.1. International consultant to prepare and conduct trainings for national- and local-level decision-makers from MONRE, Ministry of Planning and Investment (MPI), Ministry of Public Works and Transport, Ministry of Agriculture and Forestry, provincial governments, and other relevant agencies on how to incorporate integrated climate-resilient flood management into development planning for the cities of Vientiane, Paksan, Savannakhet and Pakse. | Days | 60 | 700 | 42000
| 1.1.1. International consultant to prepare and conduct trainings for relevant national- and local-level technical staff on how to use urban EbA to reduce climate-induced flooding | Days | 60 | 700 | 42000
| 1.1.1. CTA to provide technical oversight of capacity building activities to be implemented under this Component. The salary for the CTA has been weighted according to the expected tine spent per Component. It is expected that 30% of the CTA's time will be spent providing oversight for activities to be implemented under Component 1. 30% of the total CTA salary (US$180,000) has therefore been allocated accordingly to relevant activities under Component 1. It should be noted that the CTA's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the CTA's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 18000 | 18000
| 1.1.2. International consultant to provide technical support to national and local government on the use of GIS for spatial analyses. This consultant will work in collaboration with the firm contracted to conduct the spatial surveys. | Days | 60 | 700 | 42000
| 1.1.2. International expert to assist with EbA curricula development | Days | 40 | 700 | 28000
| 1.1.2. Full-time Gender and M&E Officer contracted for the duration of the project | Salary | 5 | 45000 | 225000
| 1.1.3. CTA to provide technical oversight of capacity building activities to be implemented under this Component. The salary for the CTA has been weighted according to the expected tine spent per Component. It is expected that 30% of the CTA's time will be spent providing oversight for activities to be implemented under Component 1. 30% of the total CTA salary (US$180,000) has therefore been allocated accordingly to relevant activities under Component 1. It should be noted that the CTA's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the CTA's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 18000 | 18000
| 1.2.4. International expert to conduct a capacity needs assessment of major stakeholders on implementing sustainable land use planning | Days | 80 | 700 | 56000
| 1.2.3. CTA to provide technical oversight of capacity building activities to be implemented under this Component. The salary for the CTA has been weighted according to the expected tine spent per Component. It is expected that 30% of the CTA's time will be spent providing oversight for activities to be implemented under Component 1. 30% of the total CTA salary (US$180,000) has therefore been allocated accordingly to relevant activities under Component 1. It should be noted that the CTA's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the CTA's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 18000 | 18000
| 1.2.3. International expert to assist local consultant with developing ICFMS for the four target cities at 80 days per city. ICFMS will be informed by the results from the hydrological models. | Days | 320 | 700 | 224000
| 1.2.4. International expert to assist the local consultant with developing national urban EbA guidelines. | Days | 60 | 700 | 42000
| 1.2.4. International consultant to provide recommendations on national and local-level policy reform | Days | 60 | 700 | 42000
| 2.1.1. CTA to provide technical oversight during the implementation of EbA interventions and permeable paving solutions that will be implemented under Component 2. The salary for the CTA has been weighted according to the expected tine spent per component. It is expected that 70% of the CTA's time will be spent providing oversight for activities to be implemented under Component 2. 70% of the total CTA salary (US$180,000) has therefore been allocated accordingly to relevant activities under Component 2. It should be noted that the CTA's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the CTA's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 42000 | 42000
| 2.1.1. International consultant to assist the local consultant to develop a wetland management plan for the Nong Peung wetland in Paksan, including proposing measures to reduce encroachment of the wetland; establishing measures to curb the introduction and spread of invasive species; and promote sustainable soil extraction to the North of the wetland. | Days | 35 | 700 | 24500
| 2.1.2. International consultant to conduct Mid-Term Evaluation. This evaluation is for the entire project and is budgeted under this activity as it is one of the major physical interventions of the project. | MTE contract | 1 | 95450 | 95450
| 2.2.1. International consultant to conduct Terminal Evaluation. This evaluation is for the entire project but is budgeted under this activity as it is is one of the major physical interventions of the project. | TE contract | 1 | 120750 | 120750
| 2.2.2. International expert to assist the local consultant to develop a plan for the sustainable management of urban streams in Savannakhet and Pakse. | Days | 60 | 700 | 42000
| 2.2.1. CTA to provide technical oversight during the implementation of EbA interventions and permeable paving solutions that will be implemented under Component 2. The salary for the CTA has been weighted according to the expected tine spent per component. It is expected that 70% of the CTA's time will be spent providing oversight for activities to be implemented under Component 2. 70% of the total CTA salary (US$180,000) has therefore been allocated accordingly to relevant activities under Component 2. It should be noted that the CTA's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the CTA's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 42000 | 42000
| 2.2.2. CTA to provide technical oversight during the implementation of EbA interventions and permeable paving solutions that will be implemented under Component 2. The salary for the CTA has been weighted according to the expected tine spent per component. It is expected that 70% of the CTA's time will be spent providing oversight for activities to be implemented under Component 2. 70% of the total CTA salary (US$180,000) has therefore been allocated accordingly to relevant activities under Component 2. It should be noted that the CTA's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the CTA's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 42000 | 42000
| 2.3.1. International expert to assist with the design of permeable paving solutions, as well as site-specific O&M plans, for public areas in Vientiane, Paksan, Savannakhet and Pakse. | Days | 40 | 700 | 28000
| Subtotal |  |  |  | 1233700
A2 | Local consultants to support the implementation of the project
| Activity number and item description | Unit | Quantity | Unit cost (USD) | Total
| 1.1.1. Safeguards expert charged to Component 1 to ensure that all capacity building activities are gender-inclusive and undertaken in a socially appropriate manner. It is estimated that 50% of the expert's time will be spent overseeing activities that will be implemented under Component 1. It should be noted that the safeguards expert's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the safeguards expert's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 10000 | 10000
| 1.1.1. Contract two project focal points at US$3,000 annually. (GCF) | Salary | 5 | 3000 | 15000
| 1.1.1. Contract two project focal points at US$3,000 annually. (MONRE) | Salary | 5 | 3000 | 15000
| 1.1.2. Three national researchers for data collection from primary and secondary sources | Days | 300 | 200 | 60000
| 1.1.2. Three national researchers for ground-truthing spatial wetland and stream data | Days | 90 | 200 | 18000
| 1.1.2 Local consultant to conduct land-use survey from secondary government sources. | Days | 60 | 300 | 18000
| 1.1.3. Local consultant to design four awareness-raising campaigns for Vientiane, Paksan, Savannakhet and Pakse. | Days | 80 | 300 | 24000
| 1.1.3. Local consultant to implement four awareness-raising campaigns for Vientiane, Paksan, Savannakhet and Pakse. | Days | 300 | 300 | 90000
| 1.1.3. Contract local Communications Officer on a part-time basis for the implementation of the awareness raising campaigns in the four cities at US$2,500 per month for 30 months | Months | 30 | 2500 | 75000
| 1.2.2. Local consultant to conduct stakeholder consultations in each of the four cities at US$300 per day for 20 days per city | Days | 80 | 300 | 24000
| 1.2.2. Local consultant to develop national urban EbA guidelines for the four target cities at 80 days per city. | Days | 320 | 300 | 96000
| 1.2.3. Full-time local consultant to deliver and coordinate ICFMS, including leading associated workshops and coordinating the development process through workshops etc. 50% of the total cost of this position will be funded by MONRE while the GCF will fund the remainder. | Salary | 5 | 1500 | 7500
| 1.2.3. Full-time local consultant to deliver and coordinate ICFMS, including leading associated workshops and coordinating the development process through workshops etc. 50% of the total cost of this position will be funded by MONRE while the GCF will fund the remainder. | Salary | 5 | 1500 | 7500
| 1.2.3. Safeguards expert charged to Component 1 to ensure that all capacity building activities are gender-inclusive and undertaken in a socially appropriate manner. It is estimated that 50% of the expert's time will be spent overseeing activities that will be implemented under Component 1. It should be noted that the safeguards expert's work is not limited to this activity and, although budget has only been allocated to some activities under this component, the safeguards expert's work will span across all activities to be implemented under the proposed project. | Salary | 1 | 10000 | 10000
| 1.2.3. Local consultant to develop ICFMS for the four target cities at 120 days per city. ICFMS will be informed by the results from the hydrological models. | Days | 480 | 300 | 144000
| 1.2.4. Local consultant to develop national urban EbA guidelines and provide recommendations on national and local-level policy reform | Days | 120 | 300 | 36000
| 2.1.1. Safeguards expert charged to Component 2 to ensure that the implementation of interventions, development of management plans and establishment of monitoring committees is conducted in a gender-sensitive manner. Additionally, this expert will ensure that labour work is conducted appropriately and that all workers are treated fairly. It is estimated that 50% of the expert's time will be spent overseeing activities that will be implemented under Component 2. It should be noted that the safeguards expert's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the safeguards expert's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 10000 | 10000
| 2.1.1. Local consultant to develop a wetland management plan for the Nong Peung wetland in Paksan | Days | 80 | 300 | 24000
| 2.2.2. Local consultant to develop a plan for the sustainable management of urban streams in Savannakhet and Pakse. | Days | 60 | 300 | 18000
| 2.2.2. Safeguards expert charged to Component 2 to ensure that the implementation of interventions, development of management plans and establishment of monitoring committees is conducted in a gender-sensitive manner. Additionally, this expert will ensure that labour work is conducted appropriately and that all workers are treated fairly. It is estimated that 50% of the expert's time will be spent overseeing activities that will be implemented under Component 2. It should be noted that the safeguards expert's work is not limited to this activity and, although budget has only been allocated to some activties under this component, the safeguards expert's work will span across all activties to be implemented under the proposed project. | Salary | 1 | 10000 | 10000
| 2.3.1. Local consultant to assist with the design of permeable paving solutions, including site-specific O&M plans, for public areas in Vientiane, Paksan, Savannakhet and Pakse. | Days | 60 | 300 | 18000
| Subtotal |  |  |  | 730000 | 730000
A3 | Equipment purchased for project execution
| Activity number and item description | Unit | Quantity | Unit cost | Unit costs in Year 1 | Unit costs in Year 2 | Unit costs in Year 3 | Unit costs in Year 4 | Unit costs in Year 5 | Total
| 1.1.1. Training material for four workshops (one per city) at US$1,000 per workshop | Training material | 4 | 1000 | 2000 |  | 2000 |  |  | 4000
| 1.1.1. Training material at US$1,000 per workshop | Training material | 4 | 1000 | 2000 |  | 2000 |  |  | 4000
| 1.1.2. Research and monitoring equipment for use by knowledge hub and PMU at US$50,000 lump sum. This cost includes GPS, land surveying equipment, office equipment (incl. furniture, laptops), water quality testing kits and river gauges, as well as biodiversity monitoring equipment, i.e. camera traps, binoculars and field guide books. | Equipment | 1 | 50000 | 50000 |  |  |  |  | 50000
| 1.1.2. Office equipment for knowledge hub manager at US$5,000 | Equipment | 1 | 5000 | 5000 |  |  |  |  | 5000
| 1.1.3. Developing campaign materials (including signs, leaflets, posters, radio broadcasts and workshops) at US$50,000 per city for the four cities | Campaign materials | 4 | 50000 | 200000 |  |  |  |  | 200000
| 1.2.1. Laptop, printing costs and phone costs associated with the economic valuation development at US$7,500 | Equipment | 1 | 7500 | 7500 |  |  |  |  | 7500
| 1.2.2. Five software licenses for hydrological modelling software at US$12,000 per license to be housed in appropriate institutions in each of the target cities as well as in the knowledge hub. | Software licenses | 5 | 12000 | 60000 |  |  |  |  | 60000
| 2.1.1. Purchase monitoring equipment at US$30,000. PoNRE will take ownership of this equipment, which will be used by the Community Wetland Management Committee in Paksan. This cost includes GPS, office equipment (laptop), water quality testing kits, river gauges, invasive plant management equipment; biodiversity monitoring equipment (fish monitoring equipment, binoculars, camera traps, field guides etc.) | Monitoring equipment | 1 | 30000 |  | 30000 |  |  |  | 30000
| 2.2.2. Purchase monitoring equipment at US$30,000. PoNRE will take ownership of this equipment, which will be used by the Community Stream and Drainage Management Committees that will be established in both Savannakhet and Pakse. This cost includes GPS, office equipment (laptop), water quality testing kits, river gauges, invasive plant management equipment; biodiversity monitoring equipment (fish monitoring equipment, binoculars, camera traps, field guides etc.) | Monitoring equipment | 2 | 30000 |  | 60000 |  |  |  | 60000
| 2.2.1. Purchase one 4x4 vehicle for use during the rehabilitation of streams in Savannakhet and Pakse, wetland rehabilitaiton and for travel for the PMU staff to target cities. The vehicle will be formally transferred over to MONRE at the end of the project through a transfer letter. | Vehicle | 1 | 60000 | 60000 |  |  |  |  | 60000
| 2.2.1. Maintenance costs for the vehicle purchased at US$2,000 per year | Vehicle maintenance | 5 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 10000
0
| Subtotal |  |  |  | 388500 | 92000 | 6000 | 2000 | 2000 | 490500
A4 | Professional/Contractual Services, technical assistance in the field
| Activity number and item description | Unit | Quantity | Unit cost (USD) | Total
| 1.1.1. Contractual services to design and undertake baseline studies and output-level project tracking tools such as capacity scorecards and metrics for tracking the progress of project outputs. This contractor will work in close coordination with the independent consultants contracted to conduct the MTE and TE for the project. Such coordination will ensure that monitoring results at the output-level are included in the overall project review conducted by these consultants. The cost for this contractual service has been distributed evenly (50% each) across relevant activities under Components 1 and 2. The total cost of these services will be US$100,000. | Contract | 1 | 50000 | 50000
| 1.1.2. Funding for assessments and monitoring in knowledge hub, including a full-time contract for a researcher to coordinate the knowledge hub at US$100,000 annually. | Knowledge fund | 1 | 500000 | 500000
| 1.1.2. Interpreter to be contracted for 1/3 of a year for the duration of project implementation at US$300 per day | Days | 400 | 300 | 120000
| 1.2.1. Contractual services for economic valuation of ecosystems. This cost includes integrating valuations into policy, ascertaining ecosystem services flow, promoting non-marketable ecosystem services as an income generator, enumerators and the collection of socio-economic data. | Contract | 1 | 1000000 | 1000000
| 1.2.2. Contractual services to conduct wetland assessment | Contract | 1 | 67580 | 67580
| 1.2.2. Contractual services for detailed spatial surveys in each of the four target cities at US$350,000 per survey. The cost of this contract includes cost of remote sensing data, GIS software licensing, etc. | Contract | 4 | 350000 | 1400000
| 1.2.3. Contractual services for hydrological models in each of the four target cities at US$100,000 per model. | Contract | 4 | 100000 | 400000
| 2.1.1. Contractual services to conduct hydrological assessment for Paksan wetland, incorporating findings from the hydrological models. | Contract | 1 | 65000 | 65000
| 2.1.2. Contractual services to design baseline studies and output-level project tracking tools such as capacity scorecards and metrics for tracking the progress of project outputs. These services will work in close coordination with the consultants contracted to conduct the MTE and TE for the project. Such coordination will ensure that monitoring results at the output-level are included in the overall project review conducted by these consultants. The cost for this contractual service has been distributed evenly(50% each) across the relevant activties Under Components 1 and 2. The total cost of these services will be US$100,000. | Contract | 1 | 50000 | 50000
| 2.1.2. Contractual services to restore/rehabilitate the Nong Peung wetland in Paksan at US$1,000 per ha for 800 ha. The cost includes growing of indigenous seedlings and planting activities. | Contract | 1 | 800000 | 800000
| 2.1.2. Contractual services to remove invasive plants and small man-made barriers in Nong Peung wetland. 250 ha at 10 person days per ha at USD 8 per day (minimum wage = USD 6.3 per day) plus overheads, plus follow up clearing for 3 years | Contract | 1 | 170000 | 170000
| 2.2.1. Contractual services to restore natural urban streams in Savannakhet and Pakse at US$1,200 per ha, including removing invasive plants, restoring natural aquatic vegetation, removing solid waste impeding flow, delineating stream buffer zones and installing appropriate signage. | Contract | 1 | 860000 | 860000
| 2.3.1. Contractual services to conduct site surveys to identify appropriate sites for the implementation of permeable paving solutions in public areas in Vientiane, Paksan, Savannakhet and Pakse. | Contract | 1 | 20000 | 20000
| 2.3.2. Contractual services to install permeable paving solutions in Years 2 and 3 in public areas, such as universities, schools and government offices, in Vientiane, Paksan, Savannakhet and Pakse at US$50 per square metre for a total of 18,000 m2 across the four cities | Contract | 1 | 900000 | 900000
0
| Subtotal |  |  |  | 6402580 | 6402580
A5 | Travel to project implementation and in field supervision
| Activity number and item description | Unit | Quantity | Unit cost | Unit costs in Year 1 | Unit costs in Year 2 | Unit costs in Year 3 | Unit costs in Year 4 | Unit costs in Year 5 | Total
| 1.1.1. Five flights for international consultant to prepare and conduct trainings for national- and local-level decision-makers in Vientiane, Paksan, Savannakhet and Pakse at US$1,500 per flight | Flights | 5 | 1500 | 4500 |  | 3000 |  |  | 7500
| 1.1.1. Five flights for international consultant to prepare and conduct trainings for relevant national- and local-level technical staff at US$1,500 per flight | Flights | 5 | 1500 | 4500 |  | 3000 |  |  | 7500
| 1.1.2. DSA for international expert to assist with EbA curricula development (inclusive of venue costs, transport, food and accommodation) | DSA | 40 | 194 | 7760 |  |  |  |  | 7760
| 1.1.2. International consultant to provide technical support to national and local government on the use of GIS for spatial analyses. This consultant will work in collaboration with the firm contracted to conduct the spatial surveys. | DSA | 60 | 194 | 11640 |  |  |  |  | 11640
| 1.1.2. Return flight for international consultant to provide technical support to national and local government. | Flights | 2 | 1500 | 3000 |  |  |  |  | 3000
| 1.2.4. DSA for international consultant conducting capacity needs assessment | DSA | 80 | 194 | 15520 |  |  |  |  | 15520
| 1.2.3. DSA for international expert to assist local consultant with developing ICFMS for the four target cities (inclusive of venue costs, transport, food and accommodation) | DSA | 320 | 194 | 62080 |  |  |  |  | 62080
| 1.2.4. DSA for international expert to assist the local consultant with developing national urban EbA guidelines for the four target cities (inclusive of venue costs, transport, food and accommodation) | DSA | 60 | 194 | 11640 |  |  |  |  | 11640
| 1.2.4. DSA for international consultant providing recommendations | DSA | 60 | 194 | 5820 | 5820 |  |  |  | 11640
| 2.1.2. DSA for international consultant to assist the local consultant to develop a wetland management plan for the Nong Peung wetland in Paksan, including proposing measures to reduce encroachment of the wetland; establishing measures to curb the introduction and spread of invasive species | DSA | 35 | 194 | 6790 |  |  |  |  | 6790
| 2.2.1. DSA for international expert to assist the local consultant to develop a plan for the sustainable management of urban streams in Savannakhet and Pakse. | DSA | 60 | 194 | 11640 |  |  |  |  | 11640
| 2.3.1. DSA for international expert to assist with the design of permeable paving solutions, including site-specific O&M plans, for public areas in Vientiane, Paksan, Savannakhet and Pakse. | DSA | 40 | 194 | 7760 |  |  |  |  | 7760
| 1.1.2. DSA for three national researchers at US$30 per person per day for data collection from primary and secondary sources | DSA | 300 | 30 | 9000 |  |  |  |  | 9000
| 1.1.2. DSA for three national researchers for ground-truthing spatial wetland and stream data at US$30 per person per day | DSA | 90 | 30 | 2700 |  |  |  |  | 2700
| 1.1.2 Local consultant to conduct land-use survey from secondary government sources | DSA | 60 | 30 | 1800 |  |  |  |  | 1800
| 1.1.3. DSA for local consultant to design four awareness-raising campaigns for Vientiane, Paksan, Savannakhet and Pakse at US$30 per day | DSA | 80 | 30 | 2400 |  |  |  |  | 2400
| 1.1.3. DSA for local consultant to implement four awareness-raising campaigns for Vientiane, Paksan, Savannakhet and Pakse at US$30 per day | DSA | 300 | 30 | 9000 |  |  |  |  | 9000
| 1.2.2. DSA for local consultant to conduct stakeholder consultations in each of the four cities at US$30 per day for 20 days per city | DSA | 80 | 30 | 2400 |  |  |  |  | 2400
| 1.2.2. DSA for local consultant to develop national urban EbA guidelines for the four target cities at US$30 per day for 80 days per city. | DSA | 320 | 30 |  | 9600 |  |  |  | 9600
| 1.2.4. DSA for local consultant to develop ICFMS for the four target cities at 120 days per city. ICFMS will be informed by the results from the hydrological models;at US$30 per day | DSA | 480 | 30 |  | 14400 |  |  |  | 14400
| 1.2.4. DSA for local consultant to provide recommendations on national and local-level policy reform at US$30 per day | DSA | 120 | 30 |  |  | 3600 |  |  | 3600
| 2.1.2. DSA for local consultant to develop a wetland management plan for the Nong Peung wetland in Paksan at US$30 per day | DSA | 80 | 30 | 2400 |  |  |  |  | 2400
| 2.2.1. DSA for local consultant to develop a plan for the sustainable management of urban streams in Savannakhet and Pakse at US$30 per day | DSA | 60 | 30 | 1800 |  |  |  |  | 1800
| 2.3.1. DSA for local consultant to assist with the design of permeable paving solutions for public areas in Vientiane, Paksan, Savannakhet and Pakse at US$30 per day | DSA | 60 | 30 | 1800 |  |  |  |  | 1800
| Subtotal |  |  |  | 185950 | 29820 | 9600 | 0 | 0 | 225370
A6 | Workshops, trainings and meetings
| Activity number and item description | Unit | Quantity | Unit cost | Unit costs in Year 1 | Unit costs in Year 2 | Unit costs in Year 3 | Unit costs in Year 4 | Unit costs in Year 5 | Total
| 1.1.1. Training workshops for decision-makers on how to incorporate integrated climate-resilient flood management into urban planning for the cities of Vientiane, Paksan, Savannakhet and Pakse | Workshops | 16 | 3750 | 15000 | 15000 | 15000 | 15000 |  | 60000
| 1.1.1. Training workshops for national- and city-level technical staff on best practices for using urban EbA as a flood management measure for the cities of Vientiane, Paksan, Savannakhet and Pakse. | Workshops | 16 | 3750 | 15000 | 15000 | 15000 | 15000 |  | 60000
| 1.1.1. Conduct a knowledge exchange trip for senior government representatives, technical experts and academics to a city with similar topographical, climatic and socio-economic contexts to the four target cities. This cost includes flights for 22 people at US$1,000 per flight as well as US$200 per person per day for 7 days. | Exchange trip | 1 | 52800 |  | 52800 |  |  |  | 52800
| 1.1.2. One meeting between NUoL and MoNRE to sign a MoU | Meeting | 1 | 1000 | 1000 |  |  |  |  | 1000
| 1.1.3. Two meetings per city for each year of implementation to engage with relevant private sector stakeholders at US$3,750 per meeting | Meetings | 40 | 3750 | 30000 | 30000 | 30000 | 30000 | 30000 | 150000
| 1.2.1. Workshop for national-level decision-makers on ecosystem valuations | Workshops | 1 | 20000 |  |  | 20000 |  |  | 20000
| 1.2.1. Workshop for technical backstopping (one national at US$30,000) | Workshops | 1 | 30000 |  | 30000 |  |  |  | 30000
| 1.2.3. Two workshops per city to develop ICFMS at US$3,750 per workshop | Workshops | 8 | 3750 | 30000 |  |  |  |  | 30000
| 1.2.3. Four meetings (one per city) to review ICFMS at US$3,750 per meeting | Meetings | 4 | 3750 | 15000 |  |  |  |  | 15000
| 1.2.3. Sign MoU for the development and delivery of the ICFMS | Meetings | 1 | 3750 | 3750 |  |  |  |  | 3750
| 1.2.3. Meetings to provide recommendations and policy briefs to decision-makers in four cities at US$3,750 per meeting | Meetings | 4 | 3750 | 7500 | 7500 |  |  |  | 15000
| 1.2.4. Hold annual PSC committee meetings for the duration of the project | Annual PSC meetings | 5 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | 8000
| 2.1.1. Conduct four land-use planning workshops in the four cities at US$3,750 per workshop | Workshops | 16 | 3750 | 60000 |  |  |  |  | 60000
| 2.1.1. Hold meetings with local government, relevant project stakeholders and community representatives and to establish a local-level Community Wetland Management Committee in Paksan | Meeting | 2 | 3750 | 7500 |  |  |  |  | 7500
| 2.1.1. Conduct gender workshops in each of the four target cities at US$3,750 per workshop | Workshops | 4 | 3750 | 15000 |  |  |  |  | 15000
| 2.1.2. Quarterly community engagement workshops in Paksan | Workshops | 20 | 3750 | 15000 | 15000 | 15000 | 15000 | 15000 | 75000
| 2.2.1. Two community engagement workshops for Pakse and Savannkhet for each year of project implementation | Workshops | 20 | 3750 | 15000 | 15000 | 15000 | 15000 | 15000 | 75000
| 2.2.2. Hold meetings with local government, relevant project stakeholders and community representatives and to establish a local-level Community Stream and Drainage Management Committees in both Savannakhet and Pakse | Meetings | 5 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 18750
| 2.2.2. Hold two workshops per year at US$3,750 per workshop in Savannakhet and Pakse for the duration of the project (five years) to facilitate communication and knowledge sharing between the UDAA and Community Stream and Drainage Management Committees on best practices for implementing effective waste management | Workshops | 10 | 3750 | 7500 | 7500 | 7500 | 7500 | 7500 | 37500
| 2.3.1. Two community engagement workshops in each of the four cities for three years | Workshops | 24 | 3750 | 30000 | 30000 | 30000 |  |  | 90000
| 2.3.1. Conduct validation workshops at US$3,750 in Vientiane, Paksan, Savannakhet and Pakse to validate the design of permeable paving solutions in each of the cities | Workshops | 4 | 3750 |  |  | 15000 |  |  | 15000
0
| Subtotal |  |  |  | 276000 | 226550 | 171250 | 106250 | 76250 | 856300
A7 | Operation and maintenance costs
| O&M costs | Unit | Quantity | Unit cost (USD) | Total | Costs in Year 1 | Costs in Year 2 | Costs in Year 3 | Costs in Year 4 | Costs in Year 5
| 2.1.2. O&M for restored wetland areas at 1% of total intervention cost per year | O&M | 3 | 8000 | 24000 |  |  | 8000 | 8000 | 8000
| 2.2.1. O&M for restored urban streams at 1% of total intervention cost per year | O&M | 3 | 8600 | 25800 |  |  | 8600 | 8600 | 8600
| 2.3.2. O&M for permeable pavements at 1% of total intervention cost per year | O&M | 3 | 9000 | 27000 |  |  | 9000 | 9000 | 9000
0
| Subtotal |  |  |  | 76800 | 0 | 0 | 25600 | 25600 | 25600
A8 | MONRE staff time contribution to project implementation.
MoNRE staff time
MoNRE will provide in-kind co-financing for the implementation of the proposed project. To this end, MoNRE will contribute to the organisation and coordination of workshops, meetings, awareness raising campaigns and other project activities, as well as assist with the logistics surrounding the implementation of project interventions (e.g. assisting with venue hire, office rentals and transport logistics for international consultants).
PMU | Project management costs
| PMU positions | Unit | Quantity | Unit cost (USD) | Total | Costs in Year 1 | Costs in Year 2 | Costs in Year 3 | Costs in Year 4 | Costs in Year 5
PMU1 | Procurement and Financial Officer | Annual salary | 5 | 25000 | 125000 | 25000 | 25000 | 25000 | 25000 | 25000
PMU2 | Administrative Officer | Annual salary | 5 | 20000 | 100000 | 20000 | 20000 | 20000 | 20000 | 20000
PMU3 | Project Manager | Project Manager | 5 | 40000 | 200000 | 40000 | 40000 | 40000 | 40000 | 40000
PMU4 | The Project Director (PD) will be a senior MONRE staff member who will dedicate a proportion (20%) of their time to project director responsibilities. The cost to the project for the PD's time will be US$50,000 across 5 years. MONRE will cover this amount of the Project Director's time as part of MONRE's co-financing. | 20% of Project Director's salary | 5 | 10000 | 50000 | 10000 | 10000 | 10000 | 10000 | 10000
PMU5 | Office space for five years in the PoNRE departments for use by focal points. This cost includes computers, photocopying, overheads etc. | Office space | 5 | 5000 | 25000 | 5000 | 5000 | 5000 | 5000 | 5000
| Subtotal |  |  |  | 500000 | 100000 | 100000 | 100000 | 100000 | 100000

## Title Lists
Component | Outputs | Budget Categories | List of Funding Source
Component 1. Technical and institutional capacity building to plan, design, implement and maintain integrated urban Ecosystems-based Adaptation (EbA) interventions for the reduction of climate change-induced flooding | Output 1.1 Strengthening of institutional capacity for integrated flood risk management and implementation of urban ecosystems-based adaptation and males and females with increased awareness of climate threats | Consultant - Individual - International | GCF
Component 2. Rehabilitation and protection of ecosystem in response to climate variability and change | Output 1.2 Integrated Climate-resilient Flood Management Strategies and urban EbA guidelines developed for Vientiane, Paksan, Savannakhet and Pakse, and effective Flood Risk Management Committees as coordination mechanisms | Consultant - Individual - Local | MONRE
Project Management Cost | Output 2.1 Area of wetland restored contributing to flood reduction and sustainable management of the Nong Peung wetland in Paksan | Materials & Goods
| Output 2.2 Area of urban streams restored contributing to flood reduction and sustainable management of urban streams in Savannakhet and Pakse | Office Supplies
| Output 2.3 Area of permeable paving solutions installed in public areas contributing to flood reduction in Vientiane, Paksan, Savannakhet and Pakse | Professional Services – Companies/Firm
| PMC | Travel
Workshop/Training
O&M
MONRE staff time contribution to activity
PMC staff and personnel

## Term sheet budget
Component | Output | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
1 | 1.1 | 519860 | 375020 | 328220 | 322220 | 284780 | 1830100
1 | 1.2 | 980200 | 1225180 | 787100 | 367100 | 448380 | 3807960
Component 1 subtotals |  | 1500060 | 1600200 | 1115320 | 689320 | 733160 | 5638060
2 | 2.1 | 171490 | 349180 | 299490 | 299490 | 299490 | 1419140
2 | 2.2 | 400680 | 249690 | 258290 | 258290 | 258290 | 1425240
2 | 2.3 | 254480 | 230010 | 230070 | 189000 | 189000 | 1092560
Component 2 subtotals |  | 826650 | 828880 | 787850 | 746780 | 746780 | 3936940
PMC |  | 85000 | 85000 | 85000 | 85000 | 85000 | 425000
Total | [6 empty] | 10000000

## Sheet1 (hidden)
125600 | 105400 | 58600 | 52600 | 22600 |  | 364800
519860 | 375020 | 328220 | 322220 | 284780 | 1830100 | 1830100
980200 | 1225180 | 787100 | 367100 | 448380 | 3807960 | 3807960
197490 | 315180 | 265490 | 265490 | 265490 | 1309140 | 1309140
374680 | 283690 | 292290 | 292290 | 292290 |  | 1535240
254480 | 230010 | 230070 | 189000 | 189000 |  | 1092560
85000 | 85000 | 85000 | 85000 | 85000 | 425000 | 425000
2411710 | 2514080 | 1988170 | 1521100 | 1564940 | 7372200 | 10000000
2411710 | 2514080 | 1988170 | 1521100 | 1564940 |  | 10000000