## 1st Year
Description | Procurement Method | Procurement Value | Major Responsibility | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PMU/Project Management
Staff - National | Competitive recruitment | 162600 | IUCN
Staff - Field Base | Secondment from GoSL | 66500 | IUCN
Food and Accomadation | Competitive Bidding | 6250 | IUCN
International Travel Missions- Experience sharing/training | Competitive Bidding | 22500 | PMU
03 field Vehicles- Rent | Competitive Bidding | 33600 | PMU
Vehicle Purchase (02 units) | Competitive Bidding | 100000 | PMU
Motorbikes purchase (15 units) | Competitive Bidding | 9000 | PMU
Direct Project Activities
Contracts to Farmer Associations/CBOs | Call for proposals from CBOs | 140000 | PMU
Consultancies/Contracts - Individual | Competitive Bidding | 75000 | PMU
Consultancies/Contracts - Institutes | Call for Proposals from Selected Suppliers | 4111890 | PMU
Workshops and Seminars | Competitive Bidding | 37500 | PMU
Workshops and meetings | Competitive Bidding | 37500 | PMU
Capacity building | Call for Proposals from Selected Suppliers | 117500 | PMU
Publication and communications | Competitive Bidding | 50000 | PMU
Gender mainstreaming | Call for Proposals from Selected Suppliers | 30000 | PMU
Equipment and supplies
Office Rent & Maintainance (PMU) | Competitive Bidding | 12000 | IUCN
Rent SDT Offices (06 sub basin offices) | Competitive Bidding | 10500 | PMU
Office Furniture & Equipment | Competitive Bidding | 35000 | PMU
Stationeries/ Office Supplies/Utility | Competitive Bidding | 24000 | PMU
Reporting | Call for Proposals from Selected Suppliers | 1800 | PMU
Communication | Call for Proposals from Selected Suppliers | 12000 | PMU
Direct Contracting
Competitive Bidding
Call for Proposals from Selected Suppliers
Call for proposals from CBOs
Competitive recruitment
Secondment from GoSL
PMU
IUCN
Minstry of Mahaweli/Env
ICRAF
Procurement Plan for 06 years - PMU GCF Project
Strengthening Climate Resilience of Subsistence Farmers and Agricultural Plantation Communities residing in the vulnerable river basins, watershed areas and downstream of the Knuckles Mountain Range Catchment of Sri Lanka

## 2nd Year
Description | Procurement Method | Estimated Budget | Major Responsibility | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PMU/Project Management
Staff - National | Completed in year 1 | 162600 | IUCN
Staff - Field Base | Completed in year 1 | 66500 | IUCN
Food and Accomadation | Completed in year 1 | 6250 | IUCN
03 field Vehicles- Rent | Completed in year 1 | 33600 | PMU
Direct Project Activities
Contracts to Farmer Associations/CBOs | Call for proposals from CBOs | 280000 | PMU
Consultancies/Contracts - Individual | Competitive Bidding | 150000 | PMU
Consultancies/Contracts - Institutes | Call for Proposals from Selected Suppliers | 8223780 | PMU
Workshops and Seminars | Competitive Bidding | 37500 | PMU
Workshops and meetings | Competitive Bidding | 37500 | PMU
Capacity building | Call for Proposals from Selected Suppliers | 235000 | PMU
Publication and communications | Competitive Bidding | 50000 | PMU
Gender mainstreaming | Call for Proposals from Selected Suppliers | 40000 | PMU
Equipment and supplies
Office Furniture & Equipment | Competitive Bidding | 5000 | PMU
Stationeries/ Office Supplies/Utility | Competitive Bidding | 24000 | PMU
Reporting | Call for Proposals from Selected Suppliers | 1800 | PMU
Communication | Call for Proposals from Selected Suppliers | 12000 | PMU
Direct Contracting
Competitive Bidding
Call for Proposals from Selected Suppliers
Call for proposals from CBOs
Competitive recruitment
Secondment from GoSL
PMU
IUCN
Minstry of Mahaweli/Env
ICRAF
Procurement Plan for 06 years - PMU GCF Project
Strengthening Climate Resilience of Subsistence Farmers and Agricultural Plantation Communities residing in the vulnerable river basins, watershed areas and downstream of the Knuckles Mountain Range Catchment of Sri Lanka

## 3rd Year
Description | Procurement Method | Estimated Budget | Major Responsibility | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PMU/Project Management
Staff - National | Completed in year 1 | 162600 | IUCN
Staff - Field Base | Completed in year 1 | 66500 | IUCN
Food and Accomadation | Completed in year 1 | 6250 | IUCN
03 field Vehicles- Rent | Completed in year 1 | 33600 | PMU
Direct Project Activities
Contracts to Farmer Associations/CBOs | Call for proposals from CBOs | 420000 | PMU
Consultancies/Contracts - Individual | Competitive Bidding | 225000 | PMU
Consultancies/Contracts - Institutes | Call for Proposals from Selected Suppliers | 12335670 | PMU
Workshops and Seminars | Competitive Bidding | 37500 | PMU
Workshops and meetings | Competitive Bidding | 37500 | PMU
Capacity building | Call for Proposals from Selected Suppliers | 352500 | PMU
Publication and communications | Competitive Bidding | 50000 | PMU
Gender mainstreaming | Call for Proposals from Selected Suppliers | 40000 | PMU
Equipment and supplies
Office Furniture & Equipment | Competitive Bidding | 2500 | PMU
Stationeries/ Office Supplies/Utility | Competitive Bidding | 24000 | PMU
Reporting | Call for Proposals from Selected Suppliers | 1800 | PMU
Communication | Call for Proposals from Selected Suppliers | 12000 | PMU
Direct Contracting
Competitive Bidding
Call for Proposals from Selected Suppliers
Call for proposals from CBOs
Competitive recruitment
Secondment from GoSL
PMU
IUCN
Minstry of Mahaweli/Env
ICRAF
Procurement Plan for 06 years - PMU GCF Project
Strengthening Climate Resilience of Subsistence Farmers and Agricultural Plantation Communities residing in the vulnerable river basins, watershed areas and downstream of the Knuckles Mountain Range Catchment of Sri Lanka

## 4th Year
Description | Procurement Method | Estimated Budget | Major Responsibility | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PMU/Project Management
Staff - National | Completed in year 1 | 162600 | IUCN
Staff - Field Base | Completed in year 1 | 66500 | IUCN
Food and Accomadation | Completed in year 1 | 6250 | IUCN
International Missions/Trainings | Completed in year 1 | 22500 | IUCN
03 field Vehicles- Rent | Completed in year 1 | 33600 | PMU
Direct Project Activities
Contracts to Farmer Associations/CBOs | Call for proposals from CBOs | 280000 | PMU
Consultancies/Contracts - Individual | Competitive Bidding | 150000 | PMU
Consultancies/Contracts - Institutes | Call for Proposals from Selected Suppliers | 8223780 | PMU
Workshops and Seminars | Competitive Bidding | 37500 | PMU
Workshops and meetings | Competitive Bidding | 37500 | PMU
Capacity building | Call for Proposals from Selected Suppliers | 235000 | PMU
Publication and communications | Competitive Bidding | 50000 | PMU
Gender mainstreaming | Call for Proposals from Selected Suppliers | 30000 | PMU
Equipment and supplies
Office Furniture & Equipment | Competitive Bidding | 2500 | PMU
Stationeries/ Office Supplies/Utility | Competitive Bidding | 24000 | PMU
Reporting | Call for Proposals from Selected Suppliers | 1800 | PMU
Communication | Call for Proposals from Selected Suppliers | 12000 | PMU
Direct Contracting
Competitive Bidding
Call for Proposals from Selected Suppliers
Call for proposals from CBOs
Competitive recruitment
Secondment from GoSL
PMU
IUCN
Minstry of Mahaweli/Env
ICRAF
Procurement Plan for 06 years - PMU GCF Project
Strengthening Climate Resilience of Subsistence Farmers and Agricultural Plantation Communities residing in the vulnerable river basins, watershed areas and downstream of the Knuckles Mountain Range Catchment of Sri Lanka

## 5th Year
Description | Procurement Method | Estimated Budget | Major Responsibility | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PMU/Project Management
Staff - National | Completed in year 1 | 162600 | IUCN
Staff - Field Base | Completed in year 1 | 66500 | IUCN
Food and Accomadation | Completed in year 1 | 6250 | IUCN
03 field Vehicles- Rent | Completed in year 1 | 33600 | PMU
Direct Project Activities
Contracts to Farmer Associations/CBOs | Call for proposals from CBOs | 140000 | PMU
Consultancies/Contracts - Individual | Competitive Bidding | 75000 | PMU
Consultancies/Contracts - Institutes | Call for Proposals from Selected Suppliers | 4111890 | PMU
Workshops and Seminars | Competitive Bidding | 37500 | PMU
Workshops and meetings | Competitive Bidding | 37500 | PMU
Capacity building | Call for Proposals from Selected Suppliers | 117500 | PMU
Publication and communications | Competitive Bidding | 50000 | PMU
Gender mainstreaming | Call for Proposals from Selected Suppliers | 30000 | PMU
Equipment and supplies
Office Furniture & Equipment | Competitive Bidding | 2500 | PMU
Stationeries/ Office Supplies/Utility | Competitive Bidding | 24000 | PMU
Reporting | Call for Proposals from Selected Suppliers | 1800 | PMU
Communication | Call for Proposals from Selected Suppliers | 12000 | PMU
Direct Contracting
Competitive Bidding
Call for Proposals from Selected Suppliers
Call for proposals from CBOs
Competitive recruitment
Secondment from GoSL
PMU
IUCN
Minstry of Mahaweli/Env
ICRAF
Procurement Plan for 06 years - PMU GCF Project
Strengthening Climate Resilience of Subsistence Farmers and Agricultural Plantation Communities residing in the vulnerable river basins, watershed areas and downstream of the Knuckles Mountain Range Catchment of Sri Lanka

## 6th Year
Annex 12
Description | Procurement Method | Estimated Budget | Major Responsibility | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
PMU/Project Management
Staff - National | Completed in year 1 | 162600 | IUCN
Staff - Field Base | Completed in year 1 | 66500 | IUCN
Food and Accomadation | Completed in year 1 | 6250 | IUCN
03 field Vehicles- Rent | Completed in year 1 | 33600 | PMU
Direct Project Activities
Contracts to Farmer Associations/CBOs | Call for proposals from CBOs | 140000 | PMU
Consultancies/Contracts - Individual | Competitive Bidding | 75000 | PMU
Consultancies/Contracts - Institutes | Call for Proposals from Selected Suppliers | 4111890 | PMU
Workshops and Seminars | Competitive Bidding | 37500 | PMU
Workshops and meetings | Competitive Bidding | 37500 | PMU
Capacity building | Call for Proposals from Selected Suppliers | 117500 | PMU
Publication and communications | Competitive Bidding | 50000 | PMU
Gender mainstreaming | Call for Proposals from Selected Suppliers | 30000 | PMU
Equipment and supplies
Office Furniture & Equipment | Competitive Bidding | 2500 | PMU
Stationeries/ Office Supplies/Utility | Competitive Bidding | 24000 | PMU
Reporting | Call for Proposals from Selected Suppliers | 1800 | PMU
Communication | Call for Proposals from Selected Suppliers | 12000 | PMU
Direct Contracting
Competitive Bidding
Call for Proposals from Selected Suppliers
Call for proposals from CBOs
Competitive recruitment
Secondment from GoSL
PMU
IUCN
Minstry of Mahaweli/Env
ICRAF
Procurement Plan for 06 years - PMU GCF Project
Strengthening Climate Resilience of Subsistence Farmers and Agricultural Plantation Communities residing in the vulnerable river basins, watershed areas and downstream of the Knuckles Mountain Range Catchment of Sri Lanka