## Detailed Budget
Annex 4. Detailed budget plan
Project/Programme Title: Resilience to hurricanes, floods and droughts in the building sector in Antigua and Barbuda
Output | Activity | Sub-activity | Financing Source | Budget Account Description | Notes and Assumptions* | Total cost (USD) | Amount Year 1 (USD) | Amount Year 2 (USD) | Amount Year 3 (USD) | Amount Year 4 (USD) | Amount Year 5 (USD) | Amount Year 6 (USD) | Total (USD) | Check
Output 1. Climate-proofing interventions implemented in critical public service and community buildings to improve resilience to, and recovery from, extreme climate events. | Activity 1.1. Implement climate-proofing measures on critical infrastructure. | Sub-activity 1.1.1 Develop site-specific engineering designs for climate proofing 52 priority buildings. | GCF | Professional or contractual services | A1 | 378721.8849 | 189360.9425 | 189360.9425 | 0 | 0 | 0 | 0 | 378721.8849 | TRUE
|  |  | GoAB | Professional or contractual services | A2 | 2273.3033 | 1136.6516 | 1136.6516 | 0 | 0 | 0 | 0 | 2273.3033 | TRUE
|  | Sub-activity 1.1.2 Install climate proofing measures on 52 priority buildings based on engineering designs developed in Sub-activity 1.1.1. | GCF | Professional or contractual services | A3 | 7574437.6988 | 1262406.2831 | 1262406.2831 | 1262406.2831 | 1262406.2831 | 1262406.2831 | 1262406.2831 | 7574437.6988 | TRUE
|  |  | GoAB | Professional or contractual services | A4 | 45466.0657 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 45466.0657 | TRUE
|  |  | GoAB | Professional or contractual services | A5 | 1434717.3913 | 239119.5652 | 239119.5652 | 239119.5652 | 239119.5652 | 239119.5652 | 239119.5652 | 1434717.3913 | TRUE
|  |  | GoAB | Professional or contractual services | A6 | 2679474.5493 | 446579.0916 | 446579.0916 | 446579.0916 | 446579.0916 | 446579.0916 | 446579.0916 | 2679474.5493 | TRUE
|  |  | GoAB | Professional or contractual services | A7 | 45466.0657 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 45466.0657 | TRUE
|  | Sub-activity 1.1.3 Develop site-specific operational procedures for long-term maintenance of climate-proofing interventions for each priority building and integrate these procedures into the project O&M Framework. | GCF | Local consultants | A8 | 121500 | 121500 | 0 | 0 | 0 | 0 | 0 | 121500 | TRUE
|  |  | GCF | Travel | A9 | 42120 | 42120 | 0 | 0 | 0 | 0 | 0 | 42120 | TRUE
|  |  | GCF | Training, workshops, and conferences | A10 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750 | TRUE
|  | Sub-activity 1.1.4 Design climate-resilient renewable energy solutions for priority buildings taking into consideration energy efficiency (EE) and indoor air quality for those buildings that have heating, ventilation and air conditioning (HVAC) systems. | GCF | Professional or contractual services | A11 | 401679.56 | 200839.78 | 200839.78 | 0 | 0 | 0 | 0 | 401679.56 | TRUE
|  |  | GoAB | Professional or contractual services | A12 | 4103.9502 | 2051.9751 | 2051.9751 | 0 | 0 | 0 | 0 | 4103.9502 | TRUE
|  | Sub-activity 1.1.5 Install EE and RE solutions at priority buildings. | GCF | Professional or contractual services | A13 | 7462228.526 | 1243704.7543 | 1243704.7543 | 1243704.7543 | 1243704.7543 | 1243704.7543 | 1243704.7543 | 7462228.526 | TRUE
|  |  | GoAB | Professional or contractual services | A14 | 82079.0032 | 13679.8339 | 13679.8339 | 13679.8339 | 13679.8339 | 13679.8339 | 13679.8339 | 82079.0032 | TRUE
|  |  | GoAB | Professional or contractual services | A15 | 5392323.4358 | 898720.5726 | 898720.5726 | 898720.5726 | 898720.5726 | 898720.5726 | 898720.5726 | 5392323.4358 | TRUE
|  |  | GoAB | Professional or contractual services | A16 | 48167.0201 | 24083.5101 | 24083.5101 | 0 | 0 | 0 | 0 | 48167.0201 | TRUE
|  | Sub-activity 1.1.6 Design water harvesting solutions for priority buildings as well as stormwater drainage solutions for buildings in flood risk areas. | GoAB | Professional or contractual services | A17 | 168538.8 | 84269.4 | 84269.4 | 0 | 0 | 0 | 0 | 168538.8 | TRUE
|  |  | GoAB | Professional or contractual services | A18 | 1470.5196 | 1470.5196 | 0 | 0 | 0 | 0 | 0 | 1470.5196 | TRUE
|  |  | GCF | Professional or contractual services | A19 | 11351.4422 | 0 | 11351.4422 | 0 | 0 | 0 | 0 | 11351.4422 | TRUE
|  | Sub-activity 1.1.7 Install water harvesting solutions for priority buildings as well as stormwater drainage solutions for buildings in flood risk areas. | GCF | Professional or contractual services | A20 | 3341353.1283 | 556892.1881 | 556892.1881 | 556892.1881 | 556892.1881 | 556892.1881 | 556892.1881 | 3341353.1283 | TRUE
|  |  | GoAB | Professional or contractual services | A21 | 29410.3924 | 4901.7321 | 4901.7321 | 4901.7321 | 4901.7321 | 4901.7321 | 4901.7321 | 29410.3924 | TRUE
|  |  | GoAB | Professional or contractual services | A22 | 928504.772 | 154750.7953 | 154750.7953 | 154750.7953 | 154750.7953 | 154750.7953 | 154750.7953 | 928504.772 | TRUE
|  |  | GoAB | Professional or contractual services | A23 | 1500.5302 | 1500.5302 | 0 | 0 | 0 | 0 | 0 | 1500.5302 | TRUE
|  |  | GCF | Professional or contractual services | A24 | 227028.8441 | 0 | 113514.4221 | 113514.4221 | 0 | 0 | 0 | 227028.8441 | TRUE
| Activity 1.2 Construct climate-resilient storm shelters attached to public clinics. | Sub-activity 1.2.1 Develop detailed, site-specific construction plans for hurricane shelters at five public clinics. | GCF | Professional or contractual services | A25 | 179831.25 | 89915.625 | 89915.625 | 0 | 0 | 0 | 0 | 179831.25 | TRUE
|  | Sub-activity 1.2.2 Construct hurricane shelters based on the designs developed under Sub-activity 1.2.1. | GCF | Professional or contractual services | A26 | 1198875 | 199812.5 | 199812.5 | 199812.5 | 199812.5 | 199812.5 | 199812.5 | 1198875 | TRUE
|  |  | GoAB | Professional or contractual services | A27 | 399625 | 66604.1667 | 66604.1667 | 66604.1667 | 66604.1667 | 66604.1667 | 66604.1667 | 399625 | TRUE
|  | Sub-activity 1.2.3 Equip hurricane shelters with renewable energy and climate-resilient water harvesting systems. | GCF | Professional or contractual services | A28 | 453100 | 75516.6667 | 75516.6667 | 75516.6667 | 75516.6667 | 75516.6667 | 75516.6667 | 453100 | TRUE
|  | Sub-activity 1.2.4 Develop emergency protocols for each shelter according to national guidelines. | GCF | Training, workshops, and conferences | A29 | 18750 | 0 | 18750 | 0 | 0 | 0 | 0 | 18750 | TRUE
|  |  | GCF | Local consultants | A30 | 11250 | 0 | 11250 | 0 | 0 | 0 | 0 | 11250 | TRUE
|  |  | GCF | Travel | A31 | 3900 | 0 | 3900 | 0 | 0 | 0 | 0 | 3900 | TRUE
| Activity 1.3 Construct a climate-resilient bunker to store emergency supplies for the health, energy, building and welfare sectors. | Sub-activity 1.3.1 Complete a detailed design and construction plan for the bunker. | GCF | Professional or contractual services | A32 | 489320.55 | 489320.55 | 0 | 0 | 0 | 0 | 0 | 489320.55 | TRUE
|  | Sub-activity 1.3.2 Construct the bunker based on the design in Sub-activity 1.3.1. | GCF | Professional or contractual services | A33 | 2267223 | 0 | 2267223 | 0 | 0 | 0 | 0 | 2267223 | TRUE
|  |  | GoAB | Professional or contractual services | A34 | 994914 | 0 | 994914 | 0 | 0 | 0 | 0 | 994914 | TRUE
|  |  | GCF | Equipment | A35 | 639609.7561 | 0 | 0 | 0 | 213203.252 | 213203.252 | 213203.252 | 639609.7561 | TRUE
|  |  | GCF | Equipment | A36 | 6602.333 | 0 | 6602.333 | 0 | 0 | 0 | 0 | 6602.333 | TRUE
|  | Sub-activity 1.3.3 Develop an operational protocol for the stock and distribution management of emergency supplies that will be stored within the bunker. | GCF | Training, workshops, and conferences | A37 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750 | TRUE
|  |  | GCF | International consultant | A38 | 11250 | 11250 | 0 | 0 | 0 | 0 | 0 | 11250 | TRUE
|  |  | GCF | Travel | A39 | 2340 | 2340 | 0 | 0 | 0 | 0 | 0 | 2340 | TRUE
|  |  | GCF | Travel | A40 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Local consultants | A41 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | TRUE
|  |  | GCF | Travel | A42 | 3120 | 3120 | 0 | 0 | 0 | 0 | 0 | 3120 | TRUE
|  | Sub-activity 1.3.4 Develop a battery recharge and replacement protocol for critical services. | GCF | Training, workshops, and conferences | A43 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750 | TRUE
|  |  | GCF | Local consultants | A44 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | TRUE
|  |  | GCF | Travel | A45 | 3120 | 3120 | 0 | 0 | 0 | 0 | 0 | 3120 | TRUE
| Activity 1.4 Implement measures to preserve vital information/data within public institutions. | Sub-activity 1.4.1 Develop backup protocols for critical information. | GCF | Training, workshops, and conferences | A46 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | TRUE
|  |  | GCF | International consultant | A47 | 9000 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | TRUE
|  |  | GCF | Travel | A48 | 3120 | 3120 | 0 | 0 | 0 | 0 | 0 | 3120 | TRUE
|  |  | GCF | Travel | A49 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Local consultants | A50 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | TRUE
|  |  | GCF | Travel | A51 | 6240 | 6240 | 0 | 0 | 0 | 0 | 0 | 6240 | TRUE
|  | Sub-activity 1.4.2 Train IT teams on the implementation of backup protocols. | GCF | Training, workshops, and conferences | A52 | 45000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 45000 | TRUE
|  | Sub-activity 1.4.3 Design physical protection measures for critical IT infrastructure. | GCF | Training, workshops, and conferences | A53 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | TRUE
|  |  | GCF | Professional or contractual services | A54 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | TRUE
|  | Sub-activity 1.4.4 Implement physical protection measures for critical IT infrastructure. | GCF | Training, workshops, and conferences | A55 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | TRUE
|  |  | GCF | Training, workshops, and conferences | A56 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 22500 | TRUE
Subtotal GCF cost for Output 1 | [5 empty] | 25082822.9735 | 4669079.2897 | 6262289.9369 | 3463096.8142 | 3562785.6442 | 3562785.6442 | 3562785.6442 | 25082822.9735 | TRUE
Subtotal GoAB cost for Output 1 | [5 empty] | 12258034.7989 | 1954023.6992 | 2945966.6494 | 1839511.1126 | 1839511.1126 | 1839511.1126 | 1839511.1126 | 12258034.7989 | TRUE
Subtotal Output 1 | [5 empty] | 37340857.7724 | 6623102.9889 | 9208256.5863 | 5302607.9268 | 5402296.7568 | 5402296.7568 | 5402296.7568 | 37340857.7724 | TRUE
Contingency fee for Output 1 (10% of the total cost of project interventions under this output) |  |  |  |  | A57 | 2508282.2973 | 466907.929 | 626228.9937 | 346309.6814 | 356278.5644 | 356278.5644 | 356278.5644 | 2508282.2973 | TRUE
Output 2. Climate change adaptation mainstreamed into the building sector and relevant financial mechanisms. | Activity 2.1 Mainstream climate change adaptation into the building sector by making provision for the building code in the Physical Planning Act (2003) and updating the EMS plans. | Sub-activity 2.1.1 Draft regulations for the Physical Planning Act (2003) that makes provision for the Building Code for submission to and enactment by parliament. | GCF | Local consultants | B1 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | TRUE
|  |  | GCF | Travel | B2 | 6240 | 6240 | 0 | 0 | 0 | 0 | 0 | 6240 | TRUE
|  |  | GCF | Training, workshops, and conferences | B3 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750 | TRUE
|  | Sub-activity 2.1.2. Conduct Strategic Impact Assessment (SIA) of the building code regulations to assess the environmental and social safeguards and gender risks, consequences and mitigation measures related to the enactment of these regulations. | GCF | Professional or contractual services | B4 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | TRUE
|  |  | GCF | Professional or contractual services | B5 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | TRUE
|  |  | GCF | Professional or contractual services | B6 | 25000 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | TRUE
|  |  | GCF | Professional or contractual services | B7 | 5000 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | TRUE
|  |  | GCF | Professional or contractual services | B8 | 3500 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500 | TRUE
|  |  | GCF | Professional or contractual services | B9 | 2500 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | TRUE
|  |  | GCF | Professional or contractual services | B10 | 14000 | 14000 | 0 | 0 | 0 | 0 | 0 | 14000 | TRUE
|  | Sub-activity 2.1.3 Make recommendations for the EMS Plans to be updated to include climate change adaptation measures for the building sector. | GCF | Training, workshops, and conferences | B11 | 7500 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | TRUE
|  |  | GCF | Local consultants | B12 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | TRUE
|  |  | GCF | Travel | B13 | 6240 | 6240 | 0 | 0 | 0 | 0 | 0 | 6240 | TRUE
|  |  | GCF | Training, workshops, and conferences | B14 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750 | TRUE
|  |  | GCF | Training, workshops, and conferences | B15 | 18750 | 0 | 3750 | 3750 | 3750 | 3750 | 3750 | 18750 | TRUE
|  | Sub-activity 2.1.4 Conduct annual meetings with participation from relevant stakeholders to collate and share lessons learned from implementing the EMS plans and ensure that these plans are updated regularly where necessary. | GCF | Training, workshops, and conferences | B16 | 15000 | 0 | 0 | 3750 | 3750 | 3750 | 3750 | 15000 | TRUE
|  |  | GCF | Local consultants | B17 | 27000 | 0 | 0 | 6750 | 6750 | 6750 | 6750 | 27000 | TRUE
|  |  | GCF | Training, workshops, and conferences | B18 | 15000 | 0 | 0 | 3750 | 3750 | 3750 | 3750 | 15000 | TRUE
| Activity 2.2 Mainstream climate change adaptation for the building sector into public and private financial, insurance and banking sectors. | Sub-activity 2.2.1. Consult with representatives from the public and private sectors to identify entry points for accessing the SIRF fund for climate change adaptation measures that exceed the current thresholds of the fund, including introducing incremental cost reasoning to selection criteria, combined with incentive programmes, levies, insurance/risk management products and increased replenishment. | GCF | International consultant | B19 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 45000 | TRUE
|  |  | GCF | Travel | B20 | 9360 | 0 | 9360 | 0 | 0 | 0 | 0 | 9360 | TRUE
|  |  | GCF | Travel | B21 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  | Sub-activity 2.2.2 Refine the SIRF Fund’s list of adaptation options using an evidence-based approach that draws lessons learned from the SCCF, EDA projects, as well as lessons learnt the implementation of adaptation interventions under Activity 1.1 of this project. | GCF | Training, workshops, and conferences | B22 | 67500 | 11250 | 11250 | 11250 | 11250 | 11250 | 11250 | 67500 | TRUE
|  |  | GCF | Local consultants | B23 | 9000 | 0 | 9000 | 0 | 0 | 0 | 0 | 9000 | TRUE
|  |  | GCF | Training, workshops, and conferences | B24 | 22500 | 0 | 4500 | 4500 | 4500 | 4500 | 4500 | 22500 | TRUE
|  | Sub-activity 2.2.3 Train decision-makers from NODS, DCA and PWD on how to (a) assess, calculate and report on the incremental cost of adaptation in public sector projects for the purposes of tracking the implementation of Article 2.1c of the Paris agreement (b) implement the new building codes and regulations to assess planning applications (c) to provide trained technical assistance to the SIRF Fund in the evaluation of private sector applications for loans and grants. | GCF | International consultant | B25 | 90000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 90000 | TRUE
|  |  | GCF | Travel | B26 | 18720 | 3120 | 3120 | 3120 | 3120 | 3120 | 3120 | 18720 | TRUE
|  |  | GCF | Travel | B27 | 18000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 | TRUE
|  |  | GCF | Training, workshops, and conferences | B28 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 22500 | TRUE
|  | Sub-activity 2.2.4 Collate and share lessons learned from SIRF Fund application & funding process, including fund replenishment. | GCF | Training, workshops, and conferences | B29 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 22500 | TRUE
| Activity 2.3 Train relevant staff from the National Office of Disaster Services (NODS), Development Control Authority (DCA) and the Public Works Department (PWD) as well as the private sector on operational procedures for long-term monitoring, maintenance and upscaling of climate-resilient renewable energy (RE) and water harvesting technologies in accordance with the national building code. | Sub-activity 2.3.1 Train building inspectors from DCA, building maintenance teams from PWD as well as technical staff from NODS and other relevant institutions on the implementation of the operational procedures for the long-term maintenance of climate-proofing interventions in the target buildings, based on building-specific O&M plans and updated national building code. | GCF | Training, workshops, and conferences | B30 | 45000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 45000 | TRUE
|  | Sub-activity 2.3.2 Design and implement a long-term monitoring framework for building-specific climate-proofing measures – including cost-benefit analyses – to demonstrate the long-term adaptation benefits. | GCF | International consultant | B31 | 90000 | 90000 | 0 | 0 | 0 | 0 | 0 | 90000 | TRUE
|  |  | GCF | Travel | B32 | 18720 | 18720 | 0 | 0 | 0 | 0 | 0 | 18720 | TRUE
|  |  | GCF | Travel | B33 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Training, workshops, and conferences | B34 | 3750 | 0 | 0 | 3750 | 0 | 0 | 0 | 3750 | TRUE
|  | Sub-activity 2.3.3 Partner with local training institutions such as ABICE to develop and deliver training programmes for relevant technical staff from MoW and DCA; building inspectors, engineers, architects and draughtsmen; and the private sector on best practices for implementing, monitoring and maintaining climate change adaptation technologies, including climate-resilient RE and water harvesting solutions, and how to apply the updated national building code during the installation of these technologies. | GCF | Training, workshops, and conferences | B35 | 22500 | 0 | 22500 | 0 | 0 | 0 | 0 | 22500 | TRUE
|  |  | GCF | Professional or contractual services | B36 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | TRUE
|  |  | GCF | Professional or contractual services | B37 | 750000 | 0 | 150000 | 150000 | 150000 | 150000 | 150000 | 750000 | TRUE
|  | Sub-activity 2.3.4 Design and conduct a gender-sensitive awareness campaign targeting the public and private sectors on the updated Building Code, the benefits of taking up climate-adaptive solutions within the building sector as well as the availability of certified climate change courses. | GCF | Local consultants | B38 | 27000 | 27000 | 0 | 0 | 0 | 0 | 0 | 27000 | TRUE
|  |  | GCF | Travel | B39 | 9360 | 9360 | 0 | 0 | 0 | 0 | 0 | 9360 | TRUE
|  |  | GoAB | Equipment | B40 | 60000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 60000 | TRUE
|  |  | GCF | Local consultants | B41 | 216000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000 | 216000 | TRUE
|  |  | GCF | Travel | B42 | 74880 | 12480 | 12480 | 12480 | 12480 | 12480 | 12480 | 74880 | TRUE
|  | Sub-activity 2.3.5 Develop and implement a gender-sensitive awareness-raising campaign within the government system on the availability of the courses developed under Sub-activity 2.3.3 | GCF | Local consultants | B43 | 18000 | 18000 | 0 | 0 | 0 | 0 | 0 | 18000 | TRUE
|  |  | GCF | Travel | B44 | 6240 | 6240 | 0 | 0 | 0 | 0 | 0 | 6240 | TRUE
|  |  | GoAB | Equipment | B45 | 60000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 60000 | TRUE
|  |  | GCF | Local consultants | B46 | 108000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000 | 108000 | TRUE
|  |  | GCF | Travel | B47 | 37440 | 6240 | 6240 | 6240 | 6240 | 6240 | 6240 | 37440 | TRUE
| Activity 2.4 Train the local workforce on the installation, operation and maintenance of climate-proofing measures for the targeted buildings. | Sub-activity 2.4.1 Engage with suitable training institutions such as ABICE and UWI to develop and deliver a training programme that targets the local workforce on how to install, operate and maintain climate change adaptation technologies in the building sector as well as implement early action protocols. | GCF | Training, workshops, and conferences | B48 | 22500 | 0 | 22500 | 0 | 0 | 0 | 0 | 22500 | TRUE
|  | Sub-activity 2.4.2 Develop training modules in line with regional and international occupational standards for climate change adaptation in the building sector. | GCF | Professional or contractual services | B49 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 40000 | TRUE
|  | Sub-activity 2.4.3 Deliver training modules developed under Sub-activity 2.4.2. | GCF | Professional or contractual services | B50 | 600000 | 0 | 120000 | 120000 | 120000 | 120000 | 120000 | 600000 | TRUE
|  | Sub-activity 2.4.4 Design and conduct an awareness building campaign on the opportunity for training on the installation, operation and maintenance of climate change adaptation technologies in the building sector, with the support of training institutions. | GCF | Local consultants | B51 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 18000 | TRUE
|  |  | GCF | Travel | B52 | 6240 | 0 | 6240 | 0 | 0 | 0 | 0 | 6240 | TRUE
|  |  | GoAB | Equipment | B53 | 50000 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | TRUE
|  |  | GCF | Local consultants | B54 | 135000 | 0 | 27000 | 27000 | 27000 | 27000 | 27000 | 135000 | TRUE
|  |  | GCF | Travel | B55 | 46800 | 0 | 9360 | 9360 | 9360 | 9360 | 9360 | 46800 | TRUE
Subtotal GCF cost for Output 2 | [5 empty] | 2880740 | 430890 | 650300 | 452700 | 448950 | 448950 | 448950 | 2880740 | TRUE
Subtotal GoAB cost for Output 2 | [5 empty] | 170000 | 20000 | 30000 | 30000 | 30000 | 30000 | 30000 | 170000 | TRUE
Subtotal Output 2 | [5 empty] | 3050740 | 450890 | 680300 | 482700 | 478950 | 478950 | 478950 | 3050740 | TRUE
Contingency fee for Output 2 (5% of the total cost of project interventions under this output) |  |  |  |  | B56 | 144037 | 21544.5 | 32515 | 22635 | 22447.5 | 22447.5 | 22447.5 | 144037 | TRUE
Output 3. Climate information services strengthened to facilitate early action within the building sector to respond to extreme climate events. | Activity 3.1 Climate information services strengthened to facilitate early action for extreme climate events. | Sub-activity 3.1.1 Establish a centralised online server to enhance real-time processing of climate data. | GCF | Professional or contractual services | C1 | 12000 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | TRUE
|  | Sub-activity 3.1.2 Increase the technical capacity of staff within ABMS to collect, process and manage climate data in real time. | GCF | International consultant | C2 | 15000 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | TRUE
|  |  | GCF | Travel | C3 | 3120 | 3120 | 0 | 0 | 0 | 0 | 0 | 3120 | TRUE
|  |  | GCF | Travel | C4 | 3000 | 3000 | 0 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Training, workshops, and conferences | C5 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 22500 | TRUE
|  | Sub-activity 3.1.3 Conduct a knowledge exchange trip to the nearest Regional Climate Centre (RCC), which is under the auspices of the World Meteorological Organization (WMO), to strengthen the technical and institutional capacity within ABMS for impact-based forecasting. | GCF | Training, workshops, and conferences | C6 | 3750 | 3750 | 0 | 0 | 0 | 0 | 0 | 3750 | TRUE
|  |  | GCF | Training, workshops, and conferences | C7 | 70052 | 0 | 70052 | 0 | 0 | 0 | 0 | 70052 | TRUE
|  | Sub-activity 3.1.4 Increase the technical and institutional capacity of AMBS to develop early warning information products, including infographics that are locally appropriate and easily interpreted by vulnerable communities. | GCF | International consultant | C8 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 15000 | TRUE
|  |  | GCF | Travel | C9 | 3120 | 0 | 3120 | 0 | 0 | 0 | 0 | 3120 | TRUE
|  |  | GCF | Travel | C10 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Training, workshops, and conferences | C11 | 18750 | 0 | 3750 | 3750 | 3750 | 3750 | 3750 | 18750 | TRUE
| Activity 3.2 Establish a formalised communication protocol to facilitate rapid information sharing and early action preceding an extreme climate event. | Sub-activity 3.2.1 Design and operationalise a formal communication protocol to facilitate effective communication of impact-based forecasts from ABMS to decision-makers within relevant government entities responsible for preparation ahead of an extreme climate event. | GCF | International consultant | C12 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | TRUE
|  |  | GCF | Travel | C13 | 6240 | 0 | 6240 | 0 | 0 | 0 | 0 | 6240 | TRUE
|  |  | GCF | Travel | C14 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Local consultants | C15 | 36000 | 0 | 36000 | 0 | 0 | 0 | 0 | 36000 | TRUE
|  |  | GCF | Travel | C16 | 12480 | 0 | 12480 | 0 | 0 | 0 | 0 | 12480 | TRUE
|  |  | GCF | Training, workshops, and conferences | C17 | 37500 | 0 | 7500 | 7500 | 7500 | 7500 | 7500 | 37500 | TRUE
|  |  | GCF | Local consultants | C18 | 54000 | 0 | 10800 | 10800 | 10800 | 10800 | 10800 | 54000 | TRUE
|  |  | GCF | Travel | C19 | 18720 | 0 | 3744 | 3744 | 3744 | 3744 | 3744 | 18720 | TRUE
|  |  | GoAB | Equipment | C20 | 50000 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | TRUE
|  | Sub-activity 3.2.2 Design and implement early action protocols for critical public service and community buildings with variable responses dependent on the anticipated intensity of the incoming storm. | GCF | International consultant | C21 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 30000 | TRUE
|  |  | GCF | Travel | C22 | 6240 | 0 | 6240 | 0 | 0 | 0 | 0 | 6240 | TRUE
|  |  | GCF | Travel | C23 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Local consultants | C24 | 36000 | 0 | 36000 | 0 | 0 | 0 | 0 | 36000 | TRUE
|  |  | GCF | Travel | C25 | 12480 | 0 | 12480 | 0 | 0 | 0 | 0 | 12480 | TRUE
|  |  | GCF | Local consultants | C26 | 54000 | 0 | 54000 | 0 | 0 | 0 | 0 | 54000 | TRUE
|  |  | GCF | Travel | C27 | 18720 | 0 | 18720 | 0 | 0 | 0 | 0 | 18720 | TRUE
|  |  | GoAB | Equipment | C28 | 50000 | 0 | 10000 | 10000 | 10000 | 10000 | 10000 | 50000 | TRUE
|  | Sub-activity 3.2.3 Train public and private sector actors on the application of the early action protocols designed and developed under Sub-activity 3.2.2. | GCF | Training, workshops, and conferences | C29 | 56250 | 0 | 11250 | 11250 | 11250 | 11250 | 11250 | 56250 | TRUE
|  | Sub-activity 3.2.4 Improve the capacity of ABMS to disseminate early warning information products to critical service providers as well as the private sector to facilitate early action. | GCF | International consultant | C30 | 45000 | 0 | 45000 | 0 | 0 | 0 | 0 | 45000 | TRUE
|  |  | GCF | Travel | C31 | 9360 | 0 | 9360 | 0 | 0 | 0 | 0 | 9360 | TRUE
|  |  | GCF | Travel | C32 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 3000 | TRUE
|  |  | GCF | Local consultants | C33 | 36000 | 0 | 36000 | 0 | 0 | 0 | 0 | 36000 | TRUE
|  |  | GCF | Travel | C34 | 12480 | 0 | 12480 | 0 | 0 | 0 | 0 | 12480 | TRUE
|  |  | GCF | Training, workshops, and conferences | C35 | 37500 | 0 | 7500 | 7500 | 7500 | 7500 | 7500 | 37500 | TRUE
|  |  | GCF | Training, workshops, and conferences | C36 | 18750 | 0 | 3750 | 3750 | 3750 | 3750 | 3750 | 18750 | TRUE
Subtotal GCF cost for Output 3 | [5 empty] | 746012 | 40620 | 497216 | 52044 | 52044 | 52044 | 52044 | 746012 | TRUE
Subtotal GoAB cost for Output 3 | [5 empty] | 100000 | 0 | 20000 | 20000 | 20000 | 20000 | 20000 | 100000 | TRUE
Subtotal Output 3 | [5 empty] | 846012 | 40620 | 517216 | 72044 | 72044 | 72044 | 72044 | 846012 | TRUE
Contingency fee for Output 3 (5% of the total cost of project interventions under this output) |  |  |  |  | C37 | 37300.6 | 2031 | 24860.8 | 2602.2 | 2602.2 | 2602.2 | 2602.2 | 37300.6 | TRUE
Independent Monitoring and Evaluation costs
International consultant to conduct the Independent Interim Evaluation for the project. |  |  | GCF | International consultant | M&E1 | 114400 | 0 | 0 | 114400 | 0 | 0 | 0 | 114400 | TRUE
International consultant to conduct the Final Evaluation Report for the project. |  |  | GCF | International consultant | M&E2 | 143000 | 0 | 0 | 0 | 0 | 0 | 143000 | 143000 | TRUE
Total M&E costs | [5 empty] | 257400 | 0 | 0 | 114400 | 0 | 0 | 143000 | 257400 | TRUE
Project management costs | [13 empty] | TRUE
Project Manager |  |  | GCF | Staff cost | PM1 | 240000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 240000 | TRUE
Project Coordinator |  |  | GCF | Staff cost | PM2 | 270000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000 | 270000 | TRUE
Financial Officer (This will be financed using in-kind co-financing from the GoAB.) |  |  | GoAB | Staff cost | PM3 | 120000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 120000 | TRUE
Procurement Officer (This will be financed using in-kind co-financing from the GoAB.) |  |  | GoAB | Staff cost | PM4 | 120000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | 120000 | TRUE
Administrative Officer (This will be financed using in-kind co-financing from the GoAB.) |  |  | GoAB | Staff cost | PM5 | 150000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 150000 | TRUE
Monitoring and evaluation officer specializing in training impacts on a gender basis (This will be financed using in-kind co-financing from the GoAB.) |  |  | GoAB | Staff cost | PM6 | 210000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | 210000 | TRUE
Environmental, Social and Gender Officers person |  |  | GCF | Staff cost | PM7 | 180000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 180000 | TRUE
Communications Officer (This will be financed using in-kind co-financing from the GoAB.) |  |  | GoAB | Staff cost | PM8 | 150000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 150000 | TRUE
Technical Advisors (Renewable energy and Gender sensitive training) | Technical Officer - Coordinator for the Monitoring and reporting of Public Sector adaptation Infrastructure projects (2) |  | GCF | Staff cost | PM9 | 360000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000 | 360000 | TRUE
Office space for the project management unit (This will be financed using cash and in-kind co-financing for material staff costs, split 40% and 60%, respectively.) |  |  | GoAB | Staff cost | PM10 | 180000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 180000 | TRUE
Subtotal GCF project management costs, including the MTE and TE costs (Row 167) | [5 empty] | 1307400 | 175000 | 175000 | 289400 | 175000 | 175000 | 318000 | 1307400 | TRUE | 58.43% | 62.19%
Subtotal GoAB project management costs | [5 empty] | 930000 | 155000 | 155000 | 155000 | 155000 | 155000 | 155000 | 930000 | TRUE | 41.57% | 27.14%
Total project management costs, including the MTE and TE costs (Row 167) | [5 empty] | 2237400 | 330000 | 330000 | 444400 | 330000 | 330000 | 473000 | 2237400 | TRUE
Total GCF cost for project interventions | [5 empty] | 28709574.9735 | 5140589.2897 | 7409805.9369 | 3967840.8142 | 4063779.6442 | 4063779.6442 | 4063779.6442 | 28709574.9735 | TRUE
Total GoAB cost for project interventions | [5 empty] | 12528034.7989 | 1974023.6992 | 2995966.6494 | 1889511.1126 | 1889511.1126 | 1889511.1126 | 1889511.1126 | 12528034.7989 | TRUE
Total cost of project interventions | [5 empty] | 41237609.7724 | 7114612.9889 | 10405772.5863 | 5857351.9268 | 5953290.7568 | 5953290.7568 | 5953290.7568 | 41237609.7724 | TRUE
Contingency fee requested from the GCF | [5 empty] | 2689619.8973 | 490483.429 | 683604.7937 | 371546.8814 | 381328.2644 | 381328.2644 | 381328.2644 | 2689619.8973 | TRUE
Total GCF project cost including PMC and contingency | [5 empty] | 32706594.8708 | 5806072.7186 | 8268410.7306 | 4628787.6957 | 4620107.9086 | 4620107.9086 | 4763107.9086 | 32706594.8708 | TRUE
Total GoAB project cost including PMC | [5 empty] | 13458034.7989 | 2129023.6992 | 3150966.6494 | 2044511.1126 | 2044511.1126 | 2044511.1126 | 2044511.1126 | 13458034.7989 | TRUE
Total project cost | [5 empty] | 46164629.6698 | 7935096.4178 | 11419377.38 | 6673298.8083 | 6664619.0212 | 6664619.0212 | 6807619.0212 | 46164629.6698 | TRUE
70831.4835
|  |  | #REF! | [9 empty] | 2308231.4835

## Notes and Assumptions
Detailed Budget Notes |  | Unit | Quantity | Unit cost | Total cost | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 |  |  | Total | Cash | In-kind
A1 | Contractual services for an engineer to develop site-specific engineering designs for climate-proofing 51 priority buildings. This includes an assessment of each building as well as the production of the designs for each priority building to receive climate-proofing interventions. This cost was calculated as 5% of the total installation cost of climate-proofing interventions, which is based on national standards of Antigua and Barbuda. | Contract | 1 | 378721.8849 | 378721.8849 | 189360.9425 | 189360.9425
A2 | Contractual services for an engineer to develop site-specific engineering designs for climate-proofing the Good Shepherd Children's Home. This includes an assessment of the building as well as the production of the designs for the building to receive climate-proofing interventions. This cost was calculated as 5% of the total installation cost of climate-proofing interventions, which is based on national standards of Antigua and Barbuda. (The government will be using their internal architects to do this work and this will therefore financed using in-kind co-financing). | Contract | 1 | 2273.3033 | 2273.3033 | 1136.6516 | 1136.6516 |  |  |  |  | the government will be using their internal architects to do this work. 100% in kind |  | 2273.3033 |  | 2273.3033
A3 | Contractual services to install climate-proofing measures on 51 priority buildings using the engineering designs developed. These measures include roof structural upgrades, roof cover and fastening upgrades, replacing windows and frames and replacing doors and frames. This installation includes project development, management and implementation with a 10% engineering contingency. | Contract | 1 | 7574437.6988 | 7574437.6988 | 1262406.2831 | 1262406.2831 | 1262406.2831 | 1262406.2831 | 1262406.2831 | 1262406.2831
A4 | Contractual services to install climate-proofing measures on the Good Shepherd Children's Home using the engineering designs developed. These measures include roof structural upgrades, roof cover and fastening upgrades, replacing windows and frames and replacing doors and frames. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using cash co-financing.) | Contract | 1 | 45466.0657 | 45466.0657 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | cash |  | 45466.0657 | 45466.0657
A5 | Contractual services to undertake general structural repairs required for priority buildings. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using in-kind co-financing through MoW for labour, heavy duty equipment, insurance etc.) | Contract | 1 | 1434717.3913 | 1434717.3913 | 239119.5652 | 239119.5652 | 239119.5652 | 239119.5652 | 239119.5652 | 239119.5652 | In kind MOW: labour, heavy duty equipment, insurance |  | 1434717.3913 |  | 1434717.3913
A6 | Contractual services to undertake general building repairs required for 47 priority buildings. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using in-kind co-financing through MoW for labour, heavy duty equipment, insurance etc.) | Contract | 1 | 2679474.5493 | 2679474.5493 | 446579.0916 | 446579.0916 | 446579.0916 | 446579.0916 | 446579.0916 | 446579.0916 | In kind MOW: labour, heavy duty equipment, insurance |  | 2679474.5493 |  | 2679474.5493
A7 | Contractual services to undertake general building repairs required for the Good Shepherd Children's Home. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using cash and in-kind co-financing for material and labour costs, split 70% and 30%, respectively.) | Contract | 1 | 45466.0657 | 45466.0657 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | 7577.6776 | cash and Kind |  | 45466.0657 | 31826.246 | 13639.8197
A8 | Local consultant contracted to develop site-specific operational procedures for long-term maintenance of climate-proofing interventions for each priority building. | Days | 270 | 450 | 121500 | 121500
A9 | DSA for the local consultant that will develop the site-specific operational procedures. | Days | 270 | 156 | 42120 | 42120
A10 | Hold a validation workshop with relevant stakeholders from public institutions for the integration of site-specific operational procedures into existing building O&M frameworks. | Validation meeting | 1 | 3750 | 3750 | 3750
A11 | Contractual services for an engineer to design climate-resilient renewable energy solutions for 34 priority buildings taking into consideration energy efficiency (EE) and indoor air quality. This includes an assessment of each building as well as the production of the designs for each priority building to receive renewable energy solutions. This cost was calculated as 5% of the total installation cost of climate-proofing interventions, which is based on national standards of Antigua and Barbuda. | Contract | 1 | 401679.56 | 401679.56 | 200839.78 | 200839.78
A12 | Contractual services for an engineer to design climate-resilient renewable energy solutions for the Good Shepherd Children's Home taking into consideration energy efficiency (EE) and indoor air quality. This includes an assessment of the building as well as the production of the designs for the building to receive renewable energy solutions. This cost was calculated as 5% of the total installation cost of climate-proofing interventions, which is based on national standards of Antigua and Barbuda. (This will be financed using cash co-financing.) | Contract | 1 | 4103.9502 | 4103.9502 | 2051.9751 | 2051.9751 |  |  |  |  | Cash |  | 4103.9502 | 4103.9502
A13 | Contractual services to install energy efficiency and renewable energy solutions on 34 priority buildings. These solutions include rooftop or local ground mount PV panels and Li battery banks. The installation fee includes project development, management and implementation with a 10% engineering contingency. | Contract | 1 | 7462228.526 | 7462228.526 | 1243704.7543 | 1243704.7543 | 1243704.7543 | 1243704.7543 | 1243704.7543 | 1243704.7543
A14 | Contractual services to install energy efficiency and renewable energy solutions on the Good Shepherd Children's Home. These solutions include rooftop or local ground mount PV panels and Li battery banks. The installation fee includes project development, management and implementation with a 10% engineering contingency. (This will be financed using cash and in-kind co-financing for material and labour costs, split 70% and 30%, respectively.) | Contract | 1 | 82079.0032 | 82079.0032 | 13679.8339 | 13679.8339 | 13679.8339 | 13679.8339 | 13679.8339 | 13679.8339 | 70% cash, 30% in kind |  | 82079.0032 | 57455.3022 | 24623.701
A15 | Contractual services to undertake general electrical repairs required for 52 priority buildings. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using cash and in-kind co-financing, from the ADFD and MoW, respectively. The ADFD portion will be 80% of this cost, and MoW's portion will be 20% of this cost.) | Contract | 1 | 5392323.4358 | 5392323.4358 | 898720.5726 | 898720.5726 | 898720.5726 | 898720.5726 | 898720.5726 | 898720.5726 | ADFD Loan/ cash, and 20% in kind MOW |  | 5392323.4358 | 4313858.7487 | 1078464.6872
A16 | Contractual services to undertake general electrical repairs required for the Good Shepherd Children's Home. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using cash and in-kind co-financing for material and labour costs, split 70% and 30%, respectively.) | Contract | 1 | 48167.0201 | 48167.0201 | 24083.5101 | 24083.5101 |  |  |  |  | materials (cash) and in kind installation by the Public Works; |  | 48167.0201 | 33716.9141 | 14450.106
A17 | Contractual services for an engineer to design climate-resilient water harvesting solutions for 50 priority buildings. This includes an assessment of each building as well as the production of the designs for each priority building to receive climate-resilient water harvesting solutions. This cost was calculated as 5% of the total installation cost of climate-proofing interventions, which is based on national standards of Antigua and Barbuda. (This will be financed using in-kind co-financing from the GoAB.) | Contract | 1 | 168538.8 | 168538.8 | 84269.4 | 84269.4 |  |  |  |  | In kind. Using staff of MOW |  | 168538.8 |  | 168538.8
A18 | Contractual services for an engineer to design climate-resilient water harvesting solutions for the Good Shepherd Children's Home. This includes an assessment of the building as well as the production of the designs for the building to receive climate-resilient water harvesting solutions. This cost was calculated as 5% of the total installation cost of climate-proofing interventions, which is based on national standards of Antigua and Barbuda. (This will be financed using in-kind co-financing from the GoAB.) | Contract | 1 | 1470.5196 | 1470.5196 | 1470.5196 | [5 empty] | 100% in kind |  | 1470.5196 |  | 1470.5196
A19 | Contractual services for an engineer to design stormwater drainage solutions for 14 critical buildings situated in inundation zones in the country. This includes an assessment of each building as well as the production of the designs for each priority building to receive stormwater drainage solutions. This cost was calculated as 5% of the total installation cost of climate-proofing interventions, which is based on national standards of Antigua and Barbuda. Site-specific designs will be conducted for the following critical buildings: • Barbuda Fire Station • Bendals health clinic • Bolans health clinic • Bolans Primary School • Cedar Grove Primary • Clare Hall Secondary School • Freetown Primary School • Gray's Farm Clinic • Grays Farm Police Station • Jennings Primary School • Liberta Police Station • Liberta Primary School • Ministry of Finance • Parham health clinic | Contract | 1 | 11351.4422 | 11351.4422 |  | 11351.4422
A20 | Contractual services to install climate-resilient water harvesting solutions on 50 priority buildings. These solutions include potable water reserve tanks and solar hot water units. The installation fee includes project development, management and implementation with a 10% engineering contingency. | Contract | 1 | 3341353.1283 | 3341353.1283 | 556892.1881 | 556892.1881 | 556892.1881 | 556892.1881 | 556892.1881 | 556892.1881
A21 | Contractual services to install climate-resilient water harvesting solutions on the Good Shepherd Children's Home. These solutions include potable water reserve tanks and solar hot water units. The installation fee includes project development, management and implementation with a 10% engineering contingency. (This will be financed using in-kind co-financing from the MoW.) | Contract | 1 | 29410.3924 | 29410.3924 | 4901.7321 | 4901.7321 | 4901.7321 | 4901.7321 | 4901.7321 | 4901.7321 | In kind provide by the MOW |  | 29410.3924 |  | 29410.3924
A22 | Contractual services to undertake wastewater treatment required for 45 priority buildings. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using in-kind co-financing from the MoW.) | Contract | 1 | 928504.772 | 928504.772 | 154750.7953 | 154750.7953 | 154750.7953 | 154750.7953 | 154750.7953 | 154750.7953 | in kind via budget allocation and in kind by MOW |  | 928504.772 |  | 928504.772
A23 | Contractual services to undertake wastewater treatment required for the Good Shepherd Children's Home. This installation includes project development, management and implementation with a 10% engineering contingency. (This will be financed using cash co-financing.) | Contract | 1 | 1500.5302 | 1500.5302 | 1500.5302 | [5 empty] | Cash |  | 1500.5302 | 1500.5302
A24 | Contractual services to install stormwater drainage solutions (e.g. roof guttering) on 14 critical buildings in inundation zones in the country. The total floor size of these buildings is 8,079 m2 and the cost per m2 for installing stormwater drainage solutions on these buildings is ~US$28 per m2. The total cost of the installation of these solutions is therefore ~US$227,029. Further details on the per m2 costing for this intervention are presented in the 'Cost calculations for upgrades' tab in this Excel sheet (Annex 4: Detailed budget). The installation fee includes project development, management and implementation with a 10% engineering contingency. Appropriate stormwater drainage solutions will be installed on the following critical buildings: • Barbuda Fire Station • Bendals health clinic • Bolans health clinic • Bolans Primary School • Cedar Grove Primary • Clare Hall Secondary School • Freetown Primary School • Gray's Farm Clinic • Grays Farm Police Station • Jennings Primary School • Liberta Police Station • Liberta Primary School • Ministry of Finance • Parham health clinic | Contract | 1 | 227028.8441 | 227028.8441 |  | 113514.4221 | 113514.4221
A25 | Contractual services for the engineers, architects, mechanics and other relevant personnel required for the detailed design and management of the construction process for the five hurricane shelters that will be attached to five public clinics. In addition, this cost includes site assessments and validation for construction of these shelters. The cost of these contractual services is 15% of the total construction cost of the shelters, which is in line with Antigua and Barbuda's national standards. | Contract | 1 | 179831.25 | 179831.25 | 89915.625 | 89915.625
A26 | Contractual services for the adaptation costs required to construct five hurricane shelters with a 230 m2 floor size each to be attached to five public clinics identified under Sub-activity 1.2.1. The cost of constructing these shelters is US$996 per m2 (with changes 1390.00/M2) . Using the findings of the building assessment (Annex 22) as a guide, the adaptation costs of constructing climate-resilient hurricane shelters that are able to withstand the impacts of a Category 5 hurricane is 56% of the total construction cost. (changed cost/m2 and ratio) | Contract | 1 | 239775 | 1198875 | 199812.5 | 199812.5 | 199812.5 | 199812.5 | 199812.5 | 199812.5
A27 | Contractual services for the baseline / general construction costs required to construct five hurricane shelters with a 230 m2 floor size each to be attached to five public clinics identified under Sub-activity 1.2.1. The cost of constructing these shelters is US$996 per m2. Using the findings of the building assessment (Annex 22) as a guide and adjust for actual pricing, the baseline costs of constructing climate-resilient hurricane shelters that are able to withstand the impacts of a Category 5 hurricane is 100% of the total construction cost. (This will be financed using cash and in-kind co-financing for material and labour costs, split 70% and 30%, respectively.) | Contract |  | 79925 | 399625 | 66604.1667 | 66604.1667 | 66604.1667 | 66604.1667 | 66604.1667 | 66604.1667 | Materials, Labour and Insurance will be provide (Cash and in-Kind) |  | 399625 | 279737.5 | 119887.5
A28 | Contractual services to equip the five hurricane shelters (with a 230 m2 floor size each) with renewable energy and climate-resilient water harvesting solutions. The cost of installing renewable energy solutions is US$290 per m2. The total cost of installing renewable energy solutions on all five shelters is therefore US$333,500. Additionally, the cost of installing climate-resilient water harvesting solutions is US$104 per m2. The total cost of installing climate-resilient water harvesting solutions on all five shelters is therefore US$119,600. This installation includes project development, management and implementation with a 10% engineering contingency, specifically for the installation of renewable energy and climate-resilient water harvesting solutions. | Contract | 1 | 453100 | 453100 | 75516.6667 | 75516.6667 | 75516.6667 | 75516.6667 | 75516.6667 | 75516.6667
A29 | Five stakeholder engagement workshops with relevant stakeholders from each clinic for the development of emergency protocols for each shelter. | Engagement workshops | 5 | 3750 | 18750 |  | 18750
A30 | Local consultant to develop emergency protocols for each shelter in accordance with national guidelines. | Days | 25 | 450 | 11250 |  | 11250
A31 | DSA for the local consultant that will develop the emergency protocols for each shelter attached to public clinics. | Days | 25 | 156 | 3900 |  | 3900
A32 | Contractual services for the engineers, architects, mechanics and other relevant personnel required for the detailed design and management of the construction process for the climate-resilient bunker. In addition, this cost includes site assessments and validation for construction of the bunker. The cost of these contractual services is 15% of the total construction cost of the shelters, which is in line with Antigua and Barbuda's national standards. | Contract | 1 | 489320.55 | 489320.55 | 489320.55
A33 | Contractual services for the construction of the climate-resilient bunker that is able to withstand the impacts of a Category 5 hurricane with a floor size of 749 m2 (8050 sq. ft). The purpose of this bunker will be to store emergency supplies for the health, energy, building and welfare sectors. The estimated cost of this bunker will be US$2,018 per m2. (1.5 price adjustment). | Contract | 1 | 2267223 | 2267223 |  | 2267223
A34 | Contractual services for the baseline elements (including general building activities and electrical wiring) of constructing the climate-resilient bunker that is able to withstand the impacts of a Category 5 hurricane with a 749 m2 floor. The purpose of this bunker will be to store emergency supplies for the health, energy, building and welfare sectors. The estimated cost of this bunker will be US$2,018 per m2 (1.5 price adjustment). Using the findings of the building assessment (Annex 22) as a guide, the baseline / business as usual costs of constructing the climate-resilient bunker to withstand the impacts of a Category 5 hurricane is 44% of the total construction cost. (This will be financed using in-kind co-financing from the GoAB for the value of the land, heavy duty equipment and transportation cost of materials.) | Contract | 1 | 994914 | 994914 |  | 994914 |  |  |  |  | in kind: The value of the land, heavy duty equipment, transportation cost of the materials; |  | 994914 |  | 994914
A35 | Purchase and stockpile off-site emergency renewable energy strategic stock, including PV panels, racking and BOS strategic stock. This strategic stock will be used to replace renewable energy equipment that may be damaged during a storm. | Off-site renewable energy equipment | 1 | 639609.7561 | 639609.7561 |  |  |  | 213203.252 | 213203.252 | 213203.252
A36 | Purchase and stockpile off-site emergency renewable energy strategic stock, including PV panels, racking and BOS strategic stock. This strategic stock will be used to replace renewable energy equipment that may be damaged during a storm. | Off-site renewable energy equipment | 1 | 6602.333 | 6602.333 |  | 6602.333
A37 | One stakeholder engagement workshop with relevant representatives from MoHWE, MoW, PWD, DoE, Ministry of Social Transformation and other relevant stakeholders for the development of an operational protocol for the stock and distribution management of emergency supplies that will be stored within the bunker. The bunker will be managed by a ministerial sub-committee and the Chairperson of this committee will participate in this engagement workshop. | Engagement workshop | 1 | 3750 | 3750 | 3750
A38 | International consultant to develop the operational protocol for the climate-resilient bunker based on the outcomes of the engagement workshop and in accordance with national guidelines. | Days | 15 | 750 | 11250 | 11250
A39 | DSA for the international consultant to develop the operational protocol for the climate-resilient bunker based on the outcomes of the engagement workshop and in accordance with national guidelines. | Days | 15 | 156 | 2340 | 2340
A40 | One return flight for the international consultant to develop the operational protocol for the climate-resilient bunker based on the outcomes of the engagement workshop and in accordance with national guidelines. | Return flight | 1 | 3000 | 3000 | 3000
A41 | Local consultant to assist the international consultant with developing the operational protocol for the climate-resilient bunker based on the outcomes of the engagement workshop and in accordance with national guidelines. | Days | 20 | 450 | 9000 | 9000
A42 | DSA for the local consultant contracted to assist the international consultant with developing the operational protocol for the climate-resilient bunker based on the outcomes of the engagement workshop and in accordance with national guidelines. | Days | 20 | 156 | 3120 | 3120
A43 | One engagement workshop with relevant representatives from MoHWE, MoW, PWD, DoE and other relevant stakeholders for the development of a battery recharge and replacement protocol for critical services. | Engagement workshop | 1 | 3750 | 3750 | 3750
A44 | Local consultant to develop the battery recharge and replacement protocol for critical services. | Days | 20 | 450 | 9000 | 9000
A45 | DSA for the local consultant contracted to develop the battery recharge and replacement protocol for critical services. | Days | 20 | 156 | 3120 | 3120
A46 | Four engagement workshops with representatives from hospitals, clinics, fire and police services for the development of backup protocols for the preservation of vital information. | Engagement workshops | 4 | 3750 | 15000 | 15000
A47 | International consultant to develop backup protocols for the preservation of vital information within critical public institutions such as hospitals, clinics, police and fire stations. These protocols will be informed by the engagement workshops held with relevant stakeholders from these public institutions. | Days | 20 | 450 | 9000 | 9000
A48 | DSA for the international consultant contracted to develop backup protocols. | Days | 20 | 156 | 3120 | 3120
A49 | One return flight for the international consultant contracted to develop backup protocols. | Return flight | 1 | 3000 | 3000 | 3000
A50 | Local consultant to assist the international consultant with developing backup protocols for the preservation of vital information within critical public institutions such as hospitals, clinics, police and fire stations. These protocols will be informed by the engagement workshops held with relevant stakeholders from these public institutions. | Days | 40 | 450 | 18000 | 18000
A51 | DSA for the local consultant contracted to assist the international consultant with developing the backup protocols for preserving vital information. | Days | 40 | 156 | 6240 | 6240
A52 | Two training workshops per year for IT teams housed within relevant critical public institutions on the protocols for backing up vital data hosted within these institutions. | Training workshops | 12 | 3750 | 45000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
A53 | Four engagement workshops with representatives from hospitals, clinics, fire and police services for the appropriate design of physical protection measures for critical IT infrastructure. | Engagement workshops | 4 | 3750 | 15000 | 15000
A54 | Contractual services to design physical protection measures for critical IT infrastructure based on inputs from the relevant stakeholders engaged. | Contract | 1 | 50000 | 50000 | 50000
A55 | Four training workshops for relevant stakeholders from hospitals, clinics, fire and police stations on how to implement the backup protocols for preserving vital information. | Training workshops | 4 | 3750 | 15000 | 15000
A56 | Annual workshops for relevant stakeholders from hospitals, clinics, police and fire stations on the effective implementation of backup protocols. These annual workshops will be held to ensure that the institutional capacity for the implementation of these protocols is not lost because of staff turnover etc. | Workshops | 6 | 3750 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750
A57 | A contingency fee has been included in the project budget to mitigate the risk of increasing project input costs affecting the implementation of project interventions. As noted in Annex 22: Building assessment, a post-disaster scenario in Antigua and Barbuda (whereby the country experiences a hurricane or other extreme event) results in an estimated 30% increase in input costs, particularly around materials, staff costs and equipment required to install climate-resilient solutions on infrastructure. Antigua and Barbuda is currently experiencing the post-disaster impacts of Hurricane Irma (2017), and data this is currently being collected is showing that the cost of climate-proofing critical infrastructure is significantly higher than estimated. It is also likely that Antigua and Barbuda will experience a hurricane during the project period. This would compound the post-disaster impacts of Hurricane Irma that are currently being absorbed by the national government and population. A 10% contingency is therefore being requested for Project Output 1 to mitigate the risk of the abovementioned factors affecting the implementation of project interventions. This contingency will be used only if necessary and in line with the agreements between the Accredited Entity and the GCF. | Contingency fee | 1 | 2508282.2973 | 2508282.2973 | 466907.929 | 626228.9937 | 346309.6814 | 356278.5644 | 356278.5644 | 356278.5644
B1 | Local consultant to review the Physical Planning Act and draft amendments to the act to make provision for the national building code. | Days | 40 | 450 | 18000 | 18000
B2 | DSA for local consultant contracted to draft amendments to the Physical Planning Act. | Days | 40 | 156 | 6240 | 6240
B3 | Hold a validation workshop with relevant project stakeholders from DCA, MoHWE and other relevant entities to validate the draft amendments developed by the local consultant. | Validation workshop | 1 | 3750 | 3750 | 3750
B4 | Contract for an ESS and Gender Expert for the strategic impact assessment (SIA) of the building code regulations to assess the environmental and social safeguards and gender risks, consequences and mitigation measures related to the enactment of these regulations. | Contract | 1 | 10000 | 10000 | 10000
B5 | Contract for a construction sector expert to assist with the SIA. | Contract | 1 | 15000 | 15000 | 15000
B6 | Contract for a economist to assist with conducting the trade-off analysis as well as the cost-benefit analysis for the SIA. | Contract | 1 | 25000 | 25000 | 25000
B7 | Contract for a report writer to assist with documenting the SIA. | Contract | 1 | 5000 | 5000 | 5000
B8 | Three SIA consultations | SIA consultations | 3 | 1166.6667 | 3500 | 3500
B9 | Three publications of the SIA in a local newspaper | Contract | 1 | 2500 | 2500 | 2500
B10 | NGO assessment of the inputs required to inform the SIA process | Contract | 1 | 14000 | 14000 | 14000
B11 | Conduct two workshops with relevant stakeholders from the DoE, DCA, MoW and other relevant entities to review the EMS plans and identify entry points for updating these plans to include climate change adaptation measures for the building sector. | Workshops | 2 | 3750 | 7500 | 7500
B12 | Local consultant to draft recommendations for updating the EMS plans based on the workshops conducted to include climate change adaptation for the building sector. | Days | 40 | 450 | 18000 | 18000
B13 | DSA for the local consultant to draft recommendations for the updating of the EMS plans. | Days | 40 | 156 | 6240 | 6240
B14 | Conduct one validation workshop with relevant stakeholders from the DoE, DCA, MoW and other relevant entities to validate the recommendations made for updating the EMS plans to include climate change adaptation for the building sector. | Validation workshop | 1 | 3750 | 3750 | 3750
B15 | Conduct annual workshops, starting in Year 2 and continuing for the remaining project period, with relevant stakeholders from the DoE, DCA, MoW and other relevant entities to review the EMS plans and update these plans where necessary based on changing climatic conditions. | Workshops | 5 | 3750 | 18750 |  | 3750 | 3750 | 3750 | 3750 | 3750
B16 | Annual meetings, starting in Year 3 and continuing for the duration of the implementation period, with participation from relevant stakeholders to collate and share lessons learned from implementing the EMS plans. | Meetings | 4 | 3750 | 15000 |  |  | 3750 | 3750 | 3750 | 3750
B17 | Local consultant to update the EMS plans based on the outcomes of the annual engagement workshops (@20 days per year starting in Year 3 and continuing for the duration of the project implementation period) | Days | 60 | 450 | 27000 |  |  | 6750 | 6750 | 6750 | 6750
B18 | One validation workshop annually with relevant project stakeholders to validate the revised EMS plans. | Validation workshop | 4 | 3750 | 15000 |  |  | 3750 | 3750 | 3750 | 3750
B19 | International finance expert contracted to consult with representatives from the public and private sector to identify entry points for accessing the SIRF fund for climate change adaptation measures that exceed the current thresholds of the fund, including introducing incremental cost reasoning to selection criteria, combined with incentive programmes, levies, insurance/risk management products and increased replenishment. | Days | 60 | 750 | 45000 |  | 45000
B20 | DSA for the international finance expert. | Days | 60 | 156 | 9360 |  | 9360
B21 | One return flight for the international finance expert. | Return flight | 1 | 3000 | 3000 |  | 3000
B22 | Conduct three annual engagement workshops with representatives from the SIRF Fund, relevant government entities and the private sector to facilitate interactions on how to refine the SIRF Fund's list of adaptation options using an evidenced-based approach that draws lessons from the SCCF and EDA projects as well as the implementation of on-the-ground adaptation interventions under Activity 1.1. | Engagement workshops | 18 | 3750 | 67500 | 11250 | 11250 | 11250 | 11250 | 11250 | 11250
B23 | Local consultant to develop a refined list of adaptation options for the SIRF Fund based on the engagements with relevant stakeholders and using an evidenced-based approach that draws lessons from the SCCF and EDA projects as well as the implementation of on-the-ground adaptation interventions under Activity 1.1. | Days | 20 | 450 | 9000 |  | 9000
B24 | Hold annual engagement workshops with representatives from the SIRF Fund, relevant government entities and the private sector to review the funding processes and procedures for climate proofing infrastructure and update them where necessary. | Engagement workshops | 6 | 3750 | 22500 |  | 4500 | 4500 | 4500 | 4500 | 4500
B25 | International consultant to provide annual training to decision-makers from NODS, DCA and PWD on how to access financial resources from the SIRF Fund for implementing climate change adaptation measures in the building sector. | Days | 120 | 750 | 90000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
B26 | DSA for the international consultant contracted to provide training to decision-makers on accessing financing for implementing climate change adaptation measures in the building sector. | Days | 120 | 156 | 18720 | 3120 | 3120 | 3120 | 3120 | 3120 | 3120
B27 | One return flight per year for the international consultant contracted to provide training to decision-makers on accessing financing for implementing climate change adaptation measures in the building sector. | Return flights | 6 | 3000 | 18000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000
B28 | Annual training workshops facilitated by the international consultant for decision-makers from NODS, DCA and PWD on how to access financial resources from the SIRF Fund for implementing climate change adaptation measures in the building sector. | Training workshops | 6 | 3750 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750
B29 | Annual engagement workshops to collate and share lessons learned generated from interactions on the use of the SIRF Fund as well as SIRF Fund application & funding process, including fund replenishment. | Engagement workshops | 6 | 3750 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750
B30 | Two training workshops per year for the duration of the project period for building inspectors from DCA, building maintenance teams from PWD as well as other technical staff from these institutions on the implementation of the operational procedures for the long-term maintenance of climate-proofing interventions in the target buildings, based on building-specific O&M plans and updated national building code. | Training workshops | 12 | 3750 | 45000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
B31 | International consultant to design and implement a long-term monitoring framework for building-specific climate-proofing measures – including cost-benefit analyses – to demonstrate the long-term adaptation benefits. | Days | 120 | 750 | 90000 | 90000
B32 | DSA for the international consultant contracted to design the long-term monitoring framework. | Days | 120 | 156 | 18720 | 18720
B33 | One return flight for the international consultant contracted to design the long-term monitoring framework. | Return flight | 1 | 3000 | 3000 | 3000
B34 | One engagement workshop with relevant stakeholders conducted at mid-term (Year 3) to assess the monitoring framework developed for building-specific climate-proofing measures and update the framework where necessary. | Engagement workshop | 1 | 3750 | 3750 |  |  | 3750
B35 | Engagement meetings with local training institutions such as ABICE to establish partnerships for the development and delivery of certified courses to the public and private sectors on climate change adaptation measures specific to the building sector, including best practices for implementing, monitoring and maintaining these measures in line with the national building code. | Engagement meetings | 6 | 3750 | 22500 |  | 22500
B36 | Contractual services for the partner institution to develop certified training programmes on climate change adaptation measures specific to the building sector, including best practices for implementing, monitoring and maintaining these measures in line with the national building code. | Contract | 1 | 40000 | 40000 |  | 40000
B37 | Contractual services for the annual delivery (starting in Year 2) of certified training programmes on climate change adaptation measures specific to relevant technical staff from MoW and DCA, as well as building inspectors, engineers, architects and draughtsmen on climate change adaptation technologies, including climate-resilient RE and water harvesting solutions, and how to apply the updated national building code during the installation of these technologies. | Contract | 1 | 750000 | 750000 |  | 150000 | 150000 | 150000 | 150000 | 150000
B38 | Local consultant to design a gender-sensitive awareness campaign targeting the public and private sectors on the updated Building Code, the benefits of taking up climate-adaptive solutions within the buildings sector as well as the availability of certified climate change courses. | Days | 60 | 450 | 27000 | 27000
B39 | DSA for the local consultant contracted to design the awareness raising campaign. | Days | 60 | 156 | 9360 | 9360
B40 | Purchase materials for the awareness raising campaign. (This will be financed using in-kind co-financing from the GoAB.) | Campaign materials | 6 | 10000 | 60000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | In kind |  | 60000 |  | 60000
B41 | Local consultant contracted for the annual implementation the awareness raising campaign. The Communications Officer and Monitoring and Gender Officer will assist with the implementation of the awareness raising campaign to ensure that it is conducted in a gender-sensitive and that communication of information is undertaken in an easily interpreted and locally appropriate manner. | Days | 480 | 450 | 216000 | 36000 | 36000 | 36000 | 36000 | 36000 | 36000
B42 | DSA for the local consultant to implement the awareness raising campaign. | Days | 480 | 156 | 74880 | 12480 | 12480 | 12480 | 12480 | 12480 | 12480
B43 | Local consultant to design a gender-sensitive awareness-raising campaign within the government system on the availability of the courses developed under Sub-activity 2.1.1. | Days | 40 | 450 | 18000 | 18000
B44 | DSA for the international consultant contracted to design the awareness raising campaign. | Days | 40 | 156 | 6240 | 6240
B45 | Purchase materials for the awareness raising campaign. (This will be financed using cash co-financing.) | Campaign materials | 6 | 10000 | 60000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | cash. |  | 60000 | 60000
B46 | Local consultant contracted for the annual implementation the awareness raising campaign, specifically targeting relevant government stakeholders. The Communications Officer and Monitoring and Gender Officer will assist with the implementation of the awareness raising campaign to ensure that it is conducted in a gender-sensitive and that communication of information is undertaken in an easily interpreted and locally appropriate manner. | Days | 240 | 450 | 108000 | 18000 | 18000 | 18000 | 18000 | 18000 | 18000
B47 | DSA for the local consultant to implement the awareness raising campaign. | Days | 240 | 156 | 37440 | 6240 | 6240 | 6240 | 6240 | 6240 | 6240
B48 | Engagement meetings with local training institutions such as ABICE to establish partnerships for the development and delivery of certified courses to develop and deliver a training programme that targets the local workforce on how to install, operate and maintain climate change adaptation technologies in the building sector as well as implement early action protocols. | Engagement meetings | 6 | 3750 | 22500 |  | 22500
B49 | Contractual services for the development of training modules based on the engagement meetings conducted with relevant local training institutions and in line with regional and international occupational standards for climate change adaptation in the building sector. | Contract | 1 | 40000 | 40000 |  | 40000
B50 | Contractual services for the annual delivery of training modules developed in line with regional and international occupational standards for climate change adaptation in the building sector. | Contract | 1 | 600000 | 600000 |  | 120000 | 120000 | 120000 | 120000 | 120000
B51 | Local consultant to design an awareness building campaign on the opportunity for training on the installation, operation and maintenance of climate change adaptation technologies in the building sector, with the support of training institutions. | Days | 40 | 450 | 18000 |  | 18000
B52 | DSA for the local consultant contracted to design the awareness raising campaign. | Days | 40 | 156 | 6240 |  | 6240
B53 | Purchase materials for the awareness raising campaign. (This will be financed using in-kind co-financing from the GoAB.) | Campaign materials | 5 | 10000 | 50000 |  | 10000 | 10000 | 10000 | 10000 | 10000 | In kind |  | 50000 |  | 50000
B54 | Local consultant to implement the awareness building campaign on the opportunity for training on the installation, operation and maintenance of climate change adaptation technologies in the building sector, with the support of training institutions. The Communications Officer and Monitoring and Gender Officer will assist with the implementation of the awareness raising campaign to ensure that it is conducted in a gender-sensitive and that communication of information is undertaken in an easily interpreted and locally appropriate manner. | Days | 300 | 450 | 135000 |  | 27000 | 27000 | 27000 | 27000 | 27000
B55 | DSA for the local consultant contracted to implement the awareness raising campaign. | Days | 300 | 156 | 46800 |  | 9360 | 9360 | 9360 | 9360 | 9360
B56 | A contingency fee has been included in the project budget to mitigate the risk of increasing project input costs affecting the implementation of project interventions. As noted in Annex 22: Building assessment, a post-disaster scenario in Antigua and Barbuda (whereby the country experiences a hurricane or other extreme event) results in an estimated 30% increase in input costs, particularly around materials, staff costs and equipment required to install climate-resilient solutions on infrastructure. Antigua and Barbuda is currently experiencing the post-disaster impacts of Hurricane Irma (2017), and data this is currently being collected is showing that the cost of climate-proofing critical infrastructure is significantly higher than estimated. It is also likely that Antigua and Barbuda will experience a hurricane during the project period. This would compound the post-disaster impacts of Hurricane Irma that are currently being absorbed by the national government and population. A 5% contingency is therefore being requested for Project Output 2 to mitigate the risk of the abovementioned factors affecting the implementation of project interventions. This contingency will be used only if necessary and in line with the agreements between the Accredited Entity and the GCF. | Contingency fee | 1 | 144037 | 144037 | 21544.5 | 32515 | 22635 | 22447.5 | 22447.5 | 22447.5
C1 | Contractual services for the installation of the centralised online server and associated software to be housed within ABMS. This cost also includes procurement and uninterrupted power supply, which will allow the server to function during power outages that result from a storm. | Contract | 1 | 12000 | 12000 | 12000
C2 | International consultant to develop training modules on how to collect, process and manage climate data in real time using the centralised online server. | Days | 20 | 750 | 15000 | 15000
C3 | DSA for the international consultant contracted to develop training modules on the collection, processing and management of climate data in real time using the centralised online server. | Days | 20 | 156 | 3120 | 3120
C4 | One return flight for the international consultant contracted to develop training modules on the collection, processing and management of climate data in real time using the centralised online server. | Return flight | 1 | 3000 | 3000 | 3000
C5 | Conduct annual training workshops, using the training modules developed, for relevant technical staff from ABMS on how to collect, process and manage climate data in real time using the centralised online server. | Training workshops | 6 | 3750 | 22500 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750
C6 | One meeting between the WMO Regional Climate Centre and ABMS to sign a MoU for a knowledge exchange trip to be conducted for relevant staff from ABMS to strengthen their technical and institutional capacity to implement impact-based forecasting. | Meeting | 1 | 3750 | 3750 | 3750
C7 | Conduct a knowledge exchange trip for senior staff and technical experts from ABMS to the nearest Regional Climate Centre, which is under the auspices of the World Meteorological Organization (WMO), to strengthen the technical and institutional capacity within ABMS for impact-based forecasting. This cost includes return flights for four senior staff from ABMS @US$3,000 each, DSA of US$367 each for two weeks and a two week workshop (10 days) @US$3,750 per workshop. | Knowledge exchange trip | 1 | 70052 | 70052 |  | 70052
C8 | International consultant to develop training modules for technical staff from AMBS on how to develop early warning information products, including infographics that are locally appropriate and easily interpreted by vulnerable communities. | Days | 20 | 750 | 15000 |  | 15000
C9 | DSA for the international consultant contracted to develop training modules for ABMS on how to develop early warning information products. | Days | 20 | 156 | 3120 |  | 3120
C10 | One return flight for the international consultant contracted to develop training modules for ABMS on how to develop early warning information products. | Return flight | 1 | 3000 | 3000 |  | 3000
C11 | Annual training workshops starting in Year 2 for technical staff from ABMS on how to develop early warning information products using the modules developed by the international consultant. | Training workshops | 5 | 3750 | 18750 |  | 3750 | 3750 | 3750 | 3750 | 3750
C12 | International consultant to design and operationalise a formal communication protocol to facilitate effective communication of impact-based forecasts from ABMS to decision-makers within relevant government entities responsible for preparation ahead of an extreme climate event. The Communications Officer will oversee the design and operationalisation of this protocol to ensure that the protocol is designed in a locally appropriate, easily interpreted manner. | Days | 40 | 750 | 30000 |  | 30000
C13 | DSA for the international consultant contracted to design and operationalise the communication protocol. | Days | 40 | 156 | 6240 |  | 6240
C14 | One return flight for the international consultant contracted to design and operationalise a formal communication protocol. | Return flight | 1 | 3000 | 3000 |  | 3000
C15 | Local consultant to assist the international consultant in the design and operationalisation of the communication protocol. | Days | 80 | 450 | 36000 |  | 36000
C16 | DSA for the local consultant contracted to assist the international consultant with the design and operationalisation of the communication protocol. | Days | 80 | 156 | 12480 |  | 12480
C17 | Two training workshops per year, starting in Year 2, for relevant staff from ABMS, NODS, MoW, MoHWE, MoEST and other relevant government entities on how to use the formalised communication protocol effectively. | Training workshops | 10 | 3750 | 37500 |  | 7500 | 7500 | 7500 | 7500 | 7500
C18 | Local consultant to design and conduct an awareness raising campaign within the government system on the existence and application of the formalised communication protocol to facilitate effective communication of impact-based forecasts from ABMS to decision-makers within relevant government entities responsible for preparation ahead of an extreme climate event. The Communications Officer will oversee the design and implementation of this awareness campaign to ensure that the protocol is designed in a locally appropriate, easily interpreted manner. | Days | 120 | 450 | 54000 |  | 10800 | 10800 | 10800 | 10800 | 10800
C19 | DSA for the local consultant contracted to design and implement the awareness campaign on the existence and application of the formal communication protocol. | Days | 120 | 156 | 18720 |  | 3744 | 3744 | 3744 | 3744 | 3744
C20 | Purchase campaign materials. | Campaign materials | 5 | 10000 | 50000 |  | 10000 | 10000 | 10000 | 10000 | 10000 |  |  | 50000
C21 | International consultant to design and implement early action protocols for critical public service and community buildings with variable responses dependent on the anticipated intensity of the incoming storm. The Communications Officer will oversee the design and implementation of this protocol to ensure that the protocol is designed in a locally appropriate, easily interpreted manner. | Days | 40 | 750 | 30000 |  | 30000
C22 | DSA for the international consultant contracted to design and implement the early action protocol. | Days | 40 | 156 | 6240 |  | 6240
C23 | One return flight for the international consultant contracted to design and implement the early action protocol. | Return flight | 1 | 3000 | 3000 |  | 3000
C24 | Local consultant to assist the international consultant with the design and implementation of the early action protocol. | Days | 80 | 450 | 36000 |  | 36000
C25 | DSA for the local consultant contracted to assist the international consultant with the design and implementation of the early action protocol. | Days | 80 | 156 | 12480 |  | 12480
C26 | Local consultant to design and conduct an awareness raising campaign within the government system on the existence and application of early action protocols for critical public service and community buildings with variable responses dependent on the anticipated intensity of the incoming storm. The Communications Officer will oversee the design and implementation of this awareness campaign to ensure that the protocol is designed in a locally appropriate, easily interpreted manner. | Days | 120 | 450 | 54000 |  | 54000
C27 | DSA for the local consultant contracted to design and implement the awareness campaign on the existence and application of the early action protocols. | Days | 120 | 156 | 18720 |  | 18720
C28 | Purchase campaign materials. (This will be financed using in-kind co-financing from the GoAB.) | Campaign materials | 5 | 10000 | 50000 |  | 10000 | 10000 | 10000 | 10000 | 10000 | in kind |  | 50000 |  | 50000
C29 | Three training workshops per year, starting in Year 2, for relevant staff from ABMS, NODS, MoW, MoHWE, MoEST, other relevant public sector entities and private sector representatives on how to use the early action protocol effectively. | Training workshops | 15 | 3750 | 56250 |  | 11250 | 11250 | 11250 | 11250 | 11250
C30 | International consultant to develop training modules for relevant staff from ABMS on the effective dissemination of early warning information products to critical service providers as well as the private sectors to facilitate early action. The Communications Officer will oversee the development of these training modules to ensure that they are designed to be locally appropriate and easily interpreted. | Days | 60 | 750 | 45000 |  | 45000
C31 | DSA for the international consultant contracted to develop training modules on the effective dissemination of early warning information products. | Days | 60 | 156 | 9360 |  | 9360
C32 | One return flight for the international consultant contracted to develop training modules on the effective dissemination of early warning information products. | Return flight | 1 | 3000 | 3000 |  | 3000
C33 | Local consultant to assist the international consultant with the development of training modules for relevant staff from ABMS on the effective dissemination of early warning information products to critical service providers as well as the private sectors to facilitate early action. | Days | 80 | 450 | 36000 |  | 36000
C34 | DSA for the local consultant contracted to assist the international consultant with the development of training modules for relevant staff from ABMS on the effective dissemination of early warning information products. | Days | 80 | 156 | 12480 |  | 12480
C35 | Two training workshops per year, starting in Year 2, for relevant staff from ABMS on how to effectively disseminate early warning information products that are locally appropriate and easily interpreted by all citizens of Antigua and Barbuda. These workshops will be informed by the training modules developed by the international and local consultants. | Training workshops | 10 | 3750 | 37500 |  | 7500 | 7500 | 7500 | 7500 | 7500
C36 | Annual engagement workshops for relevant staff from ABMS, NODS, MoHWE, MoEST and other relevant critical public service representatives to collate and share lessons learned generated from the use of effective methods for disseminating early warning information products. | Training workshops | 5 | 3750 | 18750 |  | 3750 | 3750 | 3750 | 3750 | 3750
C37 | A contingency fee has been included in the project budget to mitigate the risk of increasing project input costs affecting the implementation of project interventions. As noted in Annex 22: Building assessment, a post-disaster scenario in Antigua and Barbuda (whereby the country experiences a hurricane or other extreme event) results in an estimated 30% increase in input costs, particularly around materials, staff costs and equipment required to install climate-resilient solutions on infrastructure. Antigua and Barbuda is currently experiencing the post-disaster impacts of Hurricane Irma (2017), and data this is currently being collected is showing that the cost of climate-proofing critical infrastructure is significantly higher than estimated. It is also likely that Antigua and Barbuda will experience a hurricane during the project period. This would compound the post-disaster impacts of Hurricane Irma that are currently being absorbed by the national government and population. A 5% contingency is therefore being requested for Project Output 3 to mitigate the risk of the abovementioned factors affecting the implementation of project interventions. This contingency will be used only if necessary and in line with the agreements between the Accredited Entity and the GCF. | Contingency fee | 1 | 37300.6 | 37300.6 | 2031 | 24860.8 | 2602.2 | 2602.2 | 2602.2 | 2602.2
M&E1 | International consultant to conduct the Independent Interim Evaluation for the project. | IIE contract | 1 | 114400 | 114400 |  |  | 114400
M&E2 | International consultant to conduct the Final Evaluation Report for the project. | FER contract | 1 | 143000 | 143000 | [5 empty] | 143000
PMU1 | Project Manager | Salary | 6 | 40000 | 240000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000
PMU2 | Project Coordinator | Salary | 6 | 45000 | 270000 | 45000 | 45000 | 45000 | 45000 | 45000 | 45000
PMU3 | Financial Officer (This will be financed using in-kind co-financing from the GoAB.) | Salary | 6 | 20000 | 120000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | IN kind |  | 120000 |  | 120000
PMU4 | Procurement Officer (This will be financed using in-kind co-financing from the GoAB.) | Salary | 6 | 20000 | 120000 | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | In kind |  | 120000 |  | 120000
PMU5 | Administrative Officer (This will be financed using in-kind co-financing from the GoAB.) | Salary | 6 | 25000 | 150000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | In kind |  | 150000 |  | 150000
PMU6 | Monitoring and evaluation officer specializing in training impacts on a gender basis (This will be financed using in-kind co-financing from the GoAB.) | Salary | 6 | 35000 | 210000 | 35000 | 35000 | 35000 | 35000 | 35000 | 35000 | in Kind |  | 210000 |  | 210000
PMU7 | Environmental, Social and Gender Officers person | Salary | 6 | 30000 | 180000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
PMU8 | Communications Officer (This will be financed using in-kind co-financing from the GoAB.) | Salary | 6 | 25000 | 150000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | In Kind |  | 150000 |  | 150000
PMU9 | Technical Advisors (Renewable energy and Gender sensitive training) | Salary | 6 | 60000 | 360000 | 60000 | 60000 | 60000 | 60000 | 60000 | 60000
PMU10 | Office space for the project management unit (This will be financed using cash and in-kind co-financing for material staff costs, split 40% and 60%, respectively.) | Rent for office space | 6 | 30000 | 180000 | 30000 | 30000 | 30000 | 30000 | 30000 | 30000 | 40% cash, 60% in Kind |  | 180000 | 72000 | 108000
[5 empty] | 1980000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 1980000
[14 empty] | 13458034.7989 | 4899665.2572 | 8508369.5418
12528034.7989
[13 empty] | O1 | 12258034.7989 | 0
[13 empty] | O2 | 170000
[13 empty] | O3 | 100000

## Cost categories
Cost categories | Budget note descriptions for each cost category
Staff cost | Please eloborate on staff position involved in this particular stage of the project as well as associated costs
Local consultants | BN to detail unit cost and duration of consultant(s) work and position
International consultant | Similar to above (A2)
Equipment | Include machinery spec, equipment name, quantity and unit cost in BN
Training, workshops, and conferences | Ensure the number of workshops anticipated, number of people attending, target group, cost per work workshop, venue cost is provided
Travel | Breakdown travel cost information by number of people and cost per person and separating DSA where applicable.
Professional or contractual services | Identify professional costs. NB. Auditing costs are Project Management Costs.
Funding source
GCF
GoAB

## Cost calculations for upgrades
Intervention | Cost | Total building footprint (m2) | Cost per m2 | Total floor size of buildings to receive interventions | Total cost of interventions for all priority buildings
Non-adaptation upgrades
General structural repairs | 1230000 | 18860 | 65.2174 | 21999 | 1434717.3913
General building repairs | 1630000 | 18860 | 86.4263 | 31003 | 2679474.5493
General electrical | 3210000 | 18860 | 170.2015 | 31682 | 5392323.4358
Wastewater treatment | 600000 | 18860 | 31.8134 | 29186 | 928504.772
Subtotal non-adaptation upgrades |  |  |  |  | 10435020.1485
Adaptation upgrades
Extreme weather resistance (roofs, doors and windows) | 4545000 | 18860 | 240.9862 | 31431 | 7574437.6988
On-site back-up power RE supply and storage | 5470000 | 18860 | 290.0318 | 25729 | 7462228.526
Off-site emergency RE strategic stocks | 440000 | 18860 | 23.3298 | 27416 | 639609.7561
Water storage and supply | 1960000 | 18860 | 103.9236 | 32152 | 3341353.1283
Stormwater drainage | 530000 | 18860 | 28.1018 | 31963 | 898217.9215
Subtotal adaptation upgrades |  |  |  |  | 19915847.0308
Total cost of interventions |  |  |  |  | 30350867.1792
The cost calculations presented in the table above are taken from Annex 22: Building assessment. In this assessment, the cost of implementing adaptation and non-adaptation interventions was determined by square metre of floor size for the representative sample. The cost per metre squared of floor space has been extrapolated across the total relevant floor size of priority buildings to receive upgrades. The building matrix that presents the floor size of all 54 priortiy buildings to be targeted under the project is presented in Section 10 of Annex 2: Feasibility Study. Since this study was completed more detailed pricing has come into the DOE. As a result of the hurricanes in the region and the demand for building supplies the cost has increase. The % increase over cost in the techncial feasibility study is over 50%. The cost was adjust for the GCF to 50% for buyildings only. The Government will then cover the additional cost increase which is expected during the life of the project. This is only expected to impact on the building cost only and not the Renewable energy.
Intervention | Cost | Total building footprint (m2) | Cost per m2 | Total floor size of the Good Shepherd Children’s Home to receive intervention | Total cost of interventions for the Good Shepherd Children’s Home
Non-adaptation upgrades
General building repairs | 1630000 | 18860 | 86.4263 | 283 | 24458.6426
General electrical | 3210000 | 18860 | 170.2015 | 283 | 48167.0201
Wastewater treatment | 100000 | 18860 | 5.3022 | 283 | 1500.5302
Subtotal non-adaptation upgrades |  |  |  |  | 74126.193
Adaptation upgrades
Extreme weather resistance (roofs, doors and windows) | 3030000 | 18860 | 160.6575 | 283 | 45466.0657
On-site Back-Up RE power supply and storage | 5470000 | 18860 | 290.0318 | 283 | 82079.0032
Off-site emergency RE strategic stocks | 440000 | 18860 | 23.3298 | 283 | 6602.333
Water storage and supply | 1960000 | 18860 | 103.9236 | 283 | 29410.3924
Stormwater drainage | 530000 | 18860 | 28.1018 | 283 | 7952.8102
Subtotal adaptation upgrades |  |  |  |  | 171510.6045
Total cost of all interventions for Good Shepherd Children’s Home |  |  |  |  | 245636.7975
The cost calculations presented in the table above are present the non-adaptation and adaptation cost of upgrading the Good Shepherd Children's Home only. These upgrades that are considered cofinancing will be funded by the SIRF Fund and the Ministry of Finance. The SIRF Fund which is a government fund that finances climate change adaptation intiatives. The costs of the interventions presented above are taken from Annex 22: Building assessment. In this assessment, the cost of implementing adaptation and non-adaptation interventions was determined by square metre of floor size for the representative sample. The cost per metre squared of floor space has been extrapolated across the total relevant floor size of priority buildings to receive upgrades. The building matrix that presents the floor size of all 54 priortiy buildings, including the Good Shepherd's Children Home, to be targeted under the project is presented in Section 10 of Annex 2: Feasibility Study.
Note: The project cost estimates were conducted in 2018 and early 2019, 12 months after the Hurricane Season. The initial reconstruction began with materials sent from bilaterial donors such as China. This did not give the AE time to understand any price increases from the private sector. True prices are being understood now that private sector reconstruction is being undertaken. The DOE is noting a price increase of 40 - 80% on imported materials. This is mainly driven by demand from all of the countries hit by the hurricanes in 2017 and then again in 2019. The budget has therefore been increased by an additonal 50% for construction and water interventions. The RE intervention is not affected.

## Term sheet disbursement
Output | Description | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Total
Output 1 |  | 4669079.2897 | 6262289.9369 | 3463096.8142 | 3562785.6442 | 3562785.6442 | 3562785.6442 | 25082822.9735
1 | Staff cost | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Local consultants | 157500 | 11250 | 0 | 0 | 0 | 0 | 168750
1 | International consultant | 20250 | 0 | 0 | 0 | 0 | 0 | 20250
1 | Equipment | 0 | 6602.333 | 0 | 213203.252 | 213203.252 | 213203.252 | 646212.0891
1 | Training, workshops, and conferences | 67500 | 30000 | 11250 | 11250 | 11250 | 11250 | 142500
1 | Travel | 66060 | 3900 | 0 | 0 | 0 | 0 | 69960
1 | Professional or contractual services | 4357769.2897 | 6210537.6039 | 3451846.8142 | 3338332.3922 | 3338332.3922 | 3338332.3922 | 24035150.8844
Output 2 |  | 430890 | 650300 | 452700 | 448950 | 448950 | 448950 | 2880740
2 | Staff cost | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Local consultants | 135000 | 108000 | 87750 | 87750 | 87750 | 87750 | 594000
2 | International consultant | 105000 | 60000 | 15000 | 15000 | 15000 | 15000 | 225000
2 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Training, workshops, and conferences | 41250 | 79500 | 45750 | 42000 | 42000 | 42000 | 292500
2 | Travel | 74640 | 52800 | 34200 | 34200 | 34200 | 34200 | 264240
2 | Professional / Contractual Services | 75000 | 350000 | 270000 | 270000 | 270000 | 270000 | 1505000
Output 3 |  | 40620 | 497216 | 52044 | 52044 | 52044 | 52044 | 746012
3 | Staff cost | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Local consultants | 0 | 172800 | 10800 | 10800 | 10800 | 10800 | 216000
3 | International consultant | 15000 | 120000 | 0 | 0 | 0 | 0 | 135000
3 | Equipment | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Training, workshops, and conferences | 7500 | 107552 | 37500 | 37500 | 37500 | 37500 | 265052
3 | Travel | 6120 | 96864 | 3744 | 3744 | 3744 | 3744 | 117960
3 | Professional / Contractual Services | 12000 | 0 | 0 | 0 | 0 | 0 | 12000
PMC including M&E |  | 175000 | 175000 | 289400 | 175000 | 175000 | 318000 | 1307400
| Staff cost | 175000 | 175000 | 289400 | 175000 | 175000 | 318000 | 1307400
| International consultant | 0 | 0 | 114400 | 0 | 0 | 143000 | 257400
Contingency |  | 490483.429 | 683604.7937 | 371546.8814 | 381328.2644 | 381328.2644 | 381328.2644 | 2689619.8973
| Contingency fee | 490483.429 | 683604.7937 | 371546.8814 | 381328.2644 | 381328.2644 | 381328.2644 | 2689619.8973
Total |  | 5806072.7186 | 8268410.7306 | 4628787.6957 | 4620107.9086 | 4620107.9086 | 4763107.9086 | 32706594.8708
|  | 5806072.7186 | 8268410.7306 | 4628787.6957 | 4620107.9086 | 4620107.9086 | 4763107.9086
|  | 5806072.7186 | 17.75%
|  | 8268410.7306 | 25.28%
|  | 4628787.6957 | 14.15%
|  | 4620107.9086 | 14.13%
|  | 4620107.9086 | 14.13%
|  | 4763107.9086 | 14.56%