## Sheet1
Annex 5 Implementation Timetable
Project/Programme Title: ASER Solar Rural Electrification Project
COMPONENTS/OUTPUTS | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3
1) Technical assistance to the solar rural electrification stakeholders | 2021 Q1: estimation of time needed from FAA effectiveness to first disbursement received by the country
Ouput 1.1 - Capacity building of rural electrification stakeholders
Activity 1.1.1 Training on procurement procedures, project management and GCF requirements | 2021 Q4: Workshop ToR and report
Activity 1.2.1 - Seminars and trips and workshops (technology watch, public consultations, conferences, sharing of experiences, etc.) | 2021 Q3: Project Launch workshops and public consultations in different regions; 2022 Q1: technsology watch trips: ex Intersolar event; 2023 Q1: technsology watch trips: ex Intersolar event; 2024 Q2: conferences, sharing of experiences, etc.; 2026 Q1: conferences, sharing of experiences, etc.
Ouput 1.2 - Gender action plan implementation | 2023 Q2: Monitoring report of the implementation of the gender action plan; 2024 Q2: Monitoring report of the implementation of the gender action plan; 2025 Q2: Monitoring report of the implementation of the gender action plan; 2026 Q2: gender action plan evaluation of the programme
Activity 1.2.1 - gender-relevant community-organizations mapping & tutoring | 2021 Q3: Memorandum establishing committee; 2021 Q4: List of CBOs identified by village; 2022 Q2: Creation of local stakeholders committees; 2022 Q4: Meeting with local committees; 2024 Q1: income generating activities survey; 2026 Q2: income generating activities survey
Activity 1.2.2 - gender-stakeholders training (PMU - Ministry of Energy - local operators – community organizations) | 2022 Q2: Training program
Activity 1.2.3 - gender-oriented communication campaign | 2021 Q4: gender-sensitive communication campaign on the project using all media (loca radio, flyers, focus group with local committees created to facilitate the implementation of the project)
Ouput 1.3 - Environmental & social safeguards downstream activities
Activity 1.3.1 - E&S measures implementation and monitoring | 2021 Q3: implementation of DEEC / ASER convention Action Plan; 2022 Q2: E&S Monitoring report; 2023 Q2: E&S Monitoring report; 2024 Q2: E&S Monitoring report; 2025 Q2: E&S Monitoring report; 2026 Q2: E&S Monitoring report
Activity 1.3.2 - Establishment of a recycling unit for batteries and other waste (CFL, other electronics) | 2022 Q2: Terms of Reference publication; 2023 Q2: Selection of the operator and Commissioning of the facility
2) Procurement and Installation of solar powered mini-grids
Output 2.1 - Preparation of detailed Engineering Studies
Activity 2.1.1 - Site selection, engineering studies & Specific environmental and social analysis for each site | 2021 Q3: detailed preliminary project and specifications for the creation of 1,000 mini-solar; 2022 Q1: EPC ToR for Procurement
Ouput 2.2 - Supply, installation and commissioning of equipment
Activity 2.2.1 - Solar PV power plants construction and minigrid deployment | 2022 Q2: Contractualization, supply, factory inspection, installation of first kits; 2022 Q3: Installation of kits and transfer of villages to concessionnaire; 2023 Q3: Installation of kits and transfer of villages to concessionnaire; 2024 Q3: Installation of kits and transfer of villages to concessionnaire; 2025 Q3: Exploitation of all villages by concessionnaires
Activity 2.2.2 - Smart meters installation & misc. | bar: 2022 Q2 to 2026 Q2
Output 2.3 - Modern public lighting
Activity 2.3.1 - Deployments of solar street lighting | 2022 Q3: Terms of Reference publication; 2023 Q2: Installation project report; 2024 Q2: Installation project report; 2026 Q2: Installation project report
Output 2.4 - Control and supervision of work
Activity 2.4.1 - Control and supevision of work | 2022 Q2: Installation project report; 2023 Q2: Installation project report; 2024 Q2: Installation project report; 2026 Q2: Installation project report
3) Incentives for Social & Productive Use of Electricity
Output 3.1 - Gender & social connection coupons
Activity 3.1.1 - Connection of eligible social services, women& youth-entrepreneurs to the PV mini-grids | 2021 Q3: PREM baseline surveys; 2022 Q1: Coupons design workshop; 2022 Q2: Distribution of coupons to Concessionnaires; 2022 Q3: Coupon distribution monitoring and reporting; 2023 Q3: Coupon distribution monitoring and reporting; 2024 Q3: Coupon distribution monitoring and reporting; 2025 Q3: Coupon distribution monitoring and reporting
Ouput 3.2 - Microfinanced productive equipment credits guarantees
Activity 3.2.1 - Implementation of mechanism to facilitate access to productive equipment financing through microfinance | 2021 Q3: MFIs due-diligence; 2021 Q4: Guarantee issuer selection and fund allocation; 2022 Q3: Monitoring and reporting of disbursments; 2023 Q3: Monitoring and reporting of disbursments and Mid Term Evaluation; 2024 Q3: Monitoring and reporting of disbursments; 2025 Q3: Monitoring and reporting of disbursments; 2026 Q1: Final Monitoring and Evaluation Report
Project Monitoring*
Project Staffing, Project Operationalisation, Project Monitoring, Evaluation and Reporting (Inception, APR, Financial, Project Completion etc.) | 2021 Q3: Recruitment of Project Staff; 2021 Q4: Inception Report; 2022 Q3: APR; 2023 Q3: APR; 2024 Q1: Interim Evaluation; 2024 Q3: APR; 2025 Q3: Completion Report; 2026 Q3: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.