## Guidance
Guidance Note

## SUMMARY
Procurement Plan SUMMARY
Country: | Brazil
Project Name: | Planting Climate Resilience in Rural Communities of the Northeast (PCRP)
Project ID: | 2000002253
Version | 1.4
Version Date | 2020-07-23
Prepared by: | Frederico Lacerda (COA)
Approved by: | Claus Reiner (Country Director)
Procurement Category | Plan |  | Actual
Currency | USD | LCU | USD | LCU
Goods | 651581 | 0 | 0 | 0
Works | 42178 | 0 | 0 | 0
Consulting Services | 676379 | 0 | 0 | 0
TOTAL | 1370138 | 0 | 0 | 0
Prior Review Thresholds
Thresholds | Goods | Works | Non-Consulting Services | Firms - Consulting Services | Individuals - Consulting Services
Prior Review | > US$ 200,000.00 | > US$ 200,000.00 | > US$ 100,000.00 | > US$ 100,000.00 | > US$ 50,000.00
All Direct Contracting and Single-Source Procurements are Prior Review (in alignment with IFAD Procurement Handbook).
Procurement Method Thresholds
| Shopping | NCB | ICB
Goods | < US$ 100,000.00 | > US$ 100,000.00 to < US$ 200,000.00 | > US$ 200,000.00
Works | < US$ 100,000.00 | > US$ 100,000.00 to < US$ 200,000.00 | > US$ 200,000.00
Non-Consulting Services | < US$ 100,000.00 | > US$ 100,000.00 to < US$ 200,000.00 | > US$ 200,000.00
| ICS/CQS | LCS | QCBS
Individuals | < US$ 50.00 | > US$ 50,000.00 to < US$ 100,000.00 | > US$ 100,000.00
Firms | < US$ 50.00 | > US$ 50,000.00 to < US$ 100,000.00 | > US$ 100,000.00

## GOODS
[6 empty] | Plan | [6 empty] | Plan | [14 empty] | Plan | [5 empty] | 0 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
The 3 rows above are not part of the Plan and must not be modified. Copy these rows to create new procurement items or retrieve Plan Dates formulas if needed.
Procurement Methods NS: National Shopping IS: International Shopping NCB: National Competitive Bidding ICB: International Competitive Bidding LIB: Limited (International) Bidding DC: Direct Contracting
Procurement Plan - Goods
Brazil
Planting Climate Resilience in Rural Communities of the Northeast (PCRP) | [10 empty] | Total Amount
Project ID: 2000002253 | [10 empty] | USD | LCU
Prepared by: Frederico Lacerda (COA) | [10 empty] | 651581 | 0 | Plan
Approved by: Claus Reiner (Country Director) | [10 empty] | 0 | 0 | Actual
Version | 1.4 | 2020-07-23 | Basic Data | [10 empty] | Pre-Qualification | [5 empty] | Bidding Process |  |  |  | Bid Evaluation |  |  |  |  | Contract Award & Signature
AWPB/Component Ref | № | Description | Funding | Lot №/Description | Project Area | Plan vs. Actual | Pre-or Post Qualification | Prior or Post Review | Procurement Method | Envelopes | Amount (USD) | Amount (LCU) | Plan vs. Actual | Submission of PreQual Docs | No Objection Date | PreQual Invitation Date | PreQual Closing Date | Submission of PreQual Report | No Objection Date | Submission of BD | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Submission Tech Eval Rpt | No-objection Date | Submission Combined Eval Rpt* | No-objection Date | Plan vs. Actual | Issue of NOITA&Standstill | Date Contract Award | Date Contract Signature | Contract No. | Vendor Name/ID | Amount (USD) | Amount (LCU) | Remarks on National Methods
AWPB Y1 C1 | 1 | Logistics for local exchange-visits | IFAD | N/A | N/A | Plan | Post-Qual | Post Review | NS | 1 | 19022 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 19022 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C1 | 2 | Logistics for regional exchange-visits | IFAD | N/A | N/A | Plan | Post-Qual | Post Review | NS | 1 | 26051 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 26051 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 3 | Smartphones and equipments for young communicators | GOVT | N/A | N/A | Plan | Post-Qual | Prior Review | NS | 1 | 139695 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-11 | 2022-07-18 | 2022-07-19 | 2022-08-02 | N/A | N/A | 2022-08-09 | 2022-08-16 | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 139695 | 0 | Eletronic Competition
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 4 | Laptops for youths | GOVT | N/A | N/A | Plan | Post-Qual | Post Review | NS | 1 | 5905 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 5905 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 5 | Communication Equipment /e | GOVT | N/A | N/A | Plan | Post-Qual | Post Review | NS | 1 | 30706 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 30706 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 6 | Logistics for for technical meetings at the regional and local level | GOVT | N/A | N/A | Plan | Post-Qual | Post Review | NS | 1 | 11248 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 11248 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 7 | Laptops /b | GOVT | N/A | PMU | Plan | Post-Qual | Post Review | NS | 1 | 54309 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 54309 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 8 | Smarphones /c | GOVT | N/A | PMU | Plan | Post-Qual | Post Review | NS | 1 | 22719 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 22719 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 9 | Printers /d | GOVT | N/A | PMU | Plan | Post-Qual | Post Review | NS | 1 | 4499 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-07-25 | N/A | 2022-07-26 | 2022-08-09 | N/A | N/A | 2022-08-16 | N/A | Plan | 2022-08-16 | 2022-08-18 | 2022-08-20 |  |  | 4499 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 10 | Vehicles and transportation /e | GOVT | N/A | PMU | Plan | Pre-Qual | Prior Review | NCB | 1 | 337427 |  | Plan | 2022-03-21 | 2022-03-28 | 2022-03-30 | 2022-04-29 | 2022-05-13 | 2022-05-20 | 2022-05-30 | 2022-06-06 | 2022-06-08 | 2022-07-23 | N/A | N/A | 2022-08-06 | 2022-08-13 | Plan | 2022-08-25 | 2022-08-30 | 2022-09-01 |  |  | 337427 | 0 | Eletronic Competition
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual

## WORKS
[6 empty] | Plan | [6 empty] | Plan | [14 empty] | Plan | [5 empty] | 0 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
The 3 rows above are not part of the Plan and must not be modified. Copy these rows to create new procurement items or retrieve Plan Dates formulas if needed.
Procurement Methods NS: National Shopping IS: International Shopping NCB: National Competitive Bidding ICB: International Competitive Bidding LIB: Limited (International) Bidding DC: Direct Contracting
Procurement Plan - Goods
Brazil
Planting Climate Resilience in Rural Communities of the Northeast (PCRP) | [10 empty] | Total Amount
Project ID: 2000002253 | [10 empty] | USD | LCU
Prepared by: Frederico Lacerda (COA) | [10 empty] | 42178 | 0 | Plan
Approved by: Claus Reiner (Country Director) | [10 empty] | 0 | 0 | Actual
Version | 1.4 | 2020-07-23 | Basic Data | [10 empty] | Pre-Qualification | [5 empty] | Bidding Process |  |  |  | Bid Evaluation |  |  |  |  | Contract Award & Signature
AWPB/Component Ref | № | Description | Funding | Lot №/Description | Project Area | Plan vs. Actual | Pre-or Post Qualification | Prior or Post Review | Procurement Method | Envelopes | Amount (USD) | Amount (LCU) | Plan vs. Actual | Submission of PreQual Docs | No Objection Date | PreQual Invitation Date | PreQual Closing Date | Submission of PreQual Report | No Objection Date | Submission of BD | No-objection Date | Bid Invitation Date | Bid Closing-Opening | Submission Tech Eval Rpt | No-objection Date | Submission Combined Eval Rpt* | No-objection Date | Plan vs. Actual | Issue of NOITA&Standstill | Date Contract Award | Date Contract Signature | Contract No. | Vendor Name/ID | Amount (USD) | Amount (LCU)
AWPB Y1 C4 | 1 | Refurbishment of Regional and Local PMU Offices /a | GOVT | N/A | PMU | Plan | Post-Qual | Post Review | NS | 1 | 42178 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-10 | N/A | 2022-01-11 | 2022-01-25 | N/A | N/A | 2022-02-01 | N/A | Plan | 2022-02-01 | 2022-02-03 | 2022-02-05 |  |  | 42178 | 0
[6 empty] | Actual |  |  |  |  | 0 | 0 | Actual

## CONSULTING
[5 empty] | Plan | [5 empty] | Plan | [14 empty] | Plan | [8 empty] | 0 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
The 3 rows above are not part of the Plan and must not be modified. Copy these rows to create new procurement items or retrieve Plan Dates formulas if needed.
Selection Methods QCBS: Quality and Cost-Based Selection QBS: Quality-Based Selection CQS: Selection by Consultants' Qualifications LCS: Least-Cost Selection FBS Fixed Budget Selection ICS: Individual Consultants Selection SSS: Sole Source Selection
Procurement Plan - Consulting
Brazil
Planting Climate Resilience in Rural Communities of the Northeast (PCRP) | [8 empty] | Total Amount
Project ID: 2000002253 | [8 empty] | USD | LCU
Prepared by: Frederico Lacerda (COA) | [8 empty] | 676379 | 0 | Plan
Approved by: Claus Reiner (Country Director) | [8 empty] | 0 | 0 | Actual
Version | 1.4 | 2020-07-23 | Basic Data | [8 empty] | EOI Shortlist Procedure | [5 empty] | Proposal Process |  |  |  | Evaluation |  |  |  |  | Contract Award & Signature
AWPB/Component Ref | № | Description* | Funding | Project Area | Plan vs. Actual | Shortlist (Yes¦No) | Prior or Post Review | Procurement Method | Amount (USD) | Amount (LCU) | Plan vs. Actual | Submission of REOI | No Objection Date | REOI Launch Date | EOI Submission Deadline | Submission of Shortlist Report | No Objection Date | Submission of RFP/RCQ | No-objection Date | RFP/RCQ Launch Date | Proposal submission deadline | Submission of TER | No-objection Date | Submission of CER | No-objection Date | Plan vs. Actual | Issue of NOITA&Standstill | Negotiations completed | Submission of Draft Contract and MoN | No-objection Date | Date Contract Award | Date Contract Signature | Contract No. | Vendor Name/ID | Amount (USD) | Amount (LCU)
AWPB Y1 C1 | 1 | Studies to select project areas and TRIPs | GOVT | N/A | Plan | No | Post Review | ICS | 62424 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-01-10 | N/A | 2022-01-12 | 2022-02-02 | 2022-02-16 | N/A | N/A | N/A | Plan | 2022-02-28 | 2022-03-14 | 2022-03-18 | N/A | 2022-03-20 | 2022-03-27 |  |  | 62424 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 2 | Legal studies | GCF | N/A | Plan | Yes | Post Review | ICS | 20808 |  | Plan | 2022-02-07 | N/A | 2022-02-09 | 2022-03-02 | 2022-03-16 | N/A | 2022-03-20 | N/A | 2022-03-22 | 2022-04-12 | 2022-04-26 | N/A | N/A | N/A | Plan | 2022-05-08 | 2022-05-22 | 2022-05-26 | N/A | 2022-05-28 | 2022-06-04 |  |  | 20808 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 3 | Operating services | GCF | N/A | Plan | No | Post Review | QCBS | 24515 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | N/A | 2022-03-23 | 2022-05-07 | 2022-05-21 | N/A | 2022-06-04 | N/A | Plan | 2022-06-16 | 2022-07-07 | 2022-07-11 | N/A | 2022-07-13 | 2022-07-20 |  |  | 24515 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 4 | Planning and Communication Services | GCF | N/A | Plan | No | Post Review | QCBS | 15259 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | N/A | 2022-03-23 | 2022-05-07 | 2022-05-21 | N/A | 2022-06-04 | N/A | Plan | 2022-06-16 | 2022-07-07 | 2022-07-11 | N/A | 2022-07-13 | 2022-07-20 |  |  | 15259 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 5 | IT and management inputs and services | GCF | N/A | Plan | No | Post Review | QCBS | 95225 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | N/A | 2022-03-23 | 2022-05-07 | 2022-05-21 | N/A | 2022-06-04 | N/A | Plan | 2022-06-16 | 2022-07-07 | 2022-07-11 | N/A | 2022-07-13 | 2022-07-20 |  |  | 95225 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 6 | IT Services | GCF | N/A | Plan | No | Post Review | QCBS | 15259 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | N/A | 2022-03-23 | 2022-05-07 | 2022-05-21 | N/A | 2022-06-04 | N/A | Plan | 2022-06-16 | 2022-07-07 | 2022-07-11 | N/A | 2022-07-13 | 2022-07-20 |  |  | 15259 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 7 | M&E Services | GCF | N/A | Plan | No | Post Review | QCBS | 15259 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2022-03-21 | N/A | 2022-03-23 | 2022-05-07 | 2022-05-21 | N/A | 2022-06-04 | N/A | Plan | 2022-06-16 | 2022-07-07 | 2022-07-11 | N/A | 2022-07-13 | 2022-07-20 |  |  | 15259 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C3 | 8 | State-specific studies | IFAD | N/A | Plan | Yes | Prior Review | ICS | 80209 |  | Plan | 2022-02-07 | 2022-02-14 | 2022-02-16 | 2022-03-09 | 2022-03-23 | 2022-03-30 | 2022-04-03 | 2022-04-10 | 2022-04-12 | 2022-05-03 | 2022-05-17 | 2022-05-24 | N/A | N/A | Plan | 2022-06-05 | 2022-06-19 | 2022-06-23 | 2022-06-30 | 2022-07-02 | 2022-07-09 |  |  | 80209 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 9 | Project Manager | GOVT | PMU | Plan | No | Post Review | ICS | 68112 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-01 | N/A | 2021-10-03 | 2021-10-24 | 2021-11-07 | N/A | N/A | N/A | Plan | 2021-11-19 | 2021-12-03 | 2021-12-07 | N/A | 2021-12-09 | 2021-12-16 |  |  | 68112 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 10 | Project Assistant | GOVT | PMU | Plan | No | Post Review | ICS | 26280 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-01 | N/A | 2021-10-03 | 2021-10-24 | 2021-11-07 | N/A | N/A | N/A | Plan | 2021-11-19 | 2021-12-03 | 2021-12-07 | N/A | 2021-12-09 | 2021-12-16 |  |  | 26280 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 11 | Procurement Specialist | GOVT | PMU | Plan | Yes | Post Review | ICS | 58392 |  | Plan | N/A | N/A |  |  |  | N/A | 2021-10-01 | N/A | 2021-10-03 | 2021-10-24 | 2021-11-07 | N/A | N/A | N/A | Plan | 2021-11-19 | 2021-12-03 | 2021-12-07 | N/A | 2021-12-09 | 2021-12-16 |  |  | 58392 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 12 | Financial Management Specialist | GOVT | PMU | Plan | No | Post Review | ICS | 58392 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-01 | N/A | 2021-10-03 | 2021-10-24 | 2021-11-07 | N/A | N/A | N/A | Plan | 2021-11-19 | 2021-12-03 | 2021-12-07 | N/A | 2021-12-09 | 2021-12-16 |  |  | 58392 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 13 | M&E Specialist | GOVT | PMU | Plan | No | Prior Review |  | 58392 |  | Plan | N/A | N/A | 2022-02-09 | 2022-03-02 | 2022-03-16 | N/A | 2021-10-01 | N/A | 2022-03-22 | 2022-04-12 | 2022-04-26 | N/A | N/A | N/A | Plan | 2022-05-08 | 2022-05-22 | 2022-05-26 | N/A | 2022-05-28 | 2022-06-04 |  |  | 58392 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y1 C4 | 14 | M&E Analyst | GOVT | PMU | Plan | No | Post Review | ICS | 43776 |  | Plan | N/A | N/A | N/A | N/A | N/A | N/A | 2021-10-01 | N/A | 2021-10-03 | 2021-10-24 | 2021-11-07 | N/A | N/A | N/A | Plan | 2021-11-19 | 2021-12-03 | 2021-12-07 | N/A | 2021-12-09 | 2021-12-16 |  |  | 43776 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual
AWPB Y2 C4 | 15 | Audit | GCF | PMU | Plan | Yes | Post Review | ICS | 34077 |  | Plan | 2022-01-24 | N/A | 2022-01-26 | 2022-02-16 | 2022-03-02 | N/A | 2022-03-06 | N/A | 2022-03-08 | 2022-03-29 | 2022-04-12 | N/A | N/A | N/A | Plan | 2022-04-24 | 2022-05-08 | 2022-05-12 | N/A | 2022-05-14 | 2022-05-21 |  |  | 34077 | 0
[5 empty] | Actual |  |  |  | 0 | 0 | Actual | [14 empty] | Actual

## Time Estimation
Day Ranges | These tables provide estimated timelines by procurement methods, based on experience and guidance in the Procurement Handbook where specified.
The approximate number of days are used in the default Procurement Plan Formulas. Timelines in the Approx fields/Formulas are not prescriptive, and may be modified by the project.
Approx figures entered will be highlighted/flagged, if below the Minimun number of days. Zero indicates steps that are not applicable to the method, and are indicated as N/A in the Formulas.
Goods & Works
Procurement Method | Submission of PreQual docs |  |  | No Objection Date |  |  | PreQual Invitation Date |  |  | PreQual Closing Date |  |  | Submission of PreQual Report |  |  | No Objection Date |  |  | Submission of BD |  |  | No-objection Date |  |  | Bid Invitation Date |  |  | Bid Closing-Opening |  |  | Submission Tech Eval Rpt |  |  | No-objection Date |  |  | Submission Combined Eval Rpt/Bid Evaluation Report |  |  | No-objection Date |  |  | Issue of NOITA & Standstill |  |  | Date Contract Award |  |  | Date Contract Signature |  |  | Totals
| Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Approx Months/Days
Single Envelope
RFQ/Shopping (NS/IS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 1 | 5 | 21 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | 7 | 7 | 10 | 7 | 0 | 0 | 0 | 1 | 3 | 2 | 1 | 3 | 2 | 24 | 60 | 40 | 1m 9d
NCB (no PreQual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 30 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 7 | 14 | 7 | 1 | 5 | 2 | 68 | 130 | 96 | 3m 5d
ICB (no PreQual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 70 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 21 | 7 | 10 | 7 | 11 | 15 | 12 | 7 | 14 | 7 | 1 | 5 | 2 | 83 | 155 | 103 | 3m 12d
LIB (no PreQual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 70 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 21 | 7 | 10 | 7 | 11 | 15 | 12 | 7 | 14 | 7 | 1 | 5 | 2 | 83 | 155 | 103 | 3m 12d
NCB (with PreQual) | 1 | 4 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 30 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 14 | 10 | 7 | 10 | 7 | 1 | 3 | 2 | 30 | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 21 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 1 | 5 | 5 | 1 | 5 | 2 | 110 | 206 | 164 | 5m 12d
ICB (with PreQual) | 1 | 4 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 30 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 14 | 10 | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 70 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 21 | 21 | 7 | 10 | 7 | 11 | 15 | 12 | 1 | 5 | 5 | 1 | 5 | 2 | 125 | 231 | 171 | 5m 19d
LIB (with PreQual) | 1 | 4 | N/A-Start Date | 5 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 30 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 14 | 10 | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 70 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 21 | 21 | 7 | 10 | 7 | 11 | 15 | 12 | 1 | 5 | 5 | 1 | 5 | 2 | 123 | 231 | 171 | 5m 19d
Direct Contracting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 1 | 7 | 30 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21 | 7 | 7 | 10 | 7 | 0 | 0 | 0 | 7 | 14 | 7 | 1 | 5 | 2 | 34 | 96 | 45 | 1m 14d
Two Envelope
NCB (no PreQual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 30 | 45 | 45 | 3 | 21 | 3 | 7 | 10 | 7 | 3 | 7 | 7 | 7 | 10 | 7 | 11 | 15 | 12 | 7 | 14 | 7 | 1 | 5 | 2 | 78 | 147 | 99 | 3m 8d
ICB (no PreQual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 70 | 45 | 3 | 21 | 21 | 7 | 10 | 7 | 3 | 7 | 7 | 7 | 10 | 7 | 11 | 15 | 12 | 7 | 14 | 7 | 1 | 5 | 2 | 93 | 172 | 117 | 3m 26d
LIB (no PreQual) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 70 | 45 | 3 | 21 | 21 | 7 | 10 | 7 | 3 | 7 | 7 | 7 | 10 | 7 | 11 | 15 | 12 | 7 | 14 | 7 | 1 | 5 | 2 | 93 | 172 | 117 | 3m 26d
NCB (with PreQual) | 1 | 4 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 30 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 14 | 10 | 7 | 10 | 7 | 1 | 3 | 2 | 30 | 45 | 45 | 7 | 21 | 14 | 7 | 10 | 7 | 3 | 7 | 7 | 7 | 10 | 7 | 11 | 15 | 12 | 1 | 5 | 5 | 1 | 5 | 2 | 120 | 223 | 178 | 5m 26d
ICB (with PreQual) | 1 | 4 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 30 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 14 | 10 | 7 | 10 | 7 | 1 | 2 | 2 | 45 | 70 | 45 | 7 | 21 | 21 | 7 | 10 | 7 | 3 | 7 | 7 | 7 | 10 | 7 | 11 | 15 | 12 | 1 | 5 | 5 | 1 | 5 | 2 | 135 | 247 | 185 | 6m 3d
LIB (with PreQual) | 1 | 4 | N/A-Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 30 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 14 | 10 | 7 | 10 | 7 | 1 | 2 | 2 | 45 | 70 | 45 | 7 | 21 | 21 | 7 | 10 | 7 | 3 | 7 | 7 | 7 | 10 | 7 | 11 | 15 | 12 | 1 | 5 | 5 | 1 | 5 | 2 | 135 | 247 | 185 | 6m 3d
Services
Selection Method | Submission of REOI |  |  | No Objection Date |  |  | REOI Launch Date |  |  | EOI Submission Deadline |  |  | Submission of Shortlist Report |  |  | No Objection Date |  |  | Submission of RFP/RCQ |  |  | No-objection Date |  |  | RFP/RCQ Launch Date |  |  | Proposal submission deadline |  |  | Submission of TER |  |  | No-objection Date |  |  | Submission of CER |  |  | No-objection Date |  |  | Issue of NOITA & Standstill |  |  | Negotiations completed |  |  | Submission of Draft Contract and MoN |  |  | No-objection Date |  |  | Date Contract Award |  |  | Date Contract Signature |  |  | Totals
| Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Min | Max | Approx | Approx Months/Days
QCBS (w/Shortlist) | 1 | 4 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 7 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 60 | 45 | 14 | 21 | 14 | 7 | 10 | 7 | 7 | 14 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 170 | 283 | 204 | 6m 22d
FBS (w/Shortlist) | 1 | 4 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 7 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 60 | 45 | 14 | 21 | 14 | 7 | 10 | 7 | 7 | 14 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 170 | 283 | 204 | 6m 22d
LCS (w/Shortlist) | 1 | 4 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 7 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 60 | 45 | 14 | 21 | 14 | 7 | 10 | 7 | 7 | 14 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 170 | 283 | 204 | 6m 22d
QBS (w/Shortlist) | 1 | 4 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 7 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 21 | 60 | 45 | 14 | 21 | 14 | 7 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 132 | 259 | 183 | 6m 1d
CQS (w/Shortlist) | 1 | 4 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 5 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 12 | 7 | 14 | 14 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 118 | 220 | 152 | 4m 31d
ICS (w/Shortlist) | 1 | 4 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 1 | 5 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 12 | 7 | 14 | 14 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 118 | 220 | 152 | 4m 31d
QCBS (noShortlist) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 45 | 60 | 45 | 14 | 21 | 14 | 7 | 10 | 7 | 7 | 14 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 126 | 205 | 149 | 4m 28d
FBS (noShortlist) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 7 | 21 | 14 | 7 | 10 | 7 | 7 | 14 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 88 | 173 | 125 | 4m 4d
LCS (noShortlist) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 21 | 30 | 25 | 7 | 21 | 14 | 7 | 10 | 7 | 7 | 14 | 14 | 7 | 10 | 7 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 95 | 175 | 129 | 4m 8d
QBS (noShortlist) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 21 | 60 | 45 | 14 | 21 | 14 | 7 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 12 | 14 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 88 | 181 | 128 | 4m 7d
CQS (noShortlist) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 12 | 7 | 14 | 14 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 74 | 142 | 97 | 3m 6d
ICS (noShortlist) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 14 | 30 | 21 | 14 | 21 | 14 | 7 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 15 | 12 | 7 | 14 | 14 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 74 | 142 | 97 | 3m 6d
SSS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7 | N/A- Start Date | 7 | 10 | 7 | 1 | 3 | 2 | 7 | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 21 | 14 | 7 | 10 | 7 | 0 | 0 | 0 | 7 | 21 | 21 | 3 | 14 | 4 | 7 | 10 | 7 | 1 | 3 | 2 | 1 | 7 | 7 | 49 | 136 | 101 | 3m 10d
NOTE
1. Some procurement methods for low-value processes might require No Objections based on the Prior Review Thresholds. Where they do not require, No Objection number of days should be zero.
2. RFP: Request for Proposals: standard procurement document used for Services.
3. RCQ: Requests for Consultants Qualifications: Procurement document used for CQS and LCS. The RFP is used for all other procurement methods
4. Consulting services and Good/Works methods could either be used for Non-Consulting Services
5. All days are calendar days
Formulas:
Approx Months/Days = DATEDIF(0,[Approx],"YM")&"m "&DATEDIF(0,[Approx],"MD")&"d "