## RELIVE IMPLEMENTATION TABLE
RELIVE PROJECT-GUATEMALA
ANNEX 5: IMPLEMENTATION TIMETABLE | [8 empty] | Period Highlight: | 1 |  |  | Plan Duration |  |  |  |  | x | Deliverable
|  | ACTIVITY |  |  | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[10 empty] | Y1 |  |  |  | Y2 |  |  |  | Y3 |  |  |  | Y4 |  |  |  | Y5 |  |  |  | Y6 |  |  |  | Y7
[10 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
|  |  | ACTIVITY DESCRIPTION | DELIVERABLE | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Component 1 : Implementing climate resilient agricultural practices and enhancing farmers’ livelihoods | Output 1.1: Climate and agro-weather information improved and tailored to the needs of vulnerable smallholder farmers to inform adaptation measures | Activity 1.1.1 | Organize workshops for extension technicians and farmers regarding the importance of climate information and use in decision-making | Awareness raising knowledge products such as newsletters, posters and short videos. | 5 | 26 | 5 | 25 | 100% | bar: Y1 2 2 to Y7 2 26
|  | Activity 1.1.2 | Install 13 hydro-meteorological monitoring equipment for drought to inform climate resilient agricultural management strategies. | Installation and operational guidelines for agro-meteorological equipment | 2 | 11 | 4 | 6 | 100% | bar: Y1 4 4 to Y3 1 9
|  | Activity 1.1.3 | Disseminate climate information and response adaptation measures using locally-relevant delivery mechanisms as virtual platforms, electronic means, telecommunication and visits of the extension workers. | Protocols of the design and use of the information delivery mechanisms | 3 | 25 | 4 | 23 | 100% | bar: Y1 4 4 to Y7 2 26
|  | Activity 1.1.4 | Implement 4 local agro-ecological centers for climate change adaptation for knowledge generation and sharing | Management plan of the agro-ecological centers | 5 | 12 | 6 | 5 | 100% | bar: Y2 2 6 to Y3 2 10
| Output 1.2: Adaptation measures adopted to foster the resilience of coffee, cocoa and basic grain production systems | Activity 1.2.1 | Fund the implementation of the adaptation practices and gender-sensitive technology packages for staple crops, coffee and cocoa in 6,195 family farms. | Catalogue with tailored and gender-sensitive agricultural adaptation measures | 4 | 25 | 4 | 22 | 100% | bar: Y1 4 4 to Y7 3 27
|  | Activity 1.2.2 | Implement at least 10 trainings to enhance the technical and organizational capacity of 6,195 farmers for climate-risk informed planning and implementation of agricultural adaptation measures at farm level | Trainer of Trainers Manual for the implementation of climate resilience agricultural practices | 5 | 16 | 6 | 5 | 100% | bar: Y2 2 6 to Y3 2 10
|  | Activity 1.2.3 | Establish 28 women-led, farm-level seed nurseries for resilient crops and community forest nurseries | Catalogue of local and improved seeds | 5 | 11 | 5 | 8 | 100% | bar: Y2 1 5 to Y3 4 12
|  | Activity 1.2.4 | Extension workers provide technical assistance through regular consultation sessions and field visits to 6,195 small farmers. | Capacity needs report to inform the technical assistance sessions | 3 | 11 | 8 | 3 | 100% | bar: Y2 4 8 to Y3 2 10
| Output 1.3: Promotion of the resilience of livelihoods through productive diversification and market access | Activity 1.3.1 | Promote diversification of productive units in home gardens for 2,500 farm families and install 370 greenhouses micro-tunnel facilities for vegetables and poultry | Market study for the potential of revenue generation from advisories for drought, water management and agriculture | 5 | 22 | 7 | 7 | 100% | bar: Y2 3 7 to Y4 1 13
|  | Activity 1.3.2 | Organize training for 2,500 farmers to improve technical skills for enhancing coffee and cocoa value chains and to strengthen organizational capacities of producers’ associations to access markets infrastructure | Training manual on business development and management for smallholder producers’ associations | 5 | 25 | 6 | 14 | 100% | bar: Y2 2 6 to Y5 3 19
Component 2 : Promoting efficient water management for agriculture to reduce the impact of increased water scarcity | Output 2.1.1: Community-led Water Management Plans developed and implemented at micro-basin level to promote climate resilience and enhance economic productivity | Activity 2.1.1 | Establish or strengthen the capacity of 14 Local Water Committees for climate risk-informed integrated water resource management and planning instruments related to public policy on climate change | Stakeholder mapping - Manual on the management of the Local Water Committees | 3 | 25 | 3 | 6 | 100% | bar: Y1 3 3 to Y2 4 8
|  | Activity 2.1.2 | Provide technical assistance to Local Water Committees to develop and implement 14 climate risk-informed water management plans at micro-basin level which correspond to the project site. | Water Management Plans | 3 | 25 | 4 | 23 | 100% | bar: Y1 4 4 to Y7 2 26
| Output 2.2: Landscapes are climate resilient and sustain critical ecosystems services for water availability in drought periods | Activity 2.2.1 | Technical support to 19,239 smallholder farmers (women in particular) to access forest incentives | Technical reports required for accessing forest incentives. | 6 | 13 | 7 | 11 | 100% | bar: Y2 1 5; Y2 3 7 to Y5 1 17
|  | Activity 2.2.2 | Training of 90 technicians from extension services, forest regents and INAB | Training manual on the supervision of the implementation of agroforestry systems | 3 | 25 | 4 | 3 | 100% | bar: Y1 4 4 to Y2 2 6
|  | Activity 2.2.3 | Restore 13,000 ha through reforestation and agroforestry | Monitoring report for the restoration activities. | 3 | 25 | 4 | 22 | 100% | bar: Y1 4 4 to Y7 1 25
|  | Activity 2.2.4 | Evaluate forest management plans and certify their compliance to manage and allocate the necessary funds to reforest and manage 13,000 hectares of plantations and agroforestry systems | Guidelines for the access to funds of the selected smallholder farmers. | 3 | 25 | 3 | 4 | 100% | bar: Y1 3 3 to Y2 2 6
| Output 2.3: Local water collection and irrigation farm systems implemented to secure water supply for resilient livelihoods | Activity 2.3.1 | Provide trainings to improve technical capacity of 2,500 local officials and members of community organizations on the implementation and maintenance of micro-basin infrastructure | Technical manual for the construction of rooftop rainwater collection tank and installation of micro-irrigation system | 3 | 25 | 4 | 5 | 100% | bar: Y1 4 4 to Y2 4 8
|  | Activity 2.3.2 | Install farm-level drip irrigation system for using harvested water on 250 ha of farm land | Multi-year maintenance and financing plans for irrigation systems | 3 | 25 | 5 | 5 | 100% | bar: Y2 1 5 to Y3 1 9
Component 3 : Strengthening of inter-institutional coordination and local governance for agricultural resilience and water management at local and national level. | Output 3.1: Institutional systems strengthened to govern climate resilient initiatives at national and local level | Activity 3.1.1 | Provide training to 100 technicians from 28 municipal environmental units and other local government agencies on climate change and climate adpatation planning and climate resilient agricultural solutions | Technical manual on climate risk -informed water resource management for local actors. | 7 | 25 | 7 | 4 | 100% | bar: Y2 3 7 to Y3 2 10
|  | Activity 3.1.2 | Facilitate 4 meetings of 2 water management and climate change thematic roundtables including the participation of MAGA, MARN and other relevant actors to integrate agricultural resilience practices in the national action plan on adaptation to climate change. | Summaries of key messages from roundtables. | 3 | 25 | 4 | 23 | 100% | bar: Y1 4 4 to Y7 2 26
| Output 3.2: Strengthened knowledge transfer and awareness raising among institutions at national, sub-national and local levels | Activity 3.2.1 | Train and assist 90 staff members from INAB, MAGA and MARN on the management and dissemination of climate information. | Guidelines on climate adaptation planning including gender sensitization. | 3 | 25 | 9 | 18 | 100% | bar: Y3 1 9 to Y3 3 11; Y4 3 15 to Y5 1 17; Y6 1 21 to Y6 3 23; Y7 2 26
|  | Activity 3.2.2 | Train 100 at departmental and municipal level and agricultural extension workers and other staff from SNER on climate risk-informed agricultural adaptation strategies. | Technical guidelines on the design of adaptation strategies | 3 | 25 | 15 | 8 | 100% | bar: Y4 3 15 to Y6 2 22
|  | Activity 3.2.3 | Train 300 community promoters on the use of climate information and planning instruments for agriculture adaptation strategies and strengthen the capacity of 80 CADERs | Knowledge products such as posters, videos, presentations and flyers on climate change risks, vulnerabilities and adaptation solutions for agriculture and livelihoods in different local languages | 3 | 25 | 4 | 23 | 100% | bar: Y1 4 4 to Y7 2 26
|  |  | REPORTING | APR | 2 | 25 | 3 | 24 | 100% | bar: Y2 1 5; Y3 1 9; Y4 1 13; Y5 1 17; Y6 1 21; Y7 1 25
|  |  |  | Baseline, during inception of the project / Inception Report | 2 | 1 | 2 | 1 | 100% | bar: Y1 2 2
|  |  |  | An interim evaluation (Mid-Term) report within three years from the start of the project implementation (first quarter of the fourth year) | 15 | 1 | 15 | 1 | 100% | bar: Y4 3 15
|  |  |  | Final evaluation report will be due within 6 months from the end of project implementation | 28 | 1 | 28 | 1 | 100% | bar: Y7 4 28