## Annex 5. Timetable
Annex 5 Implementation Timetable
Project: Building Resilience to Climate Change in Jordan
| Year | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
| Component/Outputs | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2 Q1 | Y2 Q2 | Y2 Q3 | Y2 Q4 | Y3 Q1 | Y3 Q2 | Y3 Q3 | Y3 Q4 | Y4 Q1 | Y4 Q2 | Y4 Q3 | Y4 Q4 | Y5 Q1 | Y5 Q2 | Y5 Q3 | Y5 Q4 | Y6 Q1 | Y6 Q2 | Y6 Q3 | Y6 Q4 | Y7 Q1 | Y7 Q2 | Y7 Q3 | Y7 Q4
Component 1 : Climate resilient water systems
Output 1.1.1
Activity 1.1.1.1 | bar: 2021 Y1 Q1 to 2027 Y7 Q4
Activity 1.1.1.2 | bar: 2021 Y1 Q3 to 2026 Y6 Q2
Activity 1.1.1.3 | bar: 2022 Y2 Q2 to 2025 Y5 Q4
Activity 1.1.1.4 | bar: 2022 Y2 Q2 to 2027 Y7 Q2
Activity 1.1.1.5 | bar: 2022 Y2 Q3 to 2027 Y7 Q2
Activity 1.1.1.6 | bar: 2027 Y7 Q3 to 2027 Y7 Q4
Output 1.1.2
Activity 1.1.2.1 | bar: 2023 Y3 Q2 to 2027 Y7 Q4
Activity 1.1.2.2 | bar: 2023 Y3 Q2 to 2025 Y5 Q4
Activity 1.1.2.3 | bar: 2023 Y3 Q1 to 2024 Y4 Q4
Output 1.1.3
Activity 1.1.3.1 | bar: 2021 Y1 Q3 to 2024 Y4 Q4
Activity 1.1.3.2 | bar: 2022 Y2 Q1 to 2025 Y5 Q4
Activity 1.1.3.3 | bar: 2025 Y5 Q3 to 2025 Y5 Q4
Component 2 : Climate Change resilience for Enhanced Livelihoods and Food Security
Output 2.1.1
Activity 2.1.1.1 | bar: 2021 Y1 Q1 to 2027 Y7 Q4
Activity 2.1.1.2 | bar: 2021 Y1 Q1 to 2021 Y1 Q4; 2024 Y4 Q1 to 2024 Y4 Q2
Activity 2.1.1.3 | bar: 2021 Y1 Q1 to 2021 Y1 Q4; 2024 Y4 Q1 to 2024 Y4 Q2
Activity 2.1.1.4 | bar: 2021 Y1 Q1 to 2026 Y6 Q4
Activity 2.1.1.5 | bar: 2021 Y1 Q1 to 2026 Y6 Q4
Activity 2.1.1.6 | bar: 2021 Y1 Q1 to 2026 Y6 Q4
Activity 2.1.1.7 | bar: 2022 Y2 Q1 to 2026 Y6 Q4
Activity 2.1.1.8 | bar: 2027 Y7 Q3 to 2027 Y7 Q4
Output 2.1.2
Activity 2.1.2.1 | bar: 2021 Y1 Q3 to 2021 Y1 Q4
Activity 2.1.2.2 | bar: 2021 Y1 Q1 to 2027 Y7 Q4
Output 2.1.3
Activity 2.1.3.1 | bar: 2021 Y1 Q2 to 2021 Y1 Q4
Activity 2.1.3.2 | bar: 2021 Y1 Q3 to 2022 Y2 Q2
Activity 2.1.3.3 | bar: 2022 Y2 Q3 to 2022 Y2 Q4
Activity 2.1.3.4 | bar: 2021 Y1 Q3 to 2022 Y2 Q2
Activity 2.1.3.5 | bar: 2023 Y3 Q1 to 2026 Y6 Q4
Output 2.1.4
Activity 2.1.4.1 | bar: 2022 Y2 Q1 to 2025 Y5 Q4
Activity 2.1.4.2 | bar: 2025 Y5 Q1 to 2027 Y7 Q4
Component 3 : Scaling-up climate adaptation
Output 3.1.1
Activity 3.1.1.1 | bar: 2021 Y1 Q1 to 2027 Y7 Q4
Activity 3.1.1.2 | bar: 2021 Y1 Q1 to 2025 Y5 Q4
Output 3.1.2
Activity 3.1.2.1 | bar: 2024 Y4 Q1 to 2027 Y7 Q4
Activity 3.1.2.2 | bar: 2024 Y4 Q1 to 2027 Y7 Q4
Output 3.1.3
Activity 3.1.3.1 | bar: 2021 Y1 Q1 to 2027 Y7 Q4
Activity 3.1.3.2 | bar: 2022 Y2 Q1 to 2026 Y6 Q4
Activity 3.1.3.3 | bar: 2022 Y2 Q1 to 2025 Y5 Q4
| PMC | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Project Monitoring | 2021 Y1 Q4: AWPB; 2022 Y2 Q1: APR; 2022 Y2 Q4: AWPB; 2023 Y3 Q1: APR; 2023 Y3 Q4: AWPB; 2024 Y4 Q1: APR; 2024 Y4 Q3: Interim Evaluation; 2024 Y4 Q4: AWPB; 2025 Y5 Q1: APR; 2025 Y5 Q4: AWPB; 2026 Y6 Q1: APR; 2026 Y6 Q4: AWPB; 2027 Y7 Q1: APR; 2027 Y7 Q3: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.

## Pivot WP
This table needs to be refreshed after any change (macro available in WP template)
If the macro doesn't run, select the pivot table then menu tab: Analyze -> refresh -> refresh
Pivot table linked to the Work Plan for reporting purpose
Project title: | Building Resilience to Climate Change in Jordan
Values
Component Title | Activity | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2 Q1 | Y2 Q2 | Y2 Q3 | Y2 Q4 | Y3 Q1 | Y3 Q2 | Y3 Q3 | Y3 Q4 | Y4 Q1 | Y4 Q2 | Y4 Q3 | Y4 Q4 | Y5 Q1 | Y5 Q2 | Y5 Q3 | Y5 Q4 | Y6 Q1 | Y6 Q2 | Y6 Q3 | Y6 Q4 | Y7 Q1 | Y7 Q2 | Y7 Q3 | Y7 Q4
Component 1 : Climate resilient water systems | Activity 1.1.1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.1.2 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.1.3 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.1.4 | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.1.5 | [6 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.1.6 | [26 empty] | 1 | 1
| Activity 1.1.2.1 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.2.2 | [9 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.2.3 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.3.1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.3.2 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 1.1.3.3 | [18 empty] | 1 | 1
Component 2 : Climate Change resilience for Enhanced Livelihoods and Food Security | Activity 2.1.1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.1.2 | 1 | 1 | 1 | 1 | [8 empty] | 1 | 1
| Activity 2.1.1.3 | 1 | 1 | 1 | 1 | [8 empty] | 1 | 1
| Activity 2.1.1.4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.1.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.1.6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.1.7 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.1.8 | [26 empty] | 1 | 1
| Activity 2.1.2.1 |  |  | 1 | 1
| Activity 2.1.2.2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.3.1 |  | 1 | 1 | 1
| Activity 2.1.3.2 |  |  | 1 | 1 | 1 | 1
| Activity 2.1.3.3 | [6 empty] | 1 | 1
| Activity 2.1.3.4 |  |  | 1 | 1 | 1 | 1
| Activity 2.1.3.5 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.4.1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 2.1.4.2 | [16 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Component 3 : Scaling-up climate adaptation | Activity 3.1.1.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 3.1.1.2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 3.1.2.1 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 3.1.2.2 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 3.1.3.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 3.1.3.2 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Activity 3.1.3.3 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PMC | PMC | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Work Plan

## Annex 5 time table
If the macro doesn't run, go to "Pivot WP" and refresh it manually
| Project title: | Building Resilience to Climate Change in Jordan
| Calculated cells | Calculated cells | Select | Automatic numbering | Enter description. If needed, insert a row with the macro | Select | Select "x" for planning the activity | [39 empty] | Calculated cells | [9 empty] | Calculated cells
Sl.No | Component Title | outcome Title | Output Title | Activity | Activity Title | Lead financier | Y1 Q1 | Y1 Q2 | Y1 Q3 | Y1 Q4 | Y2 Q1 | Y2 Q2 | Y2 Q3 | Y2 Q4 | Y3 Q1 | Y3 Q2 | Y3 Q3 | Y3 Q4 | Y4 Q1 | Y4 Q2 | Y4 Q3 | Y4 Q4 | Y5 Q1 | Y5 Q2 | Y5 Q3 | Y5 Q4 | Y6 Q1 | Y6 Q2 | Y6 Q3 | Y6 Q4 | Y7 Q1 | Y7 Q2 | Y7 Q3 | Y7 Q4 | Y8 Q1 | Y8 Q2 | Y8 Q3 | Y8 Q4 | Y9 Q1 | Y9 Q2 | Y9 Q3 | Y9 Q4 | Y10 Q1 | Y10 Q2 | Y10 Q3 | Y10 Q4 | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10 | Check Costing
1 | #REF! | #REF! | Output 1.1.1: By year 7 at least 8250 buildings retrofitted with water harvesting structures | Activity 1.1.1.1 | Provide Technical assistance and oversight for water resilient systems | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y1 to Calculated cells Y7
2 | #REF! | #REF! | Output 1.1.1: By year 7 at least 8250 buildings retrofitted with water harvesting structures | Activity 1.1.1.2 | Selection of public buildings and awareness on water conservation schools and municipal officials | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q3 to Select "x" for planning the activity Y6 Q2; Calculated cells Y1 to Calculated cells Y6
3 | #REF! | #REF! | Output 1.1.1: By year 7 at least 8250 buildings retrofitted with water harvesting structures | Activity 1.1.1.3 | Construction of Rooftop rainwater harvesting system in public buildings | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q2 to Select "x" for planning the activity Y5 Q4; Calculated cells Y2 to Calculated cells Y5
4 | #REF! | #REF! | Output 1.1.1: By year 7 at least 8250 buildings retrofitted with water harvesting structures | Activity 1.1.1.4 | Select beneficiaries, provide orientation on water conservation to households | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q2 to Select "x" for planning the activity Y7 Q2; Calculated cells Y2 to Calculated cells Y7
5 | #REF! | #REF! | Output 1.1.1: By year 7 at least 8250 buildings retrofitted with water harvesting structures | Activity 1.1.1.5 | Construction of Rooftop rainwater harvesting system in households | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q3 to Select "x" for planning the activity Y7 Q2; Calculated cells Y2 to Calculated cells Y7
6 | #REF! | #REF! | Output 1.1.1: By year 7 at least 8250 buildings retrofitted with water harvesting structures | Activity 1.1.1.6 | Independent Impact assessment for C1 | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y7 Q3 to Select "x" for planning the activity Y7 Q4; Calculated cells Y7
7 | #REF! | #REF! | Output 1.1.2: By year 7, reuse of reclaimed water from 3 Waste Water Plants is optimized | Activity 1.1.2.1 | Build storage and distribution infrastructure to maximize reuse of reclaimed water from existing WWT plants | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y3 Q2 to Select "x" for planning the activity Y7 Q4; Calculated cells Y3 to Calculated cells Y7
8 | #REF! | #REF! | Output 1.1.2: By year 7, reuse of reclaimed water from 3 Waste Water Plants is optimized | Activity 1.1.2.2 | Technical assistance to MWI and Ministry of Health to assure compliance with environmental standards | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y3 Q2 to Select "x" for planning the activity Y5 Q4; Calculated cells Y3 to Calculated cells Y5
9 | #REF! | #REF! | Output 1.1.2: By year 7, reuse of reclaimed water from 3 Waste Water Plants is optimized | Activity 1.1.2.3 | Technical assistance to promote demand and safe reuse of reclaimed water, including building local capacity of farmers and Water User Associations | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y3 Q1 to Select "x" for planning the activity Y4 Q4; Calculated cells Y3 to Calculated cells Y4
10 | #REF! | #REF! | Output 1.1.3: By year 4, Landscape Resilience Investment Plan for part of the Dead Sea Basin | Activity 1.1.3.1 | Establish plan objectives and criteria | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q3 to Select "x" for planning the activity Y4 Q4; Calculated cells Y1 to Calculated cells Y4
11 | #REF! | #REF! | Output 1.1.3: By year 4, Landscape Resilience Investment Plan for part of the Dead Sea Basin | Activity 1.1.3.2 | Execute technical, economic, environmental and social feasability studies | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q1 to Select "x" for planning the activity Y5 Q4; Calculated cells Y2 to Calculated cells Y5
12 | #REF! | #REF! | Output 1.1.3: By year 4, Landscape Resilience Investment Plan for part of the Dead Sea Basin | Activity 1.1.3.3 | Disseminate and validate investment Plan | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y5 Q3 to Select "x" for planning the activity Y5 Q4; Calculated cells Y5
13 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.1 | Provide Technical assistance and oversight for climate change adaptation | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y1 to Calculated cells Y7
14 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.2 | Design appropriate modules for Climate Smart FFS | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y1 Q4; Select "x" for planning the activity Y4 Q1 to Select "x" for planning the activity Y4 Q2; Calculated cells Y1; Calculated cells Y4
15 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.3 | Training a team of Master Trainers/Facilitators | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y1 Q4; Select "x" for planning the activity Y4 Q1 to Select "x" for planning the activity Y4 Q2; Calculated cells Y1; Calculated cells Y4
16 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.4 | Identify target groups in Project Area | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y6 Q4; Calculated cells Y1 to Calculated cells Y6
17 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.5 | Scaling-up FAO collect mobile geo-referenced monitoring application of adoption rates | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y6 Q4; Calculated cells Y1 to Calculated cells Y6
18 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.6 | Conduct Climate Smart FFS | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y6 Q4; Calculated cells Y1 to Calculated cells Y6
19 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.7 | Field demostration of tested climate-adaptive innovation and practices | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q1 to Select "x" for planning the activity Y6 Q4; Calculated cells Y2 to Calculated cells Y6
20 | #REF! | #REF! | Output 2.1.1: By year 7, 6,000 Farmers trained in climate resilient production practices through FFS (4050) and field days (1950) | Activity 2.1.1.8 | Independent Impact assessment for C2 | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y7 Q3 to Select "x" for planning the activity Y7 Q4; Calculated cells Y7
21 | #REF! | #REF! | Output 2.1.2: By year 7, 30 000 Farmers reached through e-extension | Activity 2.1.2.1 | Developing climate-smart IT solutions for smart devices | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q3 to Select "x" for planning the activity Y1 Q4; Calculated cells Y1
22 | #REF! | #REF! | Output 2.1.2: By year 7, 30 000 Farmers reached through e-extension | Activity 2.1.2.2 | Disseminating climate smart-solutions and weather forecast through smart devices | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y1 to Calculated cells Y7
23 | #REF! | #REF! | Output 2.1.3: By year 3, 400 Women trained as Change Agents for Climate Adaptation | Activity 2.1.3.1 | Technical assistance in climate adaptive agriculture | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q2 to Select "x" for planning the activity Y1 Q4; Calculated cells Y1
24 | #REF! | #REF! | Output 2.1.3: By year 3, 400 Women trained as Change Agents for Climate Adaptation | Activity 2.1.3.2 | Development of training manuals and certification requirements | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q3 to Select "x" for planning the activity Y2 Q2; Calculated cells Y1 to Calculated cells Y2
25 | #REF! | #REF! | Output 2.1.3: By year 3, 400 Women trained as Change Agents for Climate Adaptation | Activity 2.1.3.3 | Scolarship for young trainers | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q3 to Select "x" for planning the activity Y2 Q4; Calculated cells Y2
26 | #REF! | #REF! | Output 2.1.3: By year 3, 400 Women trained as Change Agents for Climate Adaptation | Activity 2.1.3.4 | Competitive selection of candidates for climate wise-women | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q3 to Select "x" for planning the activity Y2 Q2; Calculated cells Y1 to Calculated cells Y2
27 | #REF! | #REF! | Output 2.1.3: By year 3, 400 Women trained as Change Agents for Climate Adaptation | Activity 2.1.3.5 | Trainings developed for climate wise-women | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y3 Q1 to Select "x" for planning the activity Y6 Q4; Calculated cells Y3 to Calculated cells Y6
28 | #REF! | #REF! | Output 2.1.4: By year 7, 15.000 Persons sensitized for climate adaptive measures | Activity 2.1.4.1 | Conducting Community dialogues for gender sensitive climate adaptation measures | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q1 to Select "x" for planning the activity Y5 Q4; Calculated cells Y2 to Calculated cells Y5
29 | #REF! | #REF! | Output 2.1.4: By year 7, 15.000 Persons sensitized for climate adaptive measures | Activity 2.1.4.2 | Organizing multi-stakeholder climate-wise women forums | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y5 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y5 to Calculated cells Y7
30 | #REF! | #REF! | Output 3.1.1: By year 6, specific policy and regulatory bottlenecks are identified and reforms initiated | Activity 3.1.1.1 | Technical assistance to the Ministry of Environment, the Ministry of Agriculture and the Ministry of Water and Irrigation to address and solve identified policy bottlenecks | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y1 to Calculated cells Y7
31 | #REF! | #REF! | Output 3.1.1: By year 6, specific policy and regulatory bottlenecks are identified and reforms initiated | Activity 3.1.1.2 | Technical Assistance to support the MWI in strenghtening the enabling environment for promotion of reuse of reclaimed water | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y5 Q4; Calculated cells Y1 to Calculated cells Y5
32 | #REF! | #REF! | Output 3.1.2: By year 6, at least 6 national curricula of vocational schools and specialized universities updated to include climate smart agriculture, water efficiency and precision agriculture | Activity 3.1.2.1 | Technical Assistance to the Ministry of Education and main Universities to update the national curricula | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y4 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y4 to Calculated cells Y7
33 | #REF! | #REF! | Output 3.1.2: By year 6, at least 6 national curricula of vocational schools and specialized universities updated to include climate smart agriculture, water efficiency and precision agriculture | Activity 3.1.2.2 | Training for teachers and professors to enable the teaching and practice of the new curricula | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y4 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y4 to Calculated cells Y7
34 | #REF! | #REF! | Output 3.1.3: By year 7 at least 6440 persons (4 governorates, 16 provinces, 324 municipalities) and private sector engaged in climate change adaptation practices | Activity 3.1.3.1 | Local engagement and dissemination process | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y1 to Calculated cells Y7
35 | #REF! | #REF! | Output 3.1.3: By year 7 at least 6440 persons (4 governorates, 16 provinces, 324 municipalities) and private sector engaged in climate change adaptation practices | Activity 3.1.3.2 | Technical Assistance to enhance local administration's and private sector actors' capacities to ensure compliance with national green construction and water saving policy framework | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q1 to Select "x" for planning the activity Y6 Q4; Calculated cells Y2 to Calculated cells Y6
36 | #REF! | #REF! | Output 3.1.3: By year 7 at least 6440 persons (4 governorates, 16 provinces, 324 municipalities) and private sector engaged in climate change adaptation practices | Activity 3.1.3.3 | Technical assistance and training to civil society organizations | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y2 Q1 to Select "x" for planning the activity Y5 Q4; Calculated cells Y2 to Calculated cells Y5
37 | PMC | PMC | PMC | PMC | PROJECT MANAGEMENT | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Select "x" for planning the activity Y7 Q4; Calculated cells Y1 to Calculated cells Y7
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70 | PMC | PMC | PMC | PMC | Project Management costs | GCF | [50 empty] | #REF! | bar: Select "x" for planning the activity Y1 Q1 to Calculated cells Y10
Refresh Pivot
WP
WORK PLAN BY ACTIVITY
Project ID
Outcomes
Outputs
Components
Work Plan
Cost table
Add a new row!
the row above will be copied
Project details
Result-based Budget
Note on H9: the Financing source is defined here and reported in the cost table
Note on BG9: Results: Yes = activity costed in the cost table No = activity not listed in the cost table Zero Cost Item = activity listed in cost table but no cost assigned

## Hoja2
Annex 5 Implementation Timetable
Project/Programme Title:
COMPONENTS/OUTPUTS | 20XX |  |  |  | 20XX |  |  |  | 20XX |  |  |  | 20XX |  |  |  | 20XX
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1
Ouput 1.1
Activity 1.1.1
Activity 1.2.1
Ouput 1.2
Activity 1.2.1
Activity 1.2.2
Ouput 1.3
Activity 1.3.1
Activity 1.3.2
Component 2
Output 2.1
Activity 2.1.1
Activity 2.1.2
Ouput 2.2
Activity 2.2.1
Activity 2.2.1
Project Monitoring* | 20XX Q2: Inception Report; 20XX Q1: APR; 20XX Q1: APR; 20XX Q3: Interim Evaluation; 20XX Q1: APR; 20XX Q1: Completion Report; 20XX Q4: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.