## Hoja 1 (hidden)
FONDO MEXICANO PARA LA CONSERVACIÓN DE LA NATURALEZA, A.C.
Procurement Plan
I. General
1. Project information: (name of project, country, Project)
2. Version of the Plan: Version 1.0 dated 30/07/2020
3. Approval Date of the procurement Plan:
4. Date of General Procurement Notice:
5. Period covered by this procurement plan: year 1
6. Other Arrangements: The project will provide subgrants to Civil Society Organization and Regional Funds. The Accredited Entity’s approved Procurement and Consultant Guidelines reviewed and accepted by the Fund will apply under these grants. Procurement will be carried out by Grant Recipients themselves and procurement plan will be agreed between the AE and Grant Recipient
| II. Goods, Works and non-consulting services. |  | tres cotizaciones y una sola fuente
1.Prior Review Threshold: Procurement Decisions subject to Prior Review by the AE/Fund
| Concept | Procurement Method | Threshold for use of method | Prior Review Threshold | Comments
1 | 30 weather stations Extech SD 700 | Three prices quotations | Up to US$100,000 | above US$100,000 | Procurement above to US$100,000 are not expected
2 | 30 Hydrometric stations Extech SD700 | Three prices quotations | Up to US$100,000 | above US$100,000
3 | 12 apple MacBook Pro | Three prices quotations | Up to US$100,000 | above US$100,000
4 | 10 Specialized software -ArcGIS Desktop, Tableau, MatLab | Three prices quotations | Up to US$100,000 | above US$100,000
5 | 7 Chairs | Three prices quotations | Up to US$100,000 | above US$100,000
6 | 7 Desk
7 | 48 Trap cameras, resolution greater then 12 megapixels and with non-visible (infrared) flash | Three prices quotations | Up to US$100,000 | above US$100,000
8 | 25 Monitoring backpacks | Three prices quotations | Up to US$100,000 | above US$100,000
9 | 2 Drons Mavic Air 2 | Three prices quotations | Up to US$100,000 | above US$100,000

## Goods
FONDO MEXICANO PARA LA CONSERVACIÓN DE LA NATURALEZA, A.C.
Procurement Plan
I. General
1. Project information: (River Restoration for Climate Adaptation (RIOS), México)
2. Version of the Plan: Version 2.0 dated 26/11/2020
3. Approval Date of the procurement Plan:
4. Date of General Procurement Notice:
5. Period covered by this procurement plan: 18 months
6. Other Arrangements:The project will provide subgrants to Civil Society Organization. The Accredited Entity’s approved Procurement and Consultant Guidelines reviewed and accepted by the Fund will apply under these subgrants (subprojects). Procurement will be carried out by Grant Recipients themselves and procurement plan will be agreed between the Accredited Entity, Executing Entity and Grant Recipient.
II. Goods, Works and non-consulting services.
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the AE/Fund
| Procurement Method | Threshold for use of method | Prior Review Threshold | Comments
1 | Three Prices Quotation | More than US$1000 less than US$100,000 |  | It is expected that in the term of the project there will be no acquisitions greater than $ 100,000
2 | Invitation to quote | More than US$100,000
3 | Direct selection | More than US$1,000 less than US$5,000 | More than US$5,000 | If the amount is greater than US$5,000 it will require the approval of the respective Technical Committee of the project and the FMCN
4 | Open National | More than US$100,000 |  | Only when there are not regional providers
5
6
2. | Prequalification (for complex Civil Works)
3. Procurement Packages with Methods and Time Schedule
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Ref. No. | (Description) | Source of Funds | Planned vs Actual |  | Procurement | Pre | Domestic Preference | Review | Date of issuance of doc’s | Bid-Opening | Date of contract | Comments
|  |  |  | Estimated | Method | qualification (yes/no) | (yes/no) | by AE/Fund |  | Date | /order signature
|  |  |  | Cost in US$ |  |  |  | (Prior / Post)
1 | 30 weather stations Extech SD 700 | GCF | Planned | 9000 | TPQ | No | yes | Post | N/A | July, 2022 | August, 2021 | Good
Actual
2 | 30 Hydrometric stations Extech SD700 | GCF | Planned | 9000 | TPQ | No | yes | Post | N/A | July, 2022 | August, 2021 | Good
Actual
3 | 12 laptops | GCF | Planned | 21978.9474 | TPQ | No | yes | Post | N/A | January, 2022 | February, 2021 | Good
Actual
4 | 12 Monitor | GCF | Planned | 2197.8947 | TPQ | No | yes | Post | N/A | January, 2022 | February, 2021 | Good
Actual
5 | 10 Specialized software -ArcGIS Desktop, Tableau, MatLab | GCF | Planned | 12500 | TPQ | No | yes | Post | N/A | August, 2022 | September, 2021 | Good
Actual
6 | 7 Chairs | GCF | Planned | 960.9684 | TPQ | No | yes | Post | N/A | January, 2022 | February, 2021 | Good
Actual
7 | 7 Desk | GCF | Planned | 1908.5053 | TPQ | No | yes | Post | N/A | January, 2022 | February, 2021 | Good
Actual
8 | Mouse, HDMI, external Keyboard | GCF | Planned | 1520.2105 | TPQ | No | yes | Post | N/A | January, 2022 | February, 2021 | Good
Actual
9 | 48 Trap cameras, resolution greater then 12 megapixels and with non-visible (infrared) flash | GCF | Planned | 14400 | TPQ | No | yes | Post | N/A | June, 2022 | July, 2021 | Good
Actual
10 | 25 Monitoring backpacks | GCF | Planned | 36842.1053 | TPQ | No | yes | Post | N/A | June, 2022 | July, 2021 | Good
Actual
11 | 2 Drons Mavic Air 2 | GCF | Planned | 3663.1579 | TPQ | No | yes | Post | N/A | June, 2022 | July, 2021 | Good
Actual
12 | Dissemination call for pproposals | GCF | Planned | 4615.7664 | TPQ | No | yes | Post | N/A | July, 2022 | July, 2021 | Non-consulting services
Actual
13 | Dropbox for five years | GCF | Planned | 4364.9858 | DS | No | yes | Post | N/A | January, 2022 | N/A | Non-consulting services
Actual
14 | Insurance for two Drones | GCF | Planned | 5952.2534 | DS | No | yes | Post | N/A | January, 2022 | N/A | Non-consulting services
Actual
15 | Certification for two Drones | GCF | Planned | 976.8421 | DS | No | yes | Post | N/A | January, 2022 | N/A | Non-consulting services
Actual
Total For Goods |  |  |  | 129881.6372
Competitive Methods are the following:
- Three prices quotations (TPQ)
- Invitation to quote
- Direct selection (DS)

## Individual consultancy
III. Selection of Consultants
1. Prior Review Threshold: Selection decisions subject to Prior Review by AE/Fund:
| Selection Method | Prior Review Threshold | Comment
1 | Consultant's Qualifications Based Selection (CQS) | More than US$50,000
2 | Quality Cost Based Selection method (QCBS) | More than US$100,000
3 | Direct Selection (DS) | More than US$5,000
Consultancy Assignments with Selection Methods and Time Schedule
Individual Consultancy
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Ref. No. | Description of Assignment | Source of Funds | Estimated Cost | Selection Method | Review by AE/Fund (Prior / Post) | Finalize shortlist Yes / No | National competitive publication Yes / No | Issuance of Expression of Interest Yes / No | Proposals Submission Date | Complete Technical Evaluation | Complete Financial Evaluation | Negotiate and Award | Comment
1 | Evaluate social vulnerability at baseline | GCF | 10526.3158 | CQS | Post | Yes | No | No | 2022-03-07 | 2022-03-21 | 2022-03-21 | 2022-04-01
2 | Facilitate workshop 1 | GCF | 12210.5263 | CQS | Post | Yes | No | No | 2022-03-07 | 2022-03-21 | 2022-03-21 | 2022-04-01
3 | Ex-ante biophysical modeling and generation of future scenarios of ecosystem services through Integrated Valuation of Ecosystem Services and Tradeoffs (InVEST) and integration of information on carbon sequestration from INEGI (41370). Economic valuation of selected ecosystem services (Pacific and Gulf) (34470 each zone). Economic analysis (estimation of opportunity cost) of restoration measures (2 sites, one on each coast) (27585). | GCF | 137894.7368 | QCBS | Prior | No | Yes | Yes | 2022-11-22 | 2022-11-30 | 2022-11-30 | 2023-01-01 | This consultancy will be for two years
Total for Consultancy |  | GCF | 160631.5789
Competitive Methods are the following:
- Quality Cost Based Selection method (QCBS)
- Consultant's Qualifications Based Selection (CQS)
- Direct selection

## Firm
III. Selection of Consultants
Consultancy Assignments with Selection Methods and Time Schedule
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Ref. No. | Description of Assignment | Source of Funds | Estimated Cost | Selection Method | Review by AE/Fund (Prior / Post) | Issuance of Expression of Interest | Finalize shorlist Yes / No | National competitive publication Yes / No | Proposals Submission Date | Complete Technical Evaluation | Complete Financial Evaluation | Negotiate and Award | Comment
1 | Specific consulting for results bases (bonus for subprojects) | GCF | 9157.8947 | QCBS | Post | No | Yes | No | 2022-03-22 | 2022-03-31 | 2022-03-31 | 2022-04-15
2 | Community water monitoring | GCF | 228872.3158 | DS | Prior | No | No | No | 2022-01-31 | N/A | N/A | 2022-02-15 | Global Water Watch Mexico is the only civil society organization works at training monitoring water quality.
3 | Contracts with Academia (Non-profit organizations) | GCF | 105263.1579 | QCBS | Post | No | Yes | No | 2021-11-22 | 2021-11-30 | 2021-11-30 | 2022-01-01
4 | Consulting to expand the database / hosting / | GCF | 13157.8947 | QCBS | Post | No | Yes | No | 2022-03-22 | 2022-03-31 | 2022-03-31 | 2022-04-15
5 | Updated platforms (hosting, project page update, sisep). Database hosting for five years | GCF | 57013.9217 | DS | Prior | No | No | No | 2022-01-31 | N/A | N/A | 2022-02-15 | The consulting firm that updates the platforms is the same one that created them
6 | Adaptation of existing communication platforms for 5 years (FR Hosting and Dropbox page) | GCF | 19954.8726 | QCBS | Post | No | Yes | No | 2022-02-22 | 31/02/2022 | 31/02/2022 | 2022-03-15
Total for Consultancy |  |  | 433420.0574
Competitive Methods are the following:
- Quality Cost Based Selection method (QCBS)
- Direct Selection (DS)

## Subprojects
IV. Selection of Subprojects
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Ref. No. | Description of Assignment | Estimated Cost | Selection Method | Review by AE/Fund (Prior / Post) | Request for proposals date | Proposals Submission Date | Complete Technical Evaluation | Complete Financial Evaluation | Negotiate and Award | Contract start | Comment
1 | 8 sub-projects (includes 10% bonus for payment by results) for the Gulf region | 1904556.4905 | Call for proposal | Prior | 2021-07-01 | 2021-09-01 | 2021-09-30 | 2021-09-30 | 2021-12-01 | 2022-01-01 | It is expected to have 7 annual subprojects during four years in each region.
2 | 7 sub-projects (includes 10% bonus for payment by results) for the Pacific region | 1666486.9292 | Call for proposal | Prior | 2021-07-01 | 2021-09-01 | 2021-09-30 | 2021-09-30 | 2021-12-01 | 2022-01-01 | It is expected to have 7 annual subprojects during four years in each region.
Total for Consultancy |  | 3571043.4197