## Index
PROCUREMENT PLAN
1. | Non Consulting Procurement Plan
2. | Consulting Procurement Plan

## 4.6. Procurement Plan - NC
GCF Summaries - Goods, Works and Non-Consulting Services Procurement Plan
Goods, Works and non-consulting services.
I. General
1. Project information: limate-smart initiatives for climate change adaptation and sustainability in prioritized agricultural production systems in Colombia
2. Version of the Plan: Version 1.0 dated 15/11/2021
3. Approval Date of the procurement Plan:
4. Date of General Procurement Notice:
5. Period covered by this procurement plan: 2022-2026
6. Other Arrangements:
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the AE/Fund
c | Procurement Method | Threshold for use of method | Prior Review Threshold | Comments
1. | Request for Quotations | * 1 Quatiotion : USD 500-1000 * 2 Quotations : USD 1001 -3000 * 3 Quotations: USD 3001 onward | The supplier must nevertheless meet all requirements for registration as a CIAT provider. | Purchases may be made without having to comply with the number of required quotations in the following cases:  When the national or international supplier is the only manufacturer.  When the national or international supplier presents a document that certifies that it is the manufacturer’s sole authorized distributor.  Any exception to these rules must be previously authorized by the Director General or whoever is acting on his behalf. The Purchasing Department must request quotations, compare prices, and verify suitability and responsibility from the recommended provider.
2. | Submission of Tenders | 1. Open (public tender). This method may not be the most recommendable in terms of efficiency because it allows the participation of suppliers who do not have the appropriate infrastructure to satisfy the Center’s needs and expectations. 2. Closed (private tender). This method restricts the participation of suppliers. They are directly invited by the Logistics Department to submit tenders. The selection and number of invited suppliers will depend on both the characteristics of the tender process and market conditions. |  | The tendering of goods and services is practical when applied to products catalogued as of frequent consumption, to obtain discounts on purchasing volumes, for long-term agreements with suppliers, or when the purchasing sum is considerable and compliance is required with technical specifications that must be developed by the supplier within the timeframe required for the process and the place determined for bidding. The terms of reference (TOR) must be provided for the process by whoever requests the service
3. | Direct Assignment | When the national or international supplier is the only manufacturer or when the national or international supplier presents a document that certifies that it is the manufacturer’s sole authorized distributor. |  | Not exceed two purchases per year as a direct purchase allocated to the same provider.
4. | Contracting / Special Purchase | Technical contracting or purchases are considered to be those that due to its specific and technical features cannot be managed by the Logistics Department alone. |  | Generally, this contracting and/or purchases are associated to technical, technological, and research activities for marketing and advertisement, amongst others and correspond to activities related to projects and/or programs that can be found in the Center
EQUIPMENT & CONSTRUCTION PROCUREMENT PLAN
Equipment Procurement Packages with Methods and Time Schedule
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Ref. No. | Contract | Source of Funds | Planned vs Actual |  | Procurement | Pre | Domestic Preference | Review | Date of issuance of doc’s | Bid-Opening | Date of contract | Comments
| (Description) |  |  | Estimated | Method | qualification (yes/no) | (yes/no) | by AE/Fund |  | Date | /order signature
|  |  |  | Cost in US$ |  |  |  | (Prior / Post)
1. | Hardware Equipments ( Server, laptops, Tablets) | GCF Loan, GCF Grant - CAF Loan | Planned | 632083.9851 | 2
| ALIANZA - Procesador GPU (Dividido 4 gremios) |  |  | 35613.6275
| ALIANZA - Procesador GPU (repartido entre 3 gremios) |  |  | 35429.0841
| ALIANZA - Servidores (distribuído entre 3 gremios) |  |  | 20999.0898
| ALIANZA - Unidad de almacenamiento (distribuido entre 3 gremios) |  |  | 5706.4579
| FEDEARROZ - Almacenamiento SAN 100 Tera bytes |  |  | 8568.8546
| FEDEARROZ - High performance computing server downscaling dinámico |  |  | 21001.2482
| FEDEARROZ – Servidor con Procesador GPU |  |  | 35613.6275
| CIMMYT- Servidor de Interfaz |  |  | 7041.232
| CIMMYT Servidor eAgrology |  |  | 4101.7106
| FENALCE - Equipo procesamiento |  |  | 5396.0042
| FENALCE - Procesador GPU |  |  | 35429.0841
| ALIANZA - Unidad de almacenamiento (distribuido entre 3 gremios) |  |  | 34016.5302
| FEDEPAPA - Servidor para administración de la plataforma |  |  | 21001.2482
| AGROSAVIA - Estaciones de cómputo |  |  | 29974.8031
| Computador Lenovo Thinkpad L390 |  |  | 2967.8023
| CENICAÑA - Laptop 1 |  |  | 5237.9383
| FEDEGAN - Servidor (sirve para actividad 2, 3, 4, 5) |  |  | 21001.2482
| Almacenamiento de 100 Tb |  |  | 24971.5082
| CENICAÑA - Computador portatil |  |  | 1798.6681
| Computador Biomega 4 Tb RAM |  |  | 33176.4323
| Computador portátil |  |  | 8993.3403
| Computador portatil + licencias |  |  | 4482.4488
| Computador y programas (pasante toma de datos) ( proyecto) |  |  | 2398.2241
| Cenicaña Equipos de cómputo |  |  | 23028.1544
| FENALCE - Servidores Fenalce (opcional, pago servidor en la nube AWS) |  |  | 21001.2482
| ALIANZA - Procesador GPU (repartido entre 6 gremios) |  |  | 5904.8474
| ALIANZA - Servidor (distribuído entre 3 gremios) |  |  | 6999.6966
| ALIANZA - Servidor (repartido entre 3 gremios) |  |  | 6999.6966
| CENICAFE - Computador Lenovo Thinkpad L390 |  |  | 2967.8023
| CENICAFE - Computador Lenovo ThinkPad L390 |  |  | 2967.8023
| Sistema de almacenamiento de bases de datos |  |  | 14917.7936
| AUGURA - Servidor de procesamiento |  |  | 32376.025
| AUGURA - Servidor de procesamiento (repartido en Act 1 y 2) |  |  | 20936.4962
| AUGURA - Sistema de almacenamiento en red |  |  | 8633.6067
| CIMMYT- Soporte a servidor |  |  | 2734.8248
| CIMMYT Soporte a servidor eAgrology |  |  | 4374.7542
| ALIANZA - Unidad de almacenamiento (distribuido entre 3 gremios) |  |  | 2852.3278
| ALIANZA - Servidor (repartido entre 3 gremios) |  |  | 6999.6966
| ASOHOFRUCOL - Servidor de procesamiento |  |  | 16188.0125
| FEDEPANELA - Servidor mediana capacidad |  |  | 10468.2481
| FENALCE - Equipos |  |  | 28179.1329
| Tabletas para encuestas |  |  | 8633.6067
2. | Weather and rainfall stations | GCF Loan, GCF Grant - CAF Loan | Planned | 442935.0663 | 2
| ALIANZA - Estación climatica |  |  | 61173.3289 | 1
| FEDEARROZ - Estaciones agrometeorlógicas para fincas digitales gama alta (adquisición x Casanare) |  |  | 12950.41 | 1
| FEDEARROZ - Estaciones agrometeorlógicas para fincas digitales gama media op. 1 (adquisición x Casanare) |  |  | 5396.0042 | 1
| FEDEARROZ - Estaciones agrometeorlógicas para fincas digitales gama media op. 2 (adquisición) |  |  | 16188.0125 | 1
| ALIANZA - Estación + pluviometro |  |  | 41915.5195 | 1
| Estaciones meteorológicas |  |  | 59955.6018 | 1
| AGROSAVIA - 2 Estaciones climáticas |  |  | 11391.5643 | 1
| AGROSAVIA - 3 estaciones agroclimáticas (considerar sensor de humedad y temperatura suelo) para Act. 4.4 y 4.5 (3 zonas) |  |  | 17087.3465 | 1
| FEDEPANELA - Estación meteorológica |  |  | 3237.6025 | 1
| FEDEGAN - Estaciones Metereologicas |  |  | 21584.0167 | 1
| AUGURA - Estaciones meteorológicas y pluviométros para Santa Marta y mantenimiento anual |  |  | 12950.41 | 1
| AUGURA - Estaciones meteorológicas y pluviométros para Urabá y mantenimiento anual |  |  | 6475.205 | 1
| FENALCE - Estaciones meteorológicas (compartidas con otros dos componentes) |  |  | 21368.1765 | 1
| ALIANZA - Estación + pluviometro |  |  | 14245.451 | 1
| ALIANZA - Estación climatica |  |  | 28836.2462 | 1
| FEDEPAPA - Estacion meteorologica |  |  | 53960.0416
| AGROSAVIA - Equipos monitoreo Clima |  |  | 44970.2987 | 1
| ASOHOFRUCOL - Estaciones meterolorologicas |  |  | 9249.8303 | 1
3. | Licesing & Software | GCF Loan, GCF Grant - CAF Loan | Planned | 265499.5654 | 2
| FEDEARROZ - Licencia de software procesamiento de imagenes (PIX4D) |  |  | 5396.0042 | 1
| FEDEPAPA - Licencia de software procesamiento de imagenes de dron (PIX4D) |  |  | 5396.0042 | 1
| FEDEPANELA - Licencia de software de procesamiento de imágenes PIX4D |  |  | 5396.0042 | 1
| FEDEGAN - Licencia de software procesamiento de imagenes (PIX4D) |  |  | 5396.0042 | 1
| AUGURA - Licencia de software para procesamiento de imágenes espectrales PIX4D |  |  | 5396.0042 | 1
| AGROSAVIA - Licencia de software para fotogrametría ENVI |  |  | 5995.5602 | 1
| AGROSAVIA - Licencias de software para interpretación de imágenes |  |  | 8393.7843 | 1
| CIMMYT Licencias eAgrology |  |  | 10561.8481 | 1
| CIMMYT- Software Interfaz |  |  | 2526.9086 | 1
| CIMMYT Software Plataforma eAgrology |  |  | 3790.3628 | 1
| CIMMYT-Licencias |  |  | 2916.8504 | 1
| CIMMYT Software análisis de redes |  |  | 3066.6571 | 1
| AGROSAVIA - Software análisis de imágenes (compartido con maíz) |  |  | 2098.4461 | 1
| FEDEPANELA - Licencia de software para procesamiento de imágenes satelitales (ERDAS, PCI) |  |  | 1859.4506 | 1
| FEDEGAN - Licencia de software SIG (ESRI) |  |  | 539.6004 | 1
| CENICAFE - Licencia Office |  |  | 2038.4905 | 1
| CENICAFE - Licencia SAP |  |  | 14163.7011 | 1
| CENICAFE - Licencias SAP |  |  | 14163.7011 | 1
| Licencia Office |  |  | 1019.2452 | 1
| ASBAMA - Software de clasificación de imágenes PCI Geomatics |  |  | 151.0881 | 1
| Cenicaña Software (agricultor, extensionista y administrador) |  |  | 36893.8616 | 1
| CENICAÑA - Software Especializado |  |  | 128339.9885 | 1
4. | Drones & Cameras | GCF Loan, GCF Grant - CAF Loan | Planned | 429834.3626 | 2
| ALIANZA - Cámara multiespectral |  |  | 5396.0042
| ALIANZA - Dron cuadricóptero (repartido entre 6 gremios) |  |  | 3237.6025
| ALIANZA - Camara medición de GEI |  |  | 1063.5137
| ALIANZA - Dron cuadricóptero (repartido entre 3 gremios) |  |  | 2997.7801
| FENALCE-Cameras – RGB, Multispectral, Lidar |  |  | 10792.0083
| FENALCE-Dron: para los dos estreses: Unmanned Ariel vehicle (UAV) |  |  | 21584.0167
| ALIANZA - Camara medición de GEI |  |  | 24282.0187
| ALIANZA - Dron cuadricóptero (repartido entre 3 gremios) |  |  | 5396.0042
| FEDEPAPA - Dron y camara |  |  | 16188.0125
| AGROSAVIA - Cámara multiespectral (compartido con maíz) |  |  | 4496.4903
| AGROSAVIA - Cámaras climáticas con fotoperiodo para cría de insectos Act. 4.4 y 4.5. |  |  | 46315.7024
| AGROSAVIA - Camara termografica |  |  | 11991.0005
| ALIANZA - Camara medición de GEI |  |  | 30352.5234
| ALIANZA - Cámara multiespectral |  |  | 3237.6025
| ALIANZA - Dron cuadricóptero (repartido entre 6 gremios) |  |  | 2158.4017
| FEDEGAN - Dron |  |  | 6475.205
| ALIANZA - Camara medición de GEI |  |  | 50362.7055
| ALIANZA - Camara medición de GEI |  |  | 20235.0156
| ALIANZA - Camara medición de GEI |  |  | 17537.0135
| ALIANZA - Camaras estaticas |  |  | 35802.7046
| AUGURA - Cámara para el dron de ala fija |  |  | 4316.8033
| AUGURA - Paquete cámara + dron cuadricóptero |  |  | 12950.41
| Cámara estática cerrada para muestreo de GEI |  |  | 2691.6025
| Cámara Nikon d3500 + lente macro |  |  | 898.9743
| FEDEARROZ - Camara medición de GEI |  |  | 32318.4284
| FEDEARROZ - Drones 2 |  |  | 21584.0167
| ALIANZA - Dron cuadricóptero (repartido entre 3 gremios) |  |  | 2997.7801
| FEDEPANELA - Camara medición de GEI |  |  | 5413.3689
| FEDEPANELA - Paquete cámara multiespectral, dron cuadricóptero |  |  | 7014.8054
| Camara y accesorios (Proyecto) |  |  | 4697.9911
| ASBAMA - Paquete cámara + dron cuadricóptero |  |  | 12950.41
| CENICAÑA - Camara fotográfica |  |  | 2098.4461
5. | Sensors & Dataloggers | GCF Loan, GCF Grant - CAF Loan | Planned | 834063.4265 | 2
| ALIANZA - Sensor de humedad+sensor matrico |  |  | 43255.3234 | 1
| FEDEARROZ - Sensor de humedad y temperatura del suelo |  |  | 14005.4487 | 1
| FEDEARROZ - Sensores (Humedad, temperatura, plantas) |  |  | 8094.0062 | 1
| FEDEARROZ - Sistemas de sensoramiento micrometeorológico |  |  | 53960.0416 | 1
| FEDEARROZ - Contadores de caudal |  |  | 6475.205 | 1
| AGROSAVIA - Sensores ópticos |  |  | 26980.0208 | 1
| FEDEARROZ - Datalogger |  |  | 8543.6733 | 1
| FEDEARROZ - Patrones de calibración |  |  | 16188.0125 | 1
| ALIANZA - Sensor de humedad+sensor matrico |  |  | 26736.7346 | 1
| FENALCE - Sensores de humedad del suelo (compartidas con otros dos componentes) |  |  | 297.0177 | 1
| termometros/higrometros analogos; Pluviometro |  |  | 1276.2911 | 1
| Medidor Nitratos, calcio |  |  | 1295.041 | 1
| FEDEPAPA - Sensores de humedad y temperatura del suelo |  |  | 25900.82 | 1
| AGROSAVIA - Medidor de Área Foliar en campo |  |  | 9592.8963 | 1
| AGROSAVIA - Medidor de balance de radiación e IAF (Idem) |  |  | 2967.8023 | 1
| AGROSAVIA - Medidor de intercambio de gases (compartido Banano Augura y ASBAMA) |  |  | 27699.488 | 1
| AGROSAVIA - Sensoramiento humedad del suelo/otros |  |  | 4316.8033 | 1
| ALIANZA - Sensor de humedad+sensor matrico |  |  | 21653.4035 | 1
| ALIANZA - Contadores de caudal |  |  | 2428.2019 | 1
| FEDEGAN - LAI meter |  |  | 45758.1153 | 1
| CENICAFE - Equipos soporte Sensores (USD 3.570) |  |  | 9631.8674 | 1
| CENICAFE - Sensor Doppler (USD 893) |  |  | 1926.3735 | 1
| AGROSAVIA - Medidor de área foliar en campo |  |  | 19185.7926 | 1
| AGROSAVIA - Medidor de Intercambio de Gases (repartido) |  |  | 55398.9761 | 1
| AGROSAVIA - Medidor Fluorescencia de Clorofilas |  |  | 11991.1204 | 1
| ALIANZA - Sensor de humedad+sensor matrico |  |  | 43409.7743 | 1
| ASOHOFRUCOL - Medidor de interambio de gases |  |  | 83937.8425 | 1
| AGROSAVIA - Sensor de temperatura corporal |  |  | 37502.2289 | 1
| AGROSAVIA - Sensores de comportamiento fisiologico (Ph, temperatura, metabolitos) |  |  | 44970.2987 | 1
| ASOHOFRUCOL - Sensores de humedad |  |  | 16667.1777 | 1
| ALIANZA - Aforo caudal + sensor ultra |  |  | 6373.4943 | 1
| ALIANZA - Sensor de humedad+sensor matrico |  |  | 65114.6614 | 1
| FEDEPANELA - Sensores (Humedad, temperatura, plantas) |  |  | 5396.0042 | 1
| ALIANZA - Sensor de humedad+sensor matrico |  |  | 48835.9961 | 1
| CENICAFE - Sistema de bombeo |  |  | 3597.3361 | 1
| Cenicaña Equipos de medición |  |  | 8854.5268 | 1
| ALIANZA - Aforo caudal + sensor ultra |  |  | 10895.1991 | 1
| FEDEGAN - Sensores humedad y temperatura suelo |  |  | 12950.41 | 1
6. | Greenhouse and plots equipment | GCF Loan, GCF Grant - CAF Loan | Planned | 135994.994 | See each one
| Extensión invernadero de altas temperaturas | GCF Loan, GCF Grant - CAF Loan | Planned | 53960.0416 | 2
| Invernadero de altas tempearutas fedearroz | GCF Loan, GCF Grant - CAF Loan | Planned | 53704.0569 | 2
| AGROSAVIA - Parcelas de escorrentía | GCF Loan, GCF Grant - CAF Loan | Planned | 8993.3403 | 2
| CENICAÑA - Implementos para formación de viveros e implementación de herramientas del paisaje | GCF Loan, GCF Grant - CAF Loan | Planned | 19337.5552 | 2
7. | Specialized Equipment > USD 100k | GCF Loan, GCF Grant - CAF Loan | Planned | 1866220.5235 | See each one
| FENALCE - Adecuación y establecimiento de unidades experimentales en campo / ha (mantenimiento, arriendo) (compartido con otros dos componentes) | GCF Loan, GCF Grant - CAF Loan | Planned | 199214.8888 | 2 or 3
| Modulo sistema de imersión in vitro | GCF Loan, GCF Grant - CAF Loan | Planned | 129504.0999 | 2 or 3
| Face CO2 | GCF Loan, GCF Grant - CAF Loan | Planned | 161880.1249 | 2 or 3
| CENICAFE - Cromatógrafo iónico (1) activo | GCF Loan, GCF Grant - CAF Loan | Planned | 100425.633 | 2 or 3
| CENICAFE - Fitotron | GCF Loan, GCF Grant - CAF Loan | Planned | 224833.5068 | 2 or 3
| Simulador de clima - Conviron | GCF Loan, GCF Grant - CAF Loan | Planned | 863360.6661 | 2 or 3
| Solución para potabilización de agua | GCF Loan, GCF Grant - CAF Loan | Planned | 94070.421 | 2 or 3
| AUGURA - Citometro de flujo | GCF Loan, GCF Grant - CAF Loan | Planned | 92931.1828 | 2 or 3
8. | Specialized Equipment > USD 20k | GCF Loan, GCF Grant - CAF Loan | Planned | 643368.5436 | See each one
| AUGURA - Bioreactor (para producción y formulación de bioprodcutos (140 L) | GCF Loan, GCF Grant - CAF Loan | Planned | 44966.7014 | 2
| Gasmet Model GT5000 Portable FTIR Multicomponent Gas Analyzer | GCF Loan, GCF Grant - CAF Loan | Planned | 49946.8894 | 2
| CIMMYT Apoyo para implementación de Hubs (plataformas, módulos y áreas de extensión) | GCF Loan, GCF Grant - CAF Loan | Planned | 43881.9493 | 2
| FEDEPAPA - LAI meter | GCF Loan, GCF Grant - CAF Loan | Planned | 45758.1153 | 2
| Solución para tratamiento de aguas residuales (5 personas/ familia) | GCF Loan, GCF Grant - CAF Loan | Planned | 35276.4079 | 2
| Solución tecnológica para energia solar | GCF Loan, GCF Grant - CAF Loan | Planned | 58794.0132 | 2
| Cenicaña Oficinas / instalaciones | GCF Loan, GCF Grant - CAF Loan | Planned | 36750.4775 | 2
| AGROSAVIA - Ecografo Dopler | GCF Loan, GCF Grant - CAF Loan | Planned | 29977.8009 | 2
| AGROSAVIA - Ensamble sensores fisiologia animal FR | GCF Loan, GCF Grant - CAF Loan | Planned | 22338.8589 | 2
| FENALCE-Drip irrigation system with water gauge | GCF Loan, GCF Grant - CAF Loan | Planned | 25900.82 | 2
| FEDEPAPA - Estufas de secado | GCF Loan, GCF Grant - CAF Loan | Planned | 20025.6507 | 2
| FEDEPANELA - Insumos para cría de muestras | GCF Loan, GCF Grant - CAF Loan | Planned | 21250.8643 | 2
| AGROSAVIA - Termos criogénicos | GCF Loan, GCF Grant - CAF Loan | Planned | 29977.8009 | 2
| FEDEGAN - Estufas de secado | GCF Loan, GCF Grant - CAF Loan | Planned | 20025.6507 | 2
| CENICAFE - CI-340 Handheld Photosynthesis System from CID Bioscience (USD 25.000) | GCF Loan, GCF Grant - CAF Loan | Planned | 26852.0285 | 2
| AUGURA - Control para el Bioreactor Industrial (140 L) | GCF Loan, GCF Grant - CAF Loan | Planned | 20984.4606 | 2
| AUGURA - Espectrofotómetro | GCF Loan, GCF Grant - CAF Loan | Planned | 36692.8283 | 2
| Freezer -20°C | GCF Loan, GCF Grant - CAF Loan | Planned | 23982.2407 | 2
| Materas siembra | GCF Loan, GCF Grant - CAF Loan | Planned | 31098.9707 | 2
| Refractómetros digitales | GCF Loan, GCF Grant - CAF Loan | Planned | 18886.0146 | 2
9. | Specialized Equipment > USD10k | GCF Loan, GCF Grant - CAF Loan | Planned | 202904.5094 | See each one
| Extractoras de yemas | GCF Loan, GCF Grant - CAF Loan | Planned | 13490.0104 | 1
| Autoclave SA 600-A con vacío y cargado automático | GCF Loan, GCF Grant - CAF Loan | Planned | 13490.0104 | 1
| ALIANZA - Repetidor | GCF Loan, GCF Grant - CAF Loan | Planned | 12913.5482 | 1
| AGROSAVIA - Plataforma aerotransportada para sensores (compartido con maíz) | GCF Loan, GCF Grant - CAF Loan | Planned | 13699.915 | 1
| AGROSAVIA - Batería Lisímetros | GCF Loan, GCF Grant - CAF Loan | Planned | 17986.6805 | 1
| AGROSAVIA - Imágenes satelitales (333 KM2) | GCF Loan, GCF Grant - CAF Loan | Planned | 11380.1728 | 1
| AGROSAVIA - Plataforma de ala fija (repartido entre caña y maíz) | GCF Loan, GCF Grant - CAF Loan | Planned | 14239.4554 | 1
| FENALCE-Waterlogging pit (cemented structure to be constructed) with inlet/out valve | GCF Loan, GCF Grant - CAF Loan | Planned | 10792.0083 | 1
| CIMMYT Material de capacitación y divulgación | GCF Loan, GCF Grant - CAF Loan | Planned | 10271.155 | 1
| CIMMYT TICS de seguimiento | GCF Loan, GCF Grant - CAF Loan | Planned | 15157.7212 | 1
| Autoclave | GCF Loan, GCF Grant - CAF Loan | Planned | 12485.7541 | 1
| Autoclave SA 600-A con vacío y cargado automático | GCF Loan, GCF Grant - CAF Loan | Planned | 13490.0104 | 1
| ALIANZA - Repetidor | GCF Loan, GCF Grant - CAF Loan | Planned | 12950.41 | 1
| Cenicaña Papelería (útiles, impresiones, pendones, folletos, etc) | GCF Loan, GCF Grant - CAF Loan | Planned | 11806.0357 | 1
| Gastos de transporte (peajes, gasolinna, etc) | GCF Loan, GCF Grant - CAF Loan | Planned | 18751.6219 | 1
10. | Specialized Equipment < USD10k | GCF Loan, GCF Grant - CAF Loan | Planned | 289598.2751 | See each one
| Agrosavia Refractometros digitales | GCF Loan, GCF Grant - CAF Loan | Planned | 1798.6681 | 1
| ALIANZA - Material divulgativo (impresiones y diseño) | GCF Loan, GCF Grant - CAF Loan | Planned | 419.1841 | 1
| CIMMYT Análisis Fitopatológico | GCF Loan, GCF Grant - CAF Loan | Planned | 2858.2412 | 1
| AGROSAVIA - Material de difusión | GCF Loan, GCF Grant - CAF Loan | Planned | 3527.9294 | 1
| Grabadora de periodista | GCF Loan, GCF Grant - CAF Loan | Planned | 148.8919 | 1
| CIMMYT-Analisis fisica suelos | GCF Loan, GCF Grant - CAF Loan | Planned | 164.0385 | 1
| CIMMYT-Analisis quimica suelos | GCF Loan, GCF Grant - CAF Loan | Planned | 271.9586 | 1
| CIMMYT-Correspondencia | GCF Loan, GCF Grant - CAF Loan | Planned | 38.3515 | 1
| CIMMYT-Distribución de semillas- Marbetes - Nacional | GCF Loan, GCF Grant - CAF Loan | Planned | 626.4079 | 1
| FENALCE - Análisis de suelos | GCF Loan, GCF Grant - CAF Loan | Planned | 129.5041 | 1
| FENALCE - Basculas analíticas | GCF Loan, GCF Grant - CAF Loan | Planned | 129.5041 | 1
| FENALCE - Hornos de secado de muestras vegetales | GCF Loan, GCF Grant - CAF Loan | Planned | 1079.2008 | 1
| FENALCE - Material divulgativo (impresiones y diseño) | GCF Loan, GCF Grant - CAF Loan | Planned | 846.703 | 1
| FENALCE - Picadora/ensiladora | GCF Loan, GCF Grant - CAF Loan | Planned | 2363.3638 | 1
| FEDEARROZ - Balanza analitica (adquisión: Huila) | GCF Loan, GCF Grant - CAF Loan | Planned | 1618.8012 | 1
| FEDEARROZ - Balanzas analiticas | GCF Loan, GCF Grant - CAF Loan | Planned | 537.6805 | 1
| Agrosavia Balanzas digitales | GCF Loan, GCF Grant - CAF Loan | Planned | 2398.2241 | 1
| FENALCE-Oxygen diffusion rate (ODR) meter | GCF Loan, GCF Grant - CAF Loan | Planned | 6475.205 | 1
| FENALCE-Portable weather station | GCF Loan, GCF Grant - CAF Loan | Planned | 5396.0042 | 1
| FENALCE-Soil moisture profile probe | GCF Loan, GCF Grant - CAF Loan | Planned | 6475.205 | 1
| Grabadora de periodista | GCF Loan, GCF Grant - CAF Loan | Planned | 148.8919 | 1
| CIMMYT Soporte de sistemas | GCF Loan, GCF Grant - CAF Loan | Planned | 2104.4416 | 1
| CIMMYT Apoyo para tablero de control | GCF Loan, GCF Grant - CAF Loan | Planned | 9232.4302 | 1
| AGROSAVIA - Analizador Elemental de Carbono y Nitrógeno | GCF Loan, GCF Grant - CAF Loan | Planned | 453.2643 | 1
| AGROSAVIA - Balanzas analiticas | GCF Loan, GCF Grant - CAF Loan | Planned | 172.6721 | 1
| AGROSAVIA - Cromatógrafo iónico | GCF Loan, GCF Grant - CAF Loan | Planned | 2158.4017 | 1
| AGROSAVIA - Espectrofotómetro de emisión atómica con plasma de acoplamiento inductivo (ICP-OES) | GCF Loan, GCF Grant - CAF Loan | Planned | 1187.1209 | 1
| AGROSAVIA - Estufa de secado | GCF Loan, GCF Grant - CAF Loan | Planned | 2158.4017 | 1
| AGROSAVIA - Hornos Microondas para digestión de tejidos vegetales | GCF Loan, GCF Grant - CAF Loan | Planned | 107.9201 | 1
| ALIANZA - Accesorios | GCF Loan, GCF Grant - CAF Loan | Planned | 3885.123 | 1
| ALIANZA - Contadores de caudal | GCF Loan, GCF Grant - CAF Loan | Planned | 3237.6025 | 1
| ALIANZA - Repetidor | GCF Loan, GCF Grant - CAF Loan | Planned | 7770.246 | 1
| FEDEPAPA - Balanzas analitica | GCF Loan, GCF Grant - CAF Loan | Planned | 12950.41 | 1
| FEDEPAPA - Sistema de riego - aspersion | GCF Loan, GCF Grant - CAF Loan | Planned | 4316.8033 | 1
| Grabadora de periodista | GCF Loan, GCF Grant - CAF Loan | Planned | 148.8919 | 1
| Mesa de selección de semilla de papa x organización | GCF Loan, GCF Grant - CAF Loan | Planned | 6381.4557 | 1
| Bascula de 100 kg x organización | GCF Loan, GCF Grant - CAF Loan | Planned | 2127.1519 | 1
| Fumigadora aspersor manual de 20 litros | GCF Loan, GCF Grant - CAF Loan | Planned | 737.1495 | 1
| ALIANZA - Accesorios | GCF Loan, GCF Grant - CAF Loan | Planned | 3875.9075 | 1
| ALIANZA - Contadores fase industrial | GCF Loan, GCF Grant - CAF Loan | Planned | 3043.2299 | 1
| Grabadora de periodista | GCF Loan, GCF Grant - CAF Loan | Planned | 148.8919 | 1
| ALIANZA - Accesorios | GCF Loan, GCF Grant - CAF Loan | Planned | 2913.8422 | 1
| ALIANZA - Repetidor | GCF Loan, GCF Grant - CAF Loan | Planned | 5827.6845 | 1
| FEDEGAN - Balanza analitica | GCF Loan, GCF Grant - CAF Loan | Planned | 6475.205 | 1
| FEDEGAN - Sistema de riego - aspersion | GCF Loan, GCF Grant - CAF Loan | Planned | 4316.8033 | 1
| Grabadora de periodista | GCF Loan, GCF Grant - CAF Loan | Planned | 74.446 | 1
| Balanza digital de precisión | GCF Loan, GCF Grant - CAF Loan | Planned | 2997.7801 | 1
| Camara termografica | GCF Loan, GCF Grant - CAF Loan | Planned | 8993.3403 | 1
| Tarimas de observacion | GCF Loan, GCF Grant - CAF Loan | Planned | 179.8668 | 1
| Cabina de Flujo Laminar | GCF Loan, GCF Grant - CAF Loan | Planned | 4352.1771 | 1
| CENICAFE - Calentadores | GCF Loan, GCF Grant - CAF Loan | Planned | 1199.112 | 1
| CENICAFE - Humidificador | GCF Loan, GCF Grant - CAF Loan | Planned | 1199.112 | 1
| CENICAFE - Módulo SAS IML | GCF Loan, GCF Grant - CAF Loan | Planned | 11580.4281 | 1
| CENICAFE - Módulo SAS/ACCPCFF | GCF Loan, GCF Grant - CAF Loan | Planned | 5023.6969 | 1
| Balanza Analítica | GCF Loan, GCF Grant - CAF Loan | Planned | 11558.2409 | 1
| CENICAFE - Molino de Martillos y cuchillas | GCF Loan, GCF Grant - CAF Loan | Planned | 5930.1972 | 1
| CENICAFE - Sistema de bombeo | GCF Loan, GCF Grant - CAF Loan | Planned | 3597.3361 | 1
| MATIS (10 unidades importacion) | GCF Loan, GCF Grant - CAF Loan | Planned | 2169.1937 | 1
| MATIS (EUR 86) | GCF Loan, GCF Grant - CAF Loan | Planned | 2227.4705 | 1
| RITA (USD 243) | GCF Loan, GCF Grant - CAF Loan | Planned | 5463.4542 | 1
| AGROSAVIA - Compra y mantenimeinto de sensores (matriciales) de humedad del suelo | GCF Loan, GCF Grant - CAF Loan | Planned | 5396.0042 | 1
| ALIANZA - Accesorios | GCF Loan, GCF Grant - CAF Loan | Planned | 7770.246 | 1
| ALIANZA - Contadores de caudal | GCF Loan, GCF Grant - CAF Loan | Planned | 6475.205 | 1
| ALIANZA - Material divulgativo (impresiones y diseño) | GCF Loan, GCF Grant - CAF Loan | Planned | 3187.6296 | 1
| ASOHOFRUCOL - Cartillas | GCF Loan, GCF Grant - CAF Loan | Planned | 6166.5536 | 1
| ASOHOFRUCOL - Estufas de secado de biomasa | GCF Loan, GCF Grant - CAF Loan | Planned | 3334.7306 | 1
| CENICAÑA - Adecuación de invernadero | GCF Loan, GCF Grant - CAF Loan | Planned | 2997.7801 | 1
| CENICAÑA - Densitometro Forestal | GCF Loan, GCF Grant - CAF Loan | Planned | 239.8224 | 1
| CENICAÑA - Esteriomicroscopio (2 equipos de Cenicaña) | GCF Loan, GCF Grant - CAF Loan | Planned | 5995.5602 | 1
| CENICAÑA - Hygro-termómetro Con Termómetro Infrarrojo | GCF Loan, GCF Grant - CAF Loan | Planned | 299.778 | 1
| CENICAÑA - Implementos para inventarios y monitoreo de fauna | GCF Loan, GCF Grant - CAF Loan | Planned | 35.049 | 1
| CENICAÑA - Lamparas para fotografía en estereomicroscopio | GCF Loan, GCF Grant - CAF Loan | Planned | 599.556 | 1
| CENICAÑA - Lente macro | GCF Loan, GCF Grant - CAF Loan | Planned | 899.334 | 1
| CENICAÑA - Sensor hydrosense campbell | GCF Loan, GCF Grant - CAF Loan | Planned | 3993.0431 | 1
| CENICAÑA - Termometros | GCF Loan, GCF Grant - CAF Loan | Planned | 3866.6921 | 1
| Microscopio triocular vertical | GCF Loan, GCF Grant - CAF Loan | Planned | 2727.9799 | 1
| NIR - Sacarosa Campo | GCF Loan, GCF Grant - CAF Loan | Planned | 6295.3382 | 1
| Panel solar portátil | GCF Loan, GCF Grant - CAF Loan | Planned | 3597.3361 | 1
| Pipetas de multicanales | GCF Loan, GCF Grant - CAF Loan | Planned | 2158.4017 | 1
| Placas multimodales para lector AND | GCF Loan, GCF Grant - CAF Loan | Planned | 7764.2504 | 1
| Potes plásticos | GCF Loan, GCF Grant - CAF Loan | Planned | 8993.3403 | 1
| Solucion de medicion para la estacion integrada de monitoreo agronomico (Sucrologger, sensores de pH, CE, NO3, K+, Na, potencial matrico, panel solar) | GCF Loan, GCF Grant - CAF Loan | Planned | 3545.0457 | 1
| ALIANZA - Insumos - Papeleria - Plotter | GCF Loan, GCF Grant - CAF Loan | Planned | 5312.7161
| ALIANZA- Parcelas de heces y orina | GCF Loan, GCF Grant - CAF Loan | Planned | 354.5046
| Materiales varios para talleres | GCF Loan, GCF Grant - CAF Loan | Planned | 2656.358
| Alianza Materiales varios para talleres |  |  | 1328.179
| Viales al vacío para ciclo de cultivo - muestreo de GEI | GCF Loan, GCF Grant - CAF Loan | Planned | 3878.9794 | 1
Total For Equipment |  |  |  | 5742503.2514
|  |  | Check | 8.3674e-10
TRAVEL & TRAINING PROCUREMENT PLAN
Travel & Training Procurement Packages with Methods and Time Schedule
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Ref. No. | Contract | Source of Funds | Planned vs Actual |  | Procurement | Pre | Domestic Preference | Review | Date of issuance of doc’s | Bid-Opening | Date of contract | Comments
| (Description) |  |  | Estimated | Method | qualification (yes/no) | (yes/no) | by AE/Fund |  | Date | /order signature
|  |  |  | Cost in US$ |  |  |  | (Prior / Post)
1 | ALIANZA - Acompañamiento visita a 4 lotes por departamento, 2 veces al año para monitoreo con dron | GCF Loan, GCF Grant - CAF Loan | Planned | 17739.159 | 1
2 | ALIANZA - Acompañamiento para el fortalecimiento y transferencia de capacidad en manejo de riesgo agroclimático | GCF Loan, GCF Grant - CAF Loan | Planned | 23375.9507 | 1
3 | ALIANZA - Acompañamiento socialización de resultados con productores 2 veces al año | GCF Loan, GCF Grant - CAF Loan | Planned | 49370.1157 | 1
4 | ALIANZA - Capacitacion Ag-Digital | GCF Loan, GCF Grant - CAF Loan | Planned | 1171.0147 | 1
5 | ALIANZA - Capacitación de técnicos del sector en el protocolo experimental y analítico para modelado de maíz | GCF Loan, GCF Grant - CAF Loan | Planned | 6475.205 | 1
6 | ALIANZA - Capacitación de técnicos del sector en los protocolos de monitoreo en finca (2 veces en 1er año) | GCF Loan, GCF Grant - CAF Loan | Planned | 12950.41 | 1
7 | ALIANZA - Capacitación en el uso de NextGen para técnicos y profesionales del sector | GCF Loan, GCF Grant - CAF Loan | Planned | 5396.0042 | 1
8 | ALIANZA - Diseño de la herramienta de captura e identificación de variables | GCF Loan, GCF Grant - CAF Loan | Planned | 1014.4488 | 1
9 | ALIANZA - Estudios de usabilidad - plataforma Aclimate - Modulo Ganaderia | GCF Loan, GCF Grant - CAF Loan | Planned | 8896.3418 | 1
10 | ALIANZA - Gira tecnica agroclimatica | GCF Loan, GCF Grant - CAF Loan | Planned | 23369.0041 | 1
11 | ALIANZA - Gira tecnica Ganaderia y Clima | GCF Loan, GCF Grant - CAF Loan | Planned | 18035.9159 | 1
12 | ALIANZA - Grupos focales para identificación de necesidades | GCF Loan, GCF Grant - CAF Loan | Planned | 24542.8519 | 1
13 | ALIANZA - Participacion en MTA | GCF Loan, GCF Grant - CAF Loan | Planned | 15178.8107 | 1
14 | ALIANZA - Reunión anual de la comunidad de práctica | GCF Loan, GCF Grant - CAF Loan | Planned | 0 | 1
15 | ALIANZA - Reunion Coordinacion parcelas experimentales | GCF Loan, GCF Grant - CAF Loan | Planned | 12095.1517 | 1
16 | ALIANZA - Reunión de capacitación de técnicos para captura de datos y seguimiento | GCF Loan, GCF Grant - CAF Loan | Planned | 1618.8012 | 1
17 | ALIANZA - Reunion Planificacion parcelas experimentales | GCF Loan, GCF Grant - CAF Loan | Planned | 1014.4488 | 1
18 | ALIANZA - Validacion de funcionamiento de equipos | GCF Loan, GCF Grant - CAF Loan | Planned | 8295.5534 | 1
19 | ALIANZA - Validación de la herramienta de captura | GCF Loan, GCF Grant - CAF Loan | Planned | 2009.3392 | 1
20 | ALIANZA - Validación de lotes monitoreados por sensoramiento remoto | GCF Loan, GCF Grant - CAF Loan | Planned | 14944.5326 | 1
21 | ALIANZA - Validación del bot con agricutores | GCF Loan, GCF Grant - CAF Loan | Planned | 31031.9983 | 1
22 | ALIANZA - Viajes técnicos de sistemas validación de la usabilidad | GCF Loan, GCF Grant - CAF Loan | Planned | 8550.3794 | 1
23 | ALIANZA - Viajes técnicos entrenamiento modelos | GCF Loan, GCF Grant - CAF Loan | Planned | 14944.5326 | 1
24 | ALIANZA - Visita apoyo para colectar información (2 veces al año, de Cali a las regiones) | GCF Loan, GCF Grant - CAF Loan | Planned | 11308.4728 | 1
25 | ALIANZA - Visita apoyo para colectar información (cinco veces al año, de Cali a las regiones) | GCF Loan, GCF Grant - CAF Loan | Planned | 6793.8725 | 1
26 | ALIANZA - Visita para implementación de servicios climáticos (1 vez al año, de Cali a las regiones) | GCF Loan, GCF Grant - CAF Loan | Planned | 22440.9127 | 1
27 | ALIANZA - Visita para implementación de servicios climáticos (2 veces al año, de Cali a las regiones) | GCF Loan, GCF Grant - CAF Loan | Planned | 11220.4563 | 1
28 | ALIANZA - Vuelos de drones | GCF Loan, GCF Grant - CAF Loan | Planned | 14192.4979 | 1
29 | ALIANZA-Viajes | GCF Loan, GCF Grant - CAF Loan | Planned | 21144.4237 | 1
30 | ALIANZA-Viajes a dias de campo | GCF Loan, GCF Grant - CAF Loan | Planned | 2632.8618 | 1
31 | CIAT - Reunión planificación - viaje nacional | GCF Loan, GCF Grant - CAF Loan | Planned | 1742.431 | 1
32 | ALIANZA - viajes acompañamiento y socialización de resultados | GCF Loan, GCF Grant - CAF Loan | Planned | 4238.6349 | 1
33 | ALIANZA - viajes a campo para toma de imágenes | GCF Loan, GCF Grant - CAF Loan | Planned | 8539.7329 | 1
34 | ALIANZA - Reunion de trabajo | GCF Loan, GCF Grant - CAF Loan | Planned | 9017.9579 | 1
35 | ALIANZA - Acompañamiento para el fortalecimiento y transferencia de capacidad en manejo de riesgo agroclimático | GCF Loan, GCF Grant - CAF Loan | Planned | 227052.562 | 1
36 | ALIANZA - Entrenamiento tecnicos de campo | GCF Loan, GCF Grant - CAF Loan | Planned | 2967.8023 | 1
37 | ALIANZA - Estudios de usabilidad - DSS - plataforma Aclimate | GCF Loan, GCF Grant - CAF Loan | Planned | 6318.4246 | 1
38 | ALIANZA - Estudios de usabilidad - plataforma Aclimate - Modulo Papa | GCF Loan, GCF Grant - CAF Loan | Planned | 12373.5815 | 1
39 | ALIANZA - Monitoreo parcelas experimentales 4 por año * localidad * 2 dias | GCF Loan, GCF Grant - CAF Loan | Planned | 38295.9172 | 1
40 | ALIANZA - Reunión anual de la comunidad de práctica | GCF Loan, GCF Grant - CAF Loan | Planned | 40642.278 | 1
41 | ALIANZA - Reunion Coordinacion parcelas experimentales - 2 por localidad*ciclo*2 dias | GCF Loan, GCF Grant - CAF Loan | Planned | 17692.3762 | 1
42 | ALIANZA - Reunion Planificacion parcelas experimentales | GCF Loan, GCF Grant - CAF Loan | Planned | 20839.682 | 1
43 | ALIANZA - Reuniones de apoyo y coordinacion (comunidad de práctica) | GCF Loan, GCF Grant - CAF Loan | Planned | 9393.7062 | 1
44 | ALIANZA - Reuniones de la comunidad de práctica | GCF Loan, GCF Grant - CAF Loan | Planned | 17565.6928 | 1
45 | ALIANZA - Reuniones de trabajo/coordinacion (comunidad de práctica) | GCF Loan, GCF Grant - CAF Loan | Planned | 11687.9754 | 1
46 | ALIANZA - Socializaciones resultados de modelos predictivos con técnicos y agricultores | GCF Loan, GCF Grant - CAF Loan | Planned | 23375.9507 | 1
47 | ALIANZA - Travel expenses Training/Workshop on Weather generators covering 1 week | GCF Loan, GCF Grant - CAF Loan | Planned | 4264.5432 | 1
48 | ALIANZA - Validación de lotes monitoreados por sensoramiento remoto | GCF Loan, GCF Grant - CAF Loan | Planned | 3464.6028 | 1
49 | ALIANZA - Viajes del equipo de la Alianza para fortalecimiento de capacidades modelación y plataforma | GCF Loan, GCF Grant - CAF Loan | Planned | 11687.9754 | 1
50 | ALIANZA - Visita apoyo para colectar información (3 veces al año, de Cali a las regiones) | GCF Loan, GCF Grant - CAF Loan | Planned | 13587.7449 | 1
51 | ALIANZA - Visita de acompañamiento para implementación de servicios climáticos (2 veces al año, de Cali a las regiones) | GCF Loan, GCF Grant - CAF Loan | Planned | 9987.9062 | 1
52 | ALIANZA - Visita para implementación de servicios climáticos (2 veces al año, de Cali a las regiones) | GCF Loan, GCF Grant - CAF Loan | Planned | 14038.7342 | 1
53 | ALIANZA - Vuelos de drones | GCF Loan, GCF Grant - CAF Loan | Planned | 12056.0349 | 1
54 | CIAT-Evaluación y codiseño de medidas para el aprovechamiento de recursos renovables | GCF Loan, GCF Grant - CAF Loan | Planned | 1703.3211 | 1
55 | Seguimiento del proceso con socios | GCF Loan, GCF Grant - CAF Loan | Planned | 7969.0741 | 1
56 | Evaluación 1 (tte aéreo, terrestre ciudad ppal) | GCF Loan, GCF Grant - CAF Loan | Planned | 2937.8245 | 1
57 | Evaluación 2 (tte aéreo, teerestre, ciudad ppal) | GCF Loan, GCF Grant - CAF Loan | Planned | 1754.3325 | 1
58 | Codiseño de sistemas forrajeros (ciudad intermedia) | GCF Loan, GCF Grant - CAF Loan | Planned | 3237.6025 | 1
59 | Evaluación productiva y ambiental | GCF Loan, GCF Grant - CAF Loan | Planned | 3150.638 | 1
60 | Evaluación económica y social (ciudad intermedia) | GCF Loan, GCF Grant - CAF Loan | Planned | 2076.5569 | 1
61 | CIAT-evaluación económica de las tecnologías (ciudad ppal) | GCF Loan, GCF Grant - CAF Loan | Planned | 4475.3381 | 1
62 | CIAT-Diagnóstico del estado actual (aéreo-terrestre, ciudad ppal) | GCF Loan, GCF Grant - CAF Loan | Planned | 3508.6651 | 1
63 | CIAT-Codiseño de medidas de adaptación y BA (aéreo-terrestre, ciudad ppal) | GCF Loan, GCF Grant - CAF Loan | Planned | 3474.1448 | 1
64 | ALIANZA - Visitas de acompañamiento a Cali - Urabá (2x año - 5 años) | GCF Loan, GCF Grant - CAF Loan | Planned | 5396.0042 | 1
65 | ALIANZA -Visitas de acompañamiento a a Cali - Santa Marta y La Guajira (3x año - 5 años) | GCF Loan, GCF Grant - CAF Loan | Planned | 16188.0125 | 1
66 | ALIANZA - Visita de acompañamiento a Palmira (5 años) | GCF Loan, GCF Grant - CAF Loan | Planned | 3237.6025 | 1
67 | ALIANZA - Capacitación | GCF Loan, GCF Grant - CAF Loan | Planned | 8579.5947 | 1
68 | ALIANZA - Monitoreo y colecta de información | GCF Loan, GCF Grant - CAF Loan | Planned | 322722.5464 | 1
69 | ALIANZA - Reunión cordinación | GCF Loan, GCF Grant - CAF Loan | Planned | 593.7763 | 1
70 | ALIANZA - Reunión cordinación en localidades - Implementación | GCF Loan, GCF Grant - CAF Loan | Planned | 144061.4189 | 1
71 | ALIANZA - Reunión cordinación en localidades - Instalación | GCF Loan, GCF Grant - CAF Loan | Planned | 46046.6676 | 1
72 | ALIANZA - Reunión cordinación en localidades - Intalación | GCF Loan, GCF Grant - CAF Loan | Planned | 42461.3542 | 1
73 | ALIANZA - Reunión cordinación/reconocimiento | GCF Loan, GCF Grant - CAF Loan | Planned | 7893.3762 | 1
74 | ALIANZA - Reunión planificación - viaje nacional | GCF Loan, GCF Grant - CAF Loan | Planned | 27283.0111 | 1
75 | ALIANZA - Reunión planificación nacionales | GCF Loan, GCF Grant - CAF Loan | Planned | 40900.8684 | 1
76 | ALIANZA - Validacion de puntos | GCF Loan, GCF Grant - CAF Loan | Planned | 1640.9573 | 1
77 | ALIANZA - Viajes a sitios experimentales | GCF Loan, GCF Grant - CAF Loan | Planned | 26563.5804 | 1
78 | ALIANZA - Visita localidades | GCF Loan, GCF Grant - CAF Loan | Planned | 150304.014 | 1
79 | ALIANZA - viajes | GCF Loan, GCF Grant - CAF Loan | Planned | 70618.5762 | 1
80 | ALIANZA - Viajes | GCF Loan, GCF Grant - CAF Loan | Planned | 19557.2274 | 1
81 | Participación como facilitadores en diversos eventos, talleres y reuniones | GCF Loan, GCF Grant - CAF Loan | Planned | 21250.8643 | 1
82 | Alianza Participación como facilitadores en diversos eventos, talleres y reuniones | GCF Loan, GCF Grant - CAF Loan | Planned | 31876.2964 | 1
83 | ALIANZA - Gastos de viaje | GCF Loan, GCF Grant - CAF Loan | Planned | 14223.4477 | 1
84 | ALIANZA- Gastos de viaje | GCF Loan, GCF Grant - CAF Loan | Planned | 15197.0765 | 1
85 | Alianza seguimiento a colecta de datos, socializaciones y reuniones gremiales | GCF Loan, GCF Grant - CAF Loan | Planned | 82297.8332 | 1
86 | ALIANZA - viajes | GCF Loan, GCF Grant - CAF Loan | Planned | 106254.3215 | 1
87 | MIN - Viajes Consultores Nacionales | GCF Loan, GCF Grant - CAF Loan | Planned | 132817.9018 | 1
88 | ALIANZA - Capacitación en el uso de NextGen para técnicos y profesionales del sector | GCF Loan, GCF Grant - CAF Loan | Planned | 5396.0042 | 1
89 | ALIANZA - Elaboración de un curso virtual (plataforma e-learning) en temas agroclimáticos para personal de Fedegan | GCF Loan, GCF Grant - CAF Loan | Planned | 2158.4017 | 1
90 | ALIANZA - Gira regionales de implementación | GCF Loan, GCF Grant - CAF Loan | Planned | 51238.3973 | 1
91 | ALIANZA - Giras Regionales | GCF Loan, GCF Grant - CAF Loan | Planned | 17531.963 | 1
92 | ALIANZA - Taller socialización resultados análisis bases de datos (1 taller por año - 2-3-4-5 y 7 localidades 30 personas) | GCF Loan, GCF Grant - CAF Loan | Planned | 11134.2219 | 1
93 | ALIANZA - Talleres de capacitación | GCF Loan, GCF Grant - CAF Loan | Planned | 529.1706 | 1
94 | ALIANZA - Talleres de socialización de resultados de los servicios climáticos generados (6) | GCF Loan, GCF Grant - CAF Loan | Planned | 38226.77 | 1
95 | ALIANZA -Dias de campo socialización uso de sensores remotos y no remotos (8 talleres, inicio 3er año, dias de campo: #talleres 2,2,4) | GCF Loan, GCF Grant - CAF Loan | Planned | 4672.9395 | 1
96 | ALIANZA - Productos agroclimaticos para el sector arrocero | GCF Loan, GCF Grant - CAF Loan | Planned | 1053.0708 | 1
97 | ALIANZA - Capacitaciones Nacionales en desarrollo y evaluación de varieades | GCF Loan, GCF Grant - CAF Loan | Planned | 29515.0893 | 1
98 | Talleres | GCF Loan, GCF Grant - CAF Loan | Planned | 17552.4117 | 1
99 | CIAT-Gira de conferencias | GCF Loan, GCF Grant - CAF Loan | Planned | 35626.5807 | 1
100 | ALIANZA - Training en huella de carbono (12 profesionales) | GCF Loan, GCF Grant - CAF Loan | Planned | 4773.6939 | 1
101 | ALIANZA - Training en huella de carbono (47 profesionales) | GCF Loan, GCF Grant - CAF Loan | Planned | 17944.0164 | 1
102 | ALIANZA - Training en huella hídrica Profesionals gremio (47 total) | GCF Loan, GCF Grant - CAF Loan | Planned | 12530.9466 | 1
103 | ALIANZA - Workshop Profesionales Gremio (10 Total/5 por taller) | GCF Loan, GCF Grant - CAF Loan | Planned | 9547.3879 | 1
104 | ALIANZA - Workshop Profesionales Gremio (15 Total) | GCF Loan, GCF Grant - CAF Loan | Planned | 1772.5228 | 1
105 | ALIANZA - Workshop Profesionales Gremio (50) | GCF Loan, GCF Grant - CAF Loan | Planned | 2398.2241 | 1
106 | Organización y logística de eventos no conciderados en los gremios, pej. Creación comunidades de práctica | GCF Loan, GCF Grant - CAF Loan | Planned | 10625.4321 | 1
107 | Alianza Organización y logística de eventos no conciderados en los gremios, pej. Creación comunidades de práctica | GCF Loan, GCF Grant - CAF Loan | Planned | 34532.6545 | 1
108 | Alianza Organización y logística de eventos no considerados en los gremios, pej. Creación comunidades de práctica | GCF Loan, GCF Grant - CAF Loan | Planned | 10625.4321 | 1
109 | 5 Grupos focales | GCF Loan, GCF Grant - CAF Loan | Planned | 52064.6175 | 1
110 | workshop | GCF Loan, GCF Grant - CAF Loan | Planned | 1460.9969 | 1
111 | Workshop 2 | GCF Loan, GCF Grant - CAF Loan | Planned | 8765.9815 | 1
Total For Traveling & Training |  |  |  | 2666516.469
|  |  | Check | 0
SERVICES PROCUREMENT PLAN
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Ref. No. | Contract | Source of Funds | Planned vs Actual |  | Procurement | Pre | Domestic Preference | Review | Date of issuance of doc’s | Bid-Opening | Date of contract | Comments
| (Description) |  |  | Estimated | Method | qualification (yes/no) | (yes/no) | by AE/Fund |  | Date | /order signature
|  |  |  | Cost in US$ |  |  |  | (Prior / Post)
1. | GHG Analysis | GCF Loan, GCF Grant - CAF Loan | Planned | 1417028.3 | 2
| ALIANZA - Analisis GEI |  |  | 1308082.1955
| ALIANZA - Analisis GEI - Invitro |  |  | 153.146
| ALIANZA - Analisis GEI parches |  |  | 14702.0135
| ALIANZA - Jornales muestreo GEI |  |  | 7632.576
| ALIANZA - Jornales muestreos GEI |  |  | 709.0091
| ALIANZA - Jornales muetreso GEI |  |  | 85749.3599
2. | Genero | GCF Loan, GCF Grant - CAF Loan | Planned | 1919413.6634 | 3
3. | ALIANZA - CSP | GCF Loan, GCF Grant - CAF Loan | Planned | 1741322.488 | 2
4. | Aplicacion de encuestas (1000 encuestas) | GCF Loan, GCF Grant - CAF Loan | Planned | 727729.7848 | 2
5. | ALIANZA - Materiales | GCF Loan, GCF Grant - CAF Loan | Planned | 305465.7805 | 1
6. | ALIANZA - Plan datos LynkBOX | GCF Loan, GCF Grant - CAF Loan | Planned | 195402.3531 | 2
7. | ALIANZA - Analisis Varios | GCF Loan, GCF Grant - CAF Loan | Planned | 251348.9562 | 2
8. | ALIANZA - Auditoria | GCF Loan, GCF Grant - CAF Loan | Planned | 122192.4697 | 2
9. | ALIANZA - Comunicaciones | GCF Loan, GCF Grant - CAF Loan | Planned | 106254.3215 | 2
10. | ALIANZA - Licensamientos | GCF Loan, GCF Grant - CAF Loan | Planned | 58152.9423 | 2
| ALIANZA - VMWare licenciamiento- Servidor GPU |  |  | 6745.0052
| ALIANZA - VMWare licenciamiento- Servidor GPU (Dividido gremios) |  |  | 33204.4755
| ALIANZA - VMWare licenciamiento- Servidor GPU (repartido en 3 gremios) |  |  | 6745.0052
| ALIANZA - VMWare licenciamiento- Servidor GPU (repartido entre 6 gremios) |  |  | 3372.5026
| ALIANZA - NVIDIA Licenciamiento- Servidor GPU (por año) |  |  | 616.2751
| ALIANZA - Seguro de los equipos sensoramiento remoto |  |  | 5312.7161
| ALIANZA - NVIDIA Licenciamiento- Servidor GPU (Divido en gremios) |  |  | 616.2751
| ALIANZA - NVIDIA Licenciamiento- Servidor GPU (por año) |  |  | 1540.6877
11. | Services < 100k | GCF Loan, GCF Grant - CAF Loan | Planned | 388532.0919 | See each one
| ALIANZA - Asesores Emeritos |  |  | 74378.025 | 2
| ALIANZA - Operaciones y Servicios |  |  | 53127.1607 | 2
| ALIANZA - Analisis calidad de agua - Hato |  |  | 53951.6761 | 2
| ALIANZA - Materiales Varios |  |  | 25177.0623 | 2
| Implementación de parcelas demostrativas con forrajes mejorados |  |  | 36962.6285 | 2
| ALIANZA - Analisis calidad de agua - Cultivo |  |  | 60267.9698 | 2
| ALIANZA - Analisis Nitrogeno mineral |  |  | 52665.0941 | 2
| ALIANZA - Viales |  |  | 32002.4753 | 2
| Generación de material transmedia para procesos de transferencia (vidoclips y/o cartillas) |  |  | 39492.9263 | 2
| ALIANZA - Analisis quimica suelos |  |  | 24706.0873 | 2
| ALIANZA- Servicio de corrección de estilo y diagramación |  |  | 26457.3059 | 2
| ALIANZA - Analisis fisica suelos |  |  | 20484.337 | 2
12. | Services < 10k | GCF Loan, GCF Grant - CAF Loan | Planned | 136744.2662 | See each one
| ALIANZA - Backup instancias en la nube |  |  | 2266.3217 | 1
| ALIANZA - Certificado SSL Wildcard |  |  | 423.3515 | 1
| ALIANZA - Certificado SSL Wildcard e Instancias en la nube |  |  | 315.9434 | 1
| ALIANZA - Dominio |  |  | 323.7602 | 1
| ALIANZA - Dominio ACLIMATE |  |  | 323.7602 | 1
| ALIANZA - Instancia en la nube |  |  | 7014.8054 | 1
| ALIANZA - Instancias en la nube |  |  | 2831.823 | 1
| ALIANZA - Licencias de servicios (Whatsapp, otros) |  |  | 3388.3481 | 1
| ALIANZA - Licencias VeeamBackup |  |  | 1618.8012 | 1
| ALIANZA - Mantenimiento de drones y sensores |  |  | 4275.1897 | 1
| ALIANZA - Mantenimiento servidores |  |  | 7628.4035 | 1
| ALIANZA - Material divulgativo |  |  | 3347.0111 | 1
| ALIANZA - Mensajeria de texto |  |  | 17416.7381 | 1
| ALIANZA - Publicaciones en revistas cientificas |  |  | 3159.545 | 1
| ALIANZA - Seguro de los equipos sensoramiento remoto |  |  | 10625.4321 | 1
| ALIANZA - Servicio de imágenes de drones |  |  | 15239.4082 | 1
| ALIANZA - Servicio de imágenes de drones |  |  | 15390.6829 | 1
| ALIANZA - VMWare licenciamiento- Servidor GPU (repartido en 3 gremios) |  |  | 2248.3351 | 1
| Material divulgativo |  |  | 5318.0609 | 1
| ALIANZA - Analisis Bromatologicos |  |  | 2127.0274 | 1
| ALIANZA - Analisis calidad de agua - Industria |  |  | 3953.3153 | 1
| ALIANZA - Analisis calidad leche |  |  | 425.4055 | 1
| ALIANZA - Analisis Producción de gas invitro |  |  | 2481.532 | 1
| ALIANZA - Calidad de leche |  |  | 3804.1315 | 1
| ALIANZA - Mano de obra |  |  | 1595.2706 | 1
| Alianza Reproducción material impreso |  |  | 9619.28 | 1
| ALIANZA- Servicio de diseño de Policy brief e infografías |  |  | 2116.5845 | 1
| Alianza Diseño productos de comunicación |  |  | 7465.998 | 1
Selection of Consultants
1. Prior Review Threshold: Selection decisions subject to Prior Review by AE/Fund:
| Selection Method | Prior Review Threshold | Comment
1.
2
3.
Consultancy Assignments with Selection Methods and Time Schedule
1 | 2 | 3 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
|  | Source of Funds |  |  |  | Issuance of Expression of Interest | Finalize shortlist and issue RFP |  |  | Complete Financial Evaluation | Negotiate and Award | Comment
Ref. No. | Description of Assignment |  | Estimated | Selection | Review |  |  | Proposals Submission | Complete Technical Evaluation
|  |  | Cost | Method | by AE/Fund |  |  | Date
(Prior / Post)
1
2
3
Convenios/Contratos con gremios

## 4.7. Procurement Plan - C
GCF Summaries - Consulting Services Procurement Plan
Selection of Consultants
I. General
1. Project information: limate-smart initiatives for climate change adaptation and sustainability in prioritized agricultural production systems in Colombia
2. Version of the Plan: Version 1.0 dated 15/11/2021
3. Approval Date of the procurement Plan:
4. Date of General Procurement Notice:
5. Period covered by this procurement plan: 2022-2026
6. Other Arrangements:
1. Prior Review Threshold: Selection decisions subject to Prior Review by AE/Fund:
| Selection Method | Prior Review Threshold | Comment
1. | Contracts for a amount up to USD 25,000 | Program Leaders and Heads of Unit are authorized to sign consultancy contracts | Selection should be on the basis of comparison of qualifications of at least three (3) candidates with a minimun relevant qualifications. For direct contracting of consultants, justification of a single applicant should include an statement indicating that the consulting involves highly specialized skills and experience and that based upon knoledge of the filed, only one person meets requirements. if there are more than one applicants but only one is available in the requered time frame, the consultant can be nominated as a sole supplier.
2 | Contracts for a amount up to USD 50,000 | Research Area Director and regional Directors are authorized to sign consultancy contracts
3. | Contracts over USD 50,000 | Must be sign by DG and need previous approval from the Contracting Committee
4 | Direct Assignment with specialized Agencies
Direct Assignment with specialized Agencies
1 | 2 | 3 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Source of Funds |  |  |  |  | Issuance of Expression of Interest | Finalize shortlist and issue RFP |  |  | Complete Financial Evaluation | Negotiate and Award | Comment
Ref. No. | Description of Assignment |  | Estimated | Estimated | Selection | Review |  |  | Proposals Submission | Complete Technical Evaluation
|  |  | Cost ( 5 years) | Cost ( 1 years - 2023) | Method | by AE/Fund |  |  | Date
(Prior / Post)
1 | Fedearroz | GCF Loan, GCF Grant - CAF Loan | 5010279.2425 | 806592.4991 | 4
2 | Fenalce | GCF Loan, GCF Grant - CAF Loan | 2595876.0113 | 333905.3738 | 4
3 | Fedepapa | GCF Loan, GCF Grant - CAF Loan | 2210277.7688 | 323946.165 | 4
4 | Fedepanela | GCF Loan, GCF Grant - CAF Loan | 2316308.5736 | 384368.1511 | 4
5 | Fedegan | GCF Loan, GCF Grant - CAF Loan | 5839352.8488 | 384417.065 | 4
6 | Fedeacafé-Cenicafé | GCF Loan, GCF Grant - CAF Loan | 3375746.2111 | 683346.1692 | 4
7 | Asbama-Augura-Asohofrucol | GCF Loan, GCF Grant - CAF Loan | 4569882.9753 | 877090.4969 | 4
8 | Asocaña-Cenicaña | GCF Loan, GCF Grant - CAF Loan | 6980004.6473 | 1825016.0594 | 4
9 | Agrosavia | GCF Loan, GCF Grant - CAF Loan | 4044800.6096 | 845263.7455 | 4
10 | CIMMYT | GCF Loan, GCF Grant - CAF Loan | 2022677.3806 | 396101.7104 | 4
11 | CIPAV | GCF Loan, GCF Grant - CAF Loan | 797342.5231 | 162310.8516 | 4
12 | Genero | GCF Loan, GCF Grant - CAF Loan | 757934.885 | 157210.8927 | 4
Total For Direct Assignment |  |  | 40520483.677
Contracts over USD 50,000
1 | 2 | 3 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Source of Funds |  |  |  |  | Issuance of Expression of Interest | Finalize shortlist and issue RFP |  |  | Complete Financial Evaluation | Negotiate and Award | Comment
Ref. No. | Description of Assignment |  | Estimated | Estimated | Selection | Review |  |  | Proposals Submission | Complete Technical Evaluation
|  |  | Cost ( 5 years) | Cost ( 1 year - 2023) | Method | by AE/Fund |  |  | Date
(Prior / Post)
1 | ALIANZA - Research assistant | GCF Loan, GCF Grant - CAF Loan | 831282.3438 | 279794.4335 | 3
2 | ALIANZA - Líder del Proyecto | GCF Loan, GCF Grant - CAF Loan | 1295555.9271 | 263210.6278 | 3
3 | Alianza - Asesores científicos | GCF Loan, GCF Grant - CAF Loan | 769344.0733 | 231481.1234 | 3
4 | ALIANZA - Jefe de Legal | GCF Loan, GCF Grant - CAF Loan | 1024302.705 | 208101.6747 | 3
5 | ALIANZA - Director Regional Americas | GCF Loan, GCF Grant - CAF Loan | 882718.401 | 179336.808 | 3
6 | ALIANZA - Carbon and water footprint specialist | GCF Loan, GCF Grant - CAF Loan | 465961.1585 | 129499.7575 | 3
7 | ALIANZA - Científico Senior - Fitopatología y Producción Sostenible | GCF Loan, GCF Grant - CAF Loan | 543248.5945 | 110368.6847 | 3
8 | CIAT - Personal de apoyo | GCF Loan, GCF Grant - CAF Loan | 531271.6073 | 107935.3893 | 3
9 | ALIANZA - Gerente Regional Financiero | GCF Loan, GCF Grant - CAF Loan | 516400.4903 | 104914.1102 | 3
10 | Position 1 | GCF Loan, GCF Grant - CAF Loan | 454760.931 | 94326.5356 | 3
11 | ALIANZA - Water and soil emission specialist | GCF Loan, GCF Grant - CAF Loan | 403647.4914 | 93944.1997 | 3
12 | ALIANZA - Socio internacional IRI para conexión y capacitaciones de pronósticos (NextGen), repartido en 6 sistemas productivos | GCF Loan, GCF Grant - CAF Loan | 179325.3225 | 89888.5922 | 3
13 | ALIANZA - Líder de Logistica | GCF Loan, GCF Grant - CAF Loan | 440640.136 | 89522.3158 | 3
14 | ALIANZA - Soil GEI emissions expert | GCF Loan, GCF Grant - CAF Loan | 229526.2878 | 88279.9231 | 3
15 | ALIANZA - Research assistant HC | GCF Loan, GCF Grant - CAF Loan | 350805.4908 | 70161.0982 | 1
16 | Alianza Experto en Evaluación de impacto y seguimiento | GCF Loan, GCF Grant - CAF Loan | 295792.4908 | 60094.4549 | 3
17 | ALIANZA - Personal de apoyo | GCF Loan, GCF Grant - CAF Loan | 353646.3995 | 59978.0592 | 3
18 | ALIANZA - Research assistant Carbon Footprint | GCF Loan, GCF Grant - CAF Loan | 119515.7107 | 59955.95 | 3
19 | ALIANZA - Asociado de Investigación | GCF Loan, GCF Grant - CAF Loan | 293738.4013 | 59677.1374 | 3
20 | ALIANZA - Científico líder de lever de la alianza | GCF Loan, GCF Grant - CAF Loan | 273564.5011 | 55578.5224 | 3
21 | ALIANZA - Soporte Logistico y Administrativo | GCF Loan, GCF Grant - CAF Loan | 265635.8037 | 53967.6946 | 3
22 | Soporte Logistico y Administrativo | GCF Loan, GCF Grant - CAF Loan | 265635.8037 | 53967.6946 | 3
23 | Alianza - Personal cientifico de apoyo | GCF Loan, GCF Grant - CAF Loan | 265635.8037 | 53967.6946 | 3
24 | ALIANZA - Coordinadora de Administración de Proyectos | GCF Loan, GCF Grant - CAF Loan | 263148.9452 | 53462.4539 | 3
Total For Contracts Over USD 50,000 |  |  | 11315104.8199
Contracts for a amount up to USD 50,000
1 | 2 | 3 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Source of Funds |  |  |  |  | Issuance of Expression of Interest | Finalize shortlist and issue RFP |  |  | Complete Financial Evaluation | Negotiate and Award | Comment
Ref. No. | Description of Assignment |  | Estimated | Estimated | Selection | Review |  |  | Proposals Submission | Complete Technical Evaluation
|  |  | Cost ( 5 years) | Cost ( 1 years - 2023) | Method | by AE/Fund |  |  | Date
(Prior / Post)
1 | Alianza Asesores científicos | GCF Loan, GCF Grant - CAF Loan | 235175.8773 | 47779.327 | 2
2 | ALIANZA - Research assistant MFL | GCF Loan, GCF Grant - CAF Loan | 234000.3274 | 46800.0655 | 2
3 | ALIANZA - Social reseacrh asistant | GCF Loan, GCF Grant - CAF Loan | 234000.3274 | 46800.0655 | 2
4 | ALIANZA - Research assistant HH | GCF Loan, GCF Grant - CAF Loan | 233805.3271 | 46761.0654 | 2
5 | Alianza Experta en Evaluación de Impacto | GCF Loan, GCF Grant - CAF Loan | 228208.5247 | 45492.5124 | 2
6 | ALIANZA - Soporte Logistico y Administrativo | GCF Loan, GCF Grant - CAF Loan | 229890.4186 | 44898.7794 | 2
7 | TEMP - Profesional Temporal Estreses Abioticos | GCF Loan, GCF Grant - CAF Loan | 212423.5864 | 43156.8753 | 2
8 | Asistente investigación | GCF Loan, GCF Grant - CAF Loan | 205367.9832 | 41723.429 | 2
9 | Asistente investigación 5 | GCF Loan, GCF Grant - CAF Loan | 205367.9832 | 41723.429 | 2
10 | Data Scientist | GCF Loan, GCF Grant - CAF Loan | 198488.9512 | 40325.8558 | 2
11 | ALIANZA - Research assistant Water Footprint | GCF Loan, GCF Grant - CAF Loan | 79740.3379 | 39970.6334 | 2
12 | Alianza Personal científico de la Alianza | GCF Loan, GCF Grant - CAF Loan | 191257.7786 | 38856.7401 | 2
13 | Alianza - Asesores científicos | GCF Loan, GCF Grant - CAF Loan | 186878.4112 | 37967.0093 | 2
14 | Estadístico con experiencia en modelación climática | GCF Loan, GCF Grant - CAF Loan | 170945.9189 | 36835.1535 | 2
15 | MIN - Technical coordinator | GCF Loan, GCF Grant - CAF Loan | 177090.5358 | 35978.4631 | 2
16 | Asistente 1(Patologia) | GCF Loan, GCF Grant - CAF Loan | 176351.939 | 35828.4066 | 2
17 | Eliel Petro | GCF Loan, GCF Grant - CAF Loan | 176351.939 | 35828.4066 | 2
18 | ALIANZA - Research assistant Forrajes | GCF Loan, GCF Grant - CAF Loan | 175664.5361 | 35132.9072 | 2
19 | Coordinador con experiencia en manejo de riesgo agroclimático | GCF Loan, GCF Grant - CAF Loan | 168580.7901 | 34249.5871 | 2
20 | ALIANZA - Asistente de Investigación | GCF Loan, GCF Grant - CAF Loan | 164986.0085 | 33519.2561 | 2
21 | ALIANZA - Analista de Proyecto | GCF Loan, GCF Grant - CAF Loan | 159232.0547 | 32350.2584 | 2
22 | ALIANZA - Asistente de Logística | GCF Loan, GCF Grant - CAF Loan | 159232.0547 | 32350.2584 | 2
23 | Alejandra Rubio | GCF Loan, GCF Grant - CAF Loan | 126029.2976 | 31858.1892 | 2
24 | Asistente 2 | GCF Loan, GCF Grant - CAF Loan | 156810.0276 | 31858.1892 | 2
25 | Alianza -Coordinador componente experto - Gestión de conocimiento, M&E | GCF Loan, GCF Grant - CAF Loan | 148756.0501 | 30221.909 | 2
26 | Técnico invernadero 4 | GCF Loan, GCF Grant - CAF Loan | 146185.7202 | 29699.7099 | 2
27 | Técnico invernadero 5 | GCF Loan, GCF Grant - CAF Loan | 146185.7202 | 29699.7099 | 2
28 | Técnico laboratorio | GCF Loan, GCF Grant - CAF Loan | 146185.7202 | 29699.7099 | 2
29 | Técnico laboratorio 4 | GCF Loan, GCF Grant - CAF Loan | 146185.7202 | 29699.7099 | 2
30 | ALIANZA - Científico fisiologo | GCF Loan, GCF Grant - CAF Loan | 143891.7272 | 29233.6526 | 2
31 | Personal científico de la Alianza | GCF Loan, GCF Grant - CAF Loan | 143443.334 | 29142.5551 | 2
32 | ALIANZA - Soil emission specialist | GCF Loan, GCF Grant - CAF Loan | 86677.9195 | 29102.4031 | 2
33 | ALIANZA - Hydrology specialist | GCF Loan, GCF Grant - CAF Loan | 67675.0443 | 27883.5967 | 2
34 | ALIANZA - Profesional con experiencia en modelación | GCF Loan, GCF Grant - CAF Loan | 137114.5726 | 27856.7772 | 2
35 | ALIANZA - Científico líder de lever de la alianza | GCF Loan, GCF Grant - CAF Loan | 135040.7422 | 27435.449 | 2
36 | Científico líder de lever de la alianza | GCF Loan, GCF Grant - CAF Loan | 132817.9018 | 26983.8473 | 2
37 | ALIANZA - Soporte Logistico y Administrativo | GCF Loan, GCF Grant - CAF Loan | 132817.9018 | 26983.8473 | 2
38 | Investigador Visitante | GCF Loan, GCF Grant - CAF Loan | 127505.1858 | 25904.4934 | 2
39 | Alianza Investigador Visitante | GCF Loan, GCF Grant - CAF Loan | 127505.1858 | 25904.4934 | 2
40 | Alianza Profesional 2 de apoyo en evaluación de impacto | GCF Loan, GCF Grant - CAF Loan | 127231.0496 | 25848.7988 | 2
41 | ALIANZA - Estadístico con experiencia en modelación climática | GCF Loan, GCF Grant - CAF Loan | 126101.7048 | 25619.3563 | 2
42 | MIN- Profesional en adaptación | GCF Loan, GCF Grant - CAF Loan | 123963.375 | 25184.9242 | 2
43 | MIN - Profesional en mitigación | GCF Loan, GCF Grant - CAF Loan | 123963.375 | 25184.9242 | 2
44 | MIN - Especialista Financiero | GCF Loan, GCF Grant - CAF Loan | 123963.375 | 25184.9242 | 2
45 | MIN - Especialista en Adquisiciones | GCF Loan, GCF Grant - CAF Loan | 123963.375 | 25184.9242 | 2
46 | Desarrollador | GCF Loan, GCF Grant - CAF Loan | 119076.6028 | 25070.6853 | 2
Total For Contracts for a amount up to USD 50,000 |  |  | 7322132.2394
Contracts for a amount up to USD 25,000
1 | 2 | 3 | 4 | 4 | 5 | 6 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  | Source of Funds |  |  |  |  | Issuance of Expression of Interest | Finalize shortlist and issue RFP |  |  | Complete Financial Evaluation | Negotiate and Award | Comment
Ref. No. | Description of Assignment |  | Estimated | Estimated | Selection | Review |  |  | Proposals Submission | Complete Technical Evaluation
|  |  | Cost ( 5 years) | Cost ( 1 years - 2023) | Method | by AE/Fund |  |  | Date
(Prior / Post)
1 | ALIANZA - Coordinador con experiencia en manejo de riesgo agroclimático | GCF Loan, GCF Grant - CAF Loan | 116434.9305 | 23655.4135 | 1
2 | Data mining expert statistician | GCF Loan, GCF Grant - CAF Loan | 114234.4856 | 23208.3618 | 1
3 | Profesional con experiencia en modelación | GCF Loan, GCF Grant - CAF Loan | 114205.2048 | 23202.413 | 1
4 | Científico experto en finanzas climáticas | GCF Loan, GCF Grant - CAF Loan | 112561.9082 | 22868.5539 | 1
5 | CIAT-Especialista en forrajes y tecnologías de mitigación | GCF Loan, GCF Grant - CAF Loan | 109010.1336 | 22146.9603 | 1
6 | Científico experto en impactos climáticos | GCF Loan, GCF Grant - CAF Loan | 108646.8394 | 22073.1519 | 1
7 | Director de Crops for Nutrition and Health | GCF Loan, GCF Grant - CAF Loan | 106254.3215 | 21587.0779 | 1
8 | Científico experto en impactos climáticos | GCF Loan, GCF Grant - CAF Loan | 105250.7069 | 21383.1793 | 1
9 | Alianza Profesional de apoyo en evaluación de impacto | GCF Loan, GCF Grant - CAF Loan | 103464.2742 | 21020.24 | 1
10 | ALIANZA - Logistic support and operation coordination | GCF Loan, GCF Grant - CAF Loan | 83305.5815 | 20167.2957 | 1
11 | Experto en Evaluación de impacto y seguimiento | GCF Loan, GCF Grant - CAF Loan | 98597.5543 | 20031.4966 | 1
12 | Profesional agronomo | GCF Loan, GCF Grant - CAF Loan | 95055.116 | 19311.7998 | 1
13 | ALIANZA - Asistente de invstigación 1 | GCF Loan, GCF Grant - CAF Loan | 93206.2908 | 18936.1847 | 1
14 | Systems Engineer, with development experience | GCF Loan, GCF Grant - CAF Loan | 92198.6301 | 18731.4641 | 1
15 | Científico experto en modelación de agrícola y de ambiente | GCF Loan, GCF Grant - CAF Loan | 92085.1696 | 18708.413 | 1
16 | Economist | GCF Loan, GCF Grant - CAF Loan | 91383.8196 | 18311.765 | 1
17 | Experta en Evaluación de Impacto | GCF Loan, GCF Grant - CAF Loan | 86678.666 | 17610.0048 | 1
18 | Professional Agrarian Sciences support sensors | GCF Loan, GCF Grant - CAF Loan | 86491.5102 | 17571.9814 | 1
19 | CIAT GALLEGO SANCHEZ, GERARDO JOSE | GCF Loan, GCF Grant - CAF Loan | 86146.8696 | 17501.9628 | 1
20 | ALIANZA - Técnico de laboratorio 1 | GCF Loan, GCF Grant - CAF Loan | 83834.6596 | 17032.2044 | 1
21 | Mathematician with a background in data science | GCF Loan, GCF Grant - CAF Loan | 83313.3146 | 16926.2858 | 1
22 | Data Scientist | GCF Loan, GCF Grant - CAF Loan | 83033.2266 | 16869.3819 | 1
23 | Systems engineer, information systems expert | GCF Loan, GCF Grant - CAF Loan | 73664.5252 | 16820.2022 | 1
24 | ALIANZA - Coordinador con experiencia en manejo de riesgo agroclimático | GCF Loan, GCF Grant - CAF Loan | 79202.3325 | 16091.0812 | 1
25 | Científico experto en finanzas climáticas | GCF Loan, GCF Grant - CAF Loan | 79012.3793 | 16052.4895 | 1
26 | Alianza - Profesional en ciencias Agrarias; sociales; comunicación social | GCF Loan, GCF Grant - CAF Loan | 78298.4472 | 15907.4441 | 1
27 | Alianza Coordinador componente experto - Gestión de conocimiento, M&E | GCF Loan, GCF Grant - CAF Loan | 74378.025 | 15110.9545 | 1
28 | ALIANZA - Estadístico con experiencia en modelación agroclimática | GCF Loan, GCF Grant - CAF Loan | 73855.1475 | 15004.7245 | 1
29 | Trabajador (G1) | GCF Loan, GCF Grant - CAF Loan | 59347.7405 | 15002.1589 | 1
30 | trabajador 1 | GCF Loan, GCF Grant - CAF Loan | 73842.5192 | 15002.1589 | 1
31 | trabajador2 | GCF Loan, GCF Grant - CAF Loan | 73842.5192 | 15002.1589 | 1
32 | Desarrollador | GCF Loan, GCF Grant - CAF Loan | 76849.2981 | 14734.4508 | 1
33 | ALIANZA - Water and soil emission specialist - Landscape | GCF Loan, GCF Grant - CAF Loan | 72250.8135 | 14678.7812 | 1
34 | Estadístico con experiencia en modelación climática | GCF Loan, GCF Grant - CAF Loan | 73820.8189 | 14487.4333 | 1
35 | CIAT-Especialista en nutrición y ganadería sostenible | GCF Loan, GCF Grant - CAF Loan | 71282.1519 | 14481.9838 | 1
36 | TEMP - Profesional Temporal Sanidad Vegetal | GCF Loan, GCF Grant - CAF Loan | 70807.8621 | 14385.6251 | 1
37 | TEMP - Profesional Temporal Sistema de informacion de variedades | GCF Loan, GCF Grant - CAF Loan | 70807.8621 | 14385.6251 | 1
38 | Coordinador con experiencia en el tema agroclimático | GCF Loan, GCF Grant - CAF Loan | 68546.7879 | 13926.2557 | 1
39 | Personal científico de la Alianza | GCF Loan, GCF Grant - CAF Loan | 66940.2225 | 13599.859 | 1
40 | Alianza - Asesores científicos de Gestion del Conocimiento | GCF Loan, GCF Grant - CAF Loan | 65168.963 | 13240.0025 | 1
41 | Alianza Profesional en ciencias sociales, Ciencias Agrarias; Comunicación Social | GCF Loan, GCF Grant - CAF Loan | 63731.2942 | 12947.9196 | 1
42 | Professional with MsC in Sig with experience in Remote Sensing | GCF Loan, GCF Grant - CAF Loan | 61271.3682 | 12943.8355 | 1
43 | CIAT- comunicaciones y generación de capacidades | GCF Loan, GCF Grant - CAF Loan | 61594.4082 | 12513.7808 | 1
44 | ALIANZA - Data Scientist | GCF Loan, GCF Grant - CAF Loan | 64182.9837 | 12370.8801 | 1
45 | Alianza Profesional 3de apoyo en evaluación de impacto | GCF Loan, GCF Grant - CAF Loan | 59122.7521 | 12011.6287 | 1
46 | ALIANZA - Científico expero en modelación de agrícola y de ambiente | GCF Loan, GCF Grant - CAF Loan | 58990.0893 | 11984.6763 | 1
47 | Ing. de datos | GCF Loan, GCF Grant - CAF Loan | 55914.4151 | 11838.0979 | 1
48 | Lever Director for Climate Action | GCF Loan, GCF Grant - CAF Loan | 57874.6038 | 11758.0496 | 1
49 | ALIANZA - Profesional con experiencia en modelación | GCF Loan, GCF Grant - CAF Loan | 55846.7401 | 11346.0602 | 1
50 | Alianza -Coordinador componente experto - Gestión de conocimiento | GCF Loan, GCF Grant - CAF Loan | 55783.5188 | 11333.2159 | 1
51 | ALIANZA - Desarrollador | GCF Loan, GCF Grant - CAF Loan | 54801.357 | 11133.6757 | 1
52 | Data Engineer | GCF Loan, GCF Grant - CAF Loan | 61863.7129 | 11098.2168 | 1
53 | Profesional 2 de apoyo en evaluación de impacto | GCF Loan, GCF Grant - CAF Loan | 54527.5927 | 11078.0566 | 1
54 | Economista | GCF Loan, GCF Grant - CAF Loan | 53579.9316 | 10885.5258 | 1
55 | Agrosavia personal de apoyo | GCF Loan, GCF Grant - CAF Loan | 53127.1607 | 10793.5389 | 1
56 | ALIANZA - Carbon and water footprint specialist | GCF Loan, GCF Grant - CAF Loan | 28453.6623 | 10736.1173 | 1
57 | ALIANZA - Data Scientist | GCF Loan, GCF Grant - CAF Loan | 94987.6757 | 10603.6115 | 1
58 | Expert professional in remote sensing and analytics | GCF Loan, GCF Grant - CAF Loan | 45583.1972 | 10489.0025 | 1
59 | Alianza - Coordinadores; Expertos | GCF Loan, GCF Grant - CAF Loan | 52808.6408 | 10446.9681 | 1
60 | Alianza Profesional en ciencias sociales ; Comunicador Social | GCF Loan, GCF Grant - CAF Loan | 50985.0354 | 10358.3357 | 1
61 | Alianza - Comunicador social con experiencia en gestión de medios sociales | GCF Loan, GCF Grant - CAF Loan | 50985.0354 | 10358.3357 | 1
62 | Alianza -Profesional en ciencias sociales con experiencia en facilitación y documentación de eventos participativos | GCF Loan, GCF Grant - CAF Loan | 50985.0354 | 10358.3357 | 1
63 | Profesional Data análisis | GCF Loan, GCF Grant - CAF Loan | 50985.0354 | 10358.3357 | 1
64 | ALIANZA -Profesional de apoyo en cadenas de valor 2 | GCF Loan, GCF Grant - CAF Loan | 137345.8886 | 9984.3833 | 1
65 | ALIANZA - Asistente de investigación | GCF Loan, GCF Grant - CAF Loan | 47814.4447 | 9714.185 | 1
66 | Alianza Asesor científico | GCF Loan, GCF Grant - CAF Loan | 47814.4447 | 9714.185 | 1
67 | CIAT-Experto en ganadería | GCF Loan, GCF Grant - CAF Loan | 47712.3933 | 9693.4518 | 1
68 | ALIANZA - Asistente de invstigación | GCF Loan, GCF Grant - CAF Loan | 46603.1454 | 9468.0923 | 1
69 | Ing. Mecatrónico Desarrollador-Electrónico- Sensores no remotos | GCF Loan, GCF Grant - CAF Loan | 53825.1873 | 9248.514 | 1
70 | Alianza - Profesional en ciencias Agrarias o sociales con afinidad o experiencia en Gestión de Conocimiento | GCF Loan, GCF Grant - CAF Loan | 45522.353 | 9248.514 | 1
71 | ALIANZA - Científico experto en finanzas climáticas | GCF Loan, GCF Grant - CAF Loan | 44445.0643 | 9029.6475 | 1
72 | Profesional de apoyo en evaluación de impacto | GCF Loan, GCF Grant - CAF Loan | 44342.0641 | 9008.7215 | 1
73 | Alianza Profesional de 3 apoyo en evaluación de impacto | GCF Loan, GCF Grant - CAF Loan | 44342.0641 | 9008.7215 | 1
74 | CIAT ESCOBAR PEREZ, ROOSEVELT HUMBERTO | GCF Loan, GCF Grant - CAF Loan | 44188.6183 | 8977.5468 | 1
75 | Alianza Experto en Evaluación de Impacto | GCF Loan, GCF Grant - CAF Loan | 43339.2517 | 8804.9859 | 1
76 | ALIANZA -Profesional de apoyo en cadenas de valor 1 | GCF Loan, GCF Grant - CAF Loan | 120235.4594 | 8740.5377 | 1
77 | ALIANZA - Científico experto en impactos climáticos | GCF Loan, GCF Grant - CAF Loan | 42991.1147 | 8734.2569 | 1
78 | ALIANZA - Principal Scientist - Land Restoration | GCF Loan, GCF Grant - CAF Loan | 34538.2665 | 8730.7209 | 1
79 | ALIANZA - Profesional en manejo de riesgo agroclimático (e.g. transferencias de estrategias de comunicación) | GCF Loan, GCF Grant - CAF Loan | 42172.3402 | 8567.9112 | 1
80 | ALIANZA - Profesional Data análisis | GCF Loan, GCF Grant - CAF Loan | 42062.6542 | 8545.6269 | 1
81 | Gloria Mosquera | GCF Loan, GCF Grant - CAF Loan | 40417.3069 | 8211.3512 | 1
82 | Científico expero en modelación de agrícola y de ambiente | GCF Loan, GCF Grant - CAF Loan | 39700.0146 | 8065.6231 | 1
83 | Alianza - Experto en comunicaciones institucionales y comunidades de práctica | GCF Loan, GCF Grant - CAF Loan | 38843.0682 | 7891.5222 | 1
84 | ALIANZA - Ing. de datos | GCF Loan, GCF Grant - CAF Loan | 20613.4058 | 7768.7517 | 1
85 | ALIANZA - Estadístico con experiencia en modelación agroclimática | GCF Loan, GCF Grant - CAF Loan | 38046.5911 | 7729.7066 | 1
86 | Profesional con experiencia en modelación de cultivo de arroz | GCF Loan, GCF Grant - CAF Loan | 38025.6165 | 7725.4453 | 1
87 | Alianza - Ciencias sociales; Comunicaciones | GCF Loan, GCF Grant - CAF Loan | 36417.8824 | 7398.8112 | 1
88 | Operario, técnico casa de malla (contratación) | GCF Loan, GCF Grant - CAF Loan | 29205.8865 | 7382.7806 | 1
89 | Alianza - Prof. coordinación capacitacion | GCF Loan, GCF Grant - CAF Loan | 57152.4558 | 7285.6388 | 1
90 | Student 1 | GCF Loan, GCF Grant - CAF Loan | 33133.9176 | 7205.4967 | 1
91 | Maria Fernanda Alvarez | GCF Loan, GCF Grant - CAF Loan | 34919.6415 | 7094.4222 | 1
92 | CIAT-experto en fisiología de cultivos | GCF Loan, GCF Grant - CAF Loan | 34602.7381 | 7030.0388 | 1
93 | ALIANZA - Professional Agrarian Sciences support sensors | GCF Loan, GCF Grant - CAF Loan | 34414.8989 | 6991.8766 | 1
94 | ALIANZA - Expert professional in remote sensing and analytics | GCF Loan, GCF Grant - CAF Loan | 34814.4584 | 6968.1327 | 1
95 | CIAT-Especialista en selección de germoplasma forrajero | GCF Loan, GCF Grant - CAF Loan | 34127.0463 | 6933.3952 | 1
96 | ALIANZA - Ing. Mecatrónico Desarrollador-Electrónico- Sensores no remotos | GCF Loan, GCF Grant - CAF Loan | 30748.8192 | 6862.3974 | 1
97 | ALIANZA - Desarrollador | GCF Loan, GCF Grant - CAF Loan | 32619.4424 | 6627.104 | 1
98 | ALIANZA - Professional with MsC in Sig with experience in Remote Sensing | GCF Loan, GCF Grant - CAF Loan | 32695.138 | 6568.4288 | 1
99 | Profesional en ciencias sociales con experiencia en GC - sistematización | GCF Loan, GCF Grant - CAF Loan | 51004.3332 | 6501.8929 | 1
100 | ALIANZA - Científico expero en modelación de agrícola y de ambiente | GCF Loan, GCF Grant - CAF Loan | 31886.5287 | 6478.2022 | 1
101 | ALIANZA - Ing. de datos | GCF Loan, GCF Grant - CAF Loan | 29988.0223 | 6473.9598 | 1
102 | ALIANZA -Profesional de apoyo en cadenas de valor 3 | GCF Loan, GCF Grant - CAF Loan | 87366.1597 | 6351.0982 | 1
103 | ALIANZA -Experto en cadenas de valor y sistemas alimentarios | GCF Loan, GCF Grant - CAF Loan | 87359.4535 | 6350.6107 | 1
104 | Alianza -Experta en Gestión de conocimiento, redes y fortalecimiento institucional | GCF Loan, GCF Grant - CAF Loan | 48362.8965 | 6161.4442 | 1
105 | Systems Engineer, with development experience | GCF Loan, GCF Grant - CAF Loan | 30252.6629 | 6146.2591 | 1
106 | ALIANZA - Ing. Mecatrónico Desarrollador-Electrónico- Sensores no remotos | GCF Loan, GCF Grant - CAF Loan | 12160.7203 | 6085.5222 | 1
107 | ALIANZA - Systems engineer, information systems expert | GCF Loan, GCF Grant - CAF Loan | 44409.7202 | 6079.0699 | 1
108 | ALIANZA - Estadístico con experiencia en modelación climática | GCF Loan, GCF Grant - CAF Loan | 29737.0782 | 6041.5107 | 1
109 | ALIANZA - Systems engineer, information systems expert | GCF Loan, GCF Grant - CAF Loan | 30246.9707 | 5936.2874 | 1
110 | Profesional Data análisis | GCF Loan, GCF Grant - CAF Loan | 29134.3229 | 5919.0524 | 1
111 | Coordinador con experiencia en manejo de riesgo agroclimático | GCF Loan, GCF Grant - CAF Loan | 28435.314 | 5777.0388 | 1
112 | ALIANZA - Data mining expert statistician | GCF Loan, GCF Grant - CAF Loan | 28381.1384 | 5766.0323 | 1
113 | Alianza Profesional en ciencias Agrarias o sociales con afinidad o experiencia en Gestión de Conocimiento | GCF Loan, GCF Grant - CAF Loan | 27313.4118 | 5549.1084 | 1
114 | Soporte Logistico y Administrativo | GCF Loan, GCF Grant - CAF Loan | 26563.5804 | 5396.7695 | 1
115 | ALIANZA - Científico experto en finanzas climáticas | GCF Loan, GCF Grant - CAF Loan | 26337.8159 | 5350.9022 | 1
116 | Profesional con experiencia en modelación | GCF Loan, GCF Grant - CAF Loan | 26141.9632 | 5311.1119 | 1
117 | ALIANZA - Profesional en economía para el trabajo de transferencia (e.g. estrategias de comunicación) | GCF Loan, GCF Grant - CAF Loan | 25671.5753 | 5215.5459 | 1
118 | CIAT-Experto en economía y género | GCF Loan, GCF Grant - CAF Loan | 25293.7576 | 5138.7869 | 1
119 | ALIANZA - Ing. de datos 1 | GCF Loan, GCF Grant - CAF Loan | 20414.218 | 4932.5408 | 1
120 | ALIANZA - Senior Soil Scientist | GCF Loan, GCF Grant - CAF Loan | 22638.5457 | 4599.3428 | 1
121 | Data Scientist | GCF Loan, GCF Grant - CAF Loan | 32018.0465 | 4498.5018 | 1
122 | Ing. de datos | GCF Loan, GCF Grant - CAF Loan | 27640.2659 | 4439.2867 | 1
123 | Expert professional in remote sensing and analytics | GCF Loan, GCF Grant - CAF Loan | 18879.5419 | 4416.4221 | 1
124 | ALIANZA - Economist | GCF Loan, GCF Grant - CAF Loan | 21668.64 | 4402.2927 | 1
125 | ALIANZA - Economist | GCF Loan, GCF Grant - CAF Loan | 21425.8541 | 4352.9673 | 1
126 | ALIANZA - Experto en cadenas de valor y sistemas alimentarios | GCF Loan, GCF Grant - CAF Loan | 58239.6357 | 4233.7405 | 1
127 | ALIANZA - Científico experto en impactos climáticos | GCF Loan, GCF Grant - CAF Loan | 20699.4256 | 4205.383 | 1
128 | ALIANZA - Mathematician with a background in data science | GCF Loan, GCF Grant - CAF Loan | 20383.4517 | 4141.1884 | 1
129 | ALIANZA - Data mining expert statistician | GCF Loan, GCF Grant - CAF Loan | 20329.8661 | 4130.3017 | 1
130 | Professional with MsC in Sig with experience in Remote Sensing | GCF Loan, GCF Grant - CAF Loan | 17473.5646 | 4087.527 | 1
131 | Expert professional in remote sensing and analytics | GCF Loan, GCF Grant - CAF Loan | 25113.469 | 4048.3869 | 1
132 | Alianza Coordinadora de capacitaciones y seguimiento | GCF Loan, GCF Grant - CAF Loan | 31751.3643 | 4047.5771 | 1
133 | ALIANZA - Mathematician with a background in data science | GCF Loan, GCF Grant - CAF Loan | 19251.0377 | 3911.1223 | 1
134 | Profesional con experiencia en asesoría organizaciona y financiera (Contratar o buscar en la alianza) | GCF Loan, GCF Grant - CAF Loan | 21071.0609 | 3807.6367 | 1
135 | Coordinador componente experto - Gestión de conocimiento, M&E | GCF Loan, GCF Grant - CAF Loan | 18594.5063 | 3777.7386 | 1
136 | Comunicador social con experiencia en gestión de medios sociales | GCF Loan, GCF Grant - CAF Loan | 18208.9412 | 3699.4056 | 1
137 | Profesional en ciencias Agrarias o sociales con afinidad o experiencia en Gestión de Conocimiento | GCF Loan, GCF Grant - CAF Loan | 18208.9412 | 3699.4056 | 1
138 | Profesional en ciencias sociales con experiencia en facilitación y documentación de eventos participativos | GCF Loan, GCF Grant - CAF Loan | 18208.9412 | 3699.4056 | 1
139 | ALIANZA - Electronic Developer Systems Engineer- Non-remote sensors | GCF Loan, GCF Grant - CAF Loan | 29020.1204 | 3699.4056 | 1
140 | CIAT-coordinador administrativo y financiero | GCF Loan, GCF Grant - CAF Loan | 18106.976 | 3678.6899 | 1
141 | ALIANZA - GEI emisions specialist | GCF Loan, GCF Grant - CAF Loan | 17614.8414 | 3578.7058 | 1
142 | Alianza Experto en comunicaciones institucionales y comunidades de práctica | GCF Loan, GCF Grant - CAF Loan | 17263.5859 | 3507.3432 | 1
143 | Alianza Programación | GCF Loan, GCF Grant - CAF Loan | 10227.6211 | 3453.9325 | 1
144 | Alianza Experta en Gestión de conocimiento, redes y fortalecimiento institucional | GCF Loan, GCF Grant - CAF Loan | 26041.5597 | 3317.7007 | 1
145 | ALIANZA - Científico experto en modelación de agrícola y de ambiente | GCF Loan, GCF Grant - CAF Loan | 15943.3759 | 3239.1238 | 1
146 | ALIANZA - Científico experto en modelación de agrícola y de ambiente | GCF Loan, GCF Grant - CAF Loan | 15943.2272 | 3239.0935 | 1
147 | Científico experto en modelación de agrícola y de ambiente | GCF Loan, GCF Grant - CAF Loan | 15943.2272 | 3239.0935 | 1
148 | ALIANZA -Profesional en sistematización de experiencias | GCF Loan, GCF Grant - CAF Loan | 41307.7003 | 3002.8705 | 1
149 | Profesional Agrónomo de apoyo en Análisis | GCF Loan, GCF Grant - CAF Loan | 14567.153 | 2959.5245 | 1
150 | Ing. Mecatrónico Desarrollador-Electrónico- Sensores no remotos | GCF Loan, GCF Grant - CAF Loan | 14553.1151 | 2959.5245 | 1
151 | Profesional Agrónomo de apoyo en Análisis | GCF Loan, GCF Grant - CAF Loan | 14567.153 | 2959.5245 | 1
152 | Professional Agrarian Sciences support sensors | GCF Loan, GCF Grant - CAF Loan | 14566.1924 | 2959.3293 | 1
153 | ALIANZA -Personal cientifico de la Alianza | GCF Loan, GCF Grant - CAF Loan | 39593.7843 | 2878.277 | 1
154 | Economista | GCF Loan, GCF Grant - CAF Loan | 14095.0395 | 2863.6079 | 1
155 | Systems engineer, information systems expert | GCF Loan, GCF Grant - CAF Loan | 12803.1274 | 2812.3811 | 1
156 | Data mining expert statistician | GCF Loan, GCF Grant - CAF Loan | 13553.244 | 2753.5344 | 1
157 | Alianza Programación | GCF Loan, GCF Grant - CAF Loan | 7670.7158 | 2590.4493 | 1
158 | CIAT-Apoyo técnico en región | GCF Loan, GCF Grant - CAF Loan | 12071.3173 | 2452.4599 | 1
159 | ALIANZA - Student 1 | GCF Loan, GCF Grant - CAF Loan | 9466.8896 | 2401.8322 | 1
160 | ALIANZA - Economista | GCF Loan, GCF Grant - CAF Loan | 11760.9508 | 2389.4046 | 1
161 | CIAT- experto en calidad forrajera | GCF Loan, GCF Grant - CAF Loan | 11662.1201 | 2369.3257 | 1
162 | ALIANZA - Ings. Datos | GCF Loan, GCF Grant - CAF Loan | 11062.0913 | 2367.6196 | 1
163 | ALIANZA - Expert professional in remote sensing and analytics | GCF Loan, GCF Grant - CAF Loan | 13144.9253 | 2189.8093 | 1
164 | CIAT-Economista | GCF Loan, GCF Grant - CAF Loan | 10082.619 | 2048.4276 | 1
165 | ALIANZA - Professional with MsC in Sig with experience in Remote Sensing | GCF Loan, GCF Grant - CAF Loan | 12166.0104 | 2026.7321 | 1
166 | ALIANZA -Profesional en sistematización de experiencias | GCF Loan, GCF Grant - CAF Loan | 27538.4668 | 2001.9136 | 1
167 | Profesional con experiencia en modelación de cultivo de arroz | GCF Loan, GCF Grant - CAF Loan | 9625.1115 | 1955.4784 | 1
168 | CIAT- colaborador en campo | GCF Loan, GCF Grant - CAF Loan | 9616.1342 | 1953.6545 | 1
169 | Ing. Datos | GCF Loan, GCF Grant - CAF Loan | 15235.5851 | 1942.1879 | 1
170 | ALIANZA - Profesional Data análisis | GCF Loan, GCF Grant - CAF Loan | 8922.3812 | 1812.7087 | 1
171 | ALIANZA - Professional Agrarian Sciences support sensors | GCF Loan, GCF Grant - CAF Loan | 8679.5953 | 1763.3833 | 1
172 | ALIANZA - Economista | GCF Loan, GCF Grant - CAF Loan | 7840.6339 | 1592.9364 | 1
173 | Ing. Sistemas Desarrollador | GCF Loan, GCF Grant - CAF Loan | 2944.8727 | 1479.6647 | 1
174 | Estudiante | GCF Loan, GCF Grant - CAF Loan | 8478.5262 | 1441.0993 | 1
175 | ALIANZA -Personal científico de la Alianza | GCF Loan, GCF Grant - CAF Loan | 19796.8922 | 1439.1385 | 1
176 | ALIANZA -Asesores cientificos | GCF Loan, GCF Grant - CAF Loan | 19796.8922 | 1439.1385 | 1
177 | ALIANZA -asesores cientificos | GCF Loan, GCF Grant - CAF Loan | 19796.8922 | 1439.1385 | 1
178 | ALIANZA - Profesional Agrónomo de apoyo en Análisis | GCF Loan, GCF Grant - CAF Loan | 6373.1294 | 1294.792 | 1
179 | ALIANZA - Estudiante 2 | GCF Loan, GCF Grant - CAF Loan | 5024.7469 | 1280.9772 | 1
180 | Estudiante | GCF Loan, GCF Grant - CAF Loan | 5281.0546 | 960.7329 | 1
181 | ALIANZA - Profesionales | GCF Loan, GCF Grant - CAF Loan | 5227.9755 | 887.8573 | 1
182 | Experto en comunicaciones institucionales y comunidades de práctica | GCF Loan, GCF Grant - CAF Loan | 4315.8965 | 876.8358 | 1
183 | Alianza Programación plataforma | GCF Loan, GCF Grant - CAF Loan | 2556.9053 | 863.4831 | 1
184 | Coordinadora de capacitaciones y seguimiento | GCF Loan, GCF Grant - CAF Loan | 6350.2729 | 809.5154 | 1
185 | Systems engineer, information systems expert | GCF Loan, GCF Grant - CAF Loan | 4476.5793 | 757.1795 | 1
186 | ALIANZA - Estudiante | GCF Loan, GCF Grant - CAF Loan | 2670.1223 | 672.513 | 1
187 | ALIANZA - Estudiantes | GCF Loan, GCF Grant - CAF Loan | 3623.5694 | 614.8691 | 1
188 | ALIANZA - IDEAM | GCF Loan, GCF Grant - CAF Loan | 1076.641 | 539.6769 | 1
189 | Experta en Gestión de conocimiento, redes y fortalecimiento institucional | GCF Loan, GCF Grant - CAF Loan | 3720.2228 | 473.9572 | 1
190 | ALIANZA - Profesional en medios, contenidos y difusión | GCF Loan, GCF Grant - CAF Loan | 663.9682 | 161.9031 | 1
191 | ALIANZA - Student 1 | GCF Loan, GCF Grant - CAF Loan | 2524.3561 | 504.8712 | 1
192 | Estudiante 2 | GCF Loan, GCF Grant - CAF Loan | 9374.37 | 1874.874 | 1
193 | Ing. Sistemas Desarrollador | GCF Loan, GCF Grant - CAF Loan | 15160.2172 | 3032.0434 | 1
194 | ALIANZA - Ing. Sistemas Desarrollador | GCF Loan, GCF Grant - CAF Loan | 7580.1086 | 1516.0217 | 1
195 | Constanza Quintero | GCF Loan, GCF Grant - CAF Loan | 17444.9289 | 3488.9858 | 1
196 | Tecnico cruzamientos (Martin Delgado) | GCF Loan, GCF Grant - CAF Loan | 29545.0112 | 5909.0022 | 1
197 | Tecnico lab- molecular | GCF Loan, GCF Grant - CAF Loan | 38784.5943 | 7756.9189 | 1
198 | ALIANZA - Carbon and water footprint specialist (G4) | GCF Loan, GCF Grant - CAF Loan | 69347.051 | 13869.4102 | 1
199 | MVR | GCF Loan, GCF Grant - CAF Loan | 71087.2673 | 14217.4535 | 1
Total For Contracts for a amount up to USD 25,000 |  |  | 8428636.3564
| Check | 3.5507e-09