## Extended timetable
Project extended timetable
| Duration (years) | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26 | Year 27 | Year 28 | Year 29 | Year 30 | Year 31 | Year 32 | Year 33 | Year 34 | Year 50
Project Facility | 14
Policy facility | 5 | Year 15: ß; Year 16: PEEB Cool
Project management unit | 14
Maximum construction period | 6
Loan repayment | 33
Expected minimum lifetime of investments | 50

## Timetable
Annex 5 Implementation Timetable
Project/Programme Title: PEEB Cool
COMPONENTS/OUTPUTS | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Project Appraisal | bar: 2022 Q1 to 2022 Q4
Contractualisation Phase | bar: 2022 Q4 to 2023 Q1
Component 1 Project Facility
Ouput 1.1: Project sponsors are supported in the various phases of their investment
Activity 1.1.1: Technical assistance support at identification and appraisal phases | bar: 2023 Q3 to 2028 Q2
Activity 1.1.2: Technical assistance at operation phase | bar: 2023 Q3 to 2033 Q1
Activity 1.1.3: Capacity reinforcement to project stakeholders | bar: 2023 Q3 to 2033 Q1
Ouput 1.2: Financing agreements are signed
Activity 1.2.1: Investment funding | bar: 2023 Q3 to 2028 Q2
Component 2: Investment and Policy Framework Facility
Ouput 2.1.Sectoral frameworks or initiatives demonstrate the potential for green recovery
Activity 2.1.1. Development of sectoral frameworks or initiatives | bar: 2023 Q3 to 2028 Q2
Output 2.2. Public policies prepare the ground for buildings sector transformation
Activity 2.2.1. Support for development of policies | bar: 2023 Q3 to 2028 Q2
Output 2.3. Private and public sector actors are enabled to work towards buildings sector transformation
Activity 2.3.1. Development of training modules | bar: 2023 Q3 to 2025 Q2
Activity 2.3.2.. Implementation of training measures | bar: 2024 Q1 to 2028 Q2
Output 2.4. Program experiences/knowledge support the global buildings sector transformation
Activity 2.4.1. Development of knowledge products | bar: 2023 Q3 to 2028 Q2
Activity 2.4.2. Dissemination of experiences | bar: 2024 Q3 to 2028 Q2
Programme Management Component | bar: 2023 Q3
Programme monitoring | 2024 Q1: APR; 2024 Q2: IR; 2025 Q1: APR; 2026 Q1: APR; 2027 Q1: APR; 2028 Q1: APR; 2028 Q3: PCD; 2028 Q4: IE; 2029 Q1: APR; 2030 Q1: APR; 2031 Q1: APR; 2032 Q1: APR; 2033 Q1: APR; 2033 Q3: CD; 2034 Q1: CR; 2034 Q2: FE
ED = Effective Date
IR = Inception Report
APR = Annual Performance Report
IE= Interim evaluation
PCD = Programme Commitment Date
CD = Completion Date
CR= Completion report
FE= Final evaluation
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.
Significant deliverables (investment and policy framework facility)
2 | 2022 Q1: Sectoral development support ongoing in at least 1/3 of countries
3 | 2022 Q1: Public policy development support ongoing for at least 50% of countries
4 | 2022 Q1: Training and awareness raising modules fully developed
5 | 2022 Q1: At least 50% of training events implemented
6 | 2022 Q1: PEEB Cool “catalogue” of planned knowledge products
7 | 2022 Q1: PEEB Cool experience disseminated in at least 10 events
8 | 2022 Q1: At least 50% of PEEB Cool countries have received TA support
9 | 2022 Q1: Financing agreements signed in at least 35% of PEEB Cool countries
3
2
4
5
6
7
8
9