## Instructions
The following considerations are important when populating the budget:
Title Lists
Before filling out the “Detailed Budget Plan” Sheet, please populate the title data in the “Title List” Sheet.
Fill out the actual names of the Components; Outputs; and List of Funding Sources. An indicative list of Budget Categories has already been provided.
Please use this list as much as possible, however if list does not adequately address, kindly add onto the list where appropriate.
The information captured in the “Title List” will feed into the drop down lists in the “Detailed Budget Plan” Sheet.
Detailed Budget Plan
The detailed breakdown of the project budget is populated in this sheet.
The Component; Output; Funding Source; and Budget Categories fields are to be populated from drop-down lists.
The data for the drop-down lists is based on the data entered in the “Title List” Sheet.
Please insert/delete rows/columns under the Component; Output; Activity; Funding Source and Budget Categories as appropriate.
Please provide the assumptions and basis of how unit cost and quantities are arrived under the Budget Notes field.
If the space provided is not enough, insert an appropriate reference and enter the detailed comments in the "Detailed budget Notes" Sheet
Detailed Budget Notes
Detailed comments on the assumptions/estimates underlying the Unit Cost/ Quantities and justifications should be provided in this sheet. Please provide as much details as possible.
Project Management Cost
Please include the Project management costs (PMC) under this component and provide details of PMC.
Project management costs (PMC) are the direct administrative costs incurred to execute a project. They should cover only incremental costs incurred due
to the GCF contribution. In most cases, these costs are directly related to the support of a dedicated project management unit (PMU) which manages
the day to day execution related activities of the project.
General Principles for PMC costs:
1. The percentage of PMC financed by GCF should not be more than the percentage share of the overall budget financed by GCF.
2. PMC budget thresholds:
> PMC exceeding 5 per cent (5%) for a funding proposal exceeding USD 3 million will require detailed documentation supporting the entire PMC budget.
> PMC exceeding 7.5 per cent (7.5%) for the proposals up to USD 3 million will require detailed documentation and justification supporting the entire PMC budget.
3. Indicative list of eligible project management costs:
> Project staffing and consultants: Project manager, Project Assistant, Procurement personnel, Finance personnel & Support/admin personnel.
> Other direct costs: Office equipment, Mission related travel cost of the PMU, Project management systems and information technology,
Office supplies, Audit cost, etc.
Please note that the examples provided are simplified for illustrative purposes only.
Thus, please regard the examples as a guidance, not binding examples.
Simplified Approval Process - Budget Preparation Guidelines

## Dashboard (hidden)
Annex 3 - Budget Plan
Brief Project/ Programme Information
Project/ Programme Title: | [7 empty] | Values
Country(ies) | [6 empty] | Component | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total Budget
Accredited Entity | [6 empty] | Component 1 | 70000 | 250000 | 350000 | 100000 | 180000 | 950000
Budget Currency | USD/GBP/JPY/EUR | [5 empty] | Component 2 | 40000 | 30000 | 30000 | 50000 | 50000 | 200000
Date of Submission | [6 empty] | Component 3 | 20000 | 30000 | 40000 | 60000 | 50000 | 200000
[7 empty] | Project Management Cost | 30000 | 40000 | 40000 | 30000 | 10000 | 150000
[7 empty] | (blank) | [5 empty] | 0
[7 empty] | Grand Total | 160000 | 350000 | 460000 | 240000 | 290000 | 1500000
Output | (All) |  |  |  |  | Component | (All)
Sum of Total Cost | Funding Source |  |  |  |  | Sum of Total Cost | Funding Source
Component | GCF | Grand Total |  |  |  | Budget Categories | GCF | Grand Total
Component 1 | 150000 | 150000 |  |  |  | Consultant - Individual - International | 150000 | 150000
Grand Total | 150000 | 150000 |  |  |  | Grand Total | 150000 | 150000
Sum of Total Cost | Column Labels
Row Labels | Co-Financer 1 | Co-Financer 2 | GCF | (blank) | Grand Total
Output 1.1 |  |  | 800000 |  | 800000
Output 1.2 | 200000 |  |  |  | 200000
Output 2.1 |  | 200000 | 150000 |  | 350000
PMC |  |  | 150000 |  | 150000
(blank) |  |  |  | 0 | 0
Grand Total | 200000 | 200000 | 1100000 | 0 | 1500000
This shape represents a slicer. Slicers are supported in Excel 2010 or later.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later.If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Title Lists
Components | Outputs | Budget Categories | List of Funding Source
Component 1: Development of technical and institutional capacity of government and civil society | Output 1.1. Improved local observation and resilient management systems for water, soil and agriculture practices | Consultant - Individual - International | GCF
Component 2: Adaptation of water management towards climate risks in coastal zones | Output 1.2. Strengthened technical capacities of decision-makers, field staff, youth, and communities for addressing water and agriculture related climate risks | Consultant - Individual - Local | Executing Entity
Component 3: Building resilience of farming communities towards climate change | Output 1.3 Improved availability and accessibility to knowledge on water and agriculture-related climate risks and adaptation options | Equipment
Project Management Cost | Output 2.1. Community-based water management is improved and adapted towards climate risks, including salt-water intrusion and extreme weather events | Materials & Goods
| Output 2.2. Mangrove ecosystems are better managed, as an ecosystem-based adaptation measure towards salt-water intrusion | Office Costs
| Output 3.1. Increased and diversified livelihoods of smallholder farmers | Professional Services – Companies/Firm | Output 1.2. Strengthened technical capacities of decision-makers and field staff for addressing water and agriculture related climate risks
| Output 3.2 Increased income options in climate-resilient economic activity along agricultural value chains | Travel
Workshop/Training
Professional Services - NGO
Local Staff - Expert
Field staff (Extensionists)
Communication
Other costs (travel expenses, publication of ToRs, translation, communication/internet…)
Grant

## Detailed Budget Plan
Project Name: Adaptation of agricultural production systems in Coastal Areas of Northwest Guinea-Bissau
Component | Output | Activity | Funding Source | Budget Categories | Detailed Budget |  |  |  | Annual Budget | [5 empty] | **Budget Notes
[5 empty] | Unit | # of Unit | Unit Cost | Total Cost | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total Budget
Component 1: Development of technical and institutional capacity of government and civil society | Output 1.1. Improved local observation and resilient management systems for water, soil and agriculture practices | A1.1.1 Conceptualization and operationalization of Observatory Groups (OG) for climate-resilient agriculture (CRA) practices and technologies and water and soil quality monitoring (WSQM) | GCF | Consultant - Individual - International | Man/day | 25 | 600 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | A1.1
|  |  | GCF | Consultant - Individual - Local | Man/day | 20 | 350 | 7000 | 7000 | 0 | 0 | 0 | 0 | 7000 | A1.2
|  |  | GCF | Workshop/Training | Lump sum | 12 | 1833.3333 | 22000 | 13200 | 2200 | 2200 | 2200 | 2200 | 22000 | A2
|  |  | GCF | Office Costs | Lump sum/OG | 2 | 19500 | 39000 | 27300 | 5850 | 1950 | 1950 | 1950 | 39000 | A3
|  |  | GCF | Local Staff - Expert | Staff/OG | 2 | 184500 | 369000 | 73800 | 73800 | 73800 | 73800 | 73800 | 369000 | A4
|  | A1.1.2 Establish Community Climate Centers (CCCs) | GCF | Consultant - Individual - Local | Man/day | 20 | 150 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000 | A5
|  |  | GCF | Materials & Goods | Unit (CCC) | 20 | 37775 | 755500 | 151100 | 302200 | 226650 | 37775 | 37775 | 755500 | A6
|  |  | Executing Entity | Materials & Goods | Unit (CCC) | 20 | 1300 | 26000 | 13000 | 13000 | 0 | 0 | 0 | 26000 | A7
|  |  | GCF | Field staff (Extensionists) | (Extensionists/region)*months | 1836 | 300 | 550800 | 61200 | 122400 | 122400 | 122400 | 122400 | 550800 | A8
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum (Extension team setup) | 1 | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | 3500 | A8
|  |  | GCF | Workshop/Training | Lump sum/meeting | 20 | 450 | 9000 | 5400 | 3600 | 0 | 0 | 0 | 9000 | A9
|  |  | GCF | Consultant - Individual - International | Man/day | 10 | 600 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | A10
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000 | A10
|  |  | GCF | Workshop/Training | Sessions/groups | 16 | 1200 | 19200 | 3840 | 3840 | 3840 | 3840 | 3840 | 19200 | A11
|  | A1.1.3 Equip OGs and CCCs with technologies for WSQM | GCF | Equipment | Lump sum | 1 | 702900 | 702900 | 210870 | 281160 | 70290 | 70290 | 70290 | 702900 | A12
|  | A1.1.4 Training of OG members, including community members and individuals on O&M of observatory equipment | GCF | Consultant - Individual - International | Man/day | 10 | 600 | 6000 | 6000 | 0 | 0 |  | 0 | 6000 | A13
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000 | A13
|  |  | GCF | Workshop/Training | Session | 16 | 1200 | 19200 | 7680 | 7680 | 1920 | 1920 | 0 | 19200 | A14
| Subtotal Output 1.1 | [6 empty] | 2559100 | 613890 | 815730 | 503050 | 314175 | 312255 | 2559100
| Output 1.2. Strengthened technical capacities of decision-makers and field staff for addressing water and agriculture related climate risks | A1.2.1 Development of Training Manuals and Modules for CRA practices and adaptation towards water and soil salinization | GCF | Consultant - Individual - International | Man/day | 35 | 600 | 21000 | 6300 | 14700 | 0 | 0 | 0 | 21000 | A15
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 4000 | 4000 | 1200 | 2800 | 0 | 0 | 0 | 4000 | A15
|  |  | GCF | Consultant - Individual - Local | Man/day | 35 | 300 | 10500 | 3150 | 7350 | 0 | 0 | 0 | 10500 | A16
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 2000 | 2000 | 600 | 1400 | 0 | 0 | 0 | 2000 | A16
|  |  | GCF | Workshop/Training | Meetings | 16 | 2250 | 36000 | 14400 | 14400 | 7200 | 0 | 0 | 36000 | A17
|  | A1.2.2 Capacity building of national-level decision-makers, local government authorities and field staff on WSQM, Adaptation and CRA practices | GCF | Workshop/Training | Training sessions/year | 4 | 21000 | 84000 | 0 | 21000 | 21000 | 21000 | 21000 | 84000 | A18
|  | A1.2.3 Train youth through vocational training courses in CRA practices, including specializations in livestock management and post-harvest practices | GCF | Workshop/Training | Lump sum | 1 | 556665 | 556665 | 0 | 194832.75 | 194832.75 | 166999.5 | 0 | 556665 | A19
|  |  | GCF | Equipment | Lump sum | 1 | 83000 | 83000 | 16600 | 41500 | 24900 | 0 | 0 | 83000 | A20
|  | A1.2.4 Conduct sensitization campaigns and address concrete barriers at community-level for CC literacy, adaptation options, and other resilience-building topics | GCF | Equipment | People | 2720 | 20 | 54400 | 0 | 43520 | 10880 | 0 | 0 | 54400 | A21.1
|  |  | GCF | Workshop/Training | People * days | 816 | 10 | 8160 | 8160 | 0 | 0 | 0 | 0 | 8160
|  |  | GCF | Workshop/Training | Months* persons | 2176 | 25 | 54400 | 0 | 13600 | 13600 | 13600 | 13600 | 54400
|  |  | Executing Entity | Workshop/Training | Months* persons | 1088 | 25 | 27200 | 0 | 6800 | 6800 | 6800 | 6800 | 27200 | A21.2
|  | A1.2.5 Mainstream environmental education in the young adult education system | GCF | Materials & Goods | Persons | 2720 | 10 | 27200 | 0 | 10880 | 16320 | 0 | 0 | 27200 | A22
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Persons | 1000 | 45 | 45000 | 0 | 18000 | 27000 | 0 | 0 | 45000
|  |  | GCF | Workshop/Training | Lump sun | 1 | 37100 | 37100 | 7420 | 7420 | 7420 | 7420 | 7420 | 37100 | A23
| Subtotal Output 1.2 | [6 empty] | 1050625 | 57830 | 398202.75 | 329952.75 | 215819.5 | 48820 | 1050625
| Output 1.3 Improved availability and accessibility to knowledge on water and agriculture-related climate risks and adaptation options | A1.3.1 Conduct Baseline Study and KAP Survey | GCF | Consultant - Individual - International | Man/day | 20 | 600 | 12000 | 12000 |  |  |  |  | 12000 | A24
|  |  | GCF | Consultant - Individual - Local | Man/day | 40 | 300 | 12000 | 9000 | 0 | 0 | 0 | 3000 | 12000
|  |  | GCF | Workshop/Training | Lump sum | 1 | 6000 | 6000 | 4500 | 0 | 0 | 0 | 1500 | 6000
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 5000 | 5000 | 3500 | 0 | 0 | 0 | 1500 | 5000
|  | A1.3.2 Elaborate a knowledge base with a collaborative e-platform for climate resilience and adaptation practices | GCF | Consultant - Individual - Local | Man/day | 30 | 350 | 10500 | 0 | 3150 | 7350 | 0 | 0 | 10500 | A25
|  |  | GCF | Equipment | Year | 4 | 400 | 1600 | 0 | 800 | 800 | 0 | 0 | 1600
|  |  | GCF | Workshop/Training | Units | 3 | 2000 | 6000 | 0 | 0 | 2000 | 2000 | 2000 | 6000
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 3000 | 3000 | 0 | 750 | 750 | 750 | 750 | 3000
|  | A1.3.3 Disseminate knowledge and information in local, national and regional workshops and forums | GCF | Equipment | Lump sum | 1 | 30500 | 30500 | 9150 | 5337.5 | 5337.5 | 5337.5 | 5337.5 | 30500 | A26
|  |  | GCF | Consultant - Individual - International | Man/day | 20 | 600 | 12000 | 12000 | 0 | 0 | 0 | 0 | 12000 | A27
|  |  | GCF | Communication | Month | 60 | 500 | 30000 | 6000 | 6000 | 6000 | 6000 | 6000 | 30000
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 3000 | 3000 | 2100 | 900 | 0 | 0 | 0 | 3000
|  |  | GCF | Workshop/Training | Unit | 9 | 6000 | 54000 | 10800 | 10800 | 10800 | 10800 | 10800 | 54000 | A28
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 5000 | 5000 | 1000 | 1000 | 1000 | 1000 | 1000 | 5000
| Subtotal Output 1.3 | [6 empty] | 190600 | 70050 | 28737.5 | 34037.5 | 25887.5 | 31887.5 | 190600
| Subtotal Component 1 | [6 empty] | 3800325 | 741770 | 1242670.25 | 867040.25 | 555882 | 392962.5 | 3800325
Component 2: Adaptation of water management towards climate risks in coastal zones | Output 2.1. Community-based water management is improved and adapted towards climate risks, including salt-water intrusion and extreme weather events | A2.1.1 Elaborate adaptation management plans (salinization of rice fields, on-site agriculture, water and coastal management) | GCF | Consultant - Individual - International | Man/day | 25 | 600 | 15000 | 15000 | 0 | 0 | 0 | 0 | 15000 | B1
|  |  | GCF | Workshop/Training | Unit | 2 | 2000 | 4000 | 4000 | 0 | 0 | 0 | 0 | 4000
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 3000 | 3000 | 3000 | 0 | 0 | 0 | 0 | 3000
|  |  | GCF | Workshop/Training | Unit | 68 | 1000 | 68000 | 0 | 34000 | 34000 | 0 | 0 | 68000 | B2
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 10000 | 10000 | 0 | 5000 | 5000 | 0 | 0 | 10000
|  | A2.1.2 Construct and rehabilitate water management infrastructures to prevent salt water intrusion in mangrove-rice paddies | GCF | Materials & Goods | Unit | 34 | 7500 | 255000 | 0 | 76500 | 102000 | 51000 | 25500 | 255000 | B3
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 10000 | 10000 |  | 2500 | 2500 | 2500 | 2500 | 10000
|  |  | Executing Entity | Materials & Goods | Lump sum | 1 | 10100 | 10100 |  | 2525 | 2525 | 2525 | 2525 | 10100 | B4
|  | A2.1.3 Establish water management systems to address water shortages for production and consumption during prolonged dry spells | GCF | Local Staff - Expert | Unit (visit) | 102 | 600 | 61200 | 12240 | 12240 | 12240 | 12240 | 12240 | 61200 | B5
|  |  | GCF | Consultant - Individual - Local | Man/day | 20 | 300 | 6000 | 6000 | 0 | 0 | 0 | 0 | 6000 | B6
|  |  | GCF | Equipment | Unit | 34 | 11829.4118 | 402200 | 0 | 100550 | 100550 | 100550 | 100550 | 402200 | B7
|  |  | GCF | Workshop/Training | Unit | 34 | 947.0588 | 32200 | 10733.3333 | 10733.3333 | 10733.3333 | 0 | 0 | 32200 | B8
|  |  | GCF | Materials & Goods | Lump sum | 1 | 323000 | 323000 | 0 | 107666.6667 | 107666.6667 | 107666.6667 | 0 | 323000 | B9
|  |  | Executing Entity | Materials & Goods | Unit | 34 | 350 | 11900 | 0 | 5950 | 5950 | 0 | 0 | 11900 | B10
|  | A2.1.4 Promote micro-scale irrigation systems to maintain agricultural production | GCF | Materials & Goods | Unit | 34 | 7614.7059 | 258900 | 0 | 64725 | 64725 | 64725 | 64725 | 258900 | B11
| Subtotal Output 2.1 | [6 empty] | 1470500 | 50973.3333 | 422390 | 447890 | 341206.6667 | 208040 | 1470500
| Output 2.2. Mangrove ecosystems are better managed, as an ecosystem-based adaptation measure towards salt-water intrusion | A2.2.1 Implement erosion control and adaptation towards sea level rise and saline water intrusion through functional reforestation of mangroves | GCF | Materials & Goods | Unit | 4 | 23250 | 93000 | 0 | 55800 | 37200 | 0 | 0 | 93000 | B12
|  |  | GCF | Workshop/Training | Unit | 34 | 647.0588 | 22000 | 0 | 6600 | 15400 | 0 | 0 | 22000 | B13
|  |  | GCF | Consultant - Individual - Local | Man/day | 20 | 300 | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000 | B14
|  |  | GCF | Communication | Lump sum | 1 | 7500 | 7500 | 0 | 3750 | 3750 | 0 | 0 | 7500
|  |  | GCF | Materials & Goods | Lump sum | 1 | 409500 | 409500 | 0 | 102375 | 102375 | 102375 | 102375 | 409500 | B15
|  | A2.2.2 Organize sensitization sessions andpromote production and dissemination on firewood saving cookstoves | GCF | Consultant - Individual - Local | Man/day | 20 | 300 | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000 | B16
|  |  | GCF | Consultant - Individual - Local | Man/months | 48 | 700 | 33600 | 0 | 8400 | 8400 | 8400 | 8400 | 33600
|  |  | GCF | Communication | Unit | 100 | 30 | 3000 | 0 | 1000 | 1000 | 1000 | 0 | 3000
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 5000 | 5000 | 0 | 2500 | 1250 | 1250 | 0 | 5000
|  |  | GCF | Materials & Goods | Unit | 3500 | 20 | 70000 | 0 | 17500 | 17500 | 17500 | 17500 | 70000 | B17
|  |  | GCF | Workshop/Training | Unit | 34 | 447.0588 | 15200 | 0 | 7600 | 7600 | 0 | 0 | 15200
| Subtotal Output 2.2 | [6 empty] | 670800 | 0 | 217525 | 194475 | 130525 | 128275 | 670800
| Subtotal Component 2 | [6 empty] | 2141300 | 50973.3333 | 639915 | 642365 | 471731.6667 | 336315 | 2141300
Component 3: Building resilience of farming communities towards climate change | Output 3.1. Increased and diversified livelihoods of smallholder farmers | A3.1.1 Establishment, organization and regular trainings in CRA practices on Model Plots | GCF | Equipment | Unit | 170 | 1960 | 333200 | 66640 | 133280 | 99960 | 33320 | 0 | 333200 | C1
|  |  | GCF | Materials & Goods | Unit | 170 | 7890 | 1341300 | 268260 | 536520 | 402390 | 134130 | 0 | 1341300 | C2
|  |  | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 84760 | 84760 | 16952 | 33904 | 25428 | 8476 | 0 | 84760
|  |  | GCF | Materials & Goods | Unit | 170 | 100 | 17000 | 0 | 8500 | 8500 | 0 | 0 | 17000 | C3
|  |  | GCF | Materials & Goods | Lump sum | 1 | 64800 | 64800 |  | 16200 | 16200 | 16200 | 16200 | 64800
|  |  | GCF | Professional Services – Companies/Firm | Unit/model plot | 4250 | 10 | 42500 |  | 10625 | 10625 | 10625 | 10625 | 42500
|  |  | GCF | Materials & Goods | Unit | 35 | 4000 | 140000 | 0 | 70000 | 70000 | 0 | 0 | 140000 | C4
|  | A3.1.2 Promote Sustainable Rice Intensification (SRI) and Climate-Resilient Rice Production (CRRP) | GCF | Consultant - Individual - Local | Man/day | 20 | 300 | 6000 | 0 | 6000 | 0 | 0 | 0 | 6000 | C5
|  |  | GCF | Local Staff - Expert | Unit | 100 | 30 | 3000 | 0 | 3000 | 0 | 0 | 0 | 3000
|  |  | GCF | Workshop/Training | Lump sum | 1 | 15000 | 15000 | 0 | 7500 | 7500 | 0 | 0 | 15000 | C6
|  |  | GCF | Equipment | Lump sum | 1 | 263750.002 | 263750.002 | 0 | 87916.6673 | 87916.6673 | 87916.6673 | 0 | 263750.002 | C7
|  | A3.1.3 Introduction and promotion of short cycle animal production | GCF | Consultant - Individual - Local | Man/day | 15 | 300 | 4500 | 4500 | 0 | 0 | 0 | 0 | 4500 | C8
|  |  | GCF | Local Staff - Expert | Unit | 10 | 200 | 2000 | 2000 | 0 | 0 | 0 | 0 | 2000
|  |  | GCF | Communication | Unit | 10 | 250 | 2500 | 1250 | 1250 | 0 | 0 | 0 | 2500
|  |  | GCF | Materials & Goods | Unit (20 households/community) | 680 | 161.7647 | 110000 | 0 | 27500 | 27500 | 27500 | 27500 | 110000 | C9
| Subtotal Output 3.1 | [6 empty] | 2430310.002 | 359602 | 942195.6673 | 756019.6673 | 318167.6673 | 54325 | 2430310.002
| Output 3.2 Increased income options in climate-resilient economic activity along agricultural value chains | A3.2.1 Support the establishment and mentoring of 40 micro-enterprises and women-led income generating activities (IGAs) along the value chain(s) | GCF | Workshop/Training | Unit | 20 | 16150 | 323000 | 0 | 0 | 96900 | 129200 | 96900 | 323000 | C10
|  |  | GCF | Grant | Unit | 40 | 12000 | 480000 | 0 | 0 | 144000 | 168000 | 168000 | 480000 | C11
|  |  | GCF | Consultant - Individual - Local | Man/Month | 60 | 650 | 39000 | 7800 | 7800 | 7800 | 7800 | 7800 | 39000
|  |  | GCF | Consultant - Individual - Local | Man/Month | 120 | 300 | 36000 | 7200 | 7200 | 7200 | 7200 | 7200 | 36000
|  | A3.2.2 Establish and upgrade commercial associations for agricultural value chain development | GCF | Workshop/Training | Lump sum | 1 | 175400 | 175400 | 0 | 0 | 58466.6667 | 58466.6667 | 58466.6667 | 175400 | C12
|  |  | GCF | Consultant - Individual - Local | Lump sum | 1 | 47300 | 47300 | 0 | 0 | 15766.6667 | 15766.6667 | 15766.6667 | 47300 | C13
| Subtotal Output 3.2 | [6 empty] | 1100700 | 15000 | 15000 | 330133.3333 | 386433.3333 | 354133.3333 | 1100700
| Subtotal Component 3 | [6 empty] | 3531010.002 | 374602 | 957195.6673 | 1086153.0007 | 704601.0007 | 408458.3333 | 3531010.002
| SUB-TOTAL | [6 empty] | 9472635.002 | 1167345.3333 | 2839780.9173 | 2595558.2507 | 1732214.6673 | 1137735.8333 | 9472635.002
Project Management Cost | PMC | Project Coordinator | GCF | Local Staff - Expert | Month | 60 | 2800 | 168000 | 33600 | 33600 | 33600 | 33600 | 33600 | 168000 | PMU
|  | 4x4 Land Cruiser PMU | GCF | Equipment | Vehicle | 1 | 48000 | 48000 | 31200 | 0 | 16800 | 0 | 0 | 48000 | PMU
|  | Responsible for M&E | Executing Entity | Local Staff - Expert | Month | 60 | 1200 | 72000 | 14400 | 14400 | 14400 | 14400 | 14400 | 72000 | PMU
|  | Financial Manager | GCF | Local Staff - Expert | Month | 60 | 1200 | 72000 | 14400 | 14400 | 14400 | 14400 | 14400 | 72000 | PMU
|  | Kickoff workshop | GCF | Workshop/Training | lump sum | 1 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000 | PMU
|  | Steering Committee Meetings | GCF | Workshop/Training | Days* Persons | 10 | 3500 | 35000 | 7000 | 7000 | 7000 | 7000 | 7000 | 35000 | PMU
|  | M&E Missions | GCF | Workshop/Training | Days*Persons | 280 | 45 | 12600 | 2520 | 2520 | 2520 | 2520 | 2520 | 12600 | PMU
|  | Audits (External & Internal) | GCF | Consultant - Individual - Local | Unit | 5 | 5000 | 25000 | 5000 | 5000 | 5000 | 5000 | 5000 | 25000 | PMU
|  | Operating fees | GCF | Other costs (travel expenses, publication of ToRs, translation, communication/internet…) | Lump sum | 1 | 28400 | 28400 | 5680 | 5680 | 5680 | 5680 | 5680 | 28400 | PMU
|  | Contingencies (Bank Costs, taxes, PCR….) | GCF | Office Costs | Lump sum | 60 | 189.41 | 11364.6 | 2272.92 | 2272.92 | 2272.92 | 2272.92 | 2272.92 | 11364.6 | PMU
| SUB-TOTAL | [6 empty] | 482364.6 | 126072.92 | 84872.92 | 101672.92 | 84872.92 | 84872.92 | 482364.6
Total Amount | [7 empty] | 9954999.602 | 1293418.2533 | 2924653.8373 | 2697231.1707 | 1817087.5873 | 1222608.7533 | 9954999.602
Total | GCF | [6 empty] | 9807799.602 | 1266018.2533 | 2881978.8373 | 2667556.1707 | 1793362.5873 | 1198883.7533 | 9807799.602
Total | Executing Entity | [6 empty] | 147200 | 27400 | 42675 | 29675 | 23725 | 23725 | 147200
Total | OSS fees (AE) | [6 empty] | 833662.9662 | 175931 | 147933 | 167933 | 147933 | 193933 | 833662.9662
**Please provide the assumptions and basis of how unit cost and quantities are arrived. Please insert an appropriate reference as illustrated and enter the detailed comments in the "Detailed budget Notes" Sheet

## Detailed Budget Notes
Note
Consultant | To detail unit cost and duration of consultant(s) work and position
Equipment | Include machinery specification, equipment name, quantity, and unit cost in budget notes and how the unit cost is arrived.
Workshop | Include the number of workshops anticipated, number of people attending, number of days, target group, cost per work workshop, venue cost, etc.
Travel | Breakdown travel cost information by number of people and cost per person and separating DSA where applicable. Also please provide the reason why international travel is needed.
Professional Services | Please provide the details of the professional services needed, purpose of the services, and also the basis of the cost estimates.
Materials & Goods | Include material and goods specification, name, quantity, and unit cost in budget notes, and how the unit cost is arrived.
Office Supplies | Include office supplies' name, quantity, and unit cost in budget notes, and how the unit cost is arrived.
PMU | PMC percentage applies on the sub-total of components/activities.
Detailed Budget Notes
(important - prepared in conjunction with Budget Plan)
A1.1 | International consultant - Conceptualization of OGs
|  | Unit | Quantity | Unit cost (USD) | Total
| Design, definition and development of the OG for climate-resistant and low-emission practices and technologies, and monitoring of water and soil quality. | Man/day | 25 | 600 | 15000
| Total (USD) |  |  |  | 15000
A1.2 | Local consultant - Conceptualization of OGs
|  | Unit | Quantity | Unit cost (USD) | Total
| Design, definition and development of the OG for climate-resistant and low-emission practices and technologies, and monitoring of water and soil quality. | Man/day | 20 | 350 | 7000
| Total (USD) |  |  |  | 7000
A2 | The OG conceptualization phase: Exchange and validation workshops of the OG conceptualization phase
|  | Unit | Quantity | Unit cost (USD) | Total
| 2 workshops are planned:the first one is to present and collect feedback on the ToRs and the second one is for the final validation of the ToRs | Workshop (Lump Sum) | 2 | 6000 | 12000
| Meetings with the national authorities for broader integration in to the national system (2 meetings/year) | Meeting (Lump Sum) | 10 | 1000 | 10000
| Total (USD) |  |  |  | 22000
A3 | Office Costs Obervartory Groups
|  | Unit | Quantity | Unit cost (USD) | Total
| Office construction/rehabilitation for 2 OGs | Lump sum | 2 | 3000 | 6000
| Office furniture (Desks, chairs, shelves, etc.) for 2 OG offices | Lump sum | 2 | 1500 | 3000
| Office Supplies (250$/OG/Month) | Lump sum | 120 | 250 | 30000
| Total (USD) |  |  |  | 39000
A4 | Operationalization of the OGs
|  | Unit | Quantity | Unit cost (USD) | Total
| Coordinators Observatory Groups (OGs) (1coordinator/OG) | Months* persons | 120 | 1000 | 120000
| Senior deputies (1Senior deputy/OG) | Months* persons | 120 | 800 | 96000
| Junior deputies (2 Junior deputies/OG) | Months* persons | 240 | 400 | 96000
| HR & procurement manager | Months* persons | 60 | 950 | 57000
| Total (USD) |  |  |  | 369000
A5 | Consultant - Individual - Local for design of CCCs
|  | Unit | Quantity | Unit cost (USD) | Total
| Design and construction plan of the CCCs | Man/day | 20 | 150 | 3000
| Total (USD) |  |  |  | 3000
A6 | Equipment, materials & goods for construction of CCCs
|  | Unit | Quantity | Unit cost (USD) | Total
Construction of 20 CCCs - estimated area of ​​200 square meters, with acquisition of cement (800 bags @USD11 per bag), masonry blocks (4,000 masonary blocks a@USD 1 per unit), nails (100 kilograms of nails at an average @USD3 per kg), insulating plaster (100 kilograms of plaster at @USD8 per kg), doors (8 doors @USD100), windows (16 windows @USD25), electrical equipment (estimated @USD750), toilet (estimated @USD700), plumbing (estimated @USD4,500), labor (estimated @USD7,225), transport of materials (@USD1,000 in material transport) and other finishes (@USD1,500 for roofs and paintings).
| Cement | bags | 16000 | 11 | 176000
| Masonary blocks | blocks | 80000 | 1 | 80000
| Nails | kg | 2000 | 3 | 6000
| Insulating plaster | kg | 2000 | 8 | 16000
| Doors | Unit | 160 | 100 | 16000
| Windows | Unit | 320 | 25 | 8000
| Electrical equipment | lump sum | 20 | 750 | 15000
| Toilet | Unit | 20 | 700 | 14000
| Plumbing | lump sum | 20 | 4500 | 90000
| Labour | lump sum | 20 | 7225 | 144500
| Transport of material | lump sum | 20 | 1000 | 20000
| Other finishes - roof and painting | lump sum | 20 | 1500 | 30000
| Legal Obligations of CCCs | Unit | 20 | 400 | 8000
| Purchase of Solar Panel Systems for (20) Community Climate Centers (Panels, Antennas, DVDs, Plasma (TV), carts. Pictures, adventures tables etc ...) | Unit | 20 | 6000 | 120000
| 2 maintenance operations of Solar Panel Systems for (20) Community Climate Centers (3rd - 5th year) | Unit * times | 40 | 300 | 12000
| Total (USD) |  |  |  | 755500
A7 | Materials & Goods for construction of CCCs
|  | Unit | Quantity | Unit cost (USD) | Total
| Provision of Local materials for the centres (Sand, Gravel, water) | Communities | 20 | 300 | 6000
| Labor for the construction of the Centres (10 people/20 centres/10 days) | People* days | 2000 | 10 | 20000
| Total (USD) |  |  |  | 26000
A8 | Extension team setup
|  | Unit | Quantity | Unit cost (USD) | Total
| 17 Extensionist/region in charge of all field activities during project lifespan (54months/extensionist) | Months | 1836 | 300 | 550800
| Other costs | Lump Sum | 1 | 3500 | 3500
| Total (USD) |  |  |  | 554300
A9 | Establishment of a management committe
|  | Unit | Quantity | Unit cost (USD) | Total
| Meeting for the establishment of a management committee | Meeting (Lump Sum) | 20 | 300 | 6000
| Other costs | Lump Sum | 20 | 150 | 3000
| Total (USD) |  |  |  | 9000
A10 | International consultant
|  | Unit | Quantity | Unit cost (USD) | Total
| Develop and elaborate training modules on various topics : management and administration, operational capacities, financial literacy and management, community sensitization and leadership, and sustainability planning | Man/day | 10 | 600 | 6000
| Other costs | Lump Sum | 1 | 3000 | 3000
| Total (USD) | Lump Sum |  |  | 9000
A11 | Training workshops for CCC committees in management and administration, operational capacities, financial literacy and management, community sensitization and leadership, and sustainability planning
|  | Unit | Quantity | Unit cost (USD) | Total
| Training in management and administration, operational capacities, financial literacy and management, community sensitization and leadership, and sustainability planning (4 training sessions/5 committees = 4 groups) | Training session | 16 | 1000 | 16000
| Other costs | Lump Sum | 16 | 200 | 3200
| Total (USD) |  |  |  | 19200
A12 | Equipment Observatory Groups and CCCs
|  | Unit | Quantity | Unit cost (USD) | Total
| Vehicles for the Observatory Groups in Oio and Cachéu - 4x4 pick ups (2 /OG) including runnig costs and legal obligations (Insurance…) | Unit | 4 | 40000 | 160000
| Motorbikes for extensionist including runnig costs and legal obligations (Insurance…) | Unit | 37 | 2300 | 85100
| Purchase of Soil and Water Quality Monitoring Kits and Equipment | Kits | 68 | 1000 | 68000
| Acquisition of devices for soil PH device (2) & salinity (2) | Devices | 68 | 400 | 27200
| Acquisition of data collection equipments (Drone, camera…) | Lump sum | 2 | 4000 | 8000
| IT equipments (laptops, printer…) | Lump sum/region | 2 | 12000 | 24000
| Other fees (Legal Obligations to dispatch devices) | Lump sum | 1 | 15000 | 15000
Fuel and maintenance of vehicles and motorbikes
| Fuel for Vehicles : The price per liter of diesel used is $1.2 | Month* Vehicle | 240 | 340 | 81600
| Fuel for Motorbikes : The price per liter of diesel used is $1.2 | Month* Motorbike | 2040 | 80 | 163200
| Maintenance Vehicles | Month* Vehicle | 240 | 100 | 24000
| Maintenance Motorbikes | Month* motorbike | 2040 | 20 | 40800
| Other fees related to transport | Month | 60 | 100 | 6000
| Total (USD) |  |  |  | 702900
A13 | International consultant
|  | Unit | Quantity | Unit cost (USD) | Total
| Develop and elaborate training modules on O&M of observatory equipment. | Man/day | 10 | 600 | 6000
| Other costs | Lump Sum | 1 | 3000 | 3000
| Total (USD) | Lump Sum |  |  | 9000
A14 | Training workshops on O&M of observatory equipment.
|  | Unit | Quantity | Unit cost (USD) | Total
| Training on O&M of observatory equipment. | Training session | 16 | 1000 | 16000
| Other costs | Lump Sum | 4 | 800 | 3200
| Total (USD) |  |  |  | 19200
A15 | International consultant
|  | Unit | Quantity | Unit cost (USD) | Total
| Development of Training manuals, Modules and Curriculums for Environmental Education, CRA practices and technologies, adaptation towards water and soil salinization | Man/day | 35 | 600 | 21000
| Other costs | Lump Sum | 1 | 4000 | 4000
| Total (USD) | Lump Sum |  |  | 25000
A16 | National consultant
|  | Unit | Quantity | Unit cost (USD) | Total
| Development of Training manuals, Modules on Environmental Education, CRA practices and technologies, adaptation towards water and soil salinization | Man/day | 35 | 300 | 10500
| Other costs | Lump Sum | 1 | 2000 | 2000
| Total (USD) | Lump Sum |  |  | 12500
A17 | Working groups validation meetings
|  | Unit | Quantity | Unit cost (USD) | Total
| Working groups validation meetings to validate all the training materials with ADPP, IBAP, MoEB, MoE, MoA | Meeting | 16 | 2000 | 32000
| Other costs | Lump Sum | 1 | 4000 | 4000
| Total (USD) | Lump Sum |  |  | 36000
A18 | Sensitazation and awarness training
|  | Unit | Quantity | Unit cost (USD) | Total
| Sensitization and awarness training on Environmental Education, CRA practices and technologies, adaptation towards water and soil salinization (strating from year 2: 4sessions/year) | 4training sessions/year | 4 | 16000 | 64000
| Other costs (travel expenses, translation, moderation, communication/internet…) (5000USD/year) | Lump Sum | 4 | 5000 | 20000
| Total (USD) |  |  |  | 84000
A19 | Workshops/ Trainings - Professional Courses for Youth
|  | Unit | Quantity | Unit cost (USD) | Total
| Promotion of technical and professional courses to 115 young people (50% women) in climate resilient agriculture (11-month agricultural course), year 2, year 3, year 4 | Students* Month | 1265 | 185 | 234025
| Promotion of a 6-month specialization course in climate-resilient agriculture and integration of the nutritional part of 115 young people (50% women) year 2, year 3, year 4 | Students* Month | 690 | 185 | 127650
| Training in livestock and animal breeding of short cycle - 3 months. (2 people / community (50% women) = 68 students / 1st and 2nd year Vocational School in Bissorã | Students* Month | 204 | 185 | 37740
| Promotion of training for young people on post-harvest practices and use of mechanized means for the development of agricultural value chains. 115 young people (50% women) 6 months (2 years) 2nd and 3rd year | Students* Month | 690 | 185 | 127650
| Training of 6 months to 160 (40 / year) young people in agribusiness and addressing components of resource optimization, such as use / waste of raw agricultural products (Year 2, 3, 4 and 5) | Students* Month | 160 | 185 | 29600
| Total (USD) |  |  |  | 556665
A20 | Equipment for Vocational Training Courses
| Teaching materials and equipment for vocational school for student practice, year 1, year 2, year 3, year 4 | Unit | Quantity | Unit cost (USD) | Total
| Tractor and accessories | Units | 1 | 40000 | 40000
| Ricer Husker | Units | 1 | 2000 | 2000
| Maize mill | Units | 1 | 2500 | 2500
| Maintenance of Tractor, Power Tiller, Peeler, Bicycle and Corn Mill for 20 quarters | lump sum | 1 | 8000 | 8000
| Material ans equipment for students | Units | 115 | 100 | 11500
| Processing materials | lump sum | 1 | 7000 | 7000
| Other | Lump Sum | 1 | 12000 | 12000
| Total (USD) |  |  |  | 83000
A21.1 | Workshops - functional literacy classes for women
|  | Unit | Quantity | Unit cost (USD) | Total
| Functional literacy classes in the context of Adaptation to Climate Change (agriculture, health, nutrition, gender equality for 2,720 people. (2nd year) materials | People | 2720 | 20 | 54400
| Identification and training of 68 community teachers of 12-day functional literacy (1st year) food per day | People * days | 816 | 10 | 8160
| Subsidy for 68 community teachers of functional literacy (2nd, 3rd. 4th and 5th year) 2/3 paid by GCF, 8 months per year | Months* persons | 2176 | 25 | 54400
| Total (USD) |  |  |  | 116960
A21.2 | Workshops - functional literacy classes for women
|  | Unit | Quantity | Unit cost (USD) | Total
| Subsidy for 68 community teachers of functional literacy (2nd, 3rd. 4th and 5th year) 1/3 paid by community - 8 months per year | Months* persons | 1088 | 25 | 27200
| Total (USD) |  |  |  | 27200
A22 | Materials & Goods for literacy classes and women's registration
|  | Unit | Quantity | Unit cost (USD) | Total
| Reproduction of functional literacy materials in the context of Adaptation to Climate Change 2,720 manuals (2nd year) | Persons | 2720 | 10 | 27200
| Conception of registration and identity card for 1,000 women beneficiaries (2nd year) 500 / region | Units | 1000 | 45 | 45000
| Total (USD) |  |  |  | 72200
A23 | Environmental Education Campaign
|  | Unit | Quantity | Unit cost (USD) | Total
| Environmental education and in schools in the project intervention areas (By teachers and students during internships) 2 times a year | Semester | 10 | 350 | 3500
| Training of (68 Youth - 2 people per community) on techniques for creating nurseries, restoration and conversion of mangroves 2 by region. (2 / community) year 1 | Trainings | 4 | 900 | 3600
| Operating Costs Schools (10 semesters / 2 schools) | Semester | 20 | 1500 | 30000
| Total (USD) |  |  |  | 37100
A24 | Baseline and KAP Survey
|  | Unit | Quantity | Unit cost (USD) | Total
| Consultant - Individual - International | Man/day | 20 | 600 | 12000
| Consultant - Individual - National | Man/day | 20 | 300 | 6000
| Consultant - Individual - National KAP Survey year 1 | Man/day | 10 | 300 | 3000
| Consultant - Individual - National KAP Survey year 5 | Man/day | 10 | 300 | 3000
| Consultation and validation meetings | Lump sum | 1 | 6000 | 6000
| Contingencies (travel expenses, publication of ToRs, validation process…) | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 35000
A25 | Design and operationalization of e-platform
|  | Unit | Quantity | Unit cost (USD) | Total
| Consultant - Individual - National: Development of a collaborative electronic platform as a knowledge base for resilience and climate adaptation practices | Man/day | 30 | 350 | 10500
| Hosting costs of the platform | Year | 4 | 400 | 1600
| Workshops for validation and training on the platform | Units | 3 | 2000 | 6000
| Other costs (travel expenses, publication of ToRs, translation…) | Lump Sum | 1 | 3000 | 3000
| Total (USD) |  |  |  | 21100
A26 | Equipment and materials for Communication
|  | Unit | Quantity | Unit cost (USD) | Total
| Digital cameras for technical communication and visibility | Unit | 1 | 2500 | 2500
| Document Production and Printing | Lump Sum | 1 | 5000 | 5000
| Visibility materials (plates, stickers, t-shirts, caps) | Lump Sum | 1 | 10000 | 10000
| Films production of good practices on climate change and resilience | Lump Sum | 1 | 8000 | 8000
| Production of radio programs on climate change and resilience | Lump Sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 30500
A27 | Consultant and responsible for the implementation of the communication strategy
|  | Unit | Quantity | Unit cost (USD) | Total
| Consultant - Individual - International | Man/day | 20 | 600 | 12000
| Responsible Communication & Visibility (all 5 years) | Month | 60 | 500 | 30000
| Contingencies (travel expenses, publication of ToRs…) | Lump Sum | 1 | 3000 | 3000
| Total (USD) |  |  |  | 45000
A28 | Workshops and meetings to disseminate Knowledge and Information
|  | Unit | Quantity | Unit cost (USD) | Total
| Series of sensitization workshops about CRA, CCA and the results of the project: Year 1 (1 workshop to validate the knowledge management strategy) ; Year 2,3,4 and 5 (2 workshops/year) | Unit | 9 | 6000 | 54000
| Other | Lump Sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 59000
B1 | Consultant - Individual - International : Development of Adaptation Plans
|  | Unit | Quantity | Unit cost (USD) | Total
| Elaborate adaptation plans (salinization of rice fields, on-site agriculture, water and coastal management). | Man/day | 25 | 600 | 15000
| Workshops for presentation and validation of plans | Units | 2 | 2000 | 4000
| Other costs (travel expenses, publication of ToRs, translation…) | Lump Sum | 1 | 3000 | 3000
| Total (USD) |  |  |  | 22000
B2 | National consultation and working groups validation meetings
|  | Unit | Quantity | Unit cost (USD) | Total
| Working groups to develop and validate 34 community adaptation plans on: • The intrusion of saline water in rice fields and management of saline groundwater • The water management plans on site and Operationalization and monitoring in the fields of general crops and horticulture. • The water management plans on site and Operationalization and monitoring in the rice fields | Lump sum | 68 | 1000 | 68000
| Other costs | Lump sum | 1 | 10000 | 10000
| Total (USD) |  |  |  | 78000
B3 | Materials & Goods - hydro-agricultural work for water management
|  | Unit | Quantity | Unit cost (USD) | Total
| Hydro-agricultural technical work for water management in plots identified as more prone to flooding. (Farmers organized in labor brigades) | Units | 34 | 6000 | 204000
| Basic materials, equipment and inputs | Lump sum | 34 | 1500 | 51000
| Other costs | Lump sum | 1 | 10000 | 10000
| Total (USD) |  |  |  | 265000
B4 | Materials & Goods - hydro-agricultural work for water management
|  | Unit | Quantity | Unit cost (USD) | Total
| Local Materials | Units | 34 | 150 | 5100
| Labor - 25 people | Persons *days | 500 | 10 | 5000
| Total (USD) |  |  |  | 10100
B5 | National consultation and support during construction of hydro-agricultural work for water management
|  | Unit | Quantity | Unit cost (USD) | Total
| Technical assistance and support from national entities (MoA, IBAP…) (3 visits/community) | Units | 102 | 600 | 61200
| Total (USD) |  |  |  | 61200
B6 | Consultant - Individual - Local
|  | Unit | Quantity | Unit cost (USD) | Total
| Mapping and evaluation of existing water points in the target areas, and subsequently develop a plan for the revitalization and establishment of water points | Man/day | 20 | 300 | 6000
| Total (USD) |  |  |  | 6000
B7 | Equipment - Establishment and revitalization of Water Points
|  | Unit | Quantity | Unit cost (USD) | Total
| Construct and equip (10) new wells (Solar system, tower and installation of access points) | Units | 10 | 25000 | 250000
| Rehabilitate and equip 24 existing wells | Units | 24 | 5000 | 120000
| Chemical and Micro-Biological Water Analysis Systems for drinking Water (5/region) | Units | 34 | 800 | 27200
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 402200
B8 | Workshop/Training : establish and strengthen Water Management Committees (WMCs)
|  | Unit | Quantity | Unit cost (USD) | Total
| Establish and strengthen Water Management Committees (WMCs) | Units | 34 | 600 | 20400
| Technical assistance and support from national entities (MoA, GDWR…) | Units | 34 | 200 | 6800
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 32200
B9 | Materials & Goods - hydro-agricultural work for water management
|  | Unit | Quantity | Unit cost (USD) | Total
| Construction of rainwater retention system in 34 model fields (17 / Region) at Community Horticulture Model Fields | Units | 34 | 8000 | 272000
| Construction of rainwater retention system in local material in 20 CCC's, 5.000 liter tanks | Units | 20 | 800 | 16000
| Logistic costs (Drivers, maintenance…) | Man/month | 120 | 250 | 30000
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 323000
B10 | Materials & Goods - hydro-agricultural work for water management
|  | Unit | Quantity | Unit cost (USD) | Total
| Provision of Local Materials (gravel, sand, etc.) | Units | 34 | 350 | 11900
| Total (USD) |  |  |  | 11900
B11 | Equipment - Irrigation setups
|  | Unit | Quantity | Unit cost (USD) | Total
| Introduction of irrigation systems adapted to specific situations, in the beneficiaries' vegetable plots. | Units | 34 | 7000 | 238000
| Technical assistance and support from national entities (MoA…) | Units | 34 | 350 | 11900
| Other costs | Lump sum | 1 | 9000 | 9000
| Total (USD) |  |  |  | 258900
B12 | Establishment of mangrove nurseries: Materials & Good
|  | Unit | Quantity | Unit cost (USD) | Total
| Materials and equipment for the creation of 4 community mangrove nurseries Oio and Cachéu (2 in each region) | Units | 4 | 20000 | 80000
| Technical assistance and support from national entities (MoA, IBAP…) (providing training and coaching support) (2000USD/Nursery) | Units | 4 | 2000 | 8000
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 93000
B13 | Workshops for establishing mangrove brigades in communities
|  | Unit | Quantity | Unit cost (USD) | Total
| Creation and training of 34 mangrove protector groups for the protection and restoration of mangroves in the communities | Units | 34 | 500 | 17000
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 22000
B14 | Local consultant for production of manuals for mangrove restoration and protection
|  | Unit | Quantity | Unit cost (USD) | Total
| Preparation of manuals of procedures and good practices for the protection and recovery of mangroves in the communities and manuals of good practices for anthropogenic activities in the natural areas of the mangroves - fishing, rice, oysters and others, | Man/days | 20 | 300 | 6000
| Reproduction of 100 manuals of procedures and good practices for the protection and recovery of mangroves in the communities. (50 Each) | Units | 100 | 30 | 3000
| Reproduction of 50 manuals of good practices for anthropogenic activities in the natural areas of the mangroves - fishing, rice, oysters and others. 1 for each community + extras | Units | 50 | 30 | 1500
| Development, printing and dissemination of popular versions of manuals for mangrove restoration and protection | Lump sum | 1 | 3000 | 3000
| Total (USD) |  |  |  | 13500
B15 | Mangrove restoration and tree planting Campaign
|  | Unit | Quantity | Unit cost (USD) | Total
| Re-populating campaign of trees in the 34 communities benefiting from the project | Units | 260000 | 1 | 260000
| Transport of plants to communities | Units | 34 | 200 | 6800
| Manpower from 34 communities of repopulation of 260 000 trees (50 people / community) | Lump sum | 1700 | 50 | 85000
| Oio and Cachéu mangrove restoration campaign - Inputs and equipment | Units | 34 | 1550 | 52700
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 409500
B16 | Local consultant
|  | Unit | Quantity | Unit cost (USD) | Total
| Local consultant for production and dissemination manuals on firewood saving cookstoves | Man/days | 20 | 300 | 6000
| Sensitazation and roll-out campaigns | Units | 100 | 30 | 3000
| Gender expert to identify and train woman groups on firewood saving cookstoves | Man/months | 48 | 700 | 33600
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 47600
B17 | Materials & Goods for improved cookstoves
|  | Unit | Quantity | Unit cost (USD) | Total
| Procurement and introduction of 3500 improved cookstoves to save wood for 34 communities benefiting from the project (50 / community) | Units | 3500 | 20 | 70000
| Women groups from 34 communities to be train on cookstoves production | Units | 34 | 300 | 10200
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 85200
C1 | Equipment - provision for Farmers' Clubs
|  | Unit | Quantity | Unit cost (USD) | Total
| Materials for 170 farmers' clubs (purchase of hoes, sickles, rakes, wheelbarrows, watering cans, water reservoirs, sprayers, forks, rope etc.) 2,335 US$ per Club | Units | 170 | 1960 | 333200
Items breakdown
| Wheel barrows, 2 per club | units | 340 | 100 | 34000
| Watering cans, 5 per club | units | 850 | 20 | 17000
| Water reservoir, 1 per club | units | 170 | 900 | 153000
| Sprayer, 1 per club | units | 170 | 60 | 10200
| Metal shovels, 5 per club | units | 850 | 10 | 8500
| Pick hoes, 5 per club | units | 850 | 20 | 17000
| 30 liter containers, 5 per club | units | 850 | 20 | 17000
| 15 liter buckets, 5 per club | units | 850 | 5 | 4250
| 20 liter container, 5 per club | units | 850 | 10 | 8500
| Machetes, 5 per club | units | 850 | 10 | 8500
| 20 liter drums, 5 per club | units | 850 | 5 | 4250
| Sickles, 5 per club | units | 850 | 10 | 8500
| Rakes, 5 per club | units | 850 | 10 | 8500
| Hoes, 5 per club | units | 850 | 10 | 8500
| Forks, 5 per club | units | 850 | 10 | 8500
| Rolls of 100 meter rope/ string, 5 per club | units | 850 | 20 | 17000
| Total (USD) |  |  |  | 333200
C2 | Equipment - establishment of CRA Model Plots
|  | Unit | Quantity | Unit cost (USD) | Total
| Creation of 170 (85 / Region) Community Horticulture Model Fields (64*50 = 3200m2); and materials for (Improved water well @USD2,500; Fencing @USD1,500; horticultural supplies @USD500; and solar pump and irrigation system @USD3,500) | Unit | 170 | 7890 | 1341300
| Legal Obligations for 170 Horticulture and Rice fields | Unit | 170 | 350 | 59500
| Logistics Manager | Months | 30 | 734 | 22020
| Legal Support | Month | 12 | 270 | 3240
| Total (USD) |  |  |  | 1426060
C3 | Materials & Goods - provision of inputs for CRA Model Plots
|  | Unit | Quantity | Unit cost (USD) | Total
| Provision of Local materials | Units | 170 | 100 | 17000
| FCs and Extensionists Offices Running costs | Lump sum | 1 | 64800 | 64800
| Labor for field fencing and land preparation (25 people days per model plot) | Units | 4250 | 10 | 42500
| Total (USD) |  |  |  | 124300
C4 | Equipment - establishment of Seed Banks
|  | Unit | Quantity | Unit cost (USD) | Total
| Creation of a seed bank adapted and resilient to the CC-EVB (Semesters, inputs, materials and equipment) 1st year and at every community | Unit | 35 | 4000 | 140000
| Total (USD) |  |  |  | 140000
C5 | Local consultant to promote Sustainable Rice Intensification (SRI) and Climate-Resilient Rice Production (CRRP).
|  | Unit | Quantity | Unit cost (USD) | Total
| Local consultant for production manuals and training modules on SRI | Man/day | 20 | 300 | 6000
| Technical assistance and support from national entities (MoA…) | Unit | 100 | 30 | 3000
| Total (USD) |  |  |  | 9000
C6 | Trainings to promote Sustainable Rice Intensification (SRI) and Climate-Resilient Rice Production (CRRP).
|  | Unit | Quantity | Unit cost (USD) | Total
| Trainings to promote Sustainable Rice Intensification (SRI) and Climate-Resilient Rice Production (CRRP). | Lumps sum | 1 | 15000 | 15000
| Total (USD) |  |  |  | 15000
C7 | Equipment
|  | Unit | Quantity | Unit cost (USD) | Total
| Provide farmers access to equipment and tools to implement SRI-CRRP (34 communities receiving basic equipment for setting up and managing the rice plots with the SRI-CRRP technique, including trenching tools, composting units, watering, transport and distribution costs) | Units | 68 | 2003.6765 | 136250.002
| Provide farmers storage equipment for rice production (34 communities receiving 5 improved 'Bembas', based on the traditional storage units for rice and seeds) | Units | 170 | 750 | 127500
| Total (USD) |  |  |  | 263750.002
C8 | Local consultant to promote short cycle animals in target communities
|  | Unit | Quantity | Unit cost (USD) | Total
| Local consultant for production manuals and dissemination manuals on short cycle animals | Man/days | 15 | 300 | 4500
| Technical assistance and support from national entities (MoA…) | Units | 10 | 200 | 2000
| Sensitization campaigns at the communities level | Units | 10 | 250 | 2500
| Total (USD) |  |  |  | 9000
C9 | Materials & Goods : provide short-cycle animals
|  | Unit | Quantity | Unit cost (USD) | Total
| Provide farmers with short-cycle animals (20 households per community) | units | 680 | 150 | 102000
| Other costs | Lumps sum | 1 | 8000 | 8000
| Total (USD) |  |  |  | 110000
C10 | Workshops and Trainings - Establishment of micro-enterprises
|  | Unit | Quantity | Unit cost (USD) | Total
| Launching a call for proposals for small grants | Lumps sum | 1 | 3000 | 3000
| Train identified and selected projects on agribusiness | Projects | 20 | 6000 | 120000
| Form and accelerate 20 existing micro-enterprises in agribusiness in the Cacheu and Oio region. | Projects | 20 | 10000 | 200000
| Total (USD) |  |  |  | 323000
C11 | Grants
|  | Unit | Quantity | Unit cost (USD) | Total
| Provide women-led income generating activities (IGAs) along the micro-enterprises value chain(s). | Grants | 40 | 12000 | 480000
| Accountant | Man/Month | 60 | 650 | 39000
| Cashiers | Man/Month | 120 | 300 | 36000
| Total (USD) |  |  |  | 555000
C12 | Workshops and Trainings - management teams of CCPCs
|  | Unit | Quantity | Unit cost (USD) | Total
| Creation of 2 agricultural community units (Community Processing and Marketing Centers - CCPC) | Units | 2 | 20000 | 40000
| Reactivation support to 2 exisintg Processing Centers in Bissorã (including Watine) | Units | 2 | 4500 | 9000
| Legal obligations of (4) agricultural community units (Community Processing and Marketing Centers - CCP) | Units | 4 | 350 | 1400
| Purchase of materials and equipment for (4) agricultural community units (Community Processing and Marketing Centers - CCP) | Units | 4 | 30000 | 120000
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 175400
C13 | Local Consultants - business planning and support
|  | Unit | Quantity | Unit cost (USD) | Total
| Mapping of structured organizations working in agribusiness in the regions of Cacheu and Oio | Unit | 1 | 4500 | 4500
| Design of the construction project for the centers ( CCPC) | Unit | 1 | 1800 | 1800
| Creation of 4 business plans | Unit | 4 | 4000 | 16000
| Creation of 2 Association | Unit | 2 | 5000 | 10000
| Capacity building sessions | Annual | 5 | 2000 | 10000
| Other costs | Lump sum | 1 | 5000 | 5000
| Total (USD) |  |  |  | 47300
| Component 1: Total A |  |  |  | 3800325
| Component 2: Total B |  |  |  | 2141300
| Component 3: Total C |  |  |  | 3531010.002
| Total activities |  |  |  | 9472635.002
PMU1 | Project Management Costs
|  | Unit | Quantity | Unit cost (USD) | Total
| Project Coordinator | Man/Month | 60 | 2800 | 168000
| 4x4 Land Cruiser PMU | Vehicle | 1 | 48000 | 48000
| Responsible for M&E | Month | 60 | 1200 | 72000
| Financial Manager | Month | 60 | 1200 | 72000
| Kickoff workshop | Lump sum | 1 | 10000 | 10000
| Steering Committee Meetings SCM | SCM | 10 | 3500 | 35000
| M&E Missions (ADPP staff only) | Days* Persons | 280 | 45 | 12600
| Audits (External & Internal) | Unit | 5 | 5000 | 25000
| Operating fees | Lump sum | 1 | 28400 | 28400
| Contingencies (Bank Costs, taxes, PCR….) | Lump sum | 60 | 189.41 | 11364.6
| Project Management Unit - Total USD |  |  |  | 482364.6
| Total Amount |  |  |  | 9954999.602

## Disbursment
| Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Component 1 | 728770 | 1222870.25 | 860240.25 | 549082 | 386162.5 | 3747125
Component 2 | 50973.3333 | 631440 | 633890 | 469206.6667 | 333790 | 2119300
Component 3 | 374602 | 957195.6673 | 1086153.0007 | 704601.0007 | 408458.3333 | 3531010.002
PMU | 111672.92 | 70472.92 | 87272.92 | 70472.92 | 70472.92 | 410364.6
OSS | 175931 | 147933 | 167933 | 147933 | 193933 | 833663
Total | 1441949.2533 | 3029911.8373 | 2835489.1707 | 1941295.5873 | 1392816.7533 | 10641462.602