## Timetable
Annex 5: Implementation Timetable
Project Title: Solomon Islands Knowledge Action Sustainability for Resilient Villages (SOLKAS)
Accredted Entity: Save the Children Australia
Submission Version 9 - April 25th 2023
[6 empty] | Project Year 1 |  |  |  | Project Year 2 |  |  |  | Project Year 3 |  |  |  | Project Year 4 |  |  |  | Project Year 5 |  |  |  | Project Year 6 |  |  |  | 2029
COMPONENTS/ OUTPUTS | DESCRIPTION | Milestone or Deliverable | Deliverable Number | By what date | 2023 |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
[6 empty] | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec
[6 empty] | Q3 2023 | Q4 2023 | Q1 2024 | Q2 2024 | Q3 2024 | Q4 2024 | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028 | Q1 2029 | Q2 2029 | Q3 2029 | Q4 2029
Staff hiring/PMU establishment
Component 1 | Community, school and youth stakeholders have increased understanding of climate change and the ability to develop and implement locally-relevant adaptation plans
Ouput 1.1 | Children, youth and communities understand the implications of climate change for schools and villages
Activity 1.1.1 | Increase school children's understanding of current climate change impacts and future risks (including curriculum materials and teacher training)
| 1.1.1.1 Assessment of existing efforts to integrate climate change into the curriculum and international best practice approaches | Assessment report | 1 | Q3 2023 |  | 1
| 1.1.1.2 Development (with MEHRD) of climate change micro-learning modules for students, for integration into school curriculum | Micro-learning modules published | 2 | Q3 2024 | [5 empty] | 2
| 1.1.1.3 Development of teacher training materials | Teacher training materials published | 3 | Q3 2024 | [5 empty] | 3
| 1.1.1.4 Pilot testing of teacher training | Pilot testing completed | 4 | Q4 2024 | [6 empty] | 4
| 1.1.1.5 Pilot testing of student curriculum materials | Pilot testing completed | 5 | Q4 2024 | [6 empty] | 5
| 1.1.1.6 Review of pilot testing and refinement of materials | Materials revised | 6 | Q4 2024 | [6 empty] | 6
Activity 1.1.2 | Increase children and community members’ capacity to understand and identify climate change and disaster risks at the local level, including to food security and nutrition
| 1.1.2.1 Development of locally relevant SBC/IEC materials to support community education (using inputs from activity 1.1.1,1.1.3, 1.3.3) | Materials published | 7 | Q4 2024 | [6 empty] | 7
| 1.1.2.2 Roll out of community education sessions (see also 1.33) | Community education sessions delivered | 8 | Q3 2028 | [21 empty] | 8
Activity 1.1.3 | Increase access to and use of climate information and early warning systems at the local level
| 1.1.3.1 Conduct review of existing access to EWS in high-risk communities (disaggregated by sex, age, disability, language/dialects etc) | Review report published | 9 | Q4 2023 |  |  | 9
| 1.1.3.2 Enhance community connectivity and EWS infrastructure where gaps exist (installation of small rooftop satellite dishes with solar PV/battery) and establish system for DRCs to on-sell data capacity to cover costs. Plus three Automatic Weather Stations | Installation of EWS systems and automatic weather stations complete | 10 | Q1 2025 | [7 empty] | 10
| 1.1.3.3 Support DRCs to develop/update EWS protocols and communications strategies (including training on CBDRM and effective responses to hazards) and ensure that warning systems reach all community members (last mile) | EWS protocols and communications strategies completed | 11 | Q3 2025 | [9 empty] | 11
| 1.1.3.4 Deliver CIS products and materials to communities from MECDM/NDMO identifying opportunities to further extend tailored materials for community-level use in target communities | CIS products delivered to communities | 12 | Q1 2029 | [23 empty] | 12
| 1.1.3.5 Disseminate climate information to target communities through a range of media, including printed materials, social media, text messages and radio (e.g. radio, drama) | Climate information disseminated | 13 | Q1 2028 | [5 empty] | 13 | [6 empty] | 13 | [6 empty] | 13
Activity 1.1.4 | Train DRCs in gender equality and disability inclusion as it relates to climate change adaptation and project implementation e.g., data collection, analysis, mainstreaming and inclusion
| 1.1.4.1: Gender Equality and Disability Inclusion training package developed (to be used for activity 2.1.4 also) | Training package published | 14 | Q4 2023 |  |  | 14
| 1.1.4.2 Deliver trainings | Gender Equality and Disability Inclusion training delivered | 15 | Q1 2025 | [7 empty] | 15
Output 1.2. | Inclusive local adaptation action plans are developed by schools and communities
Activity 1.2.1 | Increase school and community understanding of immediate locally relevant climate and disaster risks via school and community climate and disaster risk assessments
| 1.2.1.1 Support targeted schools to undertake annual climate and disaster risk assessments, via the School Climate and Disaster Risk Assessment app (developed under activity 3.1.2 and with inputs from activity 1.1.3) | Annual climate and disaster risk assessments completed | 16 | Q1 2029 |  |  |  |  | 16 |  |  | 16 |  |  |  | 16 |  |  |  | 16 |  |  |  | 16 |  |  |  | 16
| 1.2.1.2 Support DRCs in targeted communities to lead community assessments, via the Community Climate and Disaster Risk Assessment app (developed under activity 3.1.1) | Annual climate and disaster risk assessments completed | 17 | Q1 2029 |  |  |  |  | 17 |  |  | 17 |  |  |  | 17 |  |  |  | 17 |  |  |  | 17 |  |  |  | 17
Activity 1.2.2 | Support inclusive adaptation planning processes in schools and communities
| 1.2.2.1 Support participatory adaptation planning processes in targeted schools, via the School Resilience Planning app (developed under activity 3.1.2 with inputs from activity 1.2.1) | Annual adaptation plans completed | 18 | Q1 2029 |  |  |  |  | 18 |  |  | 18 |  |  |  | 18 |  |  |  | 18 |  |  |  | 18 |  |  |  | 18
| 1.2.2.2 Support DRCs to lead participatory adaptation planning processes in targeted communities, via the Community Resilience Planning app (developed under activity 3.1.1 and with inputs from activity 1.2.1 ) | Annual adaptation plans completed | 19 | Q1 2029 |  |  |  |  | 19 |  |  | 19 |  |  |  | 19 |  |  |  | 19 |  |  |  | 19 |  |  |  | 19
| 1.2.2.3 Schools key 3 years structural/infrustructural/environmental priority activities will be submitted for validation by DRCs and by MEHRD at provincial level, implementaion by SOLKAS and future projects | 3 year plans submitted | 20 | Q2 2027 | [5 empty] | 20 | [10 empty] | 20
| 1.2.2.4 Community Resilience Plans, including key priority activities for implementation by SOLKAS and future projects will be finalised and validate by community members and ward and provincial officials and update on a 3-year cycle | 3 year plans submitted | 21 | Q2 2027 | [5 empty] | 21 | [10 empty] | 21
Output 1.3 | Youth have increased skills for resilient livelihoods
Activity 1.3.1 | Support youth to effectively engage with local level adaptation planning processes
| 1.3.1.1 Work with NDMO and MPGIS to revise the village and ward DRC terms of reference to mandate youth representation | DRC Terms of Reference updated | 22 | Q3 2024 | [5 empty] | 22
| 1.3.1.2 Work with MERHD and schools for systematic engagement of children and youth in school safety and resilience | School Committee terms of reference updated | 23 | Q4 2028 | [22 empty] | 23
| 1.3.1.3 Support DRCs in targeted villages and wards to engage youth and allocate roles | DRC terms of reference updated | 24 | Q4 2028 | [22 empty] | 24
| 1.3.1.4 Develop targeted training for youth DRC and School Committee members on effective engagement in adaptation planning and implementation | Training package complete | 25 | Q3 2024 | [5 empty] | 25
| 1.3.1.5 Roll out training for youth DRC members and school committees | Training for youth DRC members and school committees completed | 26 | Q3 2027 | [5 empty] | 26 |  |  |  | 26 |  |  |  | 26 |  |  |  | 26
| 1.3.1.6 Mentoring sessions to support empowerment of girls focused on confidence building and leadership skills for adapatation | Mentoring sessions completed | 27 | Q3 2027 | [5 empty] | 27 |  |  |  | 27 |  |  |  | 27 |  |  |  | 27
| 1.3.1.7 Establish a DRC network to share experiences and build capacity | Network established | 28 | Q4 2027 | [18 empty] | 28
Activity 1.3.2 | Support youth to develop skills for resilient livelihoods in a changing climate
| 1.3.2.1 Initial and ongoing scanning of private sector to assess opportunities to link with youth entrepreneurs for livelihood resilience | Initial scan complete, ongoing monitoring process established | 29 | Q4 2026 | [14 empty] | 29
| 1.3.2.2 Review of existing training packages in Solomon Islands and the region targeted at approprate and relevant climate resilient rural livelihoods skills development, with emphasis on climate resilience and business management especially financial managment, marketing and digital solutions | Review report complete | 30 | Q4 2024 | [6 empty] | 30
| 1.3.2.3 Develop ‘flipped classroom’ and ‘micro learning’ model trainings on key issues (including climate-resilient agriculture, fisheries and livestock processes, food preservation and processing, natural resource management and nature-based solutions, non-timber forest product development, native cash cropping, etc and (link to opportunities identified in 1.3.2.1) | Training packages complete | 31 | Q3 2025 | [9 empty] | 31
| 1.3.2.4 Roll out training packages to youth in targeted communities | Trainings complete | 32 | Q2 2027 | [16 empty] | 32
| 1.3.2.5 Engage interested youth in the Youth Climate Resilient Livelihoods Incubator (under activity 2.3.1) | Outreach report submitted | 33 | Q2 2027 | [16 empty] | 33
Activity 1.3.3 | Support children and youth to develop knowledge and skills for household, school and community resilience in a changing climate
| 1.3.3.1 Roll-out children and youth-led implementation of Family Safety and Resilience Plan using FSRP App. | Roll out complete | 34 | Q3 2028 | [21 empty] | 34
| 1.3.3.2 Generate evidence on nudges and incentives to maximise behaviour change for safety and resilience at household, schools and community level | Evidence report complete | 35 | Q4 2027 | [18 empty] | 35
| 1.3.3.3 Ward and Provincial level aggregated reports provide inputs to DRCs for community-level planning | Aggregated reports produced | 36 | Q1 2028 | [11 empty] | 36 |  |  |  | 36 |  |  |  | 36
Component: 2 | Communities and schools increase climate resilience via upgraded infrastructure, increased knowledge, enhanced food and water security, and sustainable livelihoods
Output 2.1 | School buildings are retrofitted to address identified climate risks
Activity 2.1.1 | Support the implementation of School Climate and Disaster Resilience Plans
| 2.1.1.1 Use school resilience App annually for action planning at school level (using the digital toolset developed in activity 3.1.2) | Annual adaptation plans completed | 37 | Q1 2029 | [7 empty] | 37 |  |  |  | 37 |  |  |  | 37 |  |  |  | 37 |  |  |  | 37
| 2.1.1.2 Support MEHRD with development and roll out of micro-learning modules for training on schools safety and educational continuity management | Roll out complete | 38 | Q1 2029 | [23 empty] | 38
| 2.1.1.3 Support MERHD and NDMO to identify key priorities for school safety and resilience planning at Provincial and National levels | Workshop report published | 39 | Q4 2027 | [10 empty] | 39 | [7 empty] | 39
Activity 2.1.2 | Support schools to increase physical resilience to the impacts of extreme weather and climate change (retrofitting and additions)
| 2.1.2.1 Physical infrastructure risk/resilience assessment undertaken annually (in conjunction with the school climate and disaster risk assessment under activity 1.2.1) | Annual physical infrastructure reports | 40 | Q1 2029 |  |  |  |  | 40 |  |  | 40 |  |  |  | 40 |  |  |  | 40 |  |  |  | 40 |  |  |  | 40
| 2.1.2.2 Resilient infrastructure retrofits undertaken in accordance with validated plans and priorities | Retrofits complete | 41 | Q2 2027 | [16 empty] | 41
| 2.1.2.3 School WASH systems upgraded to increase climate resilience | Upgraded WASH systems installed | 42 | Q2 2027 | [16 empty] | 42
| 2.1.2.4 Solar PV systems installed at schools to increase access to energy for learning | Solar PV systems installed | 43 | Q2 2027 | [16 empty] | 43
Output 2.2 | School children have access to climate change curriculum materials
Activity 2.2.1 | Support use of climate change curriculum materials in targeted schools
| 2.2.2.1 Teacher training for climate change micro-learning modules developed in activity 1.1.1 rolled out across targeted schools | Modules complete and rolled out | 44 | Q2 2027 | [16 empty] | 44
| 2.2.2.2 Formal and informal curriculum materials developed in activity 1.1.1 rolled out in targeted schools | Curriculum materials complete and rolled out | 45 | Q4 2028 | [22 empty] | 45
| 2.2.2.3 Evaluate materials and implementation progress in year four | Evaluation report published | 46 | Q2 2027 | [16 empty] | 46
| 2.2.2.4 Update materials, if needed, based on review | Materials updated | 47 | Q2 2027 | [16 empty] | 47
Activity 2.2.2 | Provide Gender Equality, Disability and Social Inclusion capacity strengthening support to MEHRD and NDMO
| 2.2.2.1 3-day training on theoretical underpinnings and practical approaches to gender equality and disability inclusion in climate change adaptation and disaster risk reduction | Training delivered | 48 | Q1 2024 |  |  |  | 48
| 2.2.2.2 Identification of GESI focal points within MEHRD and NDMO | Focial points identified | 49 | Q1 2024 |  |  |  | 49
| 2.2.2.3 Peer to peer learning among relevant government departments on GESI with progress workshop held | Workshop held | 50 | Q1 2029 | [23 empty] | 50
Output 2.3 | Communities improve yields from small-scale agriculture and fisheries, and water storage capacity
Activity 2.3.1 | Support application of locally-led climate resilient agriculture innovations
| 2.3.1.1 Confirm and document what existing and traditional men and women agricultural practices exist in each target community and their seasonal calendar (in combination with activity 1.2.2) | Traditional agricultural practices report completed | 51 | Q2 2024 |  |  |  |  | 51
| 2.3.1.2 Climate driven risks to agriculture resources integrated into community adaptation planning processes (with activity 1.2.2) | Annual adaptation plans completed | 52 | Q1 2029 |  |  |  |  | 52 |  |  | 52 |  |  |  | 52 |  |  |  | 52 |  |  |  | 52 |  |  |  | 52
| 2.3.1.3 Identify, adapt and or develop gender sensitive and socially inclusive training materials on climate-resilient agriculture and water conservation techniques that will best suit changing conditions – including intercropping, seed selection, grafting techniques and planting, management (in combination with activity 1.3.2) | Revised climate-resilient agriculture materials published | 53 | Q2 2025 | [8 empty] | 53
| 2.3.1.4 Conduct training on climate-resilient agriculture techniques tailored to men and women roles at community level | Trainings complete | 54 | Q2 2026 | [12 empty] | 54
| 2.3.1.5 Establish field demonstrations of climate-resilient agriculture techniques tailored to men's and women's (including traditional methods where appropriate) | Field demonstration plots established | 55 | Q2 2026 | [12 empty] | 55
| 2.3.1.6 Establish new or support existing nurseries at ward level for raising climate resilient seed stocks, including native food crops varieties, and germinating seedling for food crops | Nurseries established | 56 | Q2 2026 | [12 empty] | 56
| 2.3.1.7 Distribute resilient native food crops planting materials (simple agricultural tools) to men and women farmers, including identified, locally-appropriate climate-resilient varieties of: fruit and nut trees, coconut, vegetables | Resilient native crops and tools distributed | 57 | Q3 2028 | [9 empty] | 57 |  |  |  | 57 |  |  |  | 57 |  |  |  | 57
Activity 2.3.2 | Establish/scale-up community, school and home-based kitchen gardens for enhanced nutrition utilizing climate-resilient crops
| 2.3.2.1 Deliver family-based nutrition education based on local food and kitchen gardens with diversified, climate-resilient crops and training to promote nutrition and greater use of traditional foods | Nutrition education trainings completed | 58 | Q3 2028 | [12 empty] | 58 |  |  |  |  | 58 |  |  |  | 58
| 2.3.2.2 Distribute seeds, seedlings and plants to schools, communities and households to facilitate seed exchanges and seed saving to increase local independence and resilience | Seeds, seedlings and plants distributed | 59 | Q3 2028 | [9 empty] | 59 |  |  |  | 59 |  |  |  | 59 |  |  |  | 59
| 2.3.2.3 Establish demonstration training gardens in schools and communities to raise vegetable and tree seedlings for increased climate resilient nutrition | Demonstration gardens established | 60 | Q2 2026 | [12 empty] | 60
Activity 2.3.3 | Support climate-resilient adaptations to local fisheries for food security
| 2.3.3.1 Engage communities (50%M 50%W) to determine coastal habitat and resource conditions and threats (in combination with activity 1.2.2) | Consultations completed | 61 | Q1 2029 |  |  |  |  | 61 |  |  | 61 |  |  |  | 61 |  |  |  | 61 |  |  |  | 61 |  |  |  | 61
| 2.3.3.2 Risks to fisheries resources integrated into community adaptation planning processes (with activity 1.2.2) | Annual adaptation plans completed | 62 | Q1 2029 | [23 empty] | 62
| 2.3.3.3 Develop a locally appropriate and scalable coastal resource management training program that includes key capacity areas: the effects of fishing, habitat management tools, monitoring and sustainable self-governance (in combination with activity 1.3.2) | Training program completed | 63 | Q2 2025 | [8 empty] | 63
| 2.3.3.4 Conduct training on climate-resilient fisheries and coastal resource management techniques at community level to suit men and women's different roles in fishing and CRM | Training completed | 64 | Q2 2026 | [12 empty] | 64
| 2.3.3.5 Support community-level implementation of climate-resilient fisheries management and development of locally appropriate governance mechanisms | Field assessment reports completed | 65 | Q4 2028 | [22 empty] | 65
| 2.3.3.6 Support diversification and sustainability of fisheries resources (alleviating pressures on inshore fisheries) by providing off-shore fishing equipment in targeted communities | Off-shore fishing equipment delivered | 66 | Q4 2026 | [14 empty] | 66
Activity 2.3.4 | Support application of village climate resilient water resource management techniques and technologies
| 2.3.4.1 Engage communities (50%M 50%W 50%PWD) to determine key climate risks to water resources (in combination with activity 1.2.1) | Workshops completed | 67 | Q2 2024 |  |  |  |  | 67
| 2.3.4.2 Risks to water resources integrated into community adaptation planning processes (with activity 1.2.2) | Annual adaptation plans completed | 68 | Q1 2029 |  |  |  |  | 68 |  |  | 68 |  |  |  | 68 |  |  |  | 68 |  |  |  | 68 |  |  |  | 68
| 2.3.4.3 Support implementation of priority adaptation actions, including; stabilization and afforestation of stream banks to prevent erosion and siltation of reefs, riparian habitat restoration, rainwater harvesting and storage in existing building footprint, improved efficiency of water access points and introduction of deficit irrigation techniques | Field assessment reports completed | 69 | Q2 2027 | [16 empty] | 69
Activity 2.3.5 | Strengthen agriculture extension worker service to support women’s roles in agriculture
| Activity 2.3.5.1 Conduct analysis of gender differences in access to extension services, technology adoption and agricultural productivity | Analysis published | 70 | Q4 2023 |  |  | 70
| Activity 2.3.5.2 Disseminate findings of analysis and hold action planning workshop | Workshop completed | 71 | Q1 2024 |  |  |  | 71
| Activity 2.3.5.3 Develop strategy for improving agricultural services to account for gender differences in agricultural roles and access to extension services and agricultural inputs | Strategy published | 72 | Q2 2024 |  |  |  |  | 72
| Activity 2.3.5.4 Develop training module on gender-responsive extension and advisory services | Training module published | 73 | Q4 2024 | [6 empty] | 73
| Activity 2.3.5.5 Train agricultural extension workers, and others involved in ag extension programmes, in GEDSI considerations esp. responding to women’s needs. | Trainings complete | 74 | Q2 2025 | [8 empty] | 74
Output 2.4 | Targeted youth develop sustainable livelihood opportunities
Activity 2.4.1 | Establish and scale Youth Climate Resilient Livelihoods Incubator
| 2.4.1.1 Identify best practice youth/girls entrepreneurship models in the region | Report published | 75 | Q4 2024 | [6 empty] | 75
| 2.4.1.2 Identify diverse young men and women's priorities and challenges for entrepreneuship | Report published | 76 | Q2 2025 | [8 empty] | 76
| 2.4.1.3 Work with key partners to develop incubator model suitable for the context based on evidence from current and past youth entrepreneurship efforts in Solomon Islands and the region | Incubator model design complete | 77 | Q2 2025 | [8 empty] | 77
| 2.4.1.4 Pilot in a sub-set of target communities and revise as necessary | Pilot testing completed | 78 | Q3 2025 | [9 empty] | 78
| 2.4.1.5 Scale model out to all targeted communities | Roll out complete | 79 | Q2 2028 | [20 empty] | 79
| 2.4.1.6 Undertake outreach in targeted communities to help youth generate innovative livelihood ideas for the incubator that are viable and respond to market opportunities (as identified in 1.3.2.1) | Outreach report submitted | 80 | Q2 2028 | [20 empty] | 80
| 2.4.1.7 Incubator 'challenges' held for key sectors to identify new ideas | 5 challenges completed | 81 | Q2 2028 | [20 empty] | 81
| 2.4.1.8 Youth incubator ‘ideation bootcamps’ held in regional centres /Honiara | Bootcamps completed | 82 | Q2 2028 | [20 empty] | 82
Activity 2.4.2 | Support youth to access new/emerging resilient livelihoods opportunities within and beyond communities
| 2.4.2.1 Challenge finalists supported with training (with activity 1.3.2), mentoring and facilitating connections to markets | Training, mentoring, and network activities completed | 83 | Q4 2028 | [22 empty] | 83
| 2.4.2.2 Challenge finalists pitch ideas to an expert panel and winners are selected | Pitch sessions completed | 84 | Q2 2028 | [14 empty] | 84 |  |  | 84 |  |  | 84
| 2.4.2.3 Work with partners to expand Incubator model beyond the project targeted areas | Partnership agreements in place | 85 | Q4 2028 | [22 empty] | 85
| 2.4.2.4 Link youth entrepreneurs with each other via virtual and/or analogue platforms and/or event | Platforms established | 86 | Q4 2028 | [22 empty] | 86
Component 3 | Communities and schools are making data-driven adaptation decisions, are supported by sub-national government with enhanced capacity, and have more climate resilient livelihoods
Output 3.1 | Climate Resilience Info Management System is used by schools and communities to make climate informed decisions
Activity 3.1.1 | Co-develop and deploy Climate Resilience Information Management digital toolset suite for data-driven community climate adaptation planning and decision-making
| 3.1.1.1 Global best practice for co-development of digital toolsets (includes participatory needs analysis) | Report published | 87 | Q3 2023 |  | 87
| 3.1.1.2 Four toolset modules co-developed, piloted and refined under MECDM leadership (Phase 1) | Four modules published | 88 | Q2 2024 |  |  |  |  | 88
| 3.1.1.3 Four toolset modules deployed and evaluated under MECDM leadership (Phase 2) | Four modules evaluated | 89 | Q2 2025 | [8 empty] | 89
| 3.1.1.4 Four toolset modules revised and scaled up, under MECDM leadership (Phase 3) | Four modules revised | 90 | Q4 2028 | [22 empty] | 90
| 3.1.1.5 Ward, province and national stakeholders are trained in effective use of community-based inputs for data-driven planning decision-making and resource allocation for community-based climate adaptation | Trainings complete | 91 | Q2 2026 | [12 empty] | 91
Activity 3.1.2 | Co-develop and deploy Climate Resilience Information Management digital toolsets for data-driven school-based climate adaptation planning and decision-making
| 3.1.2.1 Two toolset modules are co-developed, piloted and refined under MEHRD leadership (Phase 1) | Two modules published | 92 | Q2 2024 |  |  |  |  | 92
| 3.1.2.2 Two toolset modules deployed and evaluated under MEHRD leadership (Phase 2) | Two modules evaluated | 93 | Q2 2025 | [8 empty] | 93
| 3.1.2.3 Two toolset modules are revised and scaled up, under MEHRD leadership (Phase 4) | Two modules revised | 94 | Q4 2028 | [22 empty] | 94
| 3.1.2.4 Provincial and national stakeholders trained in use of school-based inputs for data-driven planning decision-making and resource allocation for school based climate adaptation and resilience. | Trainings complete | 95 | Q2 2026 | [12 empty] | 95
Activity 3.1.3 | Utilize project experience developing/deploying digital toolsets to inform future locally-led adaptation
| 3.1.3.1 Aggregated climate risk and adaptation action data from targeted communities and schools are utilized to identify common challenges and trends to inform government/donor supported planning and action in targeted non-targeted communities | Aggregated reports produced | 96 | Q4 2028 | [22 empty] | 96
| 3.1.3.2 Aggregated data on climate risks assessment and adaptation planning processes for community and schools will inform locally - led adaptation globally via development of knowledge products and engagement in key forums | Aggregated reports produced | 97 | Q4 2028 | [22 empty] | 97
| 3.1.3.3 Open source digital toolset suite materials are made available for adaptation and use in other projects/contexts (including future Save the Children projects) | Digital toolset materials published | 98 | Q4 2028 | [22 empty] | 98
Output 3.2 | Ward institutions have knowledge and skills to support to community adaptation
Activity 3.2.1 | Support targeted Wards and Provinces to adopt adaptive governance systems and develop adaptation plans
| 3.2.1.1 Consolidate and synthesise community analyses (from activities 1.2.1 and 1.2.2) to develop Ward level vulnerability mapping to inform planning and adaptation action | Vulnerability mapping published | 99 | Q2 2028 | [8 empty] | 99 |  |  |  | 99 |  |  |  | 99 |  |  |  | 99
| 3.2.1.2 Identify and address gaps in the integration of climate risks and adaptation actions into Ward planning and budgeting processes | Ward plans and budgets finalised | 100 | Q3 2025 | [9 empty] | 100
| 3.2.1.3 Provide training and capacity building to Ward representatives and technical advisory groups on the integration of climate change risks and adaptation actions into planning and budgeting processes (including gender-based risks of climate change and gender responsive budgeting) | Trainings complete | 101 | Q2 2026 | [12 empty] | 101
| 3.2.1.4 Provide technical assistance/ resources to subnational officials to undertake new/ updated assessments of climate and disaster risk to inform Ward development plans and budgets | Technical assistance delivered | 102 | Q3 2028 | [9 empty] | 102 |  |  |  | 102 |  |  |  | 102 |  |  |  | 102
| 3.2.1.5 Facilitate linkages between Ward Development Plans and Community Adaptation Plans to avoid duplication or contradictions, and ensure consistent planning and budgeting | Technical assistance delivered | 103 | Q3 2028 | [9 empty] | 103 |  |  |  | 103 |  |  |  | 103 |  |  |  | 103
| 3.2.1.6 Provide technical assistance/resources to local and Ward government to assess gender gaps through gender-responsive and inclusive climate change budgeting and planning | Technical assistance delivered | 104 | Q3 2028 | [9 empty] | 104 |  |  |  | 104 |  |  |  | 104 |  |  |  | 104
Activity 3.2.2 | Ongoing stakeholder engagement
| Project Inception Workshop (national) | Inception workshop completed | 105 | Q4 2023 |  |  | 105
| Project Inception Workshops (provincial x 5) | Inception workshops completed | 106 | Q4 2023 |  |  | 106
| Annual province workshops (provincial x 5) | Workshops completed | 107 | Q1 2028 | [7 empty] | 118 |  |  |  | 118 |  |  |  | 118 |  |  |  | 107
Activity 3.2.3 | Capture lessons learned, emerging themes and best practices at the community level to ensure sub-national and national planning processes are informed by local needs and that local actions support national objectives
| 3.2.3.1 Produce knowledge management products that capture and emphasise local needs of diverse groups including for men/women/youth/person with disabilities to national stakeholders directly involved in the production of high-level adaptation planning processes (Updated NDC, NAP development, UNFCCC reporting) | Knowledge management products published | 108 | Q4 2028 | [22 empty] | 108
| 3.2.3.2 Facilitate participation of communities and Wards in national and regional forums (Pacific Resilience Partnership, PIFS side events, national climate change conferences/events, other CBA/GCF project meetings) supported by governments and development partners | National and regional forums attended | 109 | Q4 2028 | [22 empty] | 109
| 3.2.3.3 Facilitate visibility and engagement of senior officials through project site visits | Project sites visited | 110 | Q3 2028 | [5 empty] | 120 |  |  |  | 120 |  |  |  | 120 |  |  |  | 120 |  |  |  | 110
| 3.2.3.4 Disseminate knowledge management products (participatory tools, videos, project reports, technical toolkits) that are translated in national languages to encourage meaningful consideration and usage at local level | Knowledge management products distributed | 111 | Q4 2028 | [22 empty] | 111
| 3.2.3.5 Increase the global adaptation knowledge base by linking project outcomes to national, regional and global processes | Linkages facilitated | 112 | Q4 2028 | [22 empty] | 112
Output 3.3 | Youth launch climate resilient livelihood options
Activity 3.3.1 | Facilitate youth entrepreneur matchmaking with private sector actors
| 3.3.1.1 Engage with private sector partners interested in engaging with Incubator on sector challenge areas as buyer or suppliers identified in 1.3.2.1 | Engagement reports submitted | 113 | Q2 2028 | [20 empty] | 113
| 3.3.1.2 Support private sector partners in fine-tuning their business model, supply chain or distribution to facilitate youth and women entrepreneur inclusion | Technical assistance delivered | 114 | Q2 2028 | [20 empty] | 114
| 3.3.1.3 Incubator-supported youth with viable resilient livelihoods ideas matched with potential private sector partners to establish/scale | Partnerships facilitated | 115 | Q4 2028 | [22 empty] | 107
Activity 3.3.2 | Provide seeding support to scale up incubated ideas
| 3.2.2.1 Identify most viable livelihood ideas under each challenge and provide further seed support to scale up businesses | Idea assessment process completed | 116 | Q4 2028 | [22 empty] | 116
| 3.2.2.2 Support most viable livelihood generators to engage with other youth by becoming Incubator Champions and mentors | Champions identified | 117 | Q4 2028 | [22 empty] | 117
Monitoring and evaluation
| Ongoing project monitoring | APR submitted | 118 | Q2 2029 |  |  | 110 |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  |  | 110 |  |  | 118
| Inception report | Inception report published | 119 | Q4 2023 |  |  | 119
| Annual performace reporting | APR submitted | 120 | Q4 2029 | [5 empty] | 114 |  |  |  | 114 |  |  |  | 114 |  |  |  | 114 |  |  |  | 114 |  |  |  |  | 120
| Baseline | Baseline report submitted | 121 | Q4 2023 |  |  | 121
| Midline | Midline report submitted | 122 | Q3 2026 | [13 empty] | 122
| Endline | Endline report submitted | 123 | Q3 2029 | [25 empty] | 123
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.