## Annex 2b_SAP_FP_SCA_SLE_SLCRP
Annex 2b | Implementation Timetable
Project Title | Sierra Leone Coastal Resilience Project (SLCRP)
Accredited Entity | Save the Children Australia
Version | Final - 29 January 2024
Activity | Description | Milestone or Deliverable | Deliverable Number | By what Quarter | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6
[5 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1 | Community mainstreaming of climate change adaptation through governance, partnerships, education and training
Outcome 1 | Coastal communities and institutions have governance structures, plans, knowledge skills and solutions in place to undertake local adaptation to climate change
Output 1.1 | Strengthened community structures, coastal governance platforms and Community Adaptation Plans (CAPs)
Activity 1.1.1 | Identify existing or establish new community structures for participatory climate responsive planning | Eligibility criteria confirmed and communities for implementation selected | 1 | Q1 Year 1 | bar: Year 1 Q1
|  | Beneficiaries selected for community-level activities | 2 | Q2 Year 1 | Year 1 Q2: 2
|  | Community Adaptation Committees (CACs) in 75 communities strengthened or established. | 3 | Q3 Year 1 | Year 1 Q3: 3
Activity 1.1.2 | Build capacity at community level for climate-responsive planning and development | 1,125 people trained on climate responsive planning and development. | 4 | Q2 Year 3 | Year 3 Q2: 4
|  | Out-of-school clubs for adolescent girls and boys established in 75 communities. | 5 | Q2 Year 5 | Year 5 Q2: 5
Activity 1.1.3 | Co-design Community Adaptation Plans (CAPs) | 75 Community Adaptation Plans (CAPs) developed. | 6 | Q2 Year 2 | Year 2 Q2: 6
Activity 1.1.4 | Establish Coastal Governance Platforms | Terms of reference for Coastal Governance Platforms finalised. | 7 | Q3 Year 2 | Year 2 Q3: 7
|  | 5 Coastal Governance Platforms established (one per district). | 8 | Q3 Year 2 | Year 2 Q3: 8
Output 1.2 | Integration of Community Adaptation Plans into Local/District Development Plans and strengthened capacity of national and sub-national government for implementing adaptation initiatives | bar: Year 1 Q2 to Year 5 Q2
Activity 1.2.1 | Develop capacity at national and subnational government levels for climate-responsive planning and development | Government capacity-building plan finalised. | 9 | Q3 Year 1 | Year 1 Q3: 9
|  | 210 government officials trained on delivering and monitoring climate change projects. | 10 | Q3 Year 1 | Year 1 Q3: 10
|  | Mechanism for last-mile dissemination of early warning developed and implemented. | 11 | Q2 Year 5 | Year 5 Q2: 11
Activity 1.2.2 | Incorporate Community Adaptation Plans into local and district development plans | 5 district development plans include with references to CAPs. | 12 | Q4 Year 3 | Year 3 Q4: 12
Output 1.3 | Small-scale WASH infrastructure (rainwater harvesting, filtration and solar hot water systems) installed and climate-resilient WASH and nutrition practices used by communities, especially women and children | bar: Year 1 Q3 to Year 5 Q2
Activity 1.3.1 | Equip communities with climate-resilient health and nutrition knowledge and skills, with a specific focus on women and children | Vulnerability assessments conducted in 75 communities. | 13 | Q4 Year 1 | Year 1 Q4: 13
|  | 13,500 people trained on WASH, health and nutrition. | 14 | Q2 Year 5 | Year 5 Q2: 14
Activity 1.3.2 | Implement climate-resilient domestic WASH solutions in communities, with a specific focus on women and children | WASH solutions installed in 75 communities | 15 | Q2 Year 5 | Year 5 Q2: 15
|  | Rainwater harvesting systems installed in 75 communities. | 16 | Q1 Year 5 | Year 5 Q1: 16
Output 1.4 | Small-scale infrastructure (incl. rainwater harvesting and solar power), climate change education and disaster risk reduction measures for schools | bar: Year 1 Q3 to Year 5 Q2
Activity 1.4.1 | Design and implement climate change education curriculum in primary schools | New climate change module finalised. | 17 | Q1 Year 2 | Year 2 Q1: 17
|  | 420 education officials, teachers and volunteer teachers trained on climate change module. | 18 | Q2 Year 5 | Year 5 Q2: 18
Activity 1.4.2 | Support district and school authorities to implement the Resilient Schools programme, including climate change planning and disaster risk management | Climate resilience incorporated into school safety plans in 75 schools. | 19 | Q4 Year 2 | Year 2 Q4: 19
|  | School disaster risk reduction manual rolled out in 75 schools. | 20 | Q4 Year 3 | Year 3 Q4: 20
|  | 75 schools equipped with climate-resilient infrastructure. | 21 | Q2 Year 5 | Year 5 Q2: 21
Component 2 | Enhanced climate resilience of food production systems and value chains to secure food and livelihoods, especially for women, youth and children
Outcome 2 | Coastal communities have climate-resilient farming, fishing and alternative livelihoods and businesses
Output 2.1 | Technologies, equipment, inputs, plans and practices for climate-resilient farming, fishing and alternative livelihoods | bar: Year 1 Q3 to Year 5 Q2
Activity 2.1.1 | Map needs for livelihood improvement and diversification in different communities and develop action plans for Sustainable Livelihoods | Livelihoods action plans completed in 75 communities. | 22 | Q4 Year 1 | Year 1 Q4: 22
Activity 2.1.2 | Enable communities to implement climate-resilient livelihoods through training and improved practices, inputs and technologies | 150 lead farmers and 300 lead fishers or fish preservation practitioners trained. | 23 | Q2 Year 5 | Year 5 Q2: 23
|  | Livelihood circles delivered by lead farmers or fish practitioners in 75 communities. | 24 | Q2 Year 5 | Year 5 Q2: 24
|  | Climate-resilient agricultural, fishing and fish preservation technologies provided to 75 target communities. | 25 | Q2 Year 5 | Year 5 Q2: 25
Activity 2.1.3 | Enable fishers, farmers and other community members to improve financial management to develop their livelihoods | 1 new VSLA group established in 75 communities. | 26 | Q4 Year 2 | Year 2 Q4: 26
|  | VSLA trainings delivered to 1,875 people. | 27 | Q1 Year 5 | Year 5 Q1: 27
Activity 2.1.4 | Enable access to climate-resilient water harvesting and storage to support livelihoods. | Water harvesting and storage technology provided in 75 communities. | 28 | Q3 Year 4 | Year 4 Q3: 28
|  | 450 people trained in operating and maintaining of agricultural water harvesting equipment. | 29 | Q3 Year 4 | Year 4 Q3: 29
Output 2.2 | Strengthened business models, skills, equipment and access to financing and markets for youth and women’s enterprises | bar: Year 1 Q4 to Year 2 Q4
Activity 2.2.1 | Equip community members with entrepreneurship and business skills for climate resilient small businesses | 9,000 community members trained on vocational and entrepreneurship skills | 30 | Q2 Year 2 | Year 2 Q2: 30
Activity 2.2.2 | Identify appropriate coastal products, develop business models and improve access to financing | 2,250 community members supported to develop business models for their products. | 31 | Q4 Year 2 | Year 2 Q4: 31
|  | 5 incubator events held. | 32 | Q2 Year 2 | Year 2 Q2: 32
Activity 2.2.3 | Strengthen value chains for existing and new coastal products | Livelihoods and market assessments produced with value chains for coastal products identified in 75 communities. | 33 | Q4 Year 2 | Year 2 Q4: 33
|  | Support to coastal business provided in 75 communities. | 34 | Q2 Year 5 | Year 5 Q2: 34
Component 3 | Ecosystem-based adaptation for coastal protection and natural resources
Outcome 3 | Mangroves are conserved and restored for coastal resilience and communities have increased capacity to co-manage mangroves with government institutions
Output 3.1 | Strengthened capacity of communities and government for climate-resilient mangrove management and alternative technologies and fuel sources that reduce mangrove wood use | bar: Year 1 Q3 to Year 5 Q2
Activity 3.1.1 | Build capacity for community-based mangrove forest management | 75 communities trained on mangrove management | 35 | Q2 Year 2 | Year 2 Q2: 35
|  | Strategy for social and behaviour change towards sustainable use of mangrove wood by communities agreed. | 36 | Q2 Year 5 | Year 3 Q4: 37
|  | Radio awareness campaign on climate-resilient sustainable mangrove rolled out in 5 districts. | 37 | Q2 Year 5 | Year 5 Q2: 37
Output 3.2 | Mangroves conserved and restored via assessments, management plans, planting and monitoring | bar: Year 1 Q3 to Year 5 Q2
Activity 3.2.1 | Develop and implement community-led mangrove conservation plans | Mangrove maps and spatial datasets produced for 75 communities | 38 | Q4 Year 1 | Year 1 Q4: 38
|  | 75 community mangrove management plans developed and integrated into CAPs. | 39 | Q2 Year 2 | Year 2 Q2: 39
Activity 3.2.2 | Community-led ecosystem monitoring and enforcement of by-laws | Mangrove monitoring and data collection protocol agreed. | 40 | Q4 Year 1 | Year 1 Q4: 40
|  | Awareness raising on by-laws conducted in 75 communities. | 41 | Q3 Year 2 | Year 2 Q3: 41
Activity 3.2.3 | Develop strategy for community-led coastal protection | Coastal protection needs assessment produced covering 75 communities. | 42 | Q1 Year 2 | Year 2 Q1: 42
|  | 75 community coastal protection plans developed. | 43 | Q4 Year 2 | Year 2 Q4: 43
Activity 3.2.4 | Restore mangroves and implement community-level strategies for coastal protection | 1 mangrove restoration protocol finalised. | 44 | Q4 Year 2 | Year 2 Q4: 44
|  | 1,000 hectares of mangroves conserved in target areas. | 45 | Q3 Year 2 | Year 2 Q3: 45
|  | 500 hectares of mangroves restored in target areas. | 46 | Q2 Year 5 | Year 5 Q2: 46
Component 4 | Monitoring, Evaluation, Accountability and Learning | bar: Year 1 Q1 to Year 5 Q4
Activity 4.1.1 | Analyse data to inform the project, and conduct routine monitoring to ensure progress by all partners | Inception report published. | 47 | Q2 Year 1 | Year 1 Q2: 47
|  | APR submitted. | 48 | Q2 Year 5 | Year 2 Q1: 48; Year 3 Q1: 48; Year 4 Q1: 48; Year 5 Q1: 48; Year 6 Q1: 48
|  | Final project review and close out held. | 49 | Q4 Year 5 | Year 5 Q4: 49
Activity 4.1.2 | Conduct baseline, mid-term and endline assessments to evaluate and ensure sustainable progress | Baseline report published. | 50 | Q2 Year 1 | Year 1 Q2: 50
|  | Interim evaluation report published. | 51 | Q4 Year 3 | Year 3 Q4: 51
|  | Final evaluation report published. | 52 | Q4 Year 5 | Year 6 Q2: 52