## Timetable
Republic of Madagascar
Increase Resilience to Climate Change of Smallholders Receiving the Services of the Inclusive Agricultural Value Chains Programme Programme (DEFIS +).
IMPLEMENTATION TIMETABLE
Activity |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
|  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20 | Q21 | Q22 | Q23 | Q24
Outcome 1. Strengthened climate resilience of agricultural production systems
Output 1.1. Improved water management for sustainable agriculture
Activity 1.1.1. Protection of irrigation schemes against climate change impacts | bar: 2024 Q4 to 2028 Q20
Activity 1.1.2. Sustainable sub-watersheds (adjacent to irrigated schemes) management and restoration of landscape | bar: 2024 Q4 to 2029 Q24
Activity 1.1.3. Strengthening capacities of Water Users Associations to manage water and apply sustainable water management practices | bar: 2024 Q4 to 2029 Q24
Activity 1.1.4. Construction of climate smart water tanks for drip-irrigation and for small livestock | bar: 2025 Q5 to 2026 Q12
Output 1.2. Enhanced agro-climatic information systems, new technologies and initiatives
Activity 1.2.1. Installation of automated agro-meteorological stations and development of flood and drought monitoring and forecasting system | bar: 2024 Q4 to 2028 Q20
Activity 1.2.2. Capacity building of decentralised government (SRM & DRAEP) | bar: 2024 Q4
Activity 1.2.3. Promotion and dissemination of meteorological and climate smart agriculture practices | bar: 2024 Q4 to 2029 Q24
Activity 1.2.4. Promotion and dissemination of sustainable home technologies and social initiatives | bar: 2024 Q4 to 2029 Q24
Outcome 2. Increased income generation through improved market accessibility
Output 2.1. Reinforced rural access roads
Activity 2.1.1. Reinforcement of unpaved rural access roads to reduce climate change impacts and water collection along these roadways for agricultural use | bar: 2024 Q4 to 2029 Q24
Output 2.2. Improved capacity to build and maintain rural infrastructure | bar: 2024 Q4 to 2029 Q24
Activity 2.2.1. Training on construction standards related to climate change | bar: 2024 Q4 to 2026 Q12
Outcome 3. Improved food and nutrition security
Output 3.1. Knowledge on climate change and food security generated and shared
Activity 3.1.1. Training rural development actors on climate change and food production systems for enhanced nutrition | bar: 2024 Q4
Activity 3.1.2. Exchange visits on climate resilient food systems | bar: 2025 Q5 to 2029 Q24
Activity 3.1.3. Capitalization of best practices and knowledge on food and nutrition security measures | bar: 2024 Q4 to 2029 Q24
Project Coordination and management
Key staff recrutement
Vehicles Procurement
Reporting, monitoring and evaluation
- Annual performance report | bar: 2025 Q5; 2026 Q9; 2027 Q13; 2028 Q17; 2029 Q21
- Joint supervision mission | bar: 2024 Q4; 2025 Q8; 2027 Q15; 2028 Q19
- Interim evaluation and mid-term review | bar: 2026 Q12
- Completion report | bar: 2029 Q22
- Final evaluation | bar: 2029 Q24
100000
143000*4400