## Implementation Plan
|  |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7
Component 1 – Enabling local government support for adaptation and mitigation | 0 | 0 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1.1. Local administrations deploy improved climate knowledge, extension and methodologies to support producers and value chain actors | 0: 0; 0: 0
1.1.1 Develop and deploy innovative and efficient extension methods for disseminating and demonstrating CRLCSA knowledge, technologies and practices in gender-responsive and socially inclusive ways
|  | 1.1.1.1 Stocktaking of extension methods and public and private extension service providers and actors and gaps/needs analysis |  | 12600
|  | 1.1.1.2 Participatory design of innovative and efficient CRLCSA extension methods including the feedback mechanisms between the services recipients and the providers |  |  | 10800
|  | 1.1.1.3 Develop/improve the Standard Operating procedures for the deployment of extension methods in each county |  |  |  | 16800
|  | 1.1.1.4 Regional and county level training for extension and cooperative departments on climate sensitive extension services |  |  |  | 7200
|  | 1.1.1.5 Monitor the effectiveness and efficiency of CRLCSA extension service |  |  |  |  | 16800 |  |  |  | 16800 |  |  |  | 16800 |  |  |  | 16800 |  |  |  | 33600
| 1.1.2 Strengthen the dissemination of climate information services to last-mile users including women, youth and PLWD through cooperatives and Farmer Organizations. | 0
|  | 1.1.2.1 Conduct a stock take and gap analysis of climate information services in each county for the 6 value chains. |  | 16800
|  | 1.1.2.2 Develop new climate information services or products for the 6 value chains in cooperation with National and County Meteorological Department |  |  | 15000
|  | 1.1.2.3 Training for agro-meteorological departments (county level) in the development and delivery of climate information services to FO and cooperatives in the 6 value chains |  |  |  | 21000 |  |  |  |  | 21000
|  | 1.1.2.4 Seasonal planning at the ward level to develop locally relevant and tailored seasonal advisories in the targeted value chains and natural resources management |  |  |  |  | 8400 |  | 0.2 |  | 8400 |  | 0.2 |  | 8400 |  | 0.2 |  | 8400 |  | 0.2 |  | 8400 |  | 0.2
|  | 1.1.2.5 Disseminate timely information on climate impacts and weather forecasts through selected community radio, social media, print channels and extension |  |  |  |  | 49000 | 0.2 | 0.2 | 0.2 | 49000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 1.1.2.6 Monitor reach and level of use for each new product. |  |  |  | 12600 |  |  |  |  | 12600 | [7 empty] | 12600
|  | 1.1.2.7 develop registry of intermediaries of climate information and weather forecast targeting disadvantage groups |  | 8400 | [6 empty] | 3000 | [7 empty] | 3000
| 1.1.3 Develop and test methodologies for decentralized carbon accounting | 0
|  | 1.1.3.1 Conduct a participatory design workshop for selecting and developing a LREB-specific decentralized carbon accounting methodology. |  |  | 15000
|  | 1.1.3.2 Set up the process for data gathering and computation |  |  |  | 12600
|  | 1.1.3.3 Develop operating manuals and guidance documents |  |  |  | 10500
|  | 1.1.3.4. Conduct learning by doing accounting exercises in each county and prepare emissions reports. | [5 empty] | 29400 | [13 empty] | 21000
| 1.1.4 Upgrade and update agricultural databases, crop and productivity datasets, cooperative census | 0
|  | 1.1.4.1 Conduct systems needs assessment and gap analysis for database in each county |  | 18000
|  | 1.1.4.2. Upgrade and update agricultural databases with technical support, draft technical and training guides and reporting schedule for dissemination purposes |  |  | 9000 |  |  | 21000 |  |  |  | 21000
|  | 1.1.4.3. Collect and analyse crop, climate, productivity, market and economic data annually through county extension services and integrate into databases. |  |  |  | 9000 |  |  | 12000 |  |  |  | 12000 |  |  |  | 12000 |  |  |  | 12000 |  |  |  | 12000
|  | 1.1.4.4. Deliver technical assistance to conduct biennial census of cooperatives |  |  |  | 9000 | [7 empty] | 9000 | [8 empty] | 6000
| 1.1.5 Assess eligible climate solutions for the agriculture sector in relation to climate impacts | 0
|  | 1.1.5.1 Training for county climate change units, meteorological departments and agriculture departments on selection of climate solutions. |  |  |  | 15000
|  | 1.1.5.2 Conduct a participatory screening and pre-selection of climate resilient, low carbon solutions and technologies for the 6 Value Chains |  |  |  |  | 21000 | [11 empty] | 21000
| 1.1.6 Share knowledge and lessons learned through existing platforms | #REF!
|  | 1.1.6.1 Identify lessons learned and best practices arising from project implementation |  |  |  | 12000 |  |  |  | 12000 |  |  |  | 12000 |  |  |  | 12000 | [5 empty] | 12000
|  | 1.1.6.2 Develop a project knowledge and learning strategy to be implemented through a suite of knowledge products, fact sheets, studies and reports |  |  |  |  | 18000 |  |  |  | 18000 |  |  |  | 18000 |  |  |  | 18000 | [5 empty] | 27000
1.1.6.3 Hold regular knowledge sharing events on project activities, outputs and components in each county and jointly with the Multi-Stakeholder Climate Change Knowledge Platform and the Council of Governors
Component 2 – Sustainable Resilient Agricultural Landscapes | 0: 0; 0: 0
2.1 Agricultural landscapes are managed under strategies that conserve, restore, and sustainably manage community forest and agriculture land, and reduce emissions
| 2.1.1 Develop county and regional climate-resilient and low-carbon agricultural landscape management strategy and implementation plan, including improved watershed management, land use planning, reforestation and natural regeneration | 0
|  | 2.1.1.1 Conduct an assessment and participatory mapping of landscape degradation in each county |  |  | 39200
|  | 2.1.1.2 Deliver training on climate resilient, low-carbon landscape management for county administrations (forestry, land, agriculture and water departments) |  |  |  | 7000
|  | 2.1.1.3 Develop, with technical assistance, a county climate resilient, low-carbon landscape management strategy |  |  |  | 14700
|  | 2.1.1.4 Raise community awareness of the benefits of ensuring restoration, conservation and sustainable management of their agriculture landscape |  |  |  | 25000 | [5 empty] | 25000
|  | 2.1.1.5 Hold a regional workshop bringing together counties for lessons sharing and development of a regional LMS | [8 empty] | 3000 | 3000
| 2.1.2 Implement and monitor climate-resilient and low-carbon landscape management plans. | 0
|  | 2.1.2.1 Draft implementation and M&E plan and budget for each climate resilient, low-carbon Landscape Management plan (LMP). |  |  |  |  | 84000
|  | 2.1.2.2. Conduct local consultations to develop LMS implementation plans those related to restoration and management of agriculture landscape |  |  |  |  | 42000 | [11 empty] | 42000
|  | 2.1.2.3 Implement the LMS with national budgets (incl. FLLOCA) through fencing/live-fencing, reforestation, afforestation and watershed management or rehabilitation in priority areas in each county. | [8 empty] | 3150000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 2.1.2.4 Implement the LMS with support from county governments in gazetted forests and water towers |  |  |  |  | 230000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 2.1.2.5. Monitor and survey state of landscape management after 5 years (along with the decentralized carbon accounting under 1.1.3) | [19 empty] | 63000
Component 3 – Resilient Livelihoods | 0: 0; 0: 0
3.1 Vulnerable smallholders adopt gender responsive and socially inclusive climate resilient and low –carbon production and processing practices, technologies, assets and risk reduction mechanisms
| 3.1.1 Deploy CRLCSA production/ processing assets and training to smallholder farmers, farmer organizations and associations | 0
|  | 3.1.1.1 Technology needs and climate vulnerability assessment and a Free Prior Informed Consent campaign |  | 12600 |  |  | 17640 |  |  |  | 20160
|  | 3.1.1.2 Targeting and group formation |  | 18900 |  |  |  | 45360 |  |  |  | 56700
|  | 3.1.1.3 Curriculum Development for the FFS |  | 14400 |  |  |  | 9600 |  |  |  | 9600
|  | 3.1.1.4 Training of trainers and facilitators |  | 28000 | 0.2 |  |  | 170100 |  |  | 4000
|  | 3.1.1.5 Deploy FFS in 14 counties |  |  |  |  | 210000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 3.1.1.6 Equipping participating counties with inputs and tools (seeds, post harvest, equipment) |  |  | 793800 | 907200 | 567000
| 3.1.2 Disseminate CRLCSA technology, knowledge and assets to cooperative members through peer-to-peer networks and exchanges | 0
|  | 3.1.2.1 Conduct Climate Clever Check and Cooperative assessment |  | 4318.067 | 0.2 | 0.2 | 4318.067 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 3.1.2.2 Transfer CRLCSA technologies through peer-to-peer training, capacity development, |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 3.1.2.3 Procure and distribute inputs and tools (seeds, post harvest, equipment) |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 3.1.2.4 Disseminate and share knowledge within and among cooperatives |  |  | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| 3.1.3 Support smallholder farmer aggregation into cooperatives and other business units as climate risk reduction and risk sharing mechanisms | 0
|  | 3.1.3.1 Deliver technical assistance to increase business and management capacities of farmers’ organizations | [8 empty] | 9000 |  |  |  | 9000 |  |  |  | 9000 |  |  |  | 9000
|  | 3.1.3.2 Increase farmers’ awareness on benefits to join cooperatives through workshops, site visits and information products |  |  |  | 9212.4659 |  |  |  | 9212.4659 |  |  |  | 9212.4659 |  |  |  | 9212.4659 |  |  |  | 9212.4659 |  | 9212.4659
|  | 3.1.3.3 Increase existing cooperative’s capacities to manage a larger amount of memberships through training and material support |  |  |  |  | 71857.2342 |  |  |  | 71857.2342 |  |  |  | 71857.2342 |  |  |  | 71857.2342 |  |  |  | 71857.2342
| 3.1.4 Support improvements in social inclusion and women's meaningful participation in climate resilient, low-carbon value chains | 0
|  | 3.1.4.1 Training for SEAH, GBV, etc. (GAP) | 9000
|  | 3.1.4.2 Deliver Women’s and Youth Leadership trainings and GALS awareness raising to Smallholders, FFS and FO including cooperatives |  |  |  |  | 21000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 3.1.4.3 Monitor gender objectives through surveys and studies (WEAI) |  |  |  | 24000 |  |  |  | 24000 |  |  |  | 24000 |  |  |  | 24000 |  |  |  | 24000 |  |  |  | 24000
Component 4 – SScaling through CRLCSA market and finance | 0: 0; 0: 0
4.1 Increased access to markets and profitability of climate smart, low carbon sustainable agricultural products | 0: 0; 0: 0
| 4.1.1 Work with buyers and aggregators to increase demand and market opportunities for CRLCSA commodities | 0
|  | 4.1.1.1 Conduct an assessment of markets and buyers demand of the targeted products including the needs in quantity and quantity of the target products and buyer’s affordability |  |  |  | 9000
|  | 4.1.1.2 Research and comparative analysis of quality, grading and pricing of products supported under the project will be conducted |  |  |  | 15600 | 15600 |  |  |  | 15600
|  | 4.1.1.3 Prepare and deliver an advertising campaign on the six targeted commodities | [5 empty] | 20000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 4.1.1.4 Provide technical assistance and business mentoring to mature cooperatives in signing purchasing agreements and contracts with identified buyers. |  |  |  |  | 15600 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 4.1.1.5 Develop and deploy innovative business hubs to promote market access and services, including business incubators for smallholder farmers pursuing nature-bsed livelihoods | [8 empty] | 175000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 4.1.1.6 Organize marketing events and awareness campaigns | [8 empty] | 25000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 4.1.1.7 Develop seasonal market insights and share with the FOs and Cooperatives (link to agricultural databases under 1.1.1) |  |  | 10000 |  |  |  | 10000 |  |  |  | 10000 |  |  |  | 10000 |  |  |  | 10000 |  |  |  | 10000
| 4.1.2 Increase access to various certification and labeling schemes | 0
|  | 4.1.2.1 Select FOs and Cooperatives and other value chain actors, such as aggregators to receive the certifications based on assessments | [12 empty] | 6000
|  | 4.1.2.2 Provide Technical Assistance, to selected cooperatives for the identification of and compliance with suitable certification or labels. | [13 empty] | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
4.2 Vulnerable smallholders and their organizations have increased access to gender-responsive and socially inclusive financial products that support climate resilient, low carbon growth | 0: 0; 0: 0
| 4.2.1 Develop gender-responsive and socially inclusive private finance tools, procedures and products to promote the upscale of CRLCSA value chains | 0
|  | 4.2.1.1 Develop new financial or revise the existing products that invest in climate resilience and low carbon value chains with financial institutions |  |  |  | 0.2 | 25000 | 0.2
|  | 4.2.1.2 Deliver training for financial institutions on the financial products supporting climate resilient, low-carbon agriculture |  |  |  |  | 10000 | 0.2 |  |  | 10000 | 0.2 |  |  | 10000 | 0.2
| 4.2.2 Support smallholders and their business units in the development of bankable business plans, with particular focus on social inclusion and gender-based access | 0
|  | 4.2.2.1 Deliver training on financial literacy and financial management to farmers, FOs and Cooperatives |  |  |  |  | 959.5705 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | 4.2.2.2 Assist the FOs, cooperatives and other rural enterprises to develop bankable business plans to invest in climate resilience and low carbon practices | [8 empty] | 67473.9429 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
| 4.2.3 Facilitate smallholders access to financial incentives schemes for agroforestry | 0
|  | 4.2.3.1 Conduct assessment of technical modalities of implementing carbon and conservation finance incentives in targeted cooperatives (including coop selection, land and scheme selection) | [11 empty] | 17500
|  | 4.2.3.2 Raise awareness of availability of carbon-based mechanisms and conservation finance (biodiversity offset) for agroforestry | [12 empty] | 2398.9261
|  | 4.2.3.3 Deliver training to selected cooperatives in relevant schemes, including all compliance and monitoring requirements. | [13 empty] | 92124.6592 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
Monitoring and Evaluation | bar: 0 to Year 6 Q4
|  | Monitoring, Ongoing | 30000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | Data Collection, compilation, publication | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | Resilience and Household Surveys and Evaluation (baseline, mid-term, final) | 100000 | [10 empty] | 0.2 | 100000 | [9 empty] | 100000 | 0.2 | 0.2 | 0.2
|  | ESMF and Safeguards Monitoring | 32000 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2
|  | APR |  |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2 |  |  |  | 0.2