## Detailed Qty and costs BF (hidden)
Component | outcome title | Output Title | Activity Title
Component 1: Landscape restoration to increase climate change resilience and mitigation, for and by local communities. | Outcome 1 : Rehabilitation of degraded lands and ecosystems. | Output 1.1: Organize 7600 community groups with a total membership of 450,000 households for land restoration and value chain development with 30% participation of women. | Activity 1.1.1 : Identification of potential sites for restoration based on analysis of climate data, GIS maps and potential for impact with local authorities and community
Activity 1.1.2 : Formation of project’s restoration teams and community management committees (leadership and field promoters – including NGOs), capacity building for all involved, with gender, mitigation/adaptation, equity, social interaction/leadership perspective
Activity 1.1.3 : Establishment of biophysical and socio-economic baselines and capacity needs assessments
Activity 1.1.4 : Hire local NGOs to identify and mobilize communities for participatory selection of the specific sites, Organize households into community groups (CG) and participation in the restoration activities
Activity 1.1.5 Inclusion of women in the restoration activities through their participation in community groups and/or formation of separate women's groups (CWGs).
Activity 1.1.6 : Training of community members in soil conservation and protection and land restoration techniques and maintenances
Activity 1.1.7: Regular surveillance, governance and management plans (including benefits that will be procured)
|  | Output 1.2: Native seed supply systems have been strengthened to ensure the availability of genetically appropriate seeds that provide increased climate resilience | Activity 1.2.1 : Identify and train community technicians on good quality and quantities of restoration seeds and native seed supply
Activity 1.2.2 : Identification and organization of community members interested in seed and seedling production for land restoration activities.
Activity 1.2.3 : Establishment of community nurseries for seedling production
Activity 1.2.4 : Local communities seed supply and create a network for seed exchange
Activity 1.2.5 : Installation of solar powered boreholes for plant nurseries and nutrition gardens
|  | Output 1.3: 150,000 hectares of highly degraded land restored through arrangements for rainwater harvesting and enhanced soil permeability by local communities supported by the project with seedlings planted for restoration | Activity 1.3.1 : Land preparation by mechanized, animal and manual traction techniques
Activity 1.3.2 : Sowing and planting in prepared sites with communities/villages
Activity 1.3.3 : Training of community members in monitoring & maintenance
|  | Output 1.4: 1150,000 ha planted with a range of species to restore and enrich the landscapes of agro-forestry, agro-ecology and silvo-pastoral systems, biomes and protected forest ecosystems | Activity 1.4.1 : Preparation of costed plans for land restoration in participation with households, local communities and project staff
Activity 1.4.2 : Land preparation by mechanized, animal and manual traction techniques
|  | Output 1.5:Local technical capacity strenghen for restoration monitoring | Activity 1.5.1 : Setting up field data collection, biophysical and social monitoring and reporting system of restored areas (linked also to Component 3)
Activity 1.5.2:Procurement of tools for land restoration and social data collection
Contingencies
Component 2.Supporting the development of climate-resilient, low emission non-timber forest product value chains benefiting vulnerable communities’ livelihoods and their food and nutrition security | Outcome 2 : Enhanced resilience of livelihoods | Output 2.1: Technical and organizational capacities of actors strengthened for value chain activities in the selected NTFP | Activity 2.1.1 : Strengthening the organizational and managerial capacities of the actors in the selected NTFP value chains (registration, structuring according to OHADA, management, admnistration, etc.)
Activity 2.1.2 : Support and faciltate the establishment and operationalization of platforms of acteurs for collaboration in the NTFP sector ( Gender sensitive)
Activity 2.1.3 : Conduct training for enhancing the capacity of local producers/collectors (men and women) to improve quality of produce and preservation of the resources
Activity 2.1.4 : Conduct technical training to improve the processing (including packaging and labelling) of the selected products
|  | Output 2.2: Improved markets inclusion for NTFP smallholder actors | Activity 2.2.1 : Promote and support a participatory assessment and monitoring/preservation of the resources for the selected NTFP
Activity 2.2.2 : Support to marketing and branding of the NTFP (promotional activities, nutritional value pamphlets of NTFP, organization of trade fairs, TV show, etc.)
Activity 2.2.3 : Support for the setting up of norms and standards to improve the marketing of the NTFP
Activity 2.2.4 : Training of value chain actors in business management
Activity 2.2.5 : Support value chains actors in the preparation of their business plans and implementation
Activity 2.2.6 : Enhance access to national, regional and international markets for NTFP
Activity 2.2.7 : Partnership with institutions (national and/or international) on emission-lowering technologies and equipment to enhance NTFP processing
|  | Output 2.3: Value chain actors have access to financial and non-financial services and products | Activity 2.3.1 : Train and sensitize value chain actors on financial institutions' offerings, financial literacy and financial record keeping
Activity 2.3.2 : Support financial institutions in developing five new financial products tailored to agriculture and NTFP value chains, of which at least one is an insurance product
Activity 2.3.3 : Train personnel from financial institutions (loan officers) on how to assess agricultural and NTFP value chain risks and climate-related risks
Activity 2.3.4 : Facilitate linkages between last-mile providers of finance (producer organizations, village savings groups, microfinance networks) and financial institutions
Activity 2.3.5 : Pilot access to credit through digital financial solutions in at least one country and facilitate scale up, if successful
Activity 2.3.6 : Improve knowledge management and exchanges to increase adoption of best practices across local financial institutions
Contingencies
Component 3.Strengthening the Great Green Wall institutions at country and regional level | Outcome 3 : Strengthened GGW institutions with effective decision-making capacity | Output 3.1:Land restoration monitoring, evaluation and reporting system of the GGW initiative at national and regional level upgraded and functional | Activity 3.1.1 : Development of SURAGGWA-specific monitoring tools including for monitoring of vegetation progress at restoration site scale by using satellite-based detection of vegetation indices, monitoring of biomass production at restoration parcel scale by using satellite-based detection of net primary production (NPP), tracking reduction of degraded land
Activity 3.1.2 : Development of regional multi-stakeholder Monitoring platform
Activity 3.1.3 : Roll out technology transfert at country and regional levels
Activity 3.1.4 : Development of documentation on SURAGGWA Monitoring system, tools and protocols for upscaling at GGWi level
Activity 3.1.5 : Technical assistance and capacity development
Activity 3.1.6 : Analyze existing mechanisms and tools throughout the PAGGW and each of the countries (overall architecture, existing institutions for data collection and processing) and identify needs (baseline)
Activity 3.1.7 : Establish a database of ongoing projects carried out by PAGGW or other actors, benefiting from the GGW label in each country
Activity 3.1.8 : Prepare regulatory national frameworks for the monitoring of all GGW labelled interventions in all GGWi countries
Activity 3.1.9 : Develop operational partnerships between the GGWi and scientific and technical institutions in the region(such as universities, research institutes, CSEs, Aghrymet, ACMAD) on issues of ecological monitoring and adaptation to climate change
Activity 3.1.10 : Strengthen the capacities of national stakeholders in the use of the tools developed by FAO (Collect Earth and Africa Deal database), and the methodology for assessing the carbon balance developed by the Ecological Monitoring Centre (EMC), the Sahara and Sahel Observatory (OSS) and CILSS.
Activity 3.1.11 : Assist in preparing the country level and PA-GGW Annual Achievement Reports as well as contribution to critical reporting frameworks such as the state of the environment (for the GGW area)
Activity 3.1.12 : Assist in preparing a regular national and regional assessment report on the implementation of the GGW compared to the 2030 targets of the SDGs.
|  | Output 3.2: National and Regional GGW institutions planning and coordination capacities strengthened | Activity 3.2.1 : Undertake a critical analysis of the existing consultation and coordination frameworks, from the local to the national level, in areas related to the GGW and recommend solutions for improving coordination mechanisms for GGW actors (baseline)
Activity 3.2.2 : Contribute to developing the GGW 2021-2025 strategy including the approach for harmonizing interventions in the GGW area and the coordination role of the GGW national institutions
Activity 3.2.3 : Assist in the regular functioning of GGW National Coalitions (organization of meetings, facilitation of working groups, communication)
Activity 3.2.4 : Engage the African Union in political support for the GGW. Prepare an outlook report, in the form of an analysis of the situation and the short- and medium-term prospects
Activity 3.2.5 : Support countries in preparing and issuing regulatory frameworks for the coordination of all the GGW labeled interventions
Activity 3.2.6 : Define the role of the GGW in Nationally Determined Contributions (NDCs), considering its specific contribution to the achievement of Goal 7 "Environmentally Sustainable and Climate Resilient Economies and Communities" of 2063 Agenda “The Africa We Want"
Activity 3.2.7 : Mobilise support in integrating GGW into the development planning frameworks including into respective sector strategies, policies and action plans and programs down to the local level
Activity 3.2.8 : SURAGGWA National Steering Committee meetings
|  | Output 3.3: The resource mobilization capacities of regional and national GGW structures are strengthened, including through facilitated access to carbon finance opportunities for sustainability and scaling up of land restoration. | Activity 3.3.1 : Consultations to determine specific needs for resource mobilization at regional and country level.
Activity 3.3.2 : Identify and analyze potential sources and mechanisms for financing GGW interventions in relation to NTFP value chain development and keep the information up to date and accessible
Activity 3.3.3 : Development of specific modules on attracting funds for the GGW Area and organizing orientation sessions for NA-GGWs.
Activity 3.3.4 : Train national institutions including Ministries of Finance & Planning on specific themes related to the mobilization of financial resources for GGW interventions including private sector resources for Value Chain development
Activity 3.3.5 : Prepare briefing sessions with social impact investors, financial institutions and organizing visits to GGW project sites.
Activity 3.3.6 : Identify and undertake the human and technical strengthening actions necessary and preliminary to the accreditation of the PAGGW as well as National GGW Agencies with the climate and development funds (GCF, adaptation fund, CIF, GEF, etc.) to support the member countries of the GGW in the increased mobilization of climate financing.
Activity 3.3.7: Facilitate access to international carbon finance for restoration
Activity 3.3.8 :Enhance carbon finance opportunities for GGW restoration from emerging carbon markets in the region
|  | Output 3.4: GGW knowledge management and communication capacities are strengthened | Activity 3.4.1 : Promote the exchange of information across SURAGGWA participating countries on sustainable land management and adaptation to climate change, in close cooperation with relevant partners and organizations
Activity 3.4.2 : Contribute to KM communities of practice and forums on important themes related to the enhancement of research results in Africa and around the world, as well as on the enhancement of traditional knowledge
Activity 3.4.3 Commission capitalization work on the lessons learned from the SURAGGWA experience and contribute to their dissemination among the GGW community
Activity 3.4.4 Train communication specialists from GGW's national structures to implement their communication plan and develop tools adapted to different target groups, particularly women and youth.
Activity 3.4.5 Develop, in relation to the different target groups identified, adapted supports and modes of information, such as: the use of social networks (Facebook, Twitter, etc.) and teleconferences, the organization of meetings; workshops, the production of films, leaflets, brochures, etc.).
Activity 3.4.6 : In consultation with the African Union Commission, take the leadership in the biannual organization of the African Drylands Week, a showcase of GGW achievements
Activity 3.4.7 : Development of Project M&E Manual, including preparation of baseline data collection sampling strategy and tools to inform mid-year and final impact evaluation
Contingencies
PMC | PMC | PMC | Activity 4.1.1 : Equipment and Goods
PMC
PMC
PMC
PMC
PMC
PMC
|  | PMC | Activity 4.1..2 : CIU Salaries
|  | PMC | Activity 4.1..3 : Office Running Costs
PMC
PMC
PMC
PMC
Refresh Pivot and generate RBB
DETAILED COSTS BY ACTIVITY
Project ID
Outcomes
Outputs
Work Plan
Cost table
Components
Project details
Result-based Budget
Refresh Pivot and generate RBB
Note on E151: Catalyse and facilitate access to carbon finance opportunities for sustainability and scaling up of land restoration
Note on E154: Catalyse and facilitate access to carbon finance opportunities for sustainability and scaling up of land restoration

## Program Timetable
Annex 5 Implementation Timetable
Project/Programme Title: Scaling-Up Resilience in Africa’s Great Green Wall (SURAGGWA)- Burkina Faso, Chad, Djibouti, Mali, Mauritania, Niger, Nigeria, Senegal
COMPONENTS/OUTPUTS |  | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7 |  |  |  | Year 8 |  |  |  | Year 9 |  |  |  | Year 10 |  |  |  | post completion
| Key deliverables | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Component 1: Large-scale landscape restoration to increase climate change resilience and mitigation, for and by local communities.
Output 1.1: Local community groups organized, trained and knowledgeable in land restoration activities and monitoring
Activity 1.1.1: Identify potential sites for restoration and to inform resource base for value chain priorities based on analysis of climate data, GIS maps and potential for impact with local authorities and community | 8 countries GIS maps and climate data on potential sites to be restored | Year 1 Q4: 8
Activity 1.1.2: Identify and mobilize communities for participatory selection of the specific sites, ensuring inclusion of women. | 24 Training and recycling sessions | Year 1 Q4: 8; Year 3 Q4: 8; Year 5 Q4: 8
Activity 1.1.3: Train programme’s restoration teams and community management organizations | 144 Decentralized CWGs trainings/Workshops | Year 2 Q4: 48; Year 4 Q4: 48; Year 6 Q4: 48
Output 1.2. Native seed supply systems strengthened to ensure the availability of genetically appropriate seeds that provide increased climate resilience.
Activity 1.2.1: Identify and train community technicians on good quality and quantities of restoration seeds and native seed supply | 96 local training by research institutions | Year 1 Q4: 48; Year 4 Q4: 48
Activity 1.2.2: Identify, organize and train community members involved in seed and seedling production for land restoration activities. | 288 Seeds producers and community members local training | Year 1 Q4: 96; Year 3 Q4: 48; Year 4 Q4: 48; Year 5 Q4: 48; Year 7 Q4: 48
Activity 1.2.3: Establish, equip and operate community nurseries for seedling production and dissemination | 706 local community nurseries | Year 1 Q4: 245; Year 2 Q4: 221; Year 3 Q4: 185; Year 4 Q4: 55
Activity 1.2.4: Local communities’ seed supply of native seeds is integrated into national seed system. | 8 functional seed supply system | Year 8 Q4: 8
Output 1.3: Targeted highly degraded lands restored through arrangements for rainwater harvesting and enhanced soil permeability and through local communities engaging in planting of seedlings and direct seeding.
Activity 1.3.1: Highly degraded land restoration plans prepared and implemented through mechanized, animal, and manual traction techniques. | 133 000 ha of highly degraded land restored with 500 community group | Year 1 Q4: 20400; Year 2 Q4: 32058; Year 3 Q4: 23245; Year 4 Q4: 18277; Year 5 Q4: 16130; Year 6 Q4: 10876.9231; Year 7 Q4: 8675; Year 8 Q4: 3577
Activity 1.3.2: Sowing and planting in prepared sites with communities/villages | 133 000 ha of highly degraded land restored with 7100 community organizations | Year 1 Q4: 20400; Year 2 Q4: 32058; Year 3 Q4: 23245; Year 4 Q4: 18277; Year 5 Q4: 16130; Year 6 Q4: 10876.9231; Year 7 Q4: 8675; Year 8 Q4: 3577
Activity 1.3.3: Training of community members in monitoring & maintenance | 480 local communities sessions | Year 1 Q4: 48; Year 2 Q4: 48; Year 3 Q4: 96; Year 4 Q4: 96; Year 5 Q4: 96; Year 6 Q4: 48; Year 7 Q4: 24; Year 8 Q4: 24
Output 1.4: Targeted moderately degraded lands planted with a range of species to restore and enrich the landscapes of agro-forestry, agro-ecology and sylvo-pastoral systems, biomes and protected forest ecosystems.
Activity 1.4.1 Sub-national moderately degraded land restoration plans prepared and implemented | 1 140 500 ha of modarated land restored | Year 1 Q4: 65503; Year 2 Q4: 203238; Year 3 Q4: 209876; Year 4 Q4: 195008; Year 5 Q4: 178194; Year 6 Q4: 159995; Year 7 Q4: 79000; Year 8 Q4: 42200; Year 9 Q4: 7500
Output 1.5: Rural community capacities strengthened for sustainable management and restoration, and verification of restoration results
Activity 1.5.1: Village technicians trained and equipped in managing restoration areas and verifying restoration results, in a participatory manner. | 258 Technicians | Year 1 Q4: 41; Year 2 Q4: 127; Year 3 Q4: 90
Component 2: Development of climate-resilient, low emission non-timber forest product (NTFP) value chains benefiting vulnerable communities’ livelihoods
Output 2.1. Climate resilient and low carbon production and processing practices in selected NTFP value chains adopted by Producer Organizations and MSMEs.
Activity 2.1.1: Train and provide TA to POs and MSMEs in selected NTFP value chains for enhanced organizational and managerial capacities (registration, structuring according to OHADA, training on management, administration etc.) | 765 Organizations of actors registred | Year 2 Q4: 190; Year 3 Q4: 165; Year 4 Q4: 150; Year 5 Q4: 120; Year 6 Q4: 68; Year 7 Q4: 62; Year 8 Q4: 10
Activity 2.1.2: Train and coach local POs and MSMEs in sustainable production and collection practices to enhance NTFP quality and availability | 138 training sessions | Year 2 Q4: 36; Year 3 Q4: 36; Year 4 Q4: 18; Year 5 Q4: 18; Year 6 Q4: 18; Year 7 Q4: 5
Activity 2.1.3: Train and coach POs and MSMEs to improve the processing practices (including packaging and labelling) of the selected products | 120 traiining sessions | Year 2 Q4: 24; Year 3 Q4: 24; Year 4 Q4: 24; Year 5 Q4: 24; Year 6 Q4: 24; Year 7 Q4: 18
Output 2.2: Increased access to markets for smallholder NTFP actors (including micro- and small enterprises)
Activity 2.2.1: Identify NTFPs with market and sustainable production potential that can be integrated in land restoration efforts funded under Component 1 | 8 countries assessment documents | Year 2 Q3: 4; Year 2 Q4: 4
Activity 2.2.2: Support to marketing and branding of the NTFP (promotional activities, nutritional value pamphlets of NTFP, organization of trade fairs, tv show, etc.) | 51 sessions and coaching | Year 2 Q4: 8; Year 3 Q4: 8; Year 4 Q4: 8; Year 5 Q4: 8; Year 6 Q4: 8; Year 7 Q4: 6; Year 8 Q4: 5
Activity 2.2.3: Support POs and MSMEs in business plan development and management. | 8 documents | Year 3 Q2: 8
Activity 2.2.4: Enhance access to national, regional and international markets for NTFP, including through the setting up of norms and standards to improve the marketing of the NTFP; | 16 information sessions | Year 2 Q4: 8; Year 3 Q3: 4; Year 3 Q4: 4; Year 10 Q3: 303634
Activity 2.2.5: Identify, train and equip POs and MSMEs with emission-lowering technologies and equipment to enhance NTFP processing | 36 processing equipment trainings | Year 2 Q4: 2; Year 3 Q3: 6; Year 4 Q3: 8; Year 5 Q3: 6; Year 6 Q3: 8; Year 7 Q3: 4; Year 8 Q3: 2
Output 2.3 Suitable credit and insurance products designed for smallholder NTFP value chain actors (PO, cooperatives, MSMEs) and increased stakeholder capacity for using these financial products in their NTFP value chain activities
Activity 2.3.1: Train and sensitize value chain actors on financial institutions' offerings, enhance financial literacy and financial record keeping | 8 country documents and training | Year 2 Q4: 6; Year 3 Q4: 2
Activity 2.3.2: Technical assistance provided to develop five new financial products (of which at least one insurance product) tailored to agriculture and NTFP value chains with financial institutions, including those collaborating with iGREENFIN. | 40 products (5 per country )
Activity 2.3.3: Train staff (loan officers and others) from financial institutions, including those collaborating with iGREENFIN, on how to assess agricultural and NTFP value chain risks and climate-related risks (national and regional level) | 640 people trained | Year 2 Q4: 213.3333; Year 3 Q4: 213.3333; Year 4 Q4: 213.3333
Activity 2.3.4: Facilitate linkages between last-mile providers of finance (producer organizations, village savings groups, microfinance networks) and financial institutions, including those participating in iGREENFIN. | 8 mapping documents | Year 2 Q4: 8
Activity 2.3.5. Pilot access to credit through digital financial solutions in at least one country and facilitate scale up, if successful | 1 Digital credit solution deployed | bar: Year 2 Q3 to Year 5 Q4
Activity 2.3.6. Improve knowledge management and exchanges to increase adoption of best practices across local financial institutions | 1 Regional workshop | bar: Year 2 Q3 to Year 2 Q4
Component 3: Strengthening the Great Green Wall institutions at country and regional level
Output 3.1: GGW Land restoration monitoring system at national and regional level upgraded and functional
Activity 3.1.1: Development, testing and deployment of National GGW land restoration monitoring tools and system | 12 operational M&E and reporting systems (countries and 1 Regional) | Year 5 Q4: 12
Activity 3.1.2: Transfer knowledge and skills for the use of the GGW Land restoration monitoring system by national and regional authorities. | 12 multi-stakeholder Monitoring platform | Year 5 Q4: 12
Activity 3.1.3: Development and deployment of regional multi-stakeholder Monitoring platform | 12 operational platforms | Year 5 Q4: 12
Activity 3.1.4: Building the capacity of NAGGW and PAGGW to establish databases of ongoing restoration projects and programmes contributing to national and regional GGW results | 1 Regional documentation | bar: Year 2 Q1 to Year 3 Q4
Activity 3.1.5: Prepare regulatory national frameworks for the surveillance of all GGW labelled interventions in all GGW countries | 12 operational M&E and reporting systems (countries and 1 Regional) | Year 5 Q4: 12
Activity 3.1.6: Develop operational partnerships between the NAGGWs and PAGGW and scientific and technical institutions in the region (such as universities, research institutes, CSEs, Agrhymet, ACMAD) on issues of ecological monitoring and adaptation to climate change | Technical assistance to 11 countries | Year 5 Q4: 12
Activity 3.1.7.: Strengthen the capacities of national stakeholders in the use of the relevant tools developed by FAO (for example, Collect Earth and Africa OpenDeal database), and other partners such as the Ecological Monitoring Centre (EMC), the Sahara and Sahel Observatory (OSS) and CILSS. | 12 operational M&E and reporting systems (countries and 1 Regional) | Year 5 Q4: 12
Output 3.2: National and Regional GGW institutions planning and coordination capacities strengthened
Activity 3.2.1: Establish National GGW Coalitions to promote coherent coordination and planning at country-level | 11 National and 1 Regional GGW institutions | Year 2 Q4: 12
Activity 3.2.2: Prepare and issue planning and regulatory frameworks for the coordination of all GGW aligned interventions (projects, programmes, activities etc…) |  | Year 2 Q4: 12
Output 3.3: National and regional climate change institutional capacities/frameworks strengthened to integrate land restoration investments in climate change adaptation and mitigation programmes
Activity 3.3.1: Strengthen public- and private sector understanding of and capacity to engage with carbon markets for climate change adaptation and mitigation through land restoration | 1 regional and 11 national structures established and/or strengthened functional technical and outreach capacities for climate-specific resource mobilization | Year 4 Q4: 12
Activity 3.3.2: Pilot the establishment of domestic carbon accounting framework that integrates agriculture and forestry in Nigeria, and identify additional countries for potential replication. |  | Year 4 Q4: 12
Output 3.4. GGW knowledge management and communication capacities strengthened for mobilizing increased support to climate-resilient land restoration
Activity 3.4.1: Develop innovative and robust methods for evaluating/demonstrating resilience benefits of climate change investments in land restoration and NTFP value chains in GGW | 176 regional and national knowledge products and communications highlighting SURAGGWA results and lessons-learned | Year 3 Q4: 44; Year 5 Q4: 44; Year 8 Q4: 82; Year 9 Q4: 6
Activity 3.4.2. Communication, visibility and dissemination of knowledge. |  | Year 3 Q4: 44; Year 5 Q4: 44; Year 8 Q4: 82; Year 9 Q4: 6
Activity 3.4.3 Train communication specialists from GGW's national structures to implement their communication plan and develop tools adapted to different target groups, particularly women and youth. |  | Year 3 Q4: 44; Year 5 Q4: 44; Year 8 Q4: 82; Year 9 Q4: 6
Activity 3.4.4 Develop, in relation to the different target groups identified, adapted supports and modes of information, such as: the use of social networks (Facebook, Twitter, etc.) and teleconferences, the organization of meetings; workshops, the production of films, leaflets, brochures, etc.). |  | Year 3 Q4: 44; Year 5 Q4: 44; Year 8 Q4: 82; Year 9 Q4: 6
Project Monitoring* |  | Year 1 Q1: Baseline survey; Year 1 Q2: Inception Report; Year 2 Q1: APR; Year 3 Q1: APR; Year 4 Q1: APR; Year 5 Q1: APR; Year 6 Q1: APR Interim Evaluation; Year 7 Q1: APR; Year 8 Q1: APR; Year 9 Q1: APR; Year 10 Q1: APR; post completion Q1: Completion Report; post completion Q2: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.