## Restoration targets
SURAGGWA-Land restoration targets
| SURAGGWA-Countries |  | Burkina Faso | Chad | Djibouti | Mali | Mauritania | Niger | Nigeria | Senegal | Average
| Implementation duration |  | 8 | 10 | 7 | 6 | 8 | 6 | 8 | 8 | 7.625
GCF financing targets ( Hectares) |  |  | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10
Burkina-Faso | 1.1 Highly Degraded Land | 4000 | 300 | 300 | 600 | 900 | 900 | 700 | 300 |  |  |  | 4000 |  | 0
| 1.2 Moderately degraded Land | 36300 | 2000 | 2000 | 5000 | 6000 | 6000 | 6000 | 6000 | 3300 |  |  | 36300 |  | 0
Chad | 1.1 Highly Degraded Land | 4500 | 0 | 500 | 500 | 600 | 800 | 800 | 800 | 500 |  |  | 4500 |  | 0
| 1.2 Moderately degraded Land | 79500 | 0 | 8000 | 10000 | 11000 | 11000 | 11000 | 11000 | 10000 | 7500 |  | 79500 |  | 0
Djibouti | 1.1 Highly Degraded Land | 2500 | 0 | 300 | 600 | 600 | 500 | 500 |  |  |  |  | 2500 |  | 0
| 1.2 Moderately degraded Land | 21000 | 0 | 5000 | 5000 | 5000 | 4000 | 2000 |  |  |  |  | 21000 |  | 0
Mali | 1.1 Highly Degraded Land | 6440 | Y2: 940; Y3: 2000; Y4: 2000; Y5: 1500 | 6440 |  | 0
| 1.2 Moderately degraded Land | 130280 | Y2: 22500; Y3: 30000; Y4: 30000; Y5: 30000; Y6: 17780 | 130280 |  | 0
Mauritania | 1.1 Highly Degraded Land | 5468 | 0 | 300 | 800 | 1200 | 1200 | 1100 | 868 |  |  |  | 5468 |  | 0
| 1.2 Moderately degraded Land | 72900 | 0 | 5000 | 10000 | 12000 | 12000 | 12000 | 12000 | 9900 |  |  | 72900 |  | 0
Niger | 1.1 Highly Degraded Land | 10403 | Y1: 300; Y2: 1200; Y3: 3000; Y4: 3000; Y5: 2903 | 10403 |  | 0
| 1.2 Moderately degraded Land | 234215 | 5000 | 30000 | 50000 | 50000 | 50000 | 49215 |  |  |  |  | 234215 |  | 0
Nigeria | 1.1 Highly Degraded Land | 13130 | 0 | 1000 | 2500 | 2500 | 2500 | 2500 | 2130 |  |  |  | 13130 |  | 0
| 1.2 Moderately degraded Land | 241000 | 0 | 30000 | 35000 | 45000 | 45000 | 45000 | 35000 | 6000 |  |  | 241000 |  | 0
Senegal | 1.1 Highly Degraded Land | 3500 | 100 | 300 | 500 | 700 | 700 | 700 | 500 | 0 |  |  | 3500 |  | 0
| 1.2 Moderately degraded Land | 26500 | 2000 | 3000 | 3500 | 4000 | 4000 | 4000 | 3000 | 3000 |  |  | 26500 |  | 0
| Total areas- GCF financing | 891636 | 9700 | 110340 | 159000 | 174500 | 173003 | 153295 | 71598 | 32700 | 7500 | 0 | 891636 | 70% | of total restauration areas
|  |  | 1.088% | 12.38% | 17.83% | 19.57% | 19.4% | 17.19% | 8.03% | 3.667% | 0.8412% | 0% | 100%
Cofinancing -Targets ( Hectares) |  |  | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10
| 1.2 Moderately degraded Land | [11 empty] | 0
Mali -FAO GEF/LDF | 1.1 Highly Degraded Land | 6000 | Y1: 1500; Y2: 3000; Y3: 1500 | 6000
| 1.2 Moderately degraded Land | 50000 | Y1: 10000; Y2: 30000; Y3: 10000 | 50000
Mauritania GOVT | 1.1 Highly Degraded Land | 24615.3846 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 3076.9231 | 0 | 0 | 24615.3846
| 1.2 Moderately degraded Land | 80000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | 0 | 80000
Mauritania GEF | 1.1 Highly Degraded Land | 8000 |  | 1000 | 1500 | 1500 | 1500 | 1500 | 1000 |  |  |  | 8000
| 1.2 Moderately degraded Land | 22000 |  | 2000 | 5000 | 5000 | 5000 | 3000 | 2000 |  |  |  | 22000
Niger GEF | 1.1 Highly Degraded Land | 11000 | Y1: 1650; Y2: 3300; Y3: 3300; Y4: 2200; Y5: 550 | 11000
| 1.2 Moderately degraded Land | 10000 | Y1: 775.6733; Y2: 2828.926; Y3: 3193.9487; Y4: 2007.6249; Y5: 1193.8271 | 10000
Nigeria WB ACReSAL | 1.1 Highly Degraded Land | 33681.5538 | Y1: 13472.6215; Y2: 16840.7769; Y3: 3368.1554 | 33681.5538
| 1.2 Moderately degraded Land | 81818.4462 | Y1: 32727.3785; Y2: 40909.2231; Y3: 8181.8446 | 81818.4462
Senegal Global Affairs Canada | 1.1 Highly Degraded Land | 0 | [10 empty] | 0
| 1.2 Moderately degraded Land | 55000 | Y1: 3000; Y2: 12000; Y3: 25000; Y4: 15000 | 55000
Total areas- Cofinancing financing |  | 382115.3846 | 76202.5963 | 124955.8491 | 74120.8718 | 38784.548 | 21320.7502 | 17576.9231 | 16076.9231 | 13076.9231 | 0 | 0 | 382115.3846 | 30% | Of total restauration areas
|  |  | 19.94% | 32.7% | 19.4% | 10.15% | 5.58% | 4.6% | 4.207% | 3.422% | 0% | 0% | 100%
GCF+Cofinancing target ( Hectares)
|  | Total | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10
Burkina-Faso | 1.1 Highly Degraded Land | 4000 | 300 | 300 | 600 | 900 | 900 | 700 | 300 | 0 | 0 | 0 | 4000
| 1.2 Moderately degraded Land | 36300 | 2000 | 2000 | 5000 | 6000 | 6000 | 6000 | 6000 | 3300 | 0 | 0 | 36300
Chad | 1.1 Highly Degraded Land | 4500 | 0 | 500 | 500 | 600 | 800 | 800 | 800 | 500 | 0 | 0 | 4500
| 1.2 Moderately degraded Land | 79500 | 0 | 8000 | 10000 | 11000 | 11000 | 11000 | 11000 | 10000 | 7500 | 0 | 79500
Djibouti | 1.1 Highly Degraded Land | 2500 | 0 | 300 | 600 | 600 | 500 | 500 | 0 | 0 | 0 | 0 | 2500
| 1.2 Moderately degraded Land | 21000 | 0 | 5000 | 5000 | 5000 | 4000 | 2000 | 0 | 0 | 0 | 0 | 21000
Mali | 1.1 Highly Degraded Land | 12440 | 1500 | 3940 | 3500 | 2000 | 1500 | 0 | 0 | 0 | 0 | 0 | 12440
| 1.2 Moderately degraded Land | 180280 | 10000 | 52500 | 40000 | 30000 | 30000 | 17780 | 0 | 0 | 0 | 0 | 180280
Mauritania | 1.1 Highly Degraded Land | 38083.3846 | 3076.9231 | 4376.9231 | 5376.9231 | 5776.9231 | 5776.9231 | 5676.9231 | 4944.9231 | 3076.9231 | 0 | 0 | 38083.3846
| 1.2 Moderately degraded Land | 174900 | 10000 | 17000 | 25000 | 27000 | 27000 | 25000 | 24000 | 19900 | 0 | 0 | 174900
Niger | 1.1 Highly Degraded Land | 21403 | 1950 | 4500 | 6300 | 5200 | 3453 | 0 | 0 | 0 | 0 | 0 | 21403
| 1.2 Moderately degraded Land | 244215 | 5775.6733 | 32828.926 | 53193.9487 | 52007.6249 | 51193.8271 | 49215 | 0 | 0 | 0 | 0 | 244215
Nigeria | 1.1 Highly Degraded Land | 46811.5538 | 13472.6215 | 17840.7769 | 5868.1554 | 2500 | 2500 | 2500 | 2130 | 0 | 0 | 0 | 46811.5538
| 1.2 Moderately degraded Land | 322818.4462 | 32727.3785 | 70909.2231 | 43181.8446 | 45000 | 45000 | 45000 | 35000 | 6000 | 0 | 0 | 322818.4462
Senegal | 1.1 Highly Degraded Land | 3500 | 100 | 300 | 500 | 700 | 700 | 700 | 500 | 0 | 0 | 0 | 3500
| 1.2 Moderately degraded Land | 81500 | 5000 | 15000 | 28500 | 19000 | 4000 | 4000 | 3000 | 3000 | 0 | 0 | 81500
| Total area | 1273751.3846 | 85902.5963 | 235295.8491 | 233120.8718 | 213284.548 | 194323.7502 | 170871.9231 | 87674.9231 | 45776.9231 | 7500 | 0 | 1273751.3846
|  |  | 6.744% | 18.47% | 18.3% | 16.74% | 15.26% | 13.41% | 6.883% | 3.594% | 0.5888% | 0% | 100%
Total restauration area (GCF financing)-( Hectares) |  |  | Y4: Average Mid-term; Y5: Global Mid-term; Y10: Final
|  |  | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10
| High degradated land (Ha) | 49941 | 700 | 4840 | 10500 | 11500 | 11003 | 6300 | 4598 | 500 | 0 | 0 | 116523.3846
| High degradated land -cumulative (Ha) |  | 700 | 5540 | 16040 | 27540 | 38543 | 44843 | 49441 | 49941 | 49941 | 49941
[6 empty] | 55.15% | 77.18% |  |  |  |  | 100%
| Moderate degradated (Ha) | 841695 | 9000 | 105500 | 148500 | 163000 | 162000 | 146995 | 67000 | 32200 | 7500 | 0 | 841695
| Moderate degradated land -cumulative (Ha) |  | 9000 | 114500 | 263000 | 426000 | 588000 | 734995 | 801995 | 834195 | 841695 | 841695
[6 empty] | 50.61% | 69.86% |  |  |  |  | 100%
|  |  | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10
Total restauration area (GCF+Cofinancing)-( Hectares) |  |  | 50.61% Y4: Average Mid-term; 69.86% Y5: Global Mid-term; 100% Y10: Final
| High degradated land (Ha) | 133237.9385 | 20399.5446 | 32057.7 | 23245.0785 | 18276.9231 | 16129.9231 | 10876.9231 | 8674.9231 | 3576.9231 | 0 | 0 | 133237.9385
| High degradated land -cumulative (Ha) |  | 20399.5446 | 52457.2446 | 75702.3231 | 93979.2462 | 110109.1692 | 120986.0923 | 129661.0154 | 133237.9385 | 133237.9385 | 133237.9385
[6 empty] | 70.53% | 82.64% |  |  |  |  | 100%
| Moderate degradated (Ha) | 1140513.4462 | 65503.0517 | 203238.1491 | 209875.7933 | 195007.6249 | 178193.8271 | 159995 | 79000 | 42200 | 7500 | 0 | 1140513.4462
| Moderate degradated land -cumulative (Ha) |  | 65503.0517 | 268741.2008 | 478616.9941 | 673624.619 | 851818.4462 | 1011813.4462 | 1090813.4462 | 1133013.4462 | 1140513.4462 | 1140513.4462
[6 empty] | 59.06% | 74.69% |  |  |  |  | 100%
| Mid term and final targets |  | 50.61% Y4: 767603.8652; 69.86% Y5: 961927.6154; 100% Y10: 1273751.3846
[6 empty] | 60.26% | 75.52% |  |  |  |  | 100%
| Community group (Number) | 0 | 67.9985 | 174.8575 | 252.3411 | 313.2642 | 367.0306 | 403.287 | 432.2034 | 444.1265 | 444.1265 | 444.1265 | 0
| community organization-(Number) | 0 | 818.7881 | 3359.265 | 5982.7124 | 8420.3077 | 10647.7306 | 12647.6681 | 13635.1681 | 14162.6681 | 14256.4181 | 14256.4181 | 0
| Cummulative Total community group and Community Organization (Number) |  | 886.7866 | 3534.1225 | 6235.0535 | 8733.5719 | 11014.7611 | 13050.9551 | 14067.3715 | 14606.7945 | 14700.5445 | 14700.5445 | 0
|  |  | 85902.5963 | 235295.8491 | 233120.8718 | 213284.548 | 194323.7502 | 170871.9231 | 87674.9231 | 45776.9231 | 7500 | 0
Technicians
| Total area High egradated land |  | 20399.5446 | 52457.2446 | 55302.7785 | 41522.0015 | 34406.8462 | 27006.8462 | 19551.8462 | 12251.8462 | 3576.9231 | 0 | 266475.8769 | 0
| 1 Technicians FOR 5 Communiy groups , Two years of supervision |  | 13.5997 | 34.9715 | 36.8685 | 27.6813 | 22.9379 | 18.0046 | 13.0346 | 8.1679 | 2.3846 | 0 | 177.6506
| Technicians without double counting 1 |  | Y1: 13.5997; Y2: 21.3718; Y3: 1.897 | 36.8685
| Total area Modare degradated land |  | 65503.0517 | 268741.2008 | 413113.9424 | 404883.4182 | 373201.452 | 338188.8271 | 238995 | 121200 | 49700 | 7500 | 2281026.8923
| 1 Technicians FOR 5 Communiy groups |  | 40.9394 | 167.9633 | 258.1962 | 253.0521 | 233.2509 | 211.368 | 149.3719 | 75.75 | 31.0625 | 4.6875 | 1425.6418
| Technicians without double counting 2 |  | Y1: 40.9394; Y2: 127.0238; Y3: 90.233 | 258.1962
|  |  | 54.5391 | 148.3956 | 92.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295.0647 |  | 36.8831 | en moyenne par pays
|  |  | 69.86% Y8: 1.4428; 69.86% Y9: 0.91669; 100% Y10: 1.6033 | 1.3612 | 2.5901 | 3.2689 | 0.88354
| BF | 30 | Y1: 15; Y2: 15
| CD | 50 | Y1: 25; Y2: 15; 69.86% Y6: 60
| DJ | 30 | Y1: 15; Y2: 15; 69.86% Y6: 86.5668
| MALI | 30 | Y1: 30; Y2: 30; 69.86% Y6: 55.0012
| Mauri | 30 | Y1: 15; Y2: 15; 69.86% Y6: 96.1971
| Niger | 30 | Y1: 30; Y2: 30; 69.86% Y6: 81.673
| Nigeria | 30 | Y1: 15; Y2: 15; 69.86% Y6: 155.4041
| Senegal | 30 | Y1: 15; Y2: 15; 69.86% Y6: 196.1333
|  | 260 | Y1: 160; Y2: 150; 69.86% Y6: 53.0126; 69.86% Y7: 500; 69.86% Y8: Mid term
BF |  | 30 | Y1: 15; Y2: 15; 69.86% Y6: 783.9882
CD |  | 50 | Y1: 25; Y2: 15
DJ | Seeds Community Group | 25 | Y1: 15; Y2: 15
MALI |  | 30 | Y1: 36; Y2: 30
Mauri |  | 20 | Y1: 32; Y2: 30
Niger |  | 30 | Y1: 30; Y2: 25; Y3: 15
Nigeria |  | 40 | Y1: 50; Y2: 40; Y3: 40
Senegal |  | 20 | Y1: 18; Y2: 15
Total |  | 245 | Y1: 221; Y2: 185; Y3: 55; 50.61% Y4: 706
|  | 6 | Y1: 12; Y2: 12; Y3: 12; 50.61% Y4: 6; 69.86% Y5: 6
|  | 6 | 12 | 12 | 12 | 6 | 6 | 6 | 6
|  | 6 | Y1: 12; Y2: 12; Y3: 12; 50.61% Y4: 6; 69.86% Y5: 6
|  | 6 | Y1: 12; Y2: 12; Y3: 12; 50.61% Y4: 6; 69.86% Y5: 6
|  | 6 | Y1: 12; Y2: 12; Y3: 12; 50.61% Y4: 6; 69.86% Y5: 6
|  | 6 | Y1: 12; Y2: 12; Y3: 12; 50.61% Y4: 6; 69.86% Y5: 6
|  | 6 | Y1: 12; Y2: 12; Y3: 12; 50.61% Y4: 6; 69.86% Y5: 6
|  | 6 | Y1: 12; Y2: 12; Y3: 12; 50.61% Y4: 6; 69.86% Y5: 6
|  | 48 | 96 | 96 | 96 | 48 | 48 | 6 | 6 |  | 444
|  |  | 25 | 15 | 15 | 10 | 10 | 10
|  | 0 | 20 | 15 | 15 | 10 | 10 | 10 | 10
|  | 0 | Y1: 20; Y2: 15; Y3: 10; 50.61% Y4: 10; 69.86% Y5: 5
|  | 0 | Y1: 25; Y2: 15; Y3: 15; 50.61% Y4: 10
|  | 0 | 25 | 15 | 15 | 10 | 10 | 10
|  | 0 | Y1: 35; Y2: 45; Y3: 35; 50.61% Y4: 35
|  | 0 | 30 | 40 | 40 | 30 | 30 | 30
|  | 0 | 10 | 5 | 5 | 5 | 3 | 2
|  | 0 | 190 | 165 | 150 | 120 | 68 | 62 | 10 | 0 | 765
|  |  | 3 | 3 | 2 | 2 | 2
|  |  | 3 | 3 | 2 | 2 | 2 | 0 | 0
|  |  | 3 | 3 | 2 | 2 | 2
|  |  | 3 | 3 | 2 | 2 | 2
|  |  | 3 | 3 | 2 | 2 | 2 | 0 | 0
|  |  | 8 | 8 | 8 | 8
|  |  | 11 | 11 | 11 | 11 | 8 | 4 | 0
|  |  | 2 | 2 | 2 | 2 | 2 | 0 | 0
|  |  | 36 | 36 | 31 | 31 | 20 | 4 | 0
|  |  | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  |  | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  |  | 3 | 3 | 3 | 3 | 3
|  |  |  | 3 | 3 | 3 | 3 | 3
|  |  | 3 | 3 | 3 | 3 | 3 | 3 | 0
|  |  | 3 | 3 | 3 | 3 | 3
|  |  | 11 | 11 | 11 | 11 | 8 | 4 | 0
|  |  | 2 | 2 | 2 | 2 | 2 | 2 | 0
|  |  | 28 | 31 | 31 | 31 | 28 | 18 | 0