## Timetable
Annex 5: Implementation Timetable
Project Title: Solomon Islands Knowledge Action Sustainability for Resilient Villages (SOLKAS)
Accredted Entity: Save the Children Australia
GCF BRACE Implementation Timetable v.B.42
|  |  |  | Project Year 1 |  |  |  | Project Year 2 |  |  |  | Project Year 3 |  |  |  | Project Year 4 |  |  |  | Project Year 5 |  |  |  | Project Year 6
Activity | Deliverable | Country | By what date | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031
|  |  |  | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sep | Oct-Dec
|  |  |  | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026 | Q1 2027 | Q2 2027 | Q3 2027 | Q4 2027 | Q1 2028 | Q2 2028 | Q3 2028 | Q4 2028 | Q1 2029 | Q2 2029 | Q3 2029 | Q4 2029 | Q1 2030 | Q2 2030 | Q3 2030 | Q4 2030 | 2031 | 2031 | 2031 | 2031
Component/Output 1.1: Enabling systems and policies are in place and supported
Activity 1.1.1 Facilitate preparation and endorsement of climate and education policies, plans, and guidelines | 3 new strategies developed with education and climate stakeholders and validated by the Ministry of Education (1 Cambodia, 2 South Sudan) | Cambodia | Q42026 |  |  |  | TRUE
|  | South Sudan | Q42026 |  |  |  | TRUE
Activity 1.1.2 Strengthen coordination on climate change within Ministries of Education and other relevant line ministries at national and sub-national level | Establishment of a cross sectorial working group with agreed ToR (Cambodia-specific) 8 multi-stakeholder dialogues held on climate change and education (4 Cambodia, 4 South Sudan) 70 climate focal points established at sub-national level (South Sudan-specific) | Cambodia | Q42026 |  |  |  | TRUE
|  | South Sudan | Q42026 |  |  |  | TRUE
Activity 1.1.3 Facilitate integration of Disaster Risk Reduction (DRR) into existing and/or new plans with education authorities | 15 education plans integrated with DRR by education authorities addressing relevant climate change hazards (9 Cambodia, 6 South Sudan) | Cambodia | Q22027 | [5 empty] | TRUE
|  | South Sudan | Q42027 | [7 empty] | TRUE
Activity 1.1.4 Support children to participate in climate change and education policy initiatives | 730 children participated in climate and education policy initiatives (500 in Cambodia, 230 South Sudan) | Cambodia | Q4Yearly |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE
|  | South Sudan | Q4Yearly |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE
Component/Output 1.2: School facilities are safer and greener
Activity 1.2.1 Develop a national standard for climate-resilient school facilities | National standard for climate-resilient school facilities approved by Ministry of Education (Cambodia-specific) | Cambodia | Q32027 | [6 empty] | TRUE
Activity 1.2.2 Retrofit school facilities, including WASH and internet connectivity, to strengthen climate resilience | Infrastructure assessment completed in 77 schools (40 Cambodia, 30 South Sudan, 7 Tonga) Infrastructure improvement plan validated by school representatives and education officials for 77 schools (40 Cambodia, 30 South Sudan, 7 Tonga) Climate resilient infrastructure, including WASH and PV installed in 77 schools (40 Cambodia, 30 South Sudan, 7 Tonga) | Cambodia | Q42029 | [15 empty] | TRUE
|  | South Sudan | Q42028 | [11 empty] | TRUE
|  | Tonga | Q42029 | [14 empty] | TRUE
Activity 1.2.3 Strengthen school communities and education officials to operate and maintain school infrastructure and facilities | 756 school staff and community members trained in school infrastructure and facility operations and maintenance (360 Cambodia, 390 South Sudan, 7 Tonga) | Cambodia | Q4 2029 | [15 empty] | TRUE
|  | South Sudan | Q42029 | [15 empty] | TRUE
|  | Tonga | Q42029 | [15 empty] | TRUE
Output 1.3: School safety and educational continuity management systems are operating effectively
Activity 1.3.1 Build capacity of national and sub-national education officials to be master trainers on climate-related school safety | 205 education officials trained to become master trainers on climate-related school resilience (25 Cambodia, 180 South Sudan) | Cambodia | Q42027 | [7 empty] | TRUE
|  | South Sudan | Q12027 |  |  |  |  | TRUE
Activity 1.3.2 Build knowledge and capacity of school management, teachers, and children to prepare climate-related school safety plans | 3,206 school staff and community members trained in climate-related school safety (2,160 Cambodia, 896 South Sudan, 150 Tonga) | Cambodia | Q22027 | [5 empty] | TRUE
|  | South Sudan | Q12027 |  |  |  |  | TRUE
|  | Tonga | Q32027 | [6 empty] | TRUE
Activity 1.3.3 Implement school-level climate-related school safety plans | School-level climate risk mapping and climate resilience plan completed in 415 schools (240 Cambodia, 75 South Sudan, 100 Tonga) | Cambodia | Q22028 | [9 empty] | TRUE
|  | South Sudan | Q42027 | [7 empty] | TRUE
|  | Tonga | Q32028 | [10 empty] | TRUE
Activity 1.3.4 Provide climate resilience tools, equipment and kits to schools | DRR tools, equipment and connectivity package delivered in 415 schools (240 Cambodia, 75 South Sudan, 100 Tonga) | Cambodia | Q32028 | [6 empty] | TRUE
|  | South Sudan | Q22027 | [5 empty] | TRUE
|  | Tonga | Q32028 | [6 empty] | TRUE
Activity 1.3.5 Strengthen access to and use of Early Warning Systems (EWS) and Climate Information Systems (CIS) in schools | 3,206 of school focal points trained in how to use early warning systems (2,160 Cambodia, 896 South Sudan, 150 in Tonga) | Cambodia | Q32028 | [7 empty] | TRUE
|  | South Sudan | Q42028 | [11 empty] | TRUE
|  | Tonga | Q32027 | [6 empty] | TRUE
Output 1.4: Climate change resilience teaching and learning embedded in national systems
Activity 1.4.1 Develop teaching and learning materials on climate change ready to implement through national, non-formal, and informal curriculum | Teaching and learning materials on climate change distributed to 1,860 schools (1,300 Cambodia, 510 South Sudan, 50 Tonga) 1 elective climate change subject developed (Tonga specific) | Cambodia | Q22027 | [5 empty] | TRUE
|  | South Sudan | Q22027 | [5 empty] | TRUE
|  | Tonga | Q32027 | [6 empty] | TRUE
Activity 1.4.2 Build knowledge and capacity of teachers and education managers to implement climate change lessons inside the classroom | 3,180 teachers and education managers trained on pedagogy for climate change, DRR and environmental education and supported to deliver lessons in the classroom (1600 Cambodia, 1530 South Sudan, 50 Tonga) | Cambodia | Q32029 | [14 empty] | TRUE
|  | South Sudan | Q12029 | [12 empty] | TRUE
|  | Tonga | Q4202029 | [15 empty] | TRUE
Activity 1.4.3 Strengthen capacity of child clubs to lead climate change initiatives in their school and community | 315 child groups mobilized to engage in education on climate change, DRR, and the environment (240 Cambodia, 75 South Sudan) | Cambodia | Q22028
|  | South Sudan | Q12028
Activity 1.4.4 Disseminate climate change teaching and learning materials through Ministry of Education e-learning and other platforms | 3 climate change teaching and learning materials uploaded to e-learning platforms (2 Cambodia, 1 Tonga) 6 radio jingles created and played at least 10 times each (South Sudan specific) | Cambodia | Q22028 | [9 empty] | TRUE
|  | South Sudan | Q12027 |  |  |  |  | TRUE
|  | Tonga | Q22029 | [13 empty] | TRUE
Activity 1.4.5 Prepare learning documents and hold events with Ministries of Education and other partners to share experience of integrating climate change into the curriculum | 2 learning documents created and 2 advocacy events completed (1 Cambodia, 1 South Sudan) | Cambodia | Q32028 | [10 empty] | TRUE
|  | South Sudan | Q12029 | [12 empty] | TRUE
Output 2.1 Key stakeholders (in BRACE countries) have access to, and the ability to interpret and utilize relevant climate information as well as participate in decision-making and influence national adaptation planning processes including within the education sector
Activity 2.1.1 Development of education sector risk analyses on the impact of climate change and climate risks on the education sector and children’s learning | 3 country reports that document the impact of climate change on the education sector | Global | Q22027 | [5 empty] | TRUE
Activity 2.1.2 Support Ministries of Education to coordinate with climate change Ministries and engage in NAP processes, including those that may feed into global decisions such as those of the UNFCCC. | 100 government officials, CSOs and other partners working on climate change and education in the three focus countries participate in learning event on education within UNFCCC processes | Global | Q42029 | [15 empty] | TRUE
Output 2.2 Key stakeholders (in BRACE countries) have increased access to, and the ability to utilize, scaled up finance for climate action in the education sector to replicate and scale BRACE to a greater percentage of the country
Activity 2.2.1 Development of climate finance mobilization road maps | 3 country climate finance roadmaps produced for Ministries of Education | Global | Q42029 | [15 empty] | TRUE
Activity 2.2.2 Direct Access Entity (DAE) support for working with the education sector on GCF projects | 3 Ministries of Education supported to prepare concept notes to access climate finance | Global | Q42029 | [19 empty] | TRUE
Output 3.1: Climate resilient education co-investment platform is established and effective in aligning strategic initiatives and financing
Activity 3.1.1 Support a BRACE Climate and Education Financing Coordination Platform, including steering committee and core team | 12 meetings of the BRACE Climate and Education Financing Coordination Platform held 10 joint actions on climate finance taken by the BRACE Climate and Education Financing Coordination Platform | Global | Q42030 | [19 empty] | TRUE
Activity 3.1.2 Face-to-Face meetings between Ministries of Education and Environment for cross-learning and building political momentum | 3 countries engaged in Face-to-Face meetings involving Ministries of Environment and Ministries of Education | Global | Q42029 | [15 empty] | TRUE
Activity 3.1.3 Map and track global climate finance opportunities in the education sector | 1 site tracking global finance opportunities in the education sector produced | Global | Q22028 | [9 empty] | TRUE
Activity 3.1.4 Support adjustments to international climate finance reporting to reflect dual-benefit investments in climate and education | 1 report outlining adjustments to international climate finance endorsed by BRACE Climate and Education Financing Coordination Platform | Global | Q32027 | [6 empty] | TRUE
Output 3.2: Key stakeholders are supported to engage in peer learning and exchange through south-south collaboration
Activity 3.2.1 Develop and host information on the CSESI knowledge management platform on climate change and education for improved evidence and learning | 1 site with information on climate change and education established within the knowledge management platform for climate and education | Global | Q42026 |  |  |  | TRUE
Activity 3.2.2 Develop guidance on climate and education for the GCF and the global education sector | 7 guidance materials on climate and education produced | Global | Q42029 | [15 empty] | TRUE
Activity 3.2.3 Organize webinars, thematic sessions and learning events on climate change and education | 12 webinars on climate and education topics completed | Global | Q42030 | [19 empty] | TRUE
Activity 3.2.4 Develop and share strategic communications materials | Total of 25 communications assets (including blogs, articles, videos) produced | Global | Q42030 | [19 empty] | TRUE
M&E | Monitoring and evaluation
| Annual performance reporting |  | Annually |  |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  |  | TRUE |  |  | TRUE
| Inception report |  | Q2 Year 1 |  | TRUE
| Baseline |  | Q2 Year 1 |  | TRUE
| Midline |  | Q2 Year 3 | [9 empty] | TRUE
| Completion |  | Q2 Year 6 | [20 empty] | TRUE
| Endline |  | Q2 Year 6 | [21 empty] | TRUE