## Implementation
Annex 5. Implementation Timetable
Project/Programme Title: Building Urban Climate Resilience through Nature-based Solutions in Ethiopia
Outcome | Output | Activity | Sub-Activity | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  | Post-project Milestone
|  |  |  | 27/Q3 | 27/Q4 | 28/Q1 | 28/Q2 | 28/Q3 | 28/Q4 | 29/Q1 | 29/Q2 | 29/Q3 | 29/Q4 | 30/Q1 | 30/Q2 | 30/Q3 | 30/Q4 | 31/Q1 | 31/Q2 | 31/Q3 | 31/Q4 | 32/Q1 | 32/Q2 | 32/Q3 | 32/Q4 | 33/Q1 | 33/Q2
Outcome 1: Enhanced and institutionalized enabling environment and operational capacity in national/sub-national institutions to integrate and scale up NbS for urban climate adaptation |  |  |  | 2 | 4 | 5 | 5 | 10 | 10 | 8 | 8 | 5 | 7 | 4 | 5 | 4 | 6 | 4 | 5 | 4 | 6 | 4 | 5 | 4 | 6
| Output 1.1. Strengthened multi-level governance systems for urban NbS implementation |  |  | 1 | 2 | 2 | 2 | 7 | 7 | 5 | 5 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4
1.1.1. Establishment of an inter-sectoral coordination mechanism for urban NbS | bar: Year 1 27/Q3 to Year 6 32/Q4
|  | 1.1.2. Development of a national urban NbS framework and supportive regulations |  | 0 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.1.2.1: Development of a national urban NbS framework aligned with local contexts and stakeholder insights | bar: Year 1 27/Q4 to Year 2 28/Q3
1.1.2.2: Revision and development of policies and regulations to enable institutional application of urban and peri-urban NbS | bar: Year 2 28/Q3 to Year 2 29/Q2
|  | 1.1.3. Integration of the urban NbS framework into national and municipal programmes |  | 0 | 0 | 0 | 0 | 2 | 3 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1
1.1.3.1: Development of NbS integration guidelines for green and climate-relevant projects | bar: Year 2 28/Q3 to Year 2 28/Q4
1.1.3.2: Development of a monitoring and evaluation system for NbS integration | bar: Year 2 28/Q3 to Year 2 28/Q4
1.1.3.3: Technical capacity development and institutional knowledge enhancement for NbS integration | bar: Year 2 28/Q4 to Year 2 29/Q2; Year 3 29/Q4; Year 3 30/Q2; Year 4 30/Q4; Year 4 31/Q2; Year 5 31/Q4; Year 5 32/Q2; Year 6 32/Q4
|  | 1.1.4. Support for planning and implementation of the urban NbS framework at municipal level |  | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1.1.4.1: Development of city-specific urban NbS frameworks and action plans | bar: Year 2 28/Q3 to Year 2 28/Q4
1.1.4.2: Implementation support for urban NbS framework | bar: Year 2 29/Q1 to Year 6 32/Q4
1.1.4.3: Capacity building for urban NbS project design | bar: Year 2 28/Q3 to Year 6 32/Q4
| Output 1.2. Improved capacity to scale up NbS throughout Ethiopia |  |  | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2
|  | 1.2.1. Conduct of research to map climate vulnerability and identify NbS opportunities |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.1.1: Methodology development for climate vulnerability assessment and data management | bar: Year 1 28/Q1 to Year 2 28/Q4
1.2.1.2: Conduct of research to develop strategic urban NbS frameworks for secondary cities | bar: Year 2 29/Q1 to Year 3 29/Q4
1.2.1.3: Development of design guidelines and toolkits for NbS implementation | bar: Year 1 27/Q3 to Year 2 29/Q2
|  | 1.2.2. Development of a centralized knowledge management framework |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 2
1.2.2.1: Establishment of an urban NbS knowledge management framework | bar: Year 1 27/Q4 to Year 2 28/Q4; Year 3 29/Q4; Year 4 30/Q4; Year 5 31/Q4; Year 6 32/Q4
1.2.2.2: Collection and management of data to assess climate vulnerability and impacts | bar: Year 2 29/Q1 to Year 6 32/Q4
Outcome 2: Reduced climate-induced vulnerability for urban residents through the implementation of target NbS projects across key areas in Addis Ababa and Jimma |  |  |  | 6 | 6 | 12 | 12 | 13 | 13 | 15 | 15 | 17 | 17 | 14 | 16 | 18 | 18 | 20 | 20 | 20 | 20 | 18 | 18 | 14 | 14
| Output 2.1. Established climate-resilient infrastruture and green spaces in Addis Ababa |  |  | 3 | 3 | 6 | 6 | 7 | 7 | 8 | 8 | 9 | 9 | 7 | 8 | 9 | 9 | 10 | 10 | 10 | 10 | 9 | 9 | 7 | 7
|  | 2.1.1. Forestland restoration and natural regeneration in the upper catchment areas of Jemo-Harbu River |  | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1
2.1.1.1: Implementation of tree planting and natural regeneration activities | bar: Year 1 27/Q3 to Year 3 29/Q4
2.1.1.2: Establishment of nurseries for indigenous and multipurpose tree species | bar: Year 1 28/Q1 to Year 5 31/Q4
2.1.1.3: Value chain assessment, training, and income-generation support | bar: Year 2 29/Q1 to Year 5 32/Q2
2.1.1.4: Establishment of community-led monitoring and sustainable forest management systems | bar: Year 4 31/Q1 to Year 6 32/Q4
|  | 2.1.2. Enhancement of climate-resilient buffer and green spaces in urban areas |  | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
2.1.2.1: Integrated planning and technical design of NbS interventions | bar: Year 1 27/Q3 to Year 2 29/Q2
2.1.2.2: Development of eco-friendly river buffer zones | bar: Year 1 28/Q1 to Year 3 29/Q4
2.1.2.3: Development of urban farming areas | bar: Year 3 29/Q3 to Year 3 29/Q4
2.1.2.4: Development of green canopies and public space enhancements | bar: Year 2 28/Q3 to Year 3 29/Q4
2.1.2.5: Community-linked maintenance and waste management for restored urban spaces | bar: Year 3 30/Q1 to Year 5 32/Q2
|  | 2.1.3. Integration of climate-smart urban agriculture into green spaces |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
2.1.3.1: Value chain analysis and establishment of climate-smart urban agriculture systems | bar: Year 3 30/Q1 to Year 6 32/Q4
2.1.3.2: CSA technical training and community capacity building | bar: Year 3 30/Q2 to Year 6 32/Q4
2.1.3.3: Market access facilitation and development of community-led sustainable livelihood models | bar: Year 4 30/Q3 to Year 6 32/Q4
|  | 2.1.4. Facilitation of community-led green infrastructure development and environmental management |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
2.1.4.1: Awareness-raising on environmental management and climate resilience | bar: Year 1 27/Q3 to Year 6 32/Q4
2.1.4.2: Operational support and capacity building for local industry, livelihood, and private groups (LLPGs) | bar: Year 1 28/Q1 to Year 6 32/Q4
2.1.4.3: Establishment of community-led monitoring and sustainable environmental management systems for NbS sites | bar: Year 3 29/Q3 to Year 6 32/Q4
| Output 2.2. Improved climate-affected ecosystems in Jimma |  |  | 3 | 3 | 6 | 6 | 6 | 6 | 7 | 7 | 8 | 8 | 7 | 8 | 9 | 9 | 10 | 10 | 10 | 10 | 9 | 9 | 7 | 7
|  | 2.2.1. Forestland conservation and restoration in the upper catchment areas of Awetu River |  | 1 | 1 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1
2.2.1.1: Implementation of tree planting and natural regeneration activities | bar: Year 1 27/Q3 to Year 3 29/Q4
2.2.1.2: Establishment of nurseries for indigenous and multipurpose tree species | bar: Year 1 28/Q1 to Year 5 31/Q4
2.2.1.3: Introduction of agroforestry in the lower area of the upper catchment | bar: Year 2 29/Q1 to Year 5 32/Q2
2.2.1.4: Establishment of community-led monitoring and sustainable forest management systems | bar: Year 4 31/Q1 to Year 6 32/Q4
|  | 2.2.2. Integrated planning and development of riverbank buffer zones |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
2.2.2.1: Integrated planning and technical design of NbS interventions | bar: Year 1 27/Q3 to Year 2 29/Q2
2.2.2.2: Development of eco-friendly river buffer zones | bar: Year 1 28/Q1 to Year 3 29/Q4
2.2.2.3: Development of urban agroforestry spaces | bar: Year 3 29/Q3 to Year 3 29/Q4
2.2.2.4: Community-linked maintenance and waste management for restored urban spaces | bar: Year 3 30/Q1 to Year 5 32/Q2
|  | 2.2.3. Introduction and establishment of climate-smart urban agriculture in green spaces |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
2.2.3.1: Value chain analysis and establishment of climate-smart urban agriculture systems | bar: Year 3 30/Q1 to Year 6 32/Q4
2.2.3.2: Establishment of climate-smart horticulture and fruit tree cultivation with community training | bar: Year 3 30/Q2 to Year 6 32/Q4
2.2.3.3: Market access facilitation and development of community-led sustainable livelihood models | bar: Year 4 30/Q3 to Year 6 32/Q4
|  | 2.2.4. Facilitation of community-led natural resource and environmental management |  | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
2.2.4.1: Awareness-raising on environmental management and climate resilience | bar: Year 1 27/Q3 to Year 6 32/Q4
2.2.4.2: Operational support and capacity building for local industry, livelihood, and private groups (LLPGs) | bar: Year 1 28/Q1 to Year 6 32/Q4
2.2.4.3: Establishment of community-led monitoring and natural resource management systems for NbS sites | bar: Year 3 29/Q3 to Year 6 32/Q4
Outcome 3: Technical and financial resources channeled to successfully scale and implement NbS projects in additional, climate-vulnerable cities |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
| Output 3.1. Mobilized resources to new urban NbS projects in priority climate-vulnerable cities |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
|  | 3.1.1. Identification of scale-up NbS projects in selected cities and co-development of detailed implementation plans |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.1.1.1: Final Selection of Target Cities and Validation of Project Scope by the Inter-Sectoral Coordination Committee for Urban NbS | bar: Year 2 29/Q1 to Year 3 29/Q4
3.1.1.2: Co-development of Detailed Implementation Plans | bar: Year 2 29/Q1 to Year 3 29/Q4
3.1.1.3: Contracting with City Administrations to Initiate Project Implementation | bar: Year 2 29/Q1 to Year 3 29/Q4
|  | 3.1.2. Administration of oversight and performance management |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0
3.1.2.1: Establishment of a Monitoring and Evaluation system with core indicators, reporting requirements, and compliance mechanisms | bar: Year 3 30/Q1 to Year 5 32/Q2
3.1.2.2: Execution of oversight activities and performance reviews for compliance, accountability, and impact measurement | bar: Year 3 30/Q1 to Year 5 32/Q2
3.1.2.3: Collection, analysis, and reporting of M&E data for decision-making and stakeholder engagement | bar: Year 3 30/Q1 to Year 5 32/Q2
Project Monitoring |  |  |  | Year 1 28/Q1: APR; Year 2 29/Q1: APR; Year 3 30/Q1: APR; Year 4 30/Q3: Interim Report; Year 4 31/Q1: APR; Year 5 32/Q1: APR; Post-project Milestone 33/Q1: Completion Report; Post-project Milestone 33/Q2: Final Evaluation