## Sheet1
Annex 5: Implementation Timetable |  |  | CODE: | Activity (with name of relevant country) | Deliverable | Inception period | Exit stage
Project Title: Establishing resilient, regenerative agricultural systems in Tonga, Vanuatu and Samoa
Accredited Entity: SPC; Version 2: 17.10.2025
| DESCRIPTION | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | After End of project Implementation
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Inception | Project set-up; establishing project team and operating systems | bar: Year 1 Q1 to Year 1 Q2
Re-validate project workplan, set stakeholder management process and communication protocols | bar: Year 1 Q1 to Year 1 Q2
| Inception report with updated workplan and detailed implementation timeline | Year 1 Q2: Inception report
Outcome 1 | Enabling enviornment strengthened for the transition to climate-resilient regenerative agriculture
Output 1.1 | Cross sectoral capacity and partnerships for the adaptive implementation of CRRA practices
Activity 1.1.1. | Establish and sustain national CRRA Muti-Stakeholder Working Groups
| Convene multi-sector working group in each country, including representatives from Ministry of Agriculture (and extension workers), agricultural research institutes responsible for monitoring system (see output 2.2), farmer associations etc. and develop TORs, governance arrangements and workplan for the group. At least 35% of the Working Group members should be women. | Year 1 Q1: Tonga, Vanuatu, Samoa
| Conduct regional technical training of all three CRRA Working Groups on CRRA and finalize of project work plan | Year 1 Q2: Tonga, Vanuatu, Samoa; Year 2 Q2: Tonga, Vanuatu, Samoa
| Review evidence collected and project progress in CRRA Working Group meetings every 6 months to prepare CRRA guidelines | Year 1 Q2: Tonga, Vanuatu, Samoa; Year 1 Q4: Tonga, Vanuatu, Samoa; Year 2 Q2: Tonga, Vanuatu, Samoa; Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q2: Tonga, Vanuatu, Samoa; Year 3 Q4: Tonga, Vanuatu, Samoa; Year 4 Q2: Tonga, Vanuatu, Samoa; Year 4 Q4: Tonga, Vanuatu, Samoa; Year 5 Q2: Tonga, Vanuatu, Samoa; Year 5 Q4: Tonga, Vanuatu, Samoa
| Annual meeting of all three CRRA Working Groups with regional project team to share learning and review progress across the regional project | Year 1 Q4: Tonga, Vanuatu, Samoa; Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q4: Tonga, Vanuatu, Samoa; Year 4 Q4: Tonga, Vanuatu, Samoa; Year 5 Q4: Tonga, Vanuatu, Samoa
Activitiy 1.1.2 | Working Groups co-design context-specific CRRA principles and practices
| Convene an in-person international advisory body of select CRRA experts to review and advise the Working Group, and participate in Regional Training session of all three CRRA working groups (see Activity 1.1.1) to finalize TORs and responsibilities | Year 1 Q2: Tonga, Vanuatu, Samoa; Year 2 Q2: Tonga, Vanuatu, Samoa
| Prepare analysis using data from the learning farms (see Sub-Activity 2.1.2.5) and evidence from other sources (including documenting traditional practices as required) and provide technical support to the Working Groups to review this evidence and then prepare and update periodically, context-specific CRRA principles and practices that form the basis of the advice provided to farmers. | Year 1 Q2: CRRA guidelines documents; Year 1 Q4: CRRA guidelines documents; Year 2 Q2: CRRA guidelines documents; Year 2 Q4: CRRA guidelines documents; Year 3 Q2: CRRA guidelines documents; Year 3 Q4: CRRA guidelines documents; Year 4 Q2: CRRA guidelines documents; Year 4 Q4: CRRA guidelines documents; Year 5 Q2: CRRA guidelines documents; Year 5 Q4: CRRA guidelines documents
| International advisors provide (remote) technical review of Working Groups' CRRA principles and practices | Year 1 Q2: Tonga, Vanuatu, Samoa; Year 1 Q4: Tonga, Vanuatu, Samoa; Year 2 Q2: Tonga, Vanuatu, Samoa; Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q2: Tonga, Vanuatu, Samoa; Year 3 Q4: Tonga, Vanuatu, Samoa; Year 4 Q2: Tonga, Vanuatu, Samoa; Year 4 Q4: Tonga, Vanuatu, Samoa; Year 5 Q2: Tonga, Vanuatu, Samoa; Year 5 Q4: Tonga, Vanuatu, Samoa
Activity 1.1.3 | Develop and implement training of trainers (ToT) programme on CRRA
| Develop training materials and delivery plan on CRRA, in collaboration with established training institutes/ associations, targeting capacity needs, interests, and potential influence in farming practices of the different ToT stakeholder groups. | Year 1 Q2: Tonga, Vanuatu, Samoa; Year 1 Q4: ToT training programme: Tonga, Vanutau, Samoa
| Conduct and evaluate training to ToT stakeholder groups, prioritising on-farm sessions and engaging with lead farmers. | Year 2 Q1: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Invite ToT stakeholder groups to participate in CRRA Working Groups to communicate their experiences of supporting farmers to adopt CRRA. | Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q4: Tonga, Vanuatu, Samoa; Year 4 Q4: Tonga, Vanuatu, Samoa; Year 5 Q4: Tonga, Vanuatu, Samoa
Ouput 1.2 | Markets enhanced to promote and incentivise CRRA initiatives
Activitiy 1.2.1 | Support farmer associations to develop viable business plans for adoption and marketing of CRRA practices
| Design and deliver intensive 20-day training sessions/ small group coaching sessions of a select group (of which 35% will be women) of lead farmers and other targeted farmers, to improve their immediate and long-term income from their farm. In each country, there will be four sessions every year in Years 2-4, with around 40 farmers per session. This will include training in good farm business management practices including strengthening their financial resilience to extreme weather events, develop business plans and adopt value addition practices. | Year 2 Q1: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
Activitiy 1.2.2 | Support agri-businesses to develop viable business plans for provision of CRRA related inputs and services
| Train and support a select group of 90 existing entrepreneurs/ companies (of which 35% will be women-led to develop business plans for developing allied services that will support CRRA, and to put in place the initial actions required to achieve this. This will involve national level intense training sessions (approximately 20-day of training annually for Years 2-4) and on-demand support provided till Year 5 and will involve engagement and interaction between the agri-businesses and relevant farmers. | Year 2 Q1: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
Activity 1.2.3 | Technical assistance to the Ministries of Agriculture to design policy enablers to encourage the adoption of CRRA and reform projects and subsidies which disincentivize CRRA.
| Carry out cost-benefit analysis of existing government schemes, agricultural projects and subsidies and particularly whether and how they are supporting the adoption of CRRA practices, and identify opportunities for policy enablers across the value chain of CRRA products to incentivize such practices | Year 2 Q1: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| CRRA Working Groups review the findings of the analysis and prioritize the areas of policy reform required | Year 2 Q3: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Develop a roadmap for reforming existing projects, financial schemes and subsidies and designing new ones, to be discussed and approved through the relevant national governance structures. It will then be reviewed and updated periodically. | Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 3 Q2: Policy roadmaps: Tonga, Vanutau, Samoa; Year 3 Q3: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Provide technical assistance to the Ministries of Agriculture to adopt and implement at least one of the identified priority policy reforms required | Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
Outcome 2 | Practices, systems and technologies adopted for Climate Resilient and Regenerative Agriculture
Output 2.1 | CRRA systems established through training, demonstration and farmer support
Activity 2.1.1 | Engage with local government and traditional structure and integrate project activities within community/ provincial plans as appropriate
| Socialize CRRA concepts and practices to key community leaders, including traditional leaders, Chiefs, community/ provincial government officers and civil society leaders, and build awareness of climate change impact on agriculture and agriculture impact on climate change; | Year 1 Q3: Tonga, Vanuatu, Samoa; Year 3 Q3: Tonga, Vanuatu, Samoa; Year 5 Q3: Tonga, Vanuatu, Samoa
| Encourage and support the local government officers to integrate the project activities within annual development plans or any community plan specifically on addressing climate change. | Year 1 Q3: Tonga, Vanuatu, Samoa; Year 1 Q4: Mainstreamed local plan: Tonga, Vanutau, Samoa; Year 3 Q3: Tonga, Vanuatu, Samoa; Year 3 Q4: Mainstreamed local plan: Tonga, Vanutau, Samoa; Year 5 Q3: Tonga, Vanuatu, Samoa; Year 5 Q4: Mainstreamed local plan: Tonga, Vanutau, Samoa
| Formal convening of community leaders at mid-point and final year of the project, but also regular updates from PMU every 6 months on project activities and results and discuss any challenges or concerns emerging from the community | Year 1 Q4: Tonga, Vanuatu, Samoa; Year 2 Q2: Tonga, Vanuatu, Samoa; Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q2: Tonga, Vanuatu, Samoa; Year 3 Q4: Tonga, Vanuatu, Samoa; Year 4 Q2: Tonga, Vanuatu, Samoa; Year 4 Q4: Tonga, Vanuatu, Samoa; Year 5 Q2: Tonga, Vanuatu, Samoa; Year 5 Q4: Tonga, Vanuatu, Samoa
Activity 2.1.2 | Implement training programmes for farmers on CRRA practices, systems and technologies
| Select and convene 20 lead farmers in each country (of which at least 50% will be women) for provincial workshops for initial sensitization to the project and CRRA practices. | Year 1 Q2: Tonga, Vanuatu, Samoa
| Prepare integrated training, piloting, monitoring plan and materials, specific for each lead farmer, for adopting and monitoring benefits of CRRA practices. This will be summarized in a Letter of Agreement with each lead farmer, which also outlines expectations of the PMU on the farmer. | Year 1 Q3: Tonga, Vanuatu, Samoa; Year 1 Q4: Individual lead farmer support plan (60)
| Deliver on-farm training, refresher training and continuous handholding for each lead farmer, for adopting and monitoring benefits of CRRA practices. This will be delivered by the ToT trained under Activity 1.1.3. | Year 1 Q3: Tonga, Vanuatu, Samoa; Year 2 Q1: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Collect data and feedback every 6 months on progress and costs/ benefits of adopting CRRA practices from learning farms, and input into internal project data tracking sheet. | Year 1 Q4: Lead farmer monitoring report; Year 2 Q2: Lead farmer monitoring report; Year 2 Q4: Lead farmer monitoring report; Year 3 Q2: Lead farmer monitoring report; Year 3 Q4: Lead farmer monitoring report; Year 4 Q2: Lead farmer monitoring report; Year 4 Q4: Lead farmer monitoring report; Year 5 Q2: Lead farmer monitoring report; Year 5 Q4: Lead farmer monitoring report
| Analyze and package the monitoring data and provide a set of recommended actions every 6 months (Y2-5) to integrate learning from the lead farmers into the CRRA guidance (for review by CRRA Working Groups) | Year 2 Q1: Evidence synthesis: Tonga, Vanuatu, Samoa; Year 2 Q3: Evidence synthesis: Tonga, Vanuatu, Samoa; Year 3 Q1: Evidence synthesis: Tonga, Vanuatu, Samoa; Year 3 Q3: Evidence synthesis: Tonga, Vanuatu, Samoa; Year 4 Q1: Evidence synthesis: Tonga, Vanuatu, Samoa; Year 4 Q3: Evidence synthesis: Tonga, Vanuatu, Samoa; Year 5 Q1: Evidence synthesis: Tonga, Vanuatu, Samoa; Year 5 Q3: Evidence synthesis: Tonga, Vanuatu, Samoa
| At the end of the project, support each learning farm to update business plan prepared at project mid-term (activity 1.2.1) and prepare a sustainability plan on how to scale up CRRA practices. | Year 3 Q2: Tonga, Vanuatu, Samoa
Activity 2.1.3 | Develop and operationalize a farmer support programme for CRRA
| •Operationalize the farmer support programme (modalities, competitive selection of providers etc.) and prepare information notes in each country, in local languages, for lead and other farmers to be circulated and explained during the training conducted under Activity 2.1.1 and Activity 2.1.4. | Year 1 Q2: Tonga, Vanuatu, Samoa; Year 1 Q3: Farmer Support Programme Operating Manual; Year 1 Q4: Tonga, Vanuatu, Samoa; Year 2 Q1: Tonga, Vanuatu, Samoa
| •Procure and distribute required inputs to support CRRA practices among lead farmers, with 50% of recipients being women. This is on the basis of the LoA with each leading farmer under Sub-Activity 2.1.2.2. | Year 1 Q3: Tonga, Vanuatu, Samoa
| •Accept applications from other farmers for the FSP via the PMU (including the provincial level officers) and competitively select every quarter. The PMU will finalize and validate the needs with each individual farmer, and a final LoA will be signed with each. The inputs will be procured and distributed amongst the other targeted farmers (approx..940). With at least 35% of recipients being female farmers. | Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| •Provide training on use and maintenance of any technology or other relevant inputs, and monitor the use and value of these inputs, during the training conducted under Activity 2.1.2 and Activity 2.1.4. | Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
Activity 2.1.4 | Facilitate active peer-to-peer learning to promote wider adoption and replication of CRRA practices
| Organise open farm workshops for select demonstration farms to showcase CRRA practices to other farmers in the locality, as well as schools, churches and other community groups (Y3-Y5) | Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Prepare training materials for on-farm training sessions on CRRA practices at select demonstration farms with interested other farmers (of which at least 50% should be women), including through the farmer association and other networks of farmers. | Year 2 Q1: Training materials for on-farm sessions; Year 2 Q2: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Deliver on-farm training sessions at select demonstration farms on CRRA practices with interested other farmers (of which at least 35% should be women), including through the farmer association and other networks of farmers. | Year 2 Q1: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
Output 2.2 | Monitoring, evaluation and knowledge systems established for continuous learning and improvement of CRRA practices
Activity 2.2.1 | Develop and disseminate knowledge products to promote wider adoption and replication of CRRA practices
| Prepare communication material, including videos, leaflets in local languages, on costs, benefits and practical advice on how to adopt CRRA practices. | Year 2 Q1: Tonga, Vanuatu, Samoa; Year 2 Q4: CRRA communication materials
| Disseminate communication material through a range of channels, including in-person through farmer associations, buyers, CBOs, on the Ministry website and through existing social media channels | Year 2 Q3: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Develop and update dedicated webpages on existing national websites and the SPC website to showcase experience, learning and research (including monitoring data) targeting both farmers but also research community and other funders | Year 2 Q3: national webpages on CRRA; Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q3: Tonga, Vanuatu, Samoa; Year 4 Q3: Tonga, Vanuatu, Samoa; Year 5 Q3: Tonga, Vanuatu, Samoa
Activity 2.2.2 | Develop / Upgrade and support the roll-out of farmer mobile phone apps in each country
| Carry out a functional review of the current design of the app in each country, and feasibility of different options for integrating CRRA practices within them | Year 2 Q1: Vanuatu, Samoa
| Provide technical assistance to the Ministry of Agriculture in Tonga to develop a prototype agricultural app, learning from the experiences of the other two countries. | Year 2 Q3: Tonga; Year 3 Q1: Tonga
| Plan, develop, continuously update the required design or re-design of the apps to provide features that will support CRRA practices, such as the type of advice being provided, and allowing farmers to input their resilience monitoring results (see Activity 2.2.3) for more customized advice. | Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Updated/ new app; Year 4 Q2: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Pilot the roll-out of the app/ redeveloped app features with select group of lead farmers (of which at least 50% should be female) to evaluate functionality and benefits, and further refine as required. | Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 3 Q4: Piloting report of app
| Encourage uptake of the farmer app within the trainings conducted under Activity 2.1.1, Activity 2.1.4. and knowledge products under Activity 2.2.1. | Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
| Develop and implement a sustainability plan for each app so they are self-sufficient for future updates and scaling-up. | Year 5 Q1: Tonga, Vanuatu, Samoa
Activitiy 2.2.3 | Develop sustainable national monitoring systems for climate resilience of agricultural systems
| Develop monitoring protocols for technical requirements and process of collecting and monitoring data for core resilience indicators | Year 2 Q1: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 3 Q3: Monitoring protocols
| Develop long-term plan for building self-sufficient institutional system for monitoring core resilience indicators at the farm level that are required for resilience and mitigation measures. | Year 2 Q3: Tonga, Vanuatu, Samoa; Year 3 Q1: Tonga, Vanuatu, Samoa; Year 3 Q3: Sustainability plan for monitoring system
| Pilot data collection for monitoring core indicators in learning farms as part of Activity 2.1.2, evaluate effectiveness and adjust monitoring protocols as required. | Year 2 Q2: Tonga, Vanuatu, Samoa; Year 2 Q4: Tonga, Vanuatu, Samoa; Year 3 Q2: Tonga, Vanuatu, Samoa; Year 3 Q4: Tonga, Vanuatu, Samoa; Year 4 Q4: Tonga, Vanuatu, Samoa; Year 5 Q2: Tonga, Vanuatu, Samoa; Year 5 Q4: Tonga, Vanuatu, Samoa
| Provide intensive training and mentoring to support national organisations to roll out data collection process across country, including via the Soils Portal. | Year 2 Q3: Tonga, Vanuatu, Samoa; Year 3 Q3: Tonga, Vanuatu, Samoa; Year 4 Q3: Tonga, Vanuatu, Samoa; Year 5 Q3: Tonga, Vanuatu, Samoa
| Establish and operationalize a system for publishing raw downloadable data on online portals such as the Pacific Soils Portal (see Activity 2.2.1.3) for the benefit of wider partners and research communities and for Ministries of Agriculture to prepare and publish analysis on the CRRA data as part of their annual reporting process | Year 3 Q2: Tonga, Vanuatu, Samoa; Year 3 Q4: Reporting protocols for monitoring data; Year 4 Q1: Tonga, Vanuatu, Samoa; Year 5 Q1: Tonga, Vanuatu, Samoa
Activity 2.2.4 | Document and share learning from the project to wider communities of practice in the region
| Organize national annual learning workshops involving all major project stakeholders to share and document internal reflection and learning on the effectiveness of the project in facilitating uptake of CRRA. Organize side-events and stalls at annual national Agricultural Shows, Agricultural Conferences and Pacific Week of Agriculture and Forestry (2025/ 2027/2029) | Year 2 Q3: Tonga, Vanuatu, Samoa; Year 3 Q3: Tonga, Vanuatu, Samoa; Year 4 Q3: Tonga, Vanuatu, Samoa
| Publish 'practitioner voices' - a series of informal blogs from individuals involved in delivering the project on their personal reflections and learning - on knowledge platforms (Activity 2.2.1.3) | Year 2 Q4: Regional; Year 3 Q4: Regional; Year 4 Q4: Regional; Year 5 Q4: Regional
| Organize final regional workshop to showcase learning and results but focused on other funders and partners to also identify opportunities to scale up through other programmes. | Year 5 Q3: Regional
| Publish final learning paper, and accompanying academic journal, to disseminate the data but also analysis on good practices and learning for uptake of CRRA. | Year 5 Q2: Regional; Year 5 Q4: Final learning paper
| Carry out in-depth studies to support the ongoing M&E of the project. | Year 3 Q2: Regional; Year 4 Q2: Regional; Year 5 Q2: Regional
Exit phase | Exit plan: Consolidate sustainability plan for knowledge and institutional resources | bar: Year 5 Q4
Close down of project | bar: Year 5 Q4
Project Monitoring* |  | Year 1 Q2: Inception Report; Year 2 Q1: APR; Year 3 Q1: APR; Year 4 Q1: APR; Year 5 Q1: APR; After End of project Implementation Q1: Final APR
Evaluation |  | Year 1 Q4: Baseline report; Year 2 Q4: Data collection for Interim Evaluation; Year 3 Q2: Interim Evaluation Report; Year 5 Q4: Data collection for Final Evaluation; After End of project Implementation Q2: Final Evaluation Report
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.