## FrontCover
JORDAN INTEGRATED LANDSCAPE MANAGEMENT INITIATIVE (JILMI)
ANNEX 5
IMPLEMENTATION TIMETABLE

## Implementation plan
Annex 5 Implementation Timetable
Project Title: Peru’s Natural Legacy – Amazon & Climate (PdP A&C): Effective Management of Peruvian Amazon Protected Areas for Climate Change Mitigation and Adaptation
OUTPUTS, ACTIVITIES, SUB-ACTIVITIES | Deliverables | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7 |  |  |  | Closure
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Output 1.1: Strengthened institutional capacity and sustainable management planning in 25 NPAs.
Activity 1.1.1: Implement physical demarcation of NPA boundaries to reduce threats across the 25 NPAs. | One demarcation needs report (disaggregated by NPA) | Year 2 Q2: One demarcation needs report (disaggregated by NPA)
| Dataset with geo-locations for demarcation infrastructure (disaggregated by NPA) | Year 3 Q2: Dataset with geo-locations for demarcation infrastructure (disaggregated by NPA)
| 15 physical demarcation markers in place | Year 6 Q4: 15 physical demarcation markers in place
| Maintenance reports (disaggregated by NPA) | Year 7 Q4: Maintenance reports (disaggregated by NPA)
| At least 120 SERNANP staff trained on demarcation processes | Year 4 Q4: At least 120 SERNANP staff trained on demarcation processes
| a. Intervention guide on demarcation b. 9 workshops with stakeholders on recognising new PA boundaries | Year 3 Q4: Intervention guide on demarcation; Year 7 Q2: 9 workshops with stakeholders on recognising new PA boundaries
Activity 1.1.2: Enhance master plans for the 25 NPAs. | a. Methodological protocol developed b. Guide developed | Year 2 Q4: a. Methodological protocol developed b. Guide developed
| At least 60 SERNANP staff trained on climate change mitigation and adaptation, including incorporating climate considerations into NPA master plans using the new protocol and guide. | Year 6 Q4: At least 60 SERNANP staff trained on climate change mitigation and adaptation, including incorporating climate considerations into NPA master plans using the new protocol and guide.
| 25 NPA master plans updated | Year 6 Q4: 25 NPA master plans updated
| a. Audiovisual material developed in Spanish and the local Indigenous language b. 25 workshops on climate change considerations each targeting 300 members of local communities c. 25 workshops for environmental educators of local educational establishments | Year 7 Q2: a. Audiovisual material developed in Spanish and the local Indigenous language b. 25 workshops on climate change considerations each targeting 300 members of local communities c. 25 workshops for environmental educators of local educational establishments
Activity 1.1.3: Strengthen governance of the 25 NPAs. | a. At least 25 meetings and 25 sets of management committees general assembly minutes for each year of the project (1 meeting per NPA) b At least 15 members of each of the 25 management committees trained on participatory management | Year 7 Q4: a. At least 25 meetings and 25 sets of management committees general assembly minutes for each year of the project (1 meeting per NPA) b At least 15 members of each of the 25 management committees trained on participatory management
| a. 3 meetings held and 3 records of National Coordination Council assembly minutes (1 for every other year of the project) b. Macroregional meeting minutes | Year 1 Q4: 1.1.3.2.a National Coordination Council assembly minutes for every other year of the project; Year 3 Q4: 1.1.3.2.a National Coordination Council assembly minutes for every other year of the project; Year 5 Q4: 1.1.3.2.a National Coordination Council assembly minutes for every other year of the project; Year 7 Q4: 1.1.3.2.a National Coordination Council assembly minutes for every other year of the project
| Annual monitoring reports on management committee capacity and inclusion of women, indigenous peoples and vulnerable groups | Year 2 Q4: Annual monitoring reports on management committee capacity and inclusion of women, indigenous peoples and vulnerable groups; Year 3 Q4: Annual monitoring reports on management committee capacity and inclusion of women, indigenous peoples and vulnerable groups; Year 4 Q4: Annual monitoring reports on management committee capacity and inclusion of women, indigenous peoples and vulnerable groups; Year 5 Q4: Annual monitoring reports on management committee capacity and inclusion of women, indigenous peoples and vulnerable groups; Year 6 Q4: Annual monitoring reports on management committee capacity and inclusion of women, indigenous peoples and vulnerable groups; Year 7 Q4: Annual monitoring reports on management committee capacity and inclusion of women, indigenous peoples and vulnerable groups
Output 1.2: Improved surveillance, control and monitoring of 25 NPAs to reduce deforestation.
Activity 1.2.1: Implement effective surveillance and control activities to reduce deforestation in the 25 NPAs. | a. 25 Equipment lists of procured equipment (1 per NPA) b. 25 Equipment maintenance reports (1 per NPA) | Year 2 Q4: a. 25 Equipment lists of procured equipment (1 per NPA)
| a. 12 workshops to train SERNANP staff completed b. Final training report (including list of staff trained) | Year 3 Q4: b. 25 Equipment maintenance reports (1 per NPA); Year 4 Q4: b. 25 Equipment maintenance reports (1 per NPA); Year 5 Q4: b. 25 Equipment maintenance reports (1 per NPA); Year 6 Q4: b. 25 Equipment maintenance reports (1 per NPA); Year 7 Q4: b. 25 Equipment maintenance reports (1 per NPA)
| 25 NPA-specific control and prevention strategy implementation reports | Year 7 Q4: 25 NPA-specific control and prevention strategy implementation reports
| 9 control posts built in strategic sectors in NPAs with a high risk of deforestation. | Year 7 Q4: 9 control posts
Activity 1.2.2: Improve environmental and biological monitoring capacity to reduce risks of deforestation in the 25 NPAs. | Tools developed (protocols, guidelines, and plans) for environmental and biological monitoring | Year 2 Q4: Tools developed (protocols, guidelines, and plans) for environmental and biological monitoring
| a. 25 Lists of procured equipment for conducting environmental and biological monitoring in the 25 NPAs. b. At least 200 SERNANP staff trained on the application of the protocols and undertaking envrionmental and biological monitoring | Year 2 Q4: a. 25 Lists of procured equipment for conducting environmental and biological monitoring in the 25 NPAs. b. At least 200 SERNANP staff trained on the application of the protocols and undertaking envrionmental and biological monitoring.
| a. 6 monitoring implementation reports (including recommendations broken down by NPA) b. 6 recommendation reports disaggregated by NPA based on monitoring analysis results c. 14 workshops to support integrating recommendations into management planning for the NPAs | Year 7 Q4: a. 6 monitoring implementation reports (including recommendations broken down by NPA) b. 6 recommendation reports disaggregated by NPA based on monitoring analysis results c. 14 workshops to support integrating recommendations into management planning for the NPAs
Activity 1.2.3: Expand existing monitoring programs to understand the impact of climate change on forest dynamics in Amazon NPAs. | a. Equipment lists for monitoring plots b. Map of 18 installed monitoring plots | Year 2 Q4: a. Equipment lists for monitoring plots; Year 3 Q4: a. Equipment lists for monitoring plots; Year 4 Q4: a. Equipment lists for monitoring plots; Year 5 Q4: a. Equipment lists for monitoring plots; Year 6 Q4: a. Equipment lists for monitoring plots; Year 7 Q4: b. Map of 18 installed monitoring plots
| a. Equipment lists for meteorological stations b. Map of 5 installed meteorological stations | Year 2 Q4: a. Equipment lists for meteorological stations; Year 7 Q4: b. Map of 5 installed meteorological stations
| Analysis report of data from the plots and weather stations. | Year 7 Q4: Analysis report of data from the plots and weather stations
| 4 workshops on the Permanent Plot Monitoring Program targeting 30 key stakeholders each | Year 7 Q4: 4 workshops on the Permanent Plot Monitoring Program targeting 30 key stakeholders each
| Virtual data platform established to monitor forest dynamics | Year 7 Q4: 1.2.3.5 Virtual data platform established
Output 1.3: Sustainable finance mechanisms established to secure long-term effective management of NPAs.
Activity 1.3.1: Develop and implement new Mechanism for Retribution of Ecosystem Services (MERESE) schemes for water to conserve and restore NPAs. | 8 workshops each targeting 60 key stakeholders (indigenous communities, farming communities, local community organizations, regional and local governments, water and sanitation companies, sanitation services administration boards, user groups, SERNANP and relevant ministries) to replicate and expand MERESE water schemes. | Year 7 Q4: 8 workshops each targeting 60 key stakeholders (indigenous communities, farming communities, local community organizations, regional and local governments, water and sanitation companies, sanitation services administration boards, user groups, SERNANP and relevant ministries) to replicate and expand MERESE water schemes.
| 4 new payment schemes for water supply or regulation agreements | Year 7 Q4: 4 new payment schemes for water supply or regulation agreements
Activity 1.3.2: Strengthen policies and local capacity to develop and implement environmental compensation mechanisms that support conservation and restoration of NPAs. | Portfolio of sites across NPAs for compensation to be implemented | Year 2 Q4: Portfolio of sites in which to compensate in NPAs
| At least 15 SERNANP staff trained on the implementation of environmental compensation | Year 7 Q4: At least 15 SERNANP staff trained on the implementation of environmental compensation
| Updated SERNANP guidelines governing environmental compensation in NPAs | Year 6 Q4: Updated SERNANP guidelines governing environmental compensation in NPAs
| a. 5 workshops with project developers to promote and implement environmental compensation b. 2 monitoring reports detailing progress of environmental compensation mechanism | Year 6 Q4: a. 5 workshops with project developers to promote and implement environmental compensation; Year 7 Q4: b 2 reports detailing progress on the implementation of the environmental compensation mechanism thanks to this activity
Activity 1.3.3: Improve sustainable tourism products in 3 NPAs to increase tourism revenue streams to the system of NPAs. | 3 NPAs with tourism products designed | Year 3 Q4: 3 NPAs with tourism products designed
| Procured infrastructure and equipment with the associated lists (disaggregated by NPA) | Year 2 Q4: Procured infrastructure and equipment with the associated lists (disaggregated by NPA)
| At least 9 tourism provider companies trained on sustainable tourism products | Year 7 Q4: At least 9 tourism provider companies trained on sustainable tourism products
| 3 reports (1 per NPA) on the implementation of promotional plans for the sustainable tourism products to support their access to domestic and foreign markets. | Year 7 Q1: 3 reports (1 per NPA) on the implementation of promotional plans for the sustainable tourism products to support their access to domestic and foreign markets.
| 3 NPAs with sustainable tourism certifications | Year 7 Q4: 3 NPAs with sustainable tourism certifications
| 3 annual tourism monitoring impact reports (1 per NPA) | Year 5 Q4: 3 annual tourism monitoring impact reports (1 per NPA); Year 6 Q4: 3 annual tourism monitoring impact reports (1 per NPA); Year 7 Q4: 3 annual tourism monitoring impact reports (1 per NPA)
Activity 1.4.1: Establish and scale bio-businesses by expanding participatory mechanisms to achieve sustainable use of natural resources and reduce deforestation in 6 NPAs. | 18 bio-business plans | Year 2 Q4: 18 bio-business plans developed
| 3 reports on establishment of participatory mechanisms (disaggregated by NPA) | Year 4 Q4: 3 reports on establishment of participatory mechanisms (disaggregated by NPA)
| a 6 product enhancement centers established b 2 reports on the use of product enhancement centers by the beneficiaries | Year 4 Q4: a 6 product enhancement centers established; Year 7 Q4: b 2 reports on the use of product enhancement centers by the beneficiaries
| 7 workshops each targeting at least 25 attendees to promote the Conservation Allies brand | Year 6 Q4: 7 workshops each targeting at least 25 attendees to promote the Conservation Allies brand
| a Attendance at 21 events to promote NPA bio-business products and the Conservation Allies brand b 7 workshops to strengthen business capacity among 350 bio-business owners in NPAs | Year 6 Q4: a Attendance at 21 events to promote NPA bio-business products and the Conservation Allies brand b 7 workshops to strengthen business capacity among 350 bio-business owners in NPAs
| Monitoring report detailing progress and effectiveness of the participatory mechanisms | Year 7 Q4: Report(s) detailing progress and effectiveness of the participatory mechanisms
Output 2.1: Climate-resilient productive practices and Ecosystem-based Adaptation implemented with 30 native communities in 5 NPAs and their buffer zones, supporting resilient livelihoods and hazard risk reduction under conditions of climate change
Activity 2.1.1: Implement climate-resilient productive practices with 30 native communities living in 5 NPAs and their buffer zones to support community-based adaptation. | 30 native community adaptation plans for climate-resilient livelihoods, with guidelines and protocols | Year 2 Q1: 30 native community adaptation plans for climate-resilient livelihoods, with guidelines and protocols.
| Interim report on 30 CRPP proposals developed by communities, including target outcomes and associated costs | Year 2 Q4: Interim report on 30 CRPP proposals developed by communities, including target outcomes and associated costs.
| Final report on the implementation of demonstration sites for CRPPs with 30 native communities (joint product with deliverable 2.1.1.4) | Year 7 Q4: Final report on the implementation of demonstration sites for CRPPs with 30 native communities (joint product with deliverable 2.1.2.4)
| Final report on the monitoring of CRPPs outcomes with 30 native communities (joint product with deliverable 2.1.1.3) | Year 7 Q4: Final report on the monitoring of CRPPs outcomes with 30 native communities (joint product with deliverable 2.1.2.3).
| Final report on the implementation of women-led climate-resilient productive practices. | Year 7 Q4: Final report on the implementation of women-led climate-resilient productive practices.
| 5 adaptation packages, 1 per protected area, integrating results of CRPPs implemented in 30 communities (joint product with deliverable 2.1.2.5). | Year 7 Q1: 5 adaptation packages, 1 per protected area, integrating results of CRPPs implemented in 30 communities (joint product with deliverable 2.1.3.5).
Activity 2.1.2: Implement Ecosystem-based Adaptation with 30 native communities living in 5 NPAs and their buffer zones to enhance and/or restore climate adaptation services. | Report on the spatial assessment of climate adaptation services in 5 NPAs | Year 2 Q1: Report on the spatial assessment of climate adaptation services in 5 protected areas.
| Interim report on 5 EbA intervention proposals, including target outcomes and associated costs | Year 2 Q4: Interim report on 5 EbA intervention proposals, including target outcomes and associated costs.
| Final report on the implementation of demonstration sites for 5 EbA interventions with native communities (joint product with deliverable 2.1.2.4) | Year 7 Q4: Final report on the implementation of demonstration sites for 5 EbA interventions with native communities (joint product with deliverable 2.1.3.4)
| Final report on the monitoring of 5 EbA intervention outcomes with native communities (joint product with deliverable 2.1.2.3) | Year 7 Q4: Final report on the monitoring of 5 EbA intervention outcomes with native communities (joint product with deliverable 2.1.3.3).
| 5 adaptation packages, 1 per protected area, integrating results of EbA interventions implemented in 5 protected areas (joint product with deliverable 2.1.1.6) | Year 7 Q1: 5 adaptation packages, 1 per protected area, integrating results of EbA interventions implemented in 5 protected areas (joint product with deliverable 2.1.2.6).
Output 2.2. Indigenous Peoples’ governance for climate risk management strengthened to implement, manage, and scale climate change adaptation solutions across an additional 162 native communities in 5 NPAs and their buffer zones.
Activity 2.2.1: Strengthen technical and administrative capacities in 8 Indigenous Organizations supporting native communities living in 5 NPAs and their buffer zones. | Capacity building report detailing the enhancement of technical capacities of 8 IIOO technical staff on the implementation of adaptation activities in 30 native communities and 3 climate risk management mechanisms | Year 7 Q4: 2.2.1.1. Capacity building report detailing the enhancement of technical capacities of 8 IIOO technical staff on the implementation of adaptation activities in 30 native communities and 3 climate risk management mechanisms.
| Capacity building report detailing the enhancement of administrative capacities of 8 IIOO technical staff on the administration of grants and the preparation of funding proposals to support additional climate adaptation efforts. | Year 7 Q4: Capacity building report detailing the enhancement of administrative capacities of 8 IIOO technical staff on the administration of grants and the preparation of funding proposals to support additional climate adaptation efforts.
Activity 2.2.2: Institutionalize Indigenous-led climate risk management to scale climate-resilient productive practices and EbA measures across 162 native communities in 5 NPAs and their buffer zones | Publication of the IIOO climate-risk management strategy | Year 2 Q4: Publication of the IIOO climate-risk management strategy; Year 7 Q4: Capacity building report detailing the enhancement of technical capacities of 8 IIOO technical staff on the implementation of adaptation activities in 30 native communities and 3 climate risk management mechanisms
| Report on the implementation of field schools between 30 target and 30 non-target communities, including detailed methodology for replication | Year 7 Q4: Report on the implementation of field schools between 30 target and 30 non-target communities, including detailed methodology for replication.
| Publication on the enhanced Indigenous EWS platform integrating climate hazards, and the operation/function of 30 new community monitoring systems integrated into the platform | Year 6 Q4: Publication on the enhanced Indigenous EWS platform integrating climate hazards, and the operation/function of 30 new community monitoring systems integrated into the platform.
| Report on results achieved through advocacy programs, detailing agreements, commitments and actions taken/to be taken regional governments working together with IIOO to scale adaptation solutions | Year 7 Q4: Report on results achieved through advocacy programs, detailing agreements, commitments and actions taken/to be taken regional governments working together with IIOO to scale adaptation solutions.
| Report for the 3 mid-term workshops, highlighting the progress of project activities, issues and challenges that may have arisen, and adaptive management needs, among others. Report for the 3 final workshops, highlighting project results and achievements, lessons learned, take-aways from project participants, vision for the future, and others. | Year 4 Q4: Published project mid-term results; 3 mid-term project workshops implemented to strengthen project implementation.; Year 7 Q4: Published final project results and lessons learned; 3 final project workshops implemented to showcase project results at a regional level.
Co-benefit 1: Preserved water provisioning and regulating services. | Baseline study MoVs: Hydrologic modeling of catchment(s) to evaluate the difference between actual land use and a counterfactual scenario (of increased deforestation and degradation) Hydrologic modeling of catchment(s) to evaluate the difference between actual land use and a counterfactual scenario (of increased deforestation and degradation) | Year 1 Q4: Baseline study; Year 7 Q4: % change from the baseline in dry season baseflow and sediment delivery
Co-benefit 2: Biodiversity protected and resilient. | Baseline report confirming the baseline in the national report, entitled XX for relevant species to be monitored MoVs: Camera traps Transect surveys NPA Reports and Databases Abundance Index (see Section E for details) | Year 1 Q4: Baseline report; Year 7 Q4: Increase of 20% from the baseline in occupancy of the Andean bear, Mountain tapir, and hunted animals
Increase of 5% in density of hunted animals in target NPAs
Increase of 10% in the abundance index of hunted animals in target NPAs
Hunted species reach “abundant” level (See Section E for details)
Reporting* | APR, Completion report, Midterm and final evaluation reports | Year 1 Q2: Inception Report; Year 2 Q1: APR; Year 3 Q1: APR; Year 4 Q1: APR; Year 4 Q3: Interim evaluation; Year 5 Q1: APR; Year 6 Q1: APR; Year 7 Q1: APR; Closure Q1: Completion report; Closure Q2: Final evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.