## Guidance
Guidance on Filling Out the Readiness Financial Proposal
The Readiness Financial Proposal consists of the following sheets:
Implementation Plan – Lists key activities for each objective, outcome, output, and timelines.
Budget Plan – Provides a detailed breakdown of financial requirements.
Payment Schedule – Outlines when funds will be disbursed based on Payment Deliverables.
Budget Notes – Includes explanations, details and justifications for budget items.
Budget Category – Classifies different budget items.
IMPORTANT NOTE – The Implementation Plan, Budget Plan, and Payment Schedule are closely linked. Ensure that the information in each section is aligned to maintain consistency in activities, costs, and disbursement schedules.
1. Implementation Plan
The Implementation Plan contains the following parts:
Objectives, Outcomes and Outputs: Objectives and Outcomes are preloaded based on the 2024-2027 Readiness Strategy. Please do not modify Objectives & Outcomes but select and use the Objectives and Outcomes as relevant to your proposal. Please insert Output numbers as indicated in the Logframe.
Activity Numbers: Please copy the activity number from the Logical Framework (Logframe) without including its description, as it is already provided in the Logframe. In the finance template, only the activity number is needed to keep it concise.
Timeframes: Clearly specify the inception period, planned duration, and a detailed yearly breakdown of activities for the first year. For subsequent years, detailed activities can be developed at the end of each preceding period.
2. Budget Plan
The Budget Plan contains the following parts:
Payment Deliverables:
  Deliverables should be directly linked to the project’s Logical Framework (Logframe), ensuring consistency with defined outputs, outcomes, and indicators. To ensure strategic alignment and result-driven implementation, all deliverables must be demonstrably structured to contribute to the results outlined in the (Revised) Readiness Results Management Framework (RRMF). Deliverables must contribute to the intended project results, using evidence-based reporting. Payment will be tied to the achievement of measurable results rather than activity completion alone.
  Provide a clear and concise title of the deliverable derived from the Logframe.
  Please use predefined budget categories from the dropdown list but add new ones if and as necessary. These new budget categories should be manually added on the Budget Category sheet.
Budget Notes: Please provide detailed explanations, further details, cost breakdowns, and necessary justifications or clarifications. The budget note identification should be identical to the ‘Budget Notes’ sheet.
Independent Evaluation: Include a separate budget line for an independent evaluation that shall be carried at the conclusion of readiness activities. This study should be conducted by an external evaluator to assess the effectiveness of the readiness activities, their impact on the country’s climate objectives, and their alignment with GCF outcomes. The evaluation will also capture lessons learned to inform and improve future readiness initiatives.
Project Management Cost (PMC): PMC should be listed separately in the budget plan and broken down by category, including personnel such as Project Manager, Assistants, Procurement, Finance, and Support/Administrative staff, and other eligible costs (ref. to the Guides for countries and DAEs to access Readiness support). PMC covers direct administrative costs necessary to manage grants, applicable only to incremental costs from GCF funding. The funding from GCF for PMC should not exceed the percentage of the total budget they finance. Budget limits for PMC are capped at 7.5 per cent of the total deliverable and evaluation budget, in line with the GCF Policy on fees for accredited entities and delivery partners https://www.greenclimate.fund/sites/default/files/document/gcf-b19-29.pdf
Contingency: A maximum of 3 per cent of total activity budget may be suggested to allow flexibility in relation to unforeseen or unplanned expenses related to the implementation of readiness activities.
Fee: Include eligible costs for GCF fees up to 8.5 per cent in line with the GCF Policy on Fees. https://www.greenclimate.fund/sites/default/files/document/gcf-b19-29.pdf
  The actual fee will be calculated based on the actual incurred expenditure at completion.
3. Payment Schedule
The Payment Schedule determines how and when funds will be disbursed, with the following parts:
Advance Payment: The payment of 25% of the contract value is payable upon contract signing, to start the activities.
Payment Deliverable: Please indicate deliverable’s title, proposed percentage of the overall budget per deliverable, and provide the USD values corresponding to each deliverable, based on the targeted completion of the deliverables.
Independent Evaluation: Insert/link USD value corresponding to the independent evaluation in the Budget Plan, in the relevant Year, based on the targeted timeline.
PMC: Insert/link USD values corresponding to PMC in the Budget Plan in the relevant Year, based on the targeted timeline.
Contingency: Insert/link USD values corresponding to Contingency in the Budget Plan in the relevant Year, based on the targeted timeline.
Fee: Insert/link USD values corresponding to Fee in the Budget Plan in the relevant Year, based on the targeted timeline.
Advance (Deduction): The advance paid at the start of the contract must be deducted from the final deliverables-based payments. The advance deduction can be included in one or more payments as necessary. Ensure that the amount is clearly indicated and adjusted to balance the total payment schedule.
General Notes
Consistency Check: Please verify that descriptions, costs, and payment amounts are consistent across all sheets.
Additional Rows: Depending on the number of deliverables or budget category lines, please insert rows while maintaining the existing format.
Clarifications: Use the ‘Budget Notes’ sheet to provide explanations when necessary.
Formula: The formulas are not locked to allow for adjustments when rows are added or modified (except for cumulative totals in the payment schedule). Please ensure that all formulas are correctly updated to reflect any changes made during the budget planning process.
Budget Notes and Budget Category: These sheets are provided as supplementary materials to the main Budget Plan as described in the budget plan section.

## Implementation Plan
Implementation Plan |  |  |  |  | Inception Period |  |  |  | Deliverable date |  |  |  | Planned duration |  |  |  | Target completion date, if different from the deliverable date
Please list all key activities (adding more rows as needed) under relevant Readiness Objective, Outcome and Output, in line with the Logical Framework (Logframe).
Objectives | Outcomes | Outputs | Activities | Year 1 | [11 empty] | Year 2 | Year 3 | Year 4
|  |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
Objective 1: Capacity-building for climate finance coordination and setting up the enabling environment for integrated climate investment | Outcome 1.1. Developing countries, through NDAs or focal points, have enhanced capacity to fulfil their roles, responsibilities and policy requirements, including coordination mechanisms to engage relevant stakeholders[1] to develop, advance, and implement NDCs, NAPs and LTS. | Example: Output 1.1.1 | Exammple: Activity 1.1.1 | bar: Year 1 M4 to Year 1 M12
|  |  | Exammple: Activity 1.1.2 | [15 empty] | To decide with MEL - keep Activities numbered, and list text of Activities in the Logframe, or list activities here only, with no Activities in the Logframe | bar: Year 1 M5 to Year 1 M10
Exammple: Activity 1.1.3 | bar: Year 1 M5 to Year 1 M12
| Outcome 1.2. Developing countries design and implement strategic frameworks (including NDC/NAP/LTS), policies and instruments, including climate investment plans, to create enabling environments for integrated climate investments. | Example: Output 1.2.1 | Example: Activity 1.2.1
Example: Activity 1.2.2
Example: Activity 1.2.3
| Outcome 1.3. Direct access applicants and accredited entities (DAEs) have met and maintained the accreditation standards of the GCF and strengthened their programming capacities, as evidenced by the development of GCF-funded activities | Example: Output 1.3.1 | Exammple: Activity 1.3.1
Exammple: Activity 1.3.2
Exammple: Activity 1.3.3
Objective 2: Paradigm-shifting GCF pipeline development and implementation for adaptation and mitigation, based on country needs and guided by USP-2 programming targets | Outcome 2.1. Developing countries have developed or updated their country programmes to guide GCF investment. | Example: Output 2.1.1 | Exammple: Activity 2.1.1
Exammple: Activity 2.1.2
Exammple: Activity 2.1.3
| Outcome 2.2. Developing countries have developed high-quality concept notes linked to approved GCF proposals for adaptation and mitigation that are aligned with the USP-2 results, including through DAEs, that build on readiness support and country programmes. | Example: Output 2.2.1 | Exammple: Activity 2.2.1
Exammple: Activity 2.2.2
Exammple: Activity 2.2.3
| Outcome 2.3. NDAs and DAEs have enhanced processes and systems to effectively oversee the implementation, financial management, monitoring and reporting of climate programmes and projects. | Example: Output 2.3.1 | Example: Output 2.3.1
Example: Output 2.3.2
Example: Output 2.3.3
Objective 3: Knowledge-sharing and learning to enhance national and regional cooperation on climate programming and financing | Outcome 3.1. Developing countries, through NDAs or focal points, have made use of knowledge products to address policy gaps and integrated climate investment programming and implementation. | Example: Output 3.1.1 | Example: Output 3.1.1
Example: Output 3.1.2
Example: Output 3.1.3
| Outcome 3.2. Enhanced collaboration among developing countries on climate change issues, evidenced by transboundary and regional cooperations/South-South cooperation. | Example: Output 3.2.1 | Example: Output 3.2.1
Example: Output 3.2.2
Example: Output 3.2.3

## Budget Plan
Budget Plan
Please specify the Budget Categories for each Deliverable that will trigger payments.
Please add rows as required. Additional budget categories may be added by manually typing them on the Budget Category sheet.
To ensure strategic alignment and result-driven implementation, all deliverables must be demonstrably structured to contribute to the results outlined in the (Revised) Readiness Results Management Framework (RRMF). Deliverables should be directly linked to the project’s Logical Framework (Logframe), ensuring consistency with defined outputs, outcomes, and indicators.
Objectives | Outcomes | Outputs | Payment Deliverable | Detailed Budget (in US$) | [5 empty] | Total Budget (per objective) | Budget notes
|  |  |  | Budget Categories choose from the drop-down list | Unit | # of Unit | Unit Cost | Total Budget (per budget category) | Total Budget (per per deliverable)
Objective 1 : Capacity-building for climate finance coordination and setting up the enabling environment for integrated climate investment | Outcome 1.1 Developing countries, through NDAs or focal points, have enhanced capacity to fulfil their roles, responsibilities and policy requirements, including coordination mechanisms to engage relevant stakeholders2 to develop, advance, and implement NDCs, NAPs and LTS. |  | Deliverable Title: Provide a clear and concise title of the deliverable derived from the Logframe. | Consultant - Individual - International | Per day | 35 | 500 | 17500 | 106500 | 106500 | A
|  |  |  | Consultant - Individual - Local | Per day | 35 | 400 | 14000 |  |  | B
|  |  |  | Professional Services – Companies/Firm | LS | 1 | 50000 | 50000 |  |  | C
|  |  |  | Workshop/Training | Event | 5 | 5000 | 25000 |  |  | D
|  |  | Deliverable Title |  |  |  |  | 0 | 0
0
0
| Outcome 1.2 Developing countries design and implement strategic frameworks (including NDC/NAP/LTS), policies and instruments, including climate investment plans, to create enabling environments for integrated climate investments. |  | Deliverable Title |  |  |  |  | 0 | 0
Targeted budget for Objective 1: 30% | [7 empty] | 0
0
The requested budget: | Outcome 1.3 Direct access applicants and accredited entities (DAEs) have met and maintained the accreditation standards of the GCF and strengthened their programming capacities, as evidenced by the development of GCF-funded activities |  | Deliverable Title |  |  |  |  | 0 | 0
100% | [7 empty] | 0
Formula Includes Proportional Allocation for Evaluation, PMC, Fee & Contingency | [7 empty] | 0
Objective 2 : Paradigmshifting GCF pipeline development and implementation for adaptation and mitigation, based on country needs and guided by USP-2 programming targets | Outcome 2.1 Developing countries have developed or updated their country programmes to guide GCF investment. |  | Deliverable Title |  |  |  |  | 0 | 0 | 0
0
0
| Outcome 2.2 Developing countries have developed high-quality concept notes linked to approved GCF proposals for adaptation and mitigation that are aligned with the USP-2 results, including through DAEs, that build on readiness support and country programmes |  | Deliverable Title |  |  |  |  | 0 | 0
0
0
0
0
Targeted budget for Objective 2: 60% | Outcome 2.3 NDAs and DAEs have enhanced processes and systems to effectively oversee the implementation, financial management, monitoring and reporting of climate programmes and projects. |  | Deliverable Title | [5 empty] | 0
The requested budget: | [7 empty] | 0
0% | [7 empty] | 0
Formula Includes Proportional Allocation for Evaluation, PMC, Fee & Contingency | [7 empty] | 0
0
Objective 3 : Knowledge-sharing and learning to enhance national and regional cooperation on climate programming and financing | Outcome 3.1 Developing countries, through NDAs or focal points, have made use of knowledge products to address policy gaps and integrated climate investment programming and implementation. |  | Deliverable Title/Description |  |  |  |  | 0 | 0 | 0
0
0
0
| Outcome 3.2 Enhanced collaboration among developing countries on climate change issues, evidenced by transboundary and regional cooperations /South-South cooperation |  | Deliverable Title |  |  |  |  | 0 | 0
Targeted budget for Objective 3: 10% | [7 empty] | 0
The requested budget:
0% | [7 empty] | 0
Formula Includes Proportional Allocation for Evaluation, PMC, Fee & Contingency | [7 empty] | 0
Total Deliverable Budget | [9 empty] | 106500
Independent Evaluation | [7 empty] | 0 | 0 | 0
106500
Project Management Cost (PMC) Up to 7.5% of Total Activity Budget |  |  |  | Audit Fee |  |  |  | 0 | Actual amount and % of PMC requested: | Maximum PMC that can be requested:
|  |  |  | Consultant - Individual - Local |  |  |  | 0
[8 empty] | 0 | do not change the formula | do not change the formula
[8 empty] | 0 | 0 | 7987.5
[8 empty] | 0 | 0% | 7.5%
Summary per Budget Category |  |  | Total (per Budget Category ) |  |  | FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Audio Visual & Printing |  |  | 0
Audit Fee |  |  | 0 |  | Total Deliverable Budget | [5 empty] | 106500
Communication |  |  | 0 |  | Independent Evaluation | [5 empty] | 0
Consultant - Individual - International |  |  | 17500 |  | Project Management Cost (PMC) |  |  |  | 0% | requested | 0
Consultant - Individual - Local |  |  | 14000 |  | Contingency |  |  |  | 2% | requested | 2130
Professional Services – Companies/Firm |  |  | 50000
Office Supplies |  |  | 0 |  | Sub-Total (Total Deliverable Budget + Evaluation+PMC+Contingency) | [5 empty] | 108630
Travel - International |  |  | 0
Travel – Local |  |  | 0 |  | Fee - Up to 8.5% of the Sub-Total | [5 empty] | 9233.55
Workshop/Training |  |  | 25000
0 |  |  | 0
0 |  |  | 0 |  | Total Project Budget | [5 empty] | 117864
0 |  |  | 0
Total Deliverable Budget |  |  | 106500 |  | Note: Please ensure that the amounts are rounded-up figures
Total Budget for NAP

## Payment Schedule
Payment Schedule
Please provide a breakdown of the payment schedule, specifying the Payment Deliverables, corresponding amounts, and expected timelines.
The deliverables should be derived from the project's Logical Framework (Logframe) to ensure coherence with the intended results of the project. It must be clearly demonstrated, with verifiable evidence of progress, how each deliverable contributes to the achievement of outcomes and outputs as defined in the (Revised) Readiness Results Management Framework (RRMF).
Payment Deliverable | Payment Schedule | Y0 | Y1 | Y2 | Y3 | Y4 | Cumulative
Advance | 25% | 29466
Deliverable Title | Please enter the proposed percentage of the overall budget per deliverable.
Add rows as necessary
|  | 29466 | 0 | 0 | 0 | 0 | 0
Independent Evaluation
PMC
Contingency
Fee
Advance (Deduction) | [5 empty] | -29466
Total |  | 29466 | 0 | 0 | 0 | -29466 | 0
* Must have clearly demonstrable link to Logframe)

## Budget Category
Budget Categories | Choose percentage
Audio Visual & Printing | 0
Audit Fee | 1%
Communication | 2%
Consultant - Individual - International | 3%
Consultant - Individual - Local
Professional Services – Companies/Firm
Office Supplies
Travel - International
Travel – Local
Workshop/Training
Choose percentage
0
1%
2%
3%

## Budget Notes
Budget Notes
Please check out the example in the table below, and remove them before including the proposal's entries
Budget Note | Detailed Description
A | Investment specialist (international consultnat) for USD17,500 at USD500/day for 35 days to oversee the investment planning and finance elements notably building investment pipelines and bringing regional and global experience.
B | Local Development Expert (local consultant) for USD14,000 at USD400/day for 35 days expert on local adaptation planning and monitoring and conduct preparatory work and further analysis for activity 3.1.1
C | Professional services - Firm : to engage a firm for USD50,000 lumpsum to implement activity 3.2.1a to conduct a technical diagnostic of 2 coastal sites and recommend solutions for each site.
D | Five one-day workshops for capacity building estimated at USD5,000 per event to include venue and catering for 25 persons (USD200/person) in each coastal community (2 localities).