## Implementation plan
Annex 5 Implementation Timetable
Project/Programme Title: Resilient Water Systems for All (RWS4All): Deep Adaptation Pathways for Water Infrastructure in Kyrgyz Republic and Tajikistan
Components | Deliverables | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Year 7 |  |  |  | Year 8 |  |  |  | Year 9 |  |  |  | Year 10 |  |  |  | Year 11 |  |  |  | Year 12 |  |  |  | Year 13 |  |  |  | Year 14 |  |  |  | Year 15 |  |  |  | Year 16
|  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2033 |  |  |  | 2034 |  |  |  | 2035 |  |  |  | 2036 |  |  |  | 2037 |  |  |  | 2038 |  |  |  | 2039 |  |  |  | 2040 |  |  |  | 2041 |  |  |  | 2042
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1: National-level Water Sector Reforms and Climate Resilience Transition Platforms
Ouput 1.1: National legal and regulatory reforms supported
Activity 1.1.1: Structural reform for the water sector to enable long-term resilience, including relevant data collection, monitoring, and reporting | • Development and delivery of water sector tariff adjustments • Implementation of standardised PSCs with climate resilience KPIs • Delivery of embedded reform support units in designated organisational counterparts | bar: 2027 Q1 to 2029 Q4
Activity 1.1.2: Mainstreaming climate adaptation and social inclusion in water services | • Climate resilience KPIs for PSCs • Social support programme standards and guidance developed | bar: 2027 Q1 to 2029 Q4
Ouput 1.2: Guidance and tools for water system operators on climate resilience and inclusion responsiveness developed Activity 1.2.2 International knowledge sharing on best practice
Activity 1.2.1: Develop national guidance and knowledge products on climate resilient water service delivery | • National CRVA standards developed and associated operationalization guidance prepared • Guidance for country and water sector mainstreaming of CRVA outcomes into engineering design criteria | bar: 2027 Q1 to 2029 Q4
Activity 1.2.2.: Develop national toolkit for scalable community engagement programmes to promote water efficiency at the customer level | • Toolkit for water efficiency technical measures developed • Implementation/roll-out plan for pilot-testing water efficiency and incentive mechanisms in selected utilities | bar: 2027 Q1 to 2029 Q4
Activity 1.2.3: International knowledge sharing on best practices for climate resilient water services | • Knowledge products (e.g., policy brief, webinar series, practitioner practical guide) developed | bar: 2027 Q1 to 2029 Q4
Ouput 1.3: Water sector climate resilience transition platform(s) established
Activity 1.3.1: Design a Climate Resilience Transition Platform (CRTP) for the water sector | • CRTP prepared and launched - first part | bar: 2027 Q1 to 2029 Q4
Activity 1.3.2: Operation of the CRTPs, including gender considerations | • Annual CRTP progress reports • Final gender and equal opportunities guidance and toolkits | bar: 2028 Q1 to 2031 Q4
Component 2: Utility-level climate resilience baselining and technical support for adaptation pathway development
Output 2.1: Adaptation pathways for priority systems developed
Activity 2.1.1: Conduct baselining and adaptation pathway development for sub-systems | • Final adaptation pathways for targeted utilities | bar: 2027 Q4 to 2032 Q4
Activity 2.1.2: Provision of detailed project preparation support for priority investments | • Completed due diligence documentation | bar: 2027 Q4 to 2032 Q4
Ouput 2.2: Enhanced adaptive capacity of water utilities through implementation of corporate development support
Activity 2.2.1: Increase adaptive capacity of water utilities through corporate development support, including gender considerations and relevant data collection, monitoring, and reporting | • Signed PSCs • Completed CDPs • Developed SPPs • Developed social support programme • Gender action plans • Trainings facilitated | bar: 2027 Q4 to 2031 Q3
Activity 2.2.2: Implement scalable community engagement programmes to promote water efficiency at the customer level | • Water efficiency toolkit applied to pilot utilities | bar: 2027 Q4 to 2031 Q3
Output 2.3: Implementation of water projects supported
Activity 2.3.1: Support provided for sub-projects to be implemented under Component 3 | • Project implementation support delivered | bar: 2027 Q4 to 2036 Q4
Component 3: Catalyse climate investments for the implementation of adaptation pathways
Output 3.1 Priority water systems deliver enhanced, climate resilient water services
Activity 3.1.1: Implemention of prioritised climate resilience investments at utility level | • Loan and investment grant agreements signed • Loan and investment grant activities completed | bar: 2027 Q2 to 2041 Q4
Project Monitoring* |  | 2027 Q2: Inception Report; 2028 Q1: APR; 2029 Q1: APR; 2030 Q1: APR; 2031 Q1: APR; 2031 Q4: Mid-term evaluation; 2032 Q1: APR; 2033 Q1: APR; 2034 Q1: APR; 2035 Q1: APR; 2036 Q1: APR; 2037 Q1: APR; 2038 Q1: APR; 2039 Q1: APR; 2040 Q1: APR; 2041 Q1: APR; 2042 Q1: Completion Report; 2042 Q4: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.