## LARACI Implementation timetable
Annex 5 Implementation Timetable
Project Title: Enhancing Sustainable Land Management and Climate-Resilient Agri-food Systems in Côte d'Ivoire (LARACI)
COMPONENTS/OUTPUTS | Year 1 |  |  |  | Year 2 |  |  |  | Year 3 |  |  |  | Year 4 |  |  |  | Year 5 |  |  |  | Year 6 |  |  |  | Dependencies (critical path / hard dependency / normal dependency)
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1: Managing climate-related risks | bar: Year 1 Q2 to Year 6 Q1
Output 1.1 Access to timely climate information and advice | bar: Year 1 Q2 to Year 6 Q1
Activity 1.1.1: Strengthen agrometeorological network | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.1.1.1 Conduct site assessment and identify station installation locations | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q2
Sub-activity 1.1.1.2 Acquire 20 new automatic agroclimatic stations | [24 empty] | Depends on: 1.1.1.1 (site assessment) | bar: Year 1 Q2
Sub-activity 1.1.1.3 Rehabilitate the existing agroclimatic station network | [24 empty] | Depends on: 1.1.1.1 (site assessment) | bar: Year 1 Q2 to Year 1 Q3
Sub-activity 1.1.1.4 Acquire tools for data collection, processing, management, and dissemination | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q3
Sub-activity 1.1.1.5 Install, commission, and provide maintenance and upkeep of automatic weather stations | [24 empty] | GATE ●: Depends on: 1.1.1.2+1.1.1.3 complete | bar: Year 1 Q3; Year 2 Q2; Year 2 Q4; Year 3 Q2; Year 3 Q4; Year 4 Q2; Year 4 Q4; Year 5 Q2; Year 5 Q4
Sub-activity 1.1.1.6 Conduct training on use and maintenance of equipment | [24 empty] | Depends on: 1.1.1.5 (installation) | bar: Year 1 Q3 to Year 1 Q4
Activity 1.1.2: Develop actionable agro-advisory | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.1.2.1 Conduct needs assessment for climate services for the 3 value chains | [24 empty] | Depends on: 1.1.1.1 needs assessment | bar: Year 2 Q2 to Year 2 Q4
Sub-activity 1.1.2.2 Develop tools | [24 empty] | Depends on: 1.1.2.1 (needs assessment) | bar: Year 1 Q4 to Year 2 Q1; Year 2 Q3 to Year 2 Q4
Sub-activity 1.1.2.3 Develop, deploy and validate integrated electronic system accessible to technical and financial partners | [24 empty] | Depends on: 1.1.2.2 (tools developed) | bar: Year 2 Q2 to Year 2 Q3
Sub-activity 1.1.2.4 Publish monthly agrometeorological bulletin | [24 empty] | GATE ●: Depends on: 1.1.2.3 deployed | bar: Year 2 Q4 to Year 5 Q4
Activity 1.1.3: Develop tools to communicate advisory | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.1.3.1 Organize national and regional (5) project advisory launch workshops | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q2
Sub-activity 1.1.3.2 Translate and broadcast messages in local radio stations in local languages | [24 empty] | Depends on: 1.1.3.1 (launch workshops) | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.1.3.3 Set up an SMS-based information dissemination system | [24 empty] | Depends on: 1.1.2.3 (SEIS deployed) | bar: Year 1 Q2
Sub-activity 1.1.3.4 Create a GIS portal interface on the FIRCA website and social media messaging | [24 empty] | Depends on: 1.1.3.1 (launch workshops) | bar: Year 1 Q2 to Year 1 Q4; Year 2 Q2 to Year 2 Q4; Year 3 Q2 to Year 3 Q4; Year 4 Q2 to Year 4 Q4
Sub-activity 1.1.3.5 Produce and disseminate communication material | [24 empty] | Depends on: 1.1.3.1 (launch workshops) | bar: Year 1 Q2; Year 1 Q4 to Year 3 Q4; Year 4 Q2 to Year 4 Q4; Year 5 Q2 to Year 5 Q4
Activity 1.1.4: Train farmers extension staff on use of climate data | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.1.4.1 Conduct a diagnosis of current knowledge of agricultural stakeholders on climate, identify gaps in the use of climate services | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q3
Sub-activity 1.1.4.2 Institute and conduct training packages for extension agents, MINEDDTE agents, community leaders, and farmer beneficiaries | [24 empty] | GATE ●: Depends on: 1.1.4.1 (diagnosis) | bar: Year 1 Q4 to Year 2 Q4; Year 3 Q2 to Year 3 Q4
Sub-activity 1.1.4.3 Equip extension agents with communication tools | [24 empty] | Depends on: 1.1.4.2 (training packages) | bar: Year 1 Q2 to Year 5 Q3
Sub-activity 1.1.4.4 Monitor producers and agricultural stakeholders on the use of CIS, and training follow-up missions | [24 empty] | Depends on: 1.1.4.2+1.1.4.3 complete | bar: Year 2 Q4; Year 3 Q4; Year 4 Q4; Year 5 Q4
Activity 1.1.5: Improve institutional arrangements | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.1.5.1 Strengthen the national framework for climate services | [24 empty] | Prerequisite: inception phase | bar: Year 2 Q1 to Year 2 Q2
Sub-activity 1.1.5.2 Create a multi-disciplinary working group to guide institutional arrangements, and a local multidisciplinary working group to operationalize the agroclimatic information management and dissemination system | [24 empty] | Depends on: 1.1.3.1 (launch workshops) | bar: Year 1 Q3; Year 2 Q2 to Year 2 Q3
Sub-activity 1.1.5.3 Ensure incorporation of climate information and prediction into planning and policy | [24 empty] | Depends on: 1.1.5.2 (working groups) | bar: Year 3 Q1 to Year 3 Q2
Output 1.2 Extension and regulatory system have increased capacity | bar: Year 1 Q2 to Year 6 Q1
Activity 1.2.1: Increased capacity of extension agents on CSA | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.2.1.1 Conduct a diagnostic, and develop validated training modules on CSA approaches for agricultural training centers | [24 empty] | Prerequisite: inception phase | bar: Year 2 Q2 to Year 2 Q3; Year 3 Q2; Year 3 Q4
Sub-activity 1.2.1.2 Equip and conduct training of trainers within agricultural training centers | [24 empty] | GATE ●: Depends on: 1.2.1.1 (diagnostic) | bar: Year 2 Q2 to Year 2 Q4; Year 3 Q2 to Year 3 Q4; Year 5 Q1
Sub-activity 1.2.1.3 Establishment of a continuous training system for extension agents to remain up to date with the latest research and developments on climate risks and CSA solutions | [24 empty] | GATE ●: Depends on: 1.2.1.1 (diagnostic) | bar: Year 2 Q3 to Year 2 Q4; Year 3 Q2 to Year 4 Q2; Year 5 Q1 to Year 5 Q2
Sub-activity 1.2.1.4 Build capacity in management and maintenance of production and processing infrastructure | [24 empty] | GATE ●: Depends on: 1.2.1.1 (diagnostic) | bar: Year 2 Q3 to Year 2 Q4; Year 3 Q3 to Year 3 Q4; Year 5 Q1
Activity 1.2.2: Develop channels for CSA recommendations | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.2.2.1 Design technical education tools on CSA and gender-sensitive dissemination materials | [24 empty] | GATE ●: Depends on: 1.2.1.1 (diagnostic) | bar: Year 2 Q2 to Year 3 Q1
Sub-activity 1.2.2.2 Train extension agents on functional literacy techniques to broaden reach | [24 empty] | Depends on: 1.2.2.1 (tools designed) | bar: Year 2 Q2 to Year 3 Q1
Sub-activity 1.2.2.3 Acquire data collection tools for technical services and zones of concentration and integrate sex and age- disaggregated data collection into extension activities to inform needs prioritization | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q2 to Year 2 Q1
Sub-activity 1.2.2.4 Develop and launch multiple ICT dissemination channels through startups/mobile phone companies | [24 empty] | GATE ●: Depends on: 1.2.1.2+1.2.2.1 complete | bar: Year 2 Q2 to Year 5 Q1
Sub-activity 1.2.2.5 Train and equip members of satellite advisory offices on CSA techniques in each project zone | [24 empty] | Depends on: 1.2.2.1 (tools designed) | bar: Year 2 Q2 to Year 3 Q1
Activity 1.2.3: Upgrade extension infrastructure and equipment | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.2.3.1 Conduct inventory of infrastructure and equipment needs for research on climate information and effective agricultural advisory services | [24 empty] | Prerequisite: inception phase
Sub-activity 1.2.3.2 Acquire and install climate-adapted research equipment in research institutes or universities | [24 empty] | GATE ●: Depends on: 1.2.3.1 (inventory) | bar: Year 1 Q2 to Year 2 Q1
Sub-activity 1.2.3.3 Equip training centers with multimedia teaching kits, along with updated CSA learning modules | [24 empty] | Depends on: 1.2.3.2 (equipment acquired) | bar: Year 2 Q2 to Year 3 Q1
Sub-activity 1.2.3.4 Provide maintenance kits for agrometeorological stations | [24 empty] | Depends on: 1.1.1.5 (stations installed) | bar: Year 2 Q2 to Year 3 Q1
Sub-activity 1.2.3.5 Equip agricultural advisors and extension agents with tablets or smartphones | [24 empty] | Depends on: 1.2.3.2 (equipment acquired) | bar: Year 2 Q2 to Year 3 Q1
Activity 1.2.4: Select and tailor CSA solutions for effective scaling | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.2.4.1 Assess existing CSA practices and conditions for adoption | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q2
Sub-activity 1.2.4.2 Organize a prioritization workshop for CSA practices applicable in the project zones by value chain | [24 empty] | GATE ●: Depends on: 1.2.4.1 (assessment) | bar: Year 1 Q2
Sub-activity 1.2.4.3 Undertake validation tests of newly selected CSA technologies in order to contextualize and demonstrate their technical and economic efficiency and performance | [24 empty] | GATE ●: Depends on: 1.2.4.2 (prioritization) | bar: Year 1 Q3 to Year 2 Q1
Sub-activity 1.2.4.4 Organize field exchange visits for technology transfer (1 visit per crop) and a workshop to present the results of the technology tests | [24 empty] | GATE ●: Depends on: 1.2.4.3 (validation) | bar: Year 2 Q2 to Year 5 Q1
Activity 1.2.5: Strengthen extension-research communication | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.2.5.1 Conduct consultation workshops on CSA for public and private stakeholders in research and extension | [24 empty] | Prerequisite: inception phase | bar: Year 2 Q2 to Year 6 Q1
Sub-activity 1.2.5.2 Establish and operationalize multi-stakeholder platforms at local and national levels | [24 empty] | Depends on: 1.2.5.1 (consultation workshops) | bar: Year 2 Q2 to Year 6 Q1
Sub-activity 1.2.5.3 Experience-sharing trips for platform members to facilitate information exchange between farmers and researchers | [24 empty] | Depends on: 1.2.5.2 (platforms established) | bar: Year 2 Q2 to Year 3 Q1; Year 4 Q2 to Year 5 Q1
Sub-activity 1.2.5.4 Fund multi-stakeholder and public-private platforms that promote the extension-research linkages for synergistic actions on the ground | [24 empty] | Depends on: 1.2.5.2 (platforms established) | bar: Year 2 Q2 to Year 5 Q1
Sub-activity 1.2.5.5 Establish a permanent mechanism for timely dissemination of new technologies and information between research centers | [24 empty] | Depends on: 1.2.5.2 (platforms established) | bar: Year 3 Q2 to Year 4 Q1
Output 1.3 Increased capacity to access financial services to manage climate-related risk | bar: Year 1 Q2 to Year 6 Q1
Activity 1.3.1: Build capacity to access financial services | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.3.1.1 Integrate into existing training programs technical assistance to improve performance and governance systems of agriculture cooperatives to meet minimum requirements to participate in formal financial markets | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q3 to Year 1 Q4; Year 2 Q3 to Year 2 Q4; Year 3 Q3 to Year 3 Q4
Sub-activity 1.3.1.2 Build capacity of finance staff to respond to the distinct and diverse needs of farmers, such as segmenting farming populations, assessing needs and constraints, customizing financial products and putting in place a monitoring and evaluation system for a full recovery of loans | [24 empty] | Depends on: 1.3.1.1 (cooperative training) | bar: Year 1 Q3 to Year 2 Q3; Year 3 Q1 to Year 3 Q3; Year 4 Q1 to Year 4 Q3; Year 5 Q1 to Year 5 Q3
Sub-activity 1.3.1.3 Build community expertise in carbon markets — aggregate smallholder credits, apply robust verification and fair benefit-sharing, and engage regulators to codify supportive carbon-trading rules | [24 empty] | Depends on: 1.3.1.1 (cooperative training) | bar: Year 1 Q4 to Year 6 Q1
Sub-activity 1.3.1.4 Train local fund managers and impact investors to originate profitable, climate-aligned deals and structure innovative vehicles that crowd in additional CSA capital | [24 empty] | Depends on: 1.3.1.1 (cooperative training) | bar: Year 1 Q4 to Year 3 Q3
Activity 1.3.2: Foster gender-sensitive policies | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.3.2.1 Map gender-smart lending policies, their adoption by local banking eco-systems and integrate persona-based lending considerations, based on women and men’s needs, behaviors and decision-making processes into tailored gender responsive credit solutions being developed in activity 1.3.1 | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q2 to Year 5 Q3
Sub-activity 1.3.2.2 Promote the establishment of agriculture disaster funds through technical assistance in a risk management strategy that will, in particular, integrate women and other vulnerable groups | [24 empty] | Depends on: 1.3.2.1 (gender policy mapping) | bar: Year 1 Q3 to Year 6 Q1
Sub-activity 1.3.2.3 Develop gender-inclusive financial services roadmap through series of workshops with selected financial and microfinance institutions | [24 empty] | Depends on: 1.3.2.1 (gender policy mapping) | bar: Year 2 Q1 to Year 6 Q1
Sub-activity 1.3.2.4: Together with MFIs, design and promote (through capacity building of agri-SMEs) gender-sensitive financial products | [24 empty] | Depends on: 1.3.2.3 (financial services roadmap) | bar: Year 2 Q1 to Year 5 Q3
Activity 1.3.3: Promote financial tools to reduce risks | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.3.3.1 Promote warehouse receipt and value-chain finance together with MFIs so farmers can pledge stocks or off-take contracts as collateral and unlock working capital | [24 empty] | GATE ●: Depends on: 1.3.1.1+1.3.4.2 complete | bar: Year 2 Q1 to Year 2 Q3
Sub-activity 1.3.3.2 Develop and promote agriculture climate index-insurance via private partnerships through education and awareness programs, recommendations for subsidies and flexible payment options (paying premiums after harvest), trust building, communication, financial literacy, and marketing and outreach campaigns in local languages | [24 empty] | GATE ●: Depends on: 1.3.1.1+1.1.2.3 complete | bar: Year 2 Q1 to Year 2 Q3; Year 3 Q1 to Year 3 Q3; Year 4 Q1 to Year 4 Q3; Year 5 Q1 to Year 5 Q3
Sub-activity 1.3.3.3 Establish value chain finance model in collaboration with private sector actors, covering input suppliers, producers, and off-takers | [24 empty] | Depends on: 1.3.3.1 (WRS established) | bar: Year 1 Q3 to Year 5 Q4
Activity 1.3.4: Reduce transaction costs | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.3.4.1: Mobilize liquid assets via savings groups, particularly for mid-term loans | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q3 to Year 3 Q2
Sub-activity 1.3.4.2 Establish a loan monitoring platform | [24 empty] | Depends on: 1.3.4.1 (savings groups) | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.3.4.3 Utilize big data and data-science services to assess risk, determine creditworthiness, and inform/guide loan provisions | [24 empty] | Depends on: 1.3.4.2 (monitoring platform) | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.3.4.4: Leverage mobile network operators ICTs to implement mobile, over-the-counter, and branchless banking in underserved areas | [24 empty] | Depends on: 1.3.4.2 (monitoring platform) | bar: Year 1 Q3 to Year 6 Q1
Activity 1.3.5: Provide CSA-relevant data | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 1.3.5.1 Leverage strengthened national CIS through systems from activity 1.1.3 to link application programming interface (API) of tools | [24 empty] | GATE ●: Depends on: 1.1.3.3 (CIS API Integration) | bar: Year 1 Q2 to Year 5 Q3
Sub-activity 1.3.5.2 Link national soil information system | [24 empty] | Depends on: 2.1.1.1 (soil maps) | bar: Year 1 Q3 to Year 5 Q3
Sub-activity 1.3.5.3 Leverage radio, mobile network providers, digital mobile applications to provide timely, accurate climate information, soil information, and other CSA-related data to producers | [24 empty] | Depends on: 1.3.5.1 (API linked) | bar: Year 1 Q2 to Year 5 Q3
Component 2: Reducing GHG emissions and enhancing soil carbon sequestration | bar: Year 1 Q2 to Year 6 Q1
Output 2.1 Integrated system for sustainable land and agroforestry | bar: Year 1 Q2 to Year 6 Q1
Activity 2.1.1: Develop soil and agroforestry recommendations | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 2.1.1.1: Employ remote sensing and digital soil libraries to develop digital maps | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 2.1.1.2: Identify and select relevant technologies, and validate and adapt these to local conditions using optimization trials | [24 empty] | Depends on: 2.1.1.1 (digital maps) | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 2.1.1.3: Identify and select tools and products to support recommended practices | [24 empty] | Depends on: 2.1.1.2 (technologies selected) | bar: Year 2 Q1 to Year 3 Q4
Sub-activity 2.1.1.4: Communicate' recommended practices | [24 empty] | GATE ●: Depends on: 2.1.1.2+2.1.1.3 complete | bar: Year 1 Q2 to Year 6 Q1
Activity 2.1.2 Develop soil and environmental information services | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 2.1.2.1: Identify and train a dedicated governmental team for SEIS | [24 empty] | Prerequisite: inception phase | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 2.1.2.2: Generate publicly accessible SEIS and maintain and update SEIS | [24 empty] | GATE ●: Depends on: 2.1.2.1 (team trained) | bar: Year 2 Q1 to Year 6 Q1
Sub-activity 2.1.2.3: Establish private industry and public sector partnerships (e.g., agribusiness, analysis laboratories, research facilities) to create or significantly increase availability of the tools and products recommended by research organizations to producers and extension agents (e.g., AfSIS, Africa; EthioSIS, Ethiopia; GhaSIS, Ghana; NiSIS, Nigeria; and TanSIS, Tanzania) | [24 empty] | Depends on: 2.1.2.2 (SEIS operational) | bar: Year 1 Q4 to Year 6 Q1
Activity 2.1.3: Tools for producer decision-making | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 2.1.3.1: Conduct gender-sensitive awareness training and public campaigns | [24 empty] | GATE ●: Depends on: 2.1.1.4+2.1.2.2 complete | bar: Year 2 Q1 to Year 6 Q1
Sub-activity 2.1.3.1: Develop gender-sensitive and practical decision-making support tools based on the SEIS and agroforestry knowledge base for use by producers and extension agents (e.g., mobile information system, call center, participatory training tools) | [24 empty] | Depends on: 2.1.1.2+2.1.2.2 (SEIS+recomm.) | bar: Year 2 Q1 to Year 6 Q1
Sub-activity 2.1.3.3: Increase producer likelihood to invest in long-term soil health | [24 empty] | Depends on: 2.1.3.1+2.1.3.2 complete | bar: Year 1 Q2 to Year 4 Q4
Component 3: Climate-smart agri-food systems | bar: Year 1 Q2 to Year 6 Q1
Output 3.1 Access to climate-smart agriculture technologies | bar: Year 1 Q2 to Year 6 Q1
Activity 3.1.1: Promote high-quality inputs | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 3.1.1.1 Identify beneficiaries (rice, yam, cassava producers, nursery operators, private seed producers, and women's groups) | [24 empty] | GATE ●: Prerequisite: inception phase | bar: Year 1 Q2 to Year 2 Q1
Sub-activity 3.1.1.2 Professionalize women’s associations in seed production and training to improve access to seed production facilities and improved seed | [24 empty] | Depends on: 3.1.1.1 (beneficiaries identified) | bar: Year 2 Q2 to Year 3 Q1
Sub-activity 3.1.1.3 Provide technical support to new cooperatives and organizations in management and meeting minimum requirements for accessing financial services | [24 empty] | Depends on: 3.1.1.1 (beneficiaries identified) | bar: Year 2 Q2 to Year 3 Q1
Sub-activity 3.1.1.4: Develop partnerships with agribusiness (SMEs) toward meeting the demands for high-quality yam, cassava, and rice agri-inputs and products | [24 empty] | Depends on: 3.1.1.1 (beneficiaries identified) | bar: Year 2 Q2 to Year 3 Q1
Activity 3.1.2: Promote high quality climate resilient planting material | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 3.1.2.1: Identify and validate climate-smart improved rice varieties for rainfed, lowland and irrigated rice systems, and improved, climate-smart varieties of cassava and yam | [24 empty] | GATE ●: Depends on: 3.1.1.1+1.2.4.3 complete | bar: Year 1 Q2 to Year 3 Q1
Sub-activity 3.1.2.2: Identify improved breeds of fish for integrated rice-fish systems | [24 empty] | Depends on: 3.1.2.1 (varieties validated) | bar: Year 1 Q2 to Year 3 Q1
Sub-activity 3.1.2.3: Deploy locally appropriate, climate-smart optimized propagation techniques for cassava and yam, as well as climate-smart rice varieties | [24 empty] | GATE ●: Depends on: 3.1.2.1 (varieties validated) | bar: Year 2 Q2 to Year 6 Q1
Activity 3.1.3: Strengthen commercialization organizations | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 3.1.3.1 Establish access to appropriate mechanization tools for processing | [24 empty] | Depends on: 3.1.1.3 (cooperatives supported) | bar: Year 2 Q2 to Year 4 Q1
Sub-activity 3.1.3.2 Provide training in new processing techniques to diversify value addition options and improve processing efficiency | [24 empty] | Depends on: 3.1.3.1 (mechanization) | bar: Year 2 Q2 to Year 4 Q1
Sub-activity 3.1.3.3 Conduct entrepreneurship training and support mentorship programs for cooperative participation in regional and national agricultural fairs | [24 empty] | Depends on: 3.1.3.1+3.1.3.2 complete | bar: Year 2 Q4 to Year 4 Q1
Sub-activity 3.1.3.4 Strengthen existing digital market information platform to facilitate sales | [24 empty] | Depends on: 3.1.1.4 (partnerships developed) | bar: Year 1 Q4 to Year 6 Q1
Activity 3.1.4: Streamline infrastructure | bar: Year 1 Q2 to Year 6 Q1
Sub-activity 3.1.4.1 Rehabilitate lowland areas | [24 empty] | GATE ●: Depends on: 3.1.4.4 E&S screening | bar: Year 2 Q2 to Year 5 Q1
Sub-activity 3.1.4.2 Install rice, yam, and cassava processing and storage facilities to mechanize production processes | [24 empty] | GATE ●: Depends on: 3.1.4.4 E&S screening | bar: Year 3 Q2 to Year 5 Q1
Sub-activity 3.1.4.3: Identify and train cooperatives and professional organizations from the three value chains to use, manage, and maintain these infrastructures | [24 empty] | GATE ●: Depends on: 3.1.4.2 (facilities installed) | bar: Year 3 Q2 to Year 5 Q1
Sub-activity 3.1.4.4 Carry out environmental and social screening and address recommendations | [24 empty] | GATE ●: PREREQUISITE for 3.1.4.1+3.1.4.2 | bar: Year 2 Q1 to Year 5 Q1
Project Monitoring* | Year 1 Q3: Inception Report; Year 2 Q1: APR; Year 3 Q1: APR; Year 4 Q1: APR; Year 4 Q2: Interim Evaluation; Year 5 Q1: APR; Year 6 Q1: Completion Report; Year 6 Q3: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.

## Legend - Dependencies
LARACI Annex 5 - Dependency Gates & Critical Path Legend
Symbol / Color | Meaning | Operational Rule
◆ Orange fill | Critical Path activity | Delay in this activity directly delays project completion. PMU monitors monthly.
● Yellow fill (GATE) | Hard dependency gate | Successor activity CANNOT begin until this gate is formally signed off. Disbursement condition.
Grey fill | Normal dependency | Logical predecessor. Successor should not begin before predecessor completes but no formal gate required.
KEY DEPENDENCY GATES (Hard Gates - require formal sign-off before successor starts)
3.1.4.4 E&S Screening | MUST complete before 3.1.4.1 and 3.1.4.2 | No physical works contract issued without site clearance record in project files.
1.2.4.2 Prioritization Workshop | MUST complete before 1.2.4.3 validation tests | No validation tests begin without approved priority list.
1.2.4.3 Validation tests | MUST complete before 1.2.4.4 field visits & mass dissemination | No Tier 2 technology added to dissemination portfolio without formal validation sign-off.
1.1.2.3 SEIS deployment | MUST complete before 1.3.5.1 API linking | No climate data API integration before SEIS is operational.
1.1.1.2+1.1.1.3 Stations | MUST complete before 1.1.1.5 installation | No commissioning before acquisition and rehabilitation complete.
CRITICAL PATH SEQUENCE
1.1.1.1 → 1.1.1.2/1.1.1.3 → 1.1.1.5 → 1.1.2.3 → 1.3.5.1 → 1.3.3.1 → 1.3.3.2 | Climate information critical path | Delays here affect financial de-risking timeline.
1.2.4.1 → 1.2.4.2 → 1.2.4.3 → 1.2.4.4 → 1.2.2.4 | Technology validation to dissemination critical path | Delays here affect adoption targets.
3.1.4.4 → 3.1.4.1 → 3.1.4.2 → 3.1.4.3 | Infrastructure critical path | E&S screening gates all physical works.
3.1.1.1 → 3.1.2.1 → 3.1.2.3 | Seed systems critical path | Beneficiary identification gates all downstream variety work.