## Implementation timetable
Annex 5 Implementation Timetable
Project Title: "Building the resilience of Togo's national health system and vulnerable communities to climate-sensitive health outcomes"
|  | Implementation period of the project |  | Implementation period of the subactivity | 1 technical procurement file, including specs, supplier selection report, and delivery certificates delivered | Deliverable
COMPONENTS/OUTPUTS | Y1 |  |  |  | Y2 |  |  |  | Y3 |  |  |  | Y4 |  |  |  | Y5 |  |  |  | Y6
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Component 1: Strengthening the surveillance system for climate-sensitive diseases | bar: Y1 Q1 to Y5 Q4
Output 1.1: Climate information to support the surveillance system for climate-sensitive health outcomes is effectively integrated
Activity 1.1.1: Improve and expand coverage of the hydrometeorological network in underserved areas
Sub-activity 1.1.1.1: Purchase and installation of automated weather stations and rain gauges | Y2 Q1: 1 technical procurement file, including specs, supplier selection report, and delivery certificates delivered; Y3 Q2: 4 new AWS procured, installed and delivered 50 rain gauges procured, installed and delivered
Sub-activity 1.1.1.2: Repair and rehabilitation of existing AWS and rain gauges | Y2 Q2: 1 national technical audit report with rehabilitation needs and field logs developed; Y2 Q3: 15 AWS and 82 rain gauges repaired and restored to real-time operational status, with maintenance teams demonstrating an absolute target of ≥40% female technicians At least 40% of technicians participating in rain gauge and weather station repair and maintenance activities are women.
Activity 1.1.2: Enhance ANAMET’s ability to manage automated meteorological data and maintain equipment
Sub-activity 1.1.2.1: Establishment of a decentralised unit in Kara | Y2 Q4: 1 building to host the maintenance workshop, storage areas and logistics taking into consideration gender needs 1 fully operational Decentralised Maintenance Centre with workshops, storage areas and logistics capacity for rapid interventions equipped
Sub-activity 1.1.2.2: Establishment of digital maintenance protocols and monitoring of hydrometeorological infrastructure and equipment | Y2 Q2: 1 fully operational digital solution for maintenance protocols and monitoring developed; Y2 Q3: 30 (ANAMET, ANPC) technical personnel trained for data upkeeping, maintenance protocols, stock availability and proactive planning
Activity 1.1.3: Strengthen the capacities of ANAMET to provide climate services for health
Sub-activity 1.1.3.1: Capacity development and dissemination of climate and health bulletins | Y1 Q4: 3 sets training material on climate and health nexus science, risk communication, health and climate bulletins developed At least five (≥ 5) staff members only from ANAMET’s technical divisions (Agrometeorological, Synoptic, Climatological, Forecasting, and Instrumentation) will be trained on climate and health nexus science, risk communication, and the development of health and climate bulletins.; Y2 Q1: 15 participants of ANAMET personnel trained; Y5 Q3: 15 monthly bulletins delivered
Sub-activity 1.1.3.2: Strengthening of managerial, organisational, and intersectoral coordination capacities | Y1 Q4: 1 log of ad hoc support provided; Y2 Q3: 1 set training material on M&E, Risk Assessment, ESS, SEAH and FM developed; Y2 Q4: 10 ANAMET personnel trained
Output 1.2: Integrated surveillance outputs are effectively used to guide climate-sensitive health outcome response, especially for vulnerable groups | bar: Y1 Q2 to Y3 Q2
Activity 1.2.1: Strengthen governance structures to foster an enabling environment for surveillance of climate-sensitive health outcomes
Sub-activity 1.2.1.1: Conduct a data landscape analysis and institutional mapping | Y1 Q4: 4 data managers trained (2 health DSNISI, 2 meteorological ANAMET) and 2 stakeholders (ANPC, GIZ) staff on data landscape analyses and institutional mapping; Y2 Q2: 1 report on prioritised technical and institutional requirements developed 1 consolidated implementation-readiness note developed
Sub-activity 1.2.1.2: Strengthening the institutional set up | Y1 Q4: 3 MoUs signed between MSHPCSUA and stakeholders; Y2 Q2: 1 set of SOPs for data collection developed; Y2 Q3: 10 data managers and technical staff trained on SOP processes and institutional mandates; Y4 Q4: 1 cooperation agreement between MSHPCSUA, WASCAL-UoL, and a university with a strong track record on climate-sensitive disease modelling signed
Sub-activity 1.2.1.3: Strengthening collaboration mechanisms | Y1 Q4: 1 Climate & Health Data Sub-Group established under the One Health Platform; Y2 Q2: 1 annual coordination forum between ministries, agencies, and development partners held; Y2 Q4: 10 institutional stakeholders trained on collaboration protocols and technical data integration
Sub-activity 1.2.1.4: Establishing the technical interoperability architecture and assurance | Y1 Q4: 1 Interoperability, Security and Compliance Framework established; Y2 Q2: Climate-health data interoperability and dashboard pilots implemented Operations & capacity institutionalisation completed
Activity 1.2.2: Leverage integrated surveillance data to create CSHO-specific models that analyse the influence of weather on transmission and inform more effective planning
Sub-activity 1.2.2.1: Establish academic exchanges and partnerships | Y2 Q4: 3 MoUs signed between Togolese universities and regional/international universities; Y5 Q2: 6 faculty members participated in short-term academic exchanges
Sub-activity 1.2.2.2: Strengthen climate- and weather-health modelling capacities | Y2 Q3: 5 professionals trained in short-term and long-term predictive/projection models for malaria and diarrhoea; Y4 Q1: 6 operational models for short-term (3) and long-term scenarios (3) of weather to malaria, diarrhoea, and heat integrating developed
Sub-activity 1.2.2.3: Enhance interpretation and application of models in real-world settings | Y2 Q3: 1 calibrated and validated standardised framework of interpretation; Y2 Q4: 2 manuals of interpretation developed; Y3 Q4: 4 health partners from MSHPCSUA and WASCAL-UoL trained to conduct model assessment and adaptation
Sub-activity 1.2.2.4: Strengthen AMR data integration into surveillance systems | Y1 Q3: 1 synthesis report on climate-AMR linkages produced; Y2 Q2: 1 national AMR Action Plan updated to incorporate climate-sensitive surveillance and decision-making developed
Sub-activity 1.2.2.5: Develop scale-up roadmap for climate- and weather-health modelling | Y5 Q1: 1 scale-up gender responsive roadmap validated
Output 1.3: An EWS for health is used by policymakers, HFs, the general and key vulnerable populations
Activity 1.3.1: Strengthen operational arrangements to implement warning services delivery
Sub-activity 1.3.1.1: Establishing the governance framework for Health Early Warning | Y1 Q3: 1 governance framework for H-EWS validated and endorsed by MoH, ANAMET, ANPC; Y2 Q1: 1 national SOPs for alert workflows finalised and disseminated; Y2 Q4: H-EWS annex integrated into national MHEWS procedures
Sub-activity 1.3.1.2: Defining thresholds and integrating data for health alerts | Y2 Q2: Alert thresholds for malaria, diarrhoeal diseases, and heat impacts defined and validated by MSHPCSUA and ANAMET incorporating gender-responsive vulnerability criteria
Sub-activity 1.3.1.3: Developing the digital platform for health alerts | Y2 Q3: 1 digital platform for H-EWS operational and linked to national MHEWS; Y2 Q4: Automated alert generation and validation workflows being functional
Sub-activity 1.3.1.4: Building capacity and ensuring sustainability of the H-EWS | Y2 Q4: 120 staff at national and regional level trained on H-EWS alert workflows; Y3 Q4: Digital helpdesk and refresher course for EWS established
Activity 1.3.2: Deliver warning messages through multiple communication channels and strengthen response in affected communities
Sub-activity 1.3.2.1: Co-developing a practical communication approach for Togo’s Early Warning System | Y3 Q2: 1 H-EWS communication methodology and toolkit developed and validated; Y3 Q4: 1 H-EWS communication strategy for Togo finalised
Sub-activity 1.3.2.2: Strengthening community capacity to understand and act on early health warnings | Y3 Q2: 1 EWS training module developed (to be delivered into the multiplier training package of 4.2.2); Y3 Q3: 3 regional joint training sessions (together with 4.2.2) reaching at least 500 multipliers (CHWs, teachers, Red Cross volunteers, local leaders) who will also be trained on EWS
Component 2: Building an enabling environment to increase health sector resilience | bar: Y1 Q1 to Y5 Q4
Output 2.1: Intersectoral collaboration, accountability, and leadership mechanisms on climate change and health issues is strengthened
Activity 2.1.1: Establish a Climate Change Unit dedicated to health and climate change issues within the MSHPCSUA
Sub-activity 2.1.1.1: Formal establishment of the CCU | Y1 Q4: 1 ministerial decree officially establishing the CCU within the MSHPCSUA, mandating a composition of ≥50% women and ≥10% women in leadership and decision-making positions 1 institutional framework document for the CCU adopted by the MSHPCSUA
Sub-activity 2.1.1.2: Capacity strengthening of the CCU | Y2 Q2: 1 institutional capacity development plan validated and adopted by MSHPCSUA; Y3 Q2: 25 staff trained on technical and managerial topics, comprising an absolute target of ≥50% women; Y4 Q3: 2 regional peer learning or exchange visits completed
Sub-activity 2.1.1.3: Operational and strategic partnerships | Y2 Q3: 3 formal cooperation agreements (MoUs/protocols) signed with strategic institutions under Output 1.2; Y2 Q4: 1 strategic partnership and donor engagement plan, including a coordination mechanism, is developed
Sub-activity 2.1.1.4: Provision of equipment and material resources for the CCU | Y2 Q2: 1 CCU with complete office setup (including IT) equipped; Y2 Q3: 1 operational 4x4 utility vehicle delivered and registered for CCU
Activity 2.1.2: Establish 5 Climate Change Units in the Regional Health Directorates
Sub-activity 2.1.2.1: Institutional set up and operationalisation of Regional CCUs | Y1 Q3: 5 CCUs established through legal documents, with the formal assignment of personnel across these units comprising an absolute target of ≥30% women (Q3/Year 1) ≥ 1 of the 5 regional CCUs will be headed by a woman from the assigned personnel, with the required technical, managerial, and leadership skills
Sub-activity 2.1.2.2: Capacity development and technical support | Y2 Q1: 15 members of the 5 CCUs trained in technical, administrative and management skills, ensuring an absolute target of ≥30% women within the training cohort; Y2 Q3: 10 regional peer-learning workshops conducted
Sub-activity 2.1.2.3: Provision of operational tools and equipment | Y2 Q2: 5 regional CCUs equipped with complete office setup (including IT)
Activity 2.1.3: Strengthen national and sub-regional coordination, knowledge, and learning mechanisms
Sub-activity 2.1.3.1: Strengthening MSHPCSUA and CCU’s strategic engagement in national multi-sectoral platforms (One Health, National Adaptation Committee) through institutional mapping, role clarification, and technical support | Y2 Q1: 1 Strategic Engagement and Coordination Plan for CCUs validated by MSHPCSUA; Y3 Q2: 1 Capacity Development Programme for One Health, National Adaptation Committee, and CCUs delivered to 15 staff, aiming for an absolute target of ≥30% female participation in the training cohort; Y5 Q2: National CCU participated in 3 climate-relevant coordination platforms
Sub-activity 2.1.3.2: Organisation and/or participation in inclusive national, regional, and international conferences, negotiations and fora | Y5 Q2: CCU/MSHPCSUA participated in 5 regional or international conferences and fora on climate change and health 2 national research-policy exchange fora conducted
Sub-activity 2.1.3.3: Promotion of regional knowledge exchange and joint learning | Y4 Q3: 1 regional or international event co-hosted by MSHPCSUA in Togo; Y4 Q4: 5 lessons learnt products produced and disseminated regionally; Y5 Q2: 3 joint learning missions conducted, with active recruitment and priority selection aiming for an absolute target of ≥30% female participation within the delegations
Output 2.2: Capacities of the health system to react to climate-sensitive health problems are built
Activity 2.2.1: Develop and implement climate and health training programmes
Sub-activity 2.2.1.1: Develop a Climate and Health Master’s programme | Y2 Q1: 1 integrated and validated Master curriculum, including (online) teaching tools; Y5 Q2: 13 students (1 cohort) successfully complete the master’s programme in Climate and Health
Sub-activity 2.2.1.2: Adapt medical support curricula by integrating climate change and health | Y1 Q3: 2 medical curricula updated, integrating climate change, AMR, and One health concepts (revised didactic and pedagogical approaches); Y1 Q4: Updated teaching materials are produced to reflect the revised curricula; Y2 Q4: 4 training sessions delivered for medical school teaching staff
Sub-activity 2.2.1.3: Promote intersectoral and participatory research on climate and health, encouraging collaboration between academic, governmental, and community actors | Y5 Q2: 2 national conferences in Togo focused on climate and health research organised
Sub-activity 2.2.1.4: Support for research proposal submissions | Y2 Q1: 1 set of training materials on research proposal development developed; Y2 Q3: 4 capacity-building workshops (80 trainees) delivered for researchers on proposal design and grant writing delivered, aiming for an absolute target of ≥30% female participation
Activity 2.2.2: Build technical capacities of key actors in the health sector in the prevention and management of climate-sensitive health outcomes through training
Sub-activity 2.2.2.1: Developing innovative blended learning formats | Y2 Q4: 30 trainers trained in 3 ToT’s sessions to build capacity, ensuring an absolute target of ≥30% women (minimum 9 out of 30 trainers)
Sub-activity 2.2.2.2: Training national and regional health personnel | Y2 Q4: 150 national and regional health workers trained, with at least 80% of nationally trained female health professionals demonstrating adequate knowledge of Respectful Maternity Care, humanised childbirth approaches, and the use of carbetocin
Sub-activity 2.2.2.3: Training of community health workers | Y2 Q4: 150 CHWs trained
Component 3: Climate-resilient and low-carbon infrastructures, technologies, and supply chain | bar: Y1 Q1 to Y5 Q4
Output 3.1: The resilience of health infrastructure is strengthened
Activity 3.1.1: Improve health infrastructures to increase resilience (water-related, heat-related, vector-related health outcomes)
Sub-activity 3.1.1.1: Consolidation of infrastructure norms and co-revision of health facilities' master plans | Y1 Q4: 1 set of resilient health infrastructure guidelines developed; Y2 Q2: 25 personnel members trained in the application of the guidelines (15 technical personnel and HF managers and 10 technical personnel from the Regional Departments)
Sub-activity 3.1.1.2: Assessment and selection of health facilities | Y1 Q3: 1 prioritisation framework for the selection of HFs; Y2 Q1: 1 list of eligible and selected HFs validated by PSC
Sub-activity 3.1.1.3: Capacity building on construction techniques and resilience measures | Y2 Q2: 1 training program developed; Y3 Q4: 225 core team of construction/Maintenance personnel trained, with priority selection aiming for an absolute target of ≥30% female participation among providers and artisans
Sub-activity 3.1.1.4: Rehabilitation of health facilities and construction of resilient maternity blocks in USP-I and II | Y2 Q1: 100% of construction plans developed or updated under the project are based on participatory needs assessments and comply with person-centred care standards by the end of the project and undergo validation by OGES, local women representatives, medical staff and project team in the design phase.; Y4 Q4: 15 HFs rehabilitated or extended or newly constructed considering climate resilience At least 60% (9 out of 15) health care facilities have separate maternity wards in accordance with the revised standard 100% (up to 15 facilities) provide gender-responsive, inclusive and confidential climate-sensitive health services 100% demonstrate effective use of accessibility features by patients with reduced mobility At least 30 staff members (2 per upgraded facility) trained on survivor-centred GBV/SEAH case management and referral protocols 3 operation and maintenance (O&M) plans developed (1 per region, covering the 15 HFs)
Sub-activity 3.1.1.5: Procurement of health facility equipment | Y5 Q1: 15 USP equipped
Activity 3.1.2: Maintain health infrastructure to increase resilience
Sub-activity 3.1.2.1: Strengthening gender transformative professional training and in-service training | Y2 Q1: 1 BT-level Technical Training module on maintenance in HFs developed 1 national recognition framework for maintenance staff implemented in 50 HFs; Y5 Q2: 20 BT students certified and included in a national technician registry, supported by targeted awareness-raising campaigns aiming for an absolute target of ≥25% female participation 200 end-user training sessions delivered
Sub-activity 3.1.2.2: Strengthening partnership engagement for maintenance | Y1 Q4: 1 Public-Private Maintenance Partnership (PPMP) Task Force established; Y2 Q2: 1 MoU signed between the MSHPCSUA and the private sector
Sub-activity 3.1.2.3: Support gender transformative and climate-sensitive operationality of maintenance in the health facilities | Y2 Q2: 3 RMCs established
Sub-activity 3.1.2.4: Support digitalisation of maintenance processes | Y2 Q3: 1 national digital inventory of health facility equipment and infrastructure completed and validated; Y3 Q2: 1 GMAO system deployed (with software, licenses, server hosting, digital devices) operationalised 6 GMAO training programmes delivered (1 for 20 principal users and 5 regional workshops for 100 users), aiming for an absolute target of ≥30% female participation within the training cohorts
Sub-activity 3.1.2.5: Support a financing mechanism for the Regional Maintenance Fund | Y1 Q3: 1 strategy for resource mobilisation developed; Y3 Q2: 75 staff members trained (45 regional and 30 prefecture level), aiming for an absolute target of ≥30% female participation within the training cohorts
Output 3.2: Prevention and treatment of CSHOs through resilient supply chains is enhanced
Activity 3.2.1: Strengthen cold chains for vaccines, climate-sensitive medicines and diagnostics
Sub-activity 3.2.1.1: Survey and strengthen cold chain and energy infrastructure | Y1 Q4: 1 assessment package of cold chain and energy infrastructure validated; Y2 Q2: End-to-end temperature monitoring operational; Y3 Q4: 15 USPs with stationary cold chain upgraded
Sub-activity 3.2.1.2: Improving cold chain transport and distribution of medicine products | Y2 Q4: 1 cold chain transport system in place (vehicles, backpack, trained personnel)
Sub-activity 3.2.1.3: Support to national e-LMIS roll-out | Y2 Q4: 1 national e-LMIS system in place and validated; Y3 Q4: 5 trainers trained, aiming for an absolute target of ≥30% female participation
Activity 3.2.2: Strengthen surveillance and monitoring of climate-sensitive health outcomes
Sub-activity 3.2.2.1: Extension of epidemiological sentinel sites for malaria | Y1 Q4: 15 new epidemiological sentinel sites functional; Y2 Q2: 60 health workers trained on malaria surveillance, aiming for an absolute target of ≥30% female participation
Sub-activity 3.2.2.2: Expansion towards entomological and parasitological sentinel sites for malaria | Y2 Q2: 6 entomological and parasitological sentinel sites operational; Y2 Q3: Protocols for insecticide resistance and parasite monitoring validated
Sub-activity 3.2.2.3: Expansion towards climatological sentinel sites for diarrhoeal diseases | Y2 Q3: 6 climatological sentinel sites operational 20 health and environmental officers trained on integrated climate-health surveillance, aiming for an absolute target of ≥30% female participation
Sub-activity 3.2.2.4: Pilot of fever clinics in sentinel sites | Y1 Q3: 15 fever clinics established and equipped; Y2 Q2: 60 health professionals trained and deployed, aiming for an absolute target of ≥30% female participation
Sub-activity 3.2.2.5: Strengthening of monthly data quality reviews and reporting at district and regional levels | Y5 Q3: 6 districts in data improvement supported (focal point coaching, monitoring meetings) All project-supported surveillance systems configured to report sex-disaggregated data on climate-sensitive health outcomes 30 data managers trained on eDQR, including the mandatory provision of one female-only training session for women staff of ministerial data units (DSNISI) to build leadership and confidence Gamification dashboards in DHIS2 operation in the 3 regions By end of project, 100% of the project-supported surveillance systems (epidemiological, entomological, and climatological sentinel sites) regularly produce report including sex-disaggregated data on at least 3 priority climate-sensitive health (Q2/Year 5)
Activity 3.2.3: Strengthen diagnostic and treatment of climate-sensitive health outcomes
Sub-activity 3.2.3.1: Institutionalise diagnostics and strengthen laboratory systems for climate‑sensitive diseases | Y2 Q2: 900,000 rapid diagnostic tests available in targeted areas for 3 years; Y4 Q4: 1 operational procedure validated and disseminated
Sub-activity 3.2.3.2: Strengthening access to essential medicines and preventative services | Y2 Q2: 1 set of pharmacovigilance guidelines developed and disseminated; Y5 Q3: Heat-resilient essential medicines available in the 3 regions 2 studies of therapeutic efficacy of anti-malaria drugs published
Sub-activity 3.2.3.3: Regional access to essential climate-relevant medicines | Y5 Q2: 10 HFs supplied with climate‑relevant medicines through regional procurement agreements
Component 4: Enhancing community adaptation and engagement | bar: Y1 Q1 to Y5 Q4
Output 4.1: Improve community infrastructures to be more resilient to water-related climate-sensitive health outcomes
Activity 4.1.1: Improve community infrastructure to be more resilient to water-related climate-sensitive diseases
Sub-activity 4.1.1.1: Rehabilitate water supply systems in schools | Y4 Q4: 15 schools with drinking water supply systems installed/rehabilitated
Sub-activity 4.1.1.2 Implement improved sanitation facilities in schools | Y4 Q3: 15 schools with improved sanitation blocks installed/rehabilitated 5 DEWATS treatment facilities installed
Sub-activity 4.1.1.3: Build capacity for WASH infrastructure management in schools | Y2 Q3: 1 WASH in Schools framework developed; Y3 Q1: 3 workshops on WASH facility management conducted (including participants from the 15 schools), aiming for an absolute target of ≥30% female participation 15 MH awareness sessions in the 15 targeted schools 750 reusable sanitary pad kits distributed to girls in the 15 schools by trained multipliers Formal agreement between the municipal emptying service in place for all schools signed
Sub-activity 4.1.1.4: Promote WASH innovations for community behaviour change | Y1 Q4: WASH products distributed in 15 Sanimarkets; Y2 Q4: 3 training in the 15 Sanimarkets on innovative WASH products delivered 15 functional selling points for MH products established
Activity 4.1.2: Strengthen community engagement and local government capacity for integrated health, sanitation, and malaria control interventions
Sub-activity 4.1.2.1: Pilot innovative and environmentally safe anti-larval interventions | Y2 Q3: 1 training manual for CHW to include safe anti-larval interventions updated; Y2 Q4: 30 local providers selected and trained on mosquito screen production and installation, aiming for an absolute target of ≥30% female participation; Y3 Q3: 16 community awareness and marketing campaigns on mosquito nets in the targeted areas delivered
Sub-activity 4.1.2.2: Develop or update communal hygiene and sanitation plan incorporating malaria prevention and control | Y2 Q2: 80 municipal staff (10 per municipality) trained on integrated planning, aiming for an absolute target of ≥30% female participation; Y2 Q4: 8 communal hygiene and sanitation plans updated or developed
Sub-activity 4.1.2.3: Strengthen communal coordination of health, sanitation, and vector control interventions | Y2 Q4: 2 workshops on strengthening communal communication of 15 local HF committees delivered, aiming for an absolute target of ≥20% female participation
Output 4.2: Community awareness and understanding of climate-health linkages are enhanced
Activity 4.2.1: Develop communication messages, tools, and channels for different key populations to alert them on climate induced changes to health risks
Sub-activity 4.2.1.1: Evaluate and refine the SBC Strategy and Toolkit | Y2 Q1: 1 SBC Toolkit based on evaluation results revised
Sub-activity 4.2.1.2: Develop a translation and communication guide for climate-health concepts | Y2 Q2: 1 Translation and Communication Guide formally endorsed by the TWG and integrated into the national SBC Climate and Health Toolkit with the participation of ≥ 1 woman, 1 LC representative, and 1 representative of persons with disabilities in the development process.
Sub-activity 4.2.1.3: Evaluate, monitor impact, and adapt the SBC Climate and Health Strategy | Y5 Q3: 1 final consolidated evaluation and lessons-learned report feeding into the national SBC Toolkit developed
Activity 4.2.2: Strengthen the capacities of multipliers at community level on the links between climate change and health
Sub-activity 4.2.2.1: Develop and deliver localised training programs for community-level multipliers on climate–health risks | Y3 Q4: 20 trainers trained through ToT, ensuring an absolute target of ≥40% women (minimum 8 participants) 500 multipliers trained in climate-health SBCC approaches and impact measuring, with recruitment ensuring a final pool of ≥125 women and ≥2 representatives per local community
Sub-activity 4.2.2.2: Develop and provide multipliers with tailored communication materials and tools to engage their communities | Y2 Q3: 1 toolkit containing at least 4 audience-specific communication formats developed; Y2 Q4: 3 toolkit translations in key local languages validated; Y3 Q4: 4,000 toolkits distributed
Sub-activity 4.2.2.3: Coordinate and implement interpersonal communication campaigns through multipliers | Y2 Q3: 8 Community SBCC Action Plans developed; Y5 Q3: 4 community sensitisation campaigns conducted annually across 8 target municipalities
Activity 4.2.3: Raise awareness through different communication channels to encourage behaviour change and strengthen ownership of community members
Sub-activity 4.2.3.1: Storyboarding, production, and pre-testing of campaigns | Y3 Q2: 1 campaigns produced in final media-ready formats; Y3 Q3: All campaign materials translated and adapted into local languages for rollout 1 comprehensive mapping and analysis of existing gender and positive masculinity campaigns
Sub-activity 4.2.3.2: Rollout, monitoring, and adaptive feedback | Y5 Q3: 1 integrated campaign in the targeted areas completed
Project Monitoring* | Y1 Q2: Inception Report; Y2 Q1: APR; Y3 Q1: APR; Y3 Q3: MTR; Y4 Q1: APR; Y5 Q1: APR; Y6 Q1: Project Completion Report; Y6 Q3: Final Evaluation Report
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.