## Sheet1
Annex 5 Implementation Timetable
Project/Programme Title: Forest Landscape Restoration for Climate Benefits and Resilience (Fiji FLR)
OUTCOMES / OUTPUTS | Inception Phase (6 mo) | Y1 |  |  |  | Y2 |  |  |  | Y3 |  |  |  | Y4 |  |  |  | Y5 |  |  |  | Y6 |  |  |  | Y7 |  |  |  | Y8
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Outcome 1: Strengthened regulatory framework for integrated landscape management aimed at climate change adaptation and mitigation​ | bar: Y8 Q1 to Y8 Q2
Output 1.1: Strengthened institutional coordination and multi-sectoral collaboration on applying R2R approaches | bar: Y1 Q1 to Y2 Q4
Activity 1.1.1: Institutionalize inter-sectoral and inclusive collaborative mechanisms | bar: Y1 Q1 to Y7 Q4
1.1.1.1: Design planning of the MSP on R2R |  | Y3 Q2: Updated coordination mechanism for sustainable landscape planning created and formalized.
1.1.1.2: Establish multi-stakeholder mechanisms based on local policy frameworks |  | Y3 Q2: Multi-stakeholder platform started up.
1.1.1.3: Develop a tool aggregating and displaying up-to-date information on climate risks, finance, and projects |  | Y3 Q1: dashboard tool on climate project activities and M&E targeting developed
Activity 1.1.2: Establish Natural Resources Management (NRM)-related Public-Private-Community Partnerships mechanisms | bar: Y1 Q1 to Y3 Q4
1.1.2.1: Develop intervention guidelines based on the existing legal framework (PPP Act, 2006) |  | Y2 Q3: 1 Guideline for NRM related Public-Private-Community partnerships established.
1.1.2.2: Ensure the legal framework for engagement of stakeholders and trustfulness of agreements |  | Y3 Q2: 1 NRM/Public-Private-Community partnerships template agreement fulfilling all legal requirements established.
1.1.2.3: Develop guidelines for the monitoring of the execution of Public-Private-Community Partnerships |  | Y3 Q4: 1 Guideline for NRM related Public-Private-Community partnerships monitoring established.
Activity 1.1.3: Establish community-supported ecological monitoring across the target districts | bar: Y1 Q1 to Y7 Q4
1.1.3.1: Develop a community-supported ecological monitoring framework |  | Y2 Q2: 1 Guideline for community-based monitoring established.
1.1.3.2: Develop training and engagement guideline |  | Y2 Q4: 195 people from the districts engaged in the monitoring of project activities
1.1.3.3: Carry out training on the implementation of community-supported ecological monitoring across the target districts |  | Y3 Q4: 800 community members trained
1.1.3.4 Implement community-supported ecological monitoring across funded investments in project areas |  | Y6 Q4: 73,737 ha of forests under ecological monitoring of institutional stakeholders, supported by community monitoring
Output 1.2: Key forest policies and land management regulations are updated, reviewed, and/or developed | bar: Y1 Q1 to Y5 Q4
Activity 1.2.1: Update of key natural resources management policies for climate resilience and mitigation | bar: Y1 Q3 to Y5 Q4
1.2.1.1: Develop forest harvesting regulations |  | Y5 Q4: 1 updated final draft protected/conservation areas policy framework
1.2.1.2: Support the update of the land and resource use policy to institutionalize the plan building approach, methodology and governance with TLTB and customary practices |  | Y5 Q4: 1 updated land and resource planning policy updated including the strategic environmental assessment of land planning policy
1.2.1.3: Update the draft policy framework for Protected Areas |  | Y5 Q4: 1 reviewed and updated Forest Reserves Management Plan
1.2.1.4: Carry out stakeholder consultations to validate documentation |  | Y4 Q4: 1 Guideline on policy and governance monitoring and enforcement. Feedback on all draft policies has been obtained from stakeholder consultations
Activity 1.2.2: Develop and introduce the standards and code of practices necessary to ensure climate change mainstreaming via sustainable forest management and forest landscape restoration | bar: Y1 Q1 to Y6 Q4
1.2.2.1: Update the Forest Harvesting Code of Practice (2013) on plantation and woodlots |  | Y4 Q3: 1 Updated Forest Code of Practice is updated; Y4 Q4: 1 Tool for SFM compliant with Forest Harvesting Code of Practice and Forest Certification Standard.
1.2.2.2: Develop strategies and guidelines for forestry related investments (i.e. afforestation, reforestation, natural regeneration, restoration, and plantation) |  | Y4 Q2: 3 guidelines and related standards related to afforestation, reforestation, and plantation practices.
1.2.2.3: Finalize strategy, action plan and guidelines for short Rotation Plantation (SRP) for energy purposes |  | Y2 Q1: 1 action plan including geospatial mapping for soils with high potential for SRP.; Y3 Q2: 1 National strategy for SRP for energy purposes
1.2.2.4: Update of the MoAW Farm Management Plan with climate resilient and mitigative practices and technologies |  | Y3 Q1: 1 soil fertility map, including methodology to maintain fertility over time; Y4 Q4: 1 Updated MoAW Farm Management Plan
1.2.2.5: Carry out stakeholder consultations to validate produced guidelines and strategies |  | Y4 Q4: All produced standards and code of practices have been validated by key stakeholders
Activity 1.2.3 : Prepare Fiji and communities for accessing carbon trading schemes to increase Fiji’s climate financing options |  | Y4 Q2: 2 standards for blue and green carbon finance trading schemes, compliant with international market requirements.
1.2.3.1: Locate and hire expertise for development of standards. |  | Y2 Q1: Expertise for the development of standards is hired; Y4 Q4: Draft pipeline of future investment opportunities to be supported by carbon schemes
1.2.3.2: Support the development of carbon finance standards and governance mechanisms (green and blue carbon). |  | Y4 Q4: 2 standards for blue and green carbon finance trading schemes, compliant with international market requirements.
Activity: 1.2.4: Assess with stakeholders available options to adopt forest ecosystem services incentives and levy | bar: Y1 Q1 to Y4 Q4
1.2.4.1: Identify Forest ecosystem services and monetize their value and contribution to the national economy. |  | Y2 Q4: Identifaction of Forest ecosystem services and monetization of their their value and contribution to the national economy carried out
1.2.4.2: Engage with stakeholders. |  | Y3 Q3: Feedback from stakeholders on mechanisms has been obtained
1.2.4.3: Design the levy mechanisms and governance (e.g. standard(s) and guidelines for calculation, collection, redistribution, and monitoring). |  | Y3 Q4: 1 draft levy mechanism is produced 1 draft levy governance guideline is produced
1.2.4.4: Finalize the Levy and incorporate it in the current policy dialogue |  | Y4 Q4: 1 levy mechanism is produced and available 1 levy governance guideline is produced and available
Activity 1.2.5: Disseminate policies across institutions and communities | bar: Y1 Q1 to Y5 Q4
1.2.5.1: Identify service providers and bid contracts to develop a Communication Plan. |  | Y2 Q3: 1 communication and dissemination strategy
1.2.5.2: Prepare awareness materials and organize awareness and outreach for behavioral change. |  | Y3 Q2: 1 awareness-raising campaign per division and related dissemination materials.; Y4 Q1: 150 representatives from 15 provinces and 50 representatives of contractors/ and CSOs engaged in implementing the new policy framework, standards, strategies, and others developed by the project.
Output 1.3: Climate responsive land use plans at landscape scale developed | bar: Y1 Q1 to Y7 Q4
Activity 1.3.1: Design climate risk informed and integrated participatory community landscape management and investment plans (CLMP) | bar: Y1 Q1 to Y7 Q4
1.3.1.1: Coordinate and merge existing plans (e.g. national TLTB plan) and prepare overall CLMP guidelines and outlines |  | Y3 Q4: • 30 landscape investments and management plans included in the TLTB national master plan with communities.
1.3.1.2: Identify key persons to be involved among institutions and communities |  | Y1 Q4: Key persons to be involved identified
1.3.1.3: Identify through a national bid CSOs that will support local stakeholders developing the CLMPs |  | Y3 Q4: • 100 representatives from 20 target districts trained in the design, implementation, and execution of CLMPs.
1.3.1.4: Collect and secure environmental, social, economic, and administrative data and documents |  | Y4 Q2: Environmental, social, economica and administrative data and documents collected and secured
1.3.1.5: Identify community priorities and establish strategies for landscape management |  | Y4 Q2: Community priorities and strategies for landscape management identified
1.3.1.6: Carry out land planning and strategic environmental assessment of actions identified by communities |  | Y4 Q4: Land planning and strategic enviornmental assessment of actions identified
1.3.1.7: Ensure participatory review of the plans |  | Y4 Q4: • 1 set of guidelines for community development projects rather than cash payments as incentives.
1.3.1.8: Address capacity gaps for CLMP Implementation. |  | Y4 Q4: • 1 set of financial literacy guidelines for communities
1.3.1.9: Facilitate public-private and community agreements for the CLMPs |  | Y3 Q4: • 10 agreements between MoFF, private sector stakeholders, and communities established.
Activity 1.3.2 – Facilitate Sustainable Forest Management for permanent forest estates via public-private partnerships | bar: Y2 Q1 to Y4 Q4
1.3.2.1: Develop and disseminate information and materials to raise awareness |  | Y4 Q4: • 10,000 ha of permanent forest estates established.
1.3.2.2: Train stakeholders in sustainable forest management practices and approaches |  | Y3 Q4: • 10 companies trained on sustainable forestry and climate smart product development.
1.3.2.3: Identify forest estates that have potential for SFM |  | Y3 Q4: Forest estates with potential for SFM identified
1.3.2.4: Create the linkages and liaise between landowners, private sector, and the state |  | Y3 Q4: Linked between landowners, priavte sector and state established
1.3.2.5: Support contracts and other legal tools to ensure the management of forests according to the forest code and sustainability standards (i.e. FSC certification) |  | Y2 Q4: contracts and other legal tools to ensure the management of forests according to the forest code and sustainability standards (i.e. FSC certification) supported
Activity 1.3.3 Transfer knowledge produced by the project to national stakeholders in charge of formal and informal education of youth and professionals | bar: Y2 Q1 to Y3 Q4; Y5 Q1 to Y7 Q4
1.3.3.1: Enhance the learning offer of universities and technical colleges |  | Y6 Q4: • Integration of updated knowledge on introduced practices and technologies in the teachings of 4 national education entities (3 universities and 1 technical college)
1.3.3.2: Train teachers and professors in introduced practices and technologies |  | Y7 Q4: • 20 teachers/professors trained in CAS
1.3.3.3: Assess capacity needs of service providers (e.g. consultancy firms, accountants, others) |  | Y5 Q4: Capacity Needs of service providers assessed
1.3.3.4: Provide tailored training for service providers |  | Y6 Q4: •Tailored training for 5 service providers on the elaboration/implementation of climate risk-informed land use plans.
Outcome 2: Climate resilience of local communities through climate-adaptive forest management increased while contributing to mitigation and food security
Output 2.1: Technical and knowledge capacity to produce climate-adaptive seedlings established | bar: Y1 Q1 to Y2 Q4
Activity 2.1.1: Upgrade knowledge on FLR and climate-adaptive nurseries development | bar: Y1 Q1 to Y3 Q4; Y6 Q4
2.1.1.1: Develop protocols and standards to produce climate adaptive seedlings |  | Y2 Q4: 1 guideline on nursery establishment and management • 1 protocol on seed collection, production and management
2.1.1.2: Develop protocols and standards for the implementation and monitoring of FLR interventions |  | Y2 Q4: • 1 handbook and guidelines on FLR implementation and monitoring
2.1.1.3: Train forestry professionals and field operators from institutions, academia, and CSO |  | Y3 Q4: 110 staff from 50 public/community nurseries and 10 staff from 5 private forest nurseries trained.
Activity 2.1.2: Expand and upgrade existing nurseries | bar: Y1 Q1 to Y7 Q4
2.1.2.1: Purchase and install infrastructure, materials, and equipment for upgrades and seeds/seedlings handling operations |  | Y3 Q2: 9 public and 5 private nurseries supported and upscaled 473 temporary community nurseries established/expanded
2.1.2.2: Train operators on climate adaptive silviculture procedures |  | Y3 Q4: • 128 staff from public and private nurseries trained on sustainable and adaptive seedlings collection, handling, planting, and maintenance production • 718 people from communities trained on high quality climate adaptive seedlings production
2.1.2.3: Support community groups in business management to run the nurseries during the project | bar: Y1 Q1 to Y3 Q4
2.1.2.4: Initiate the production of seedlings |  | Y2 Q4: Production start up conculded
2.1.2.5: Monitoring and quality insurance of seedlings production |  | Y7 Q4: • 8 million climate adaptive seedlings produced
Output 2.2: Community- and farmer enterprise-led FLR for afforestation and conservation of High Conservation Value Forests established | bar: Y1 Q1 to Y2 Q4
Activity 2.2.1: Implement community-led forestry investments identified in the CLMPs | bar: Y1 Q1 to Y7 Q4
2.2.1.1: Confirm investment sites and investment models |  | Y2 Q4: Investment sites and investment models confirmed
2.2.1.2: Train stakeholders on introduced practices and technologies |  | Y6 Q4: 100 stakeholders trained in introduced practices and technologies
2.2.1.3: Carry out land preparation |  | Y6 Q4: Land preparation for planting of species concluded
2.2.1.4: Source and transport of seedlings |  | Y7 Q4: Transport of seedlings to project sites concluded
2.2.1.5: Carry out planting activities |  | Y6 Q4: Community planting of 5,750 ha mixed species Community restoration of upland waterways and Riparian zones totaling 5,000 ha
2.2.1.6: Maintain sites |  | Y7 Q4: Maintenance of sites within project activities concluded Natural regeneration of 5,000 ha degraded forests
Activity 2.2.2: Establish community-supported High Conservation Value Forests | bar: Y1 Q1 to Y3 Q1
2.2.2.1: Confirm sites and conservation models |  | Y2 Q4: Sites and conservation models confirmed
2.2.2.2: Establish PPP agreements for conservation |  | Y2 Q4: PPP agreements for conservation established
2.2.2.3: Prepare documentation for formal recognition of sites as protected areas |  | Y3 Q1: 12,000 ha of HCVF established
Outcome 3: Strengthened financial mechanisms and private sector involvement in climate change related investments for sustainability, food security and scale-up
Output 3.1: Forest ecosystem services certification is accessible to stakeholders | bar: Y1 Q1 to Y2 Q4
Activity 3.1.1. – Support private sector companies in adopting the Forest Stewardship Council (FSC) certification and integrating the FSC Ecosystem Services Procedure (ES PRO) | bar: Y1 Q1 to Y7 Q4
3.1.1.1: Carry out training of stakeholders for the implementation of FSC and FSC ES PRO |  | Y6 Q4: 50 private sector companies staff trained on FSC/FSC ES PRO methodologies and approaches
3.1.1.2: Support private sector companies in carrying out FSC ES PRO and ecosystem impact claims |  | Y6 Q4: Private sector companies supported in carrying out FSC ES PRO and ecsystem impact claims
3.1.1.3: Assess impacts of FSC ES PRO application in project areas |  | Y6 Q4: 1 external survey to inform about the impact of FSC ESPRO applications
Activity 3.1.2. – Support communities’ adoption of the Forest Stewardship Council certification and the integration of the FSC Ecosystem Services Procedure | bar: Y2 Q1 to Y2 Q4
3.1.2.1: Carry out training of communities for the implementation of FSC and FSC ES PRO |  | Y2 Q3: Guidelines for the community implementation of FSC/FSC ES PRO (or similar) and ecosystem claims developed; Y2 Q4: 100 representatives of communities trained on FSC/FSC ES PRO procedures or similar
3.1.2.2: Support communities in carrying out FSC ES PRO and ecosystem impact claims |  | Y6 Q4: Communities supported in carrying out FSC ES PRO and ecosystem impact claims
3.1.2.3: Assess impacts of FSC ES PRO application in project areas |  | Y7 Q4: 1 external survey to inform about the impact of FSC ESPRO applications finalized
Output 3.2: Design of improved financial mechanisms supported and made accessible to communities and the private sector | bar: Y1 Q1 to Y2 Q4
Activity 3.2.1 – Strengthen/de-constrain existing forestry financial mechanisms of the FDB and other national financing institutions (NFIs) to support sustainable natural resources management (SNRM) | bar: Y1 Q1 to Y7 Q4
3.2.1.1: Revise available financial instruments to integrate opportunities for FLR investments |  | Y2 Q4: •Revision of 30 existing financial instruments of the FDB and other financing institutions to verify potential for enhancement of FLR investments
3.2.1.2: Organize review sessions with stakeholders to assess FDB’s financial mechanisms and their possible impact on FLR and SFM approaches uptake | bar: Y1 Q1 to Y6 Q4
3.2.1.3: Identify derisking opportunities with stakeholders |  | Y2 Q1: •1 derisking mechanisms and related guidelines produced and validated by stakeholders; Y5 Q1: event
3.2.1.4: carry out tailored training for financing institutions on FLR investments |  | Y7 Q4: •20 representatives of financing institutions trained on FLR investments
Activity 3.2.2 – Facilitate the enhancement and upgrade of forestry financial products to ensure effectiveness and efficiency of resilience investments | bar: Y1 Q1 to Y4 Q4
3.2.2.1: Assess and evaluate the existing forestry and agroforestry portfolio and market demand | bar: Y2 Q1 to Y3 Q4
3.2.2.2: Technical assistance provided to enhance and upgrade sustainable forestry financial products |  | Y4 Q4: • 1 policy statement from the FDB to guide its activities in sustainable forestry investments • 1 strategy of the FDB to increase the uptake of sustainable forestry financial products in Fiji • 1 procedure (incl. formats/templates) to request, assess and evaluate sustainable forestry investments including MRV system for the FDB • 1 upgraded sustainable forestry financial mechanism available to FDB
3.2.2.3: Support staff of financing institutions in the development of sustainable and bankable forestry projects |  | Y4 Q4: staff of financing institutions in the development of sustainable and bankable forestry projects supported
Activity 3.2.3 – Support the capacity of public and private financial institutions (FIs) to identify climate risk investments and to ensure Paris Alignment | bar: Y1 Q1 to Y3 Q4
3.2.3.1: Develop training programs and guidelines for FDB and FIs in Fiji |  | Y2 Q4: training programs and guidelines for FDP and Fis finalized
3.2.3.2: Carry out tailored training to Fis |  | Y3 Q4: • 10 staff of Fijian FIs trained on climate related risks assessment and the Paris Alignment
3.2.3.3: Provide technical assistance to FDB and other FIs in Fiji to contribute to reaching the Paris Agreement targets of its portfolio |  | Y2 Q4: • 1 guidance note/toolkit for Paris Agreement alignment • 1 carbon accounting and monitoring toolkit mainstreamed among banks to assess GHG emission of portfolios and pipeline investments
Output 3.3: Support the restoration and SFM of commercially logged over natural forests and plantations | bar: Y1 Q1 to Y2 Q4
Activity 3.3.1. Facilitate the restoration and SFM of degraded and logged over natural forests on community land following climate adaptive silviculture approaches | bar: Y1 Q1 to Y7 Q1
3.3.1.1 Confirm investment sites and investment models |  | Y2 Q4: Investment Sites and Models confirmed
3.3.1.2: Technical assistance for land preparation, sourcing and planting of seedlings and maintenance of FLR interventions |  | Y6 Q4: • 6,000 ha of logged over forest naturally regenerated and under SFM • 500 ha of forest reforested
3.3.1.3: Train stakeholders on introduced practices and technologies |  | Y7 Q1: • 30 private stakeholders trained in climate smart technologies and A/R codes of practice/regulations
3.3.1.4: Disseminate the mechanisms and governance procedures across stakeholders and train public and private experts |  | Y4 Q4: • 950 experts from the private sector, communities, CSOs, public companies, and institutional stakeholders trained
Activity 3.3.2: Facilitate the introduction of FLR and SFM on degraded lands and commercial plantation areas following climate-adaptive silviculture approaches | bar: Y1 Q1 to Y7 Q4
3.3.2.1: Facilitate Public-Private-Community Partnership to accelerate reforestation |  | Y2 Q4: PPCP to accelerate reforestation facilitated
3.3.2.2: Confirm investment sites and investment models |  | Y2 Q4: Investment sites and models confirmed
3.3.2.3: Train stakeholders on introduced practices and technologies |  | Y7 Q1: Training of stakeholders in synergy with other project activities concluded
3.3.2.4: Carry out land preparation |  | Y6 Q4: Land preparation concluded
3.3.2.5: Source and transport of seedlings |  | Y7 Q4: Sourcing and transporting of seedlings concluded
3.3.2.6: Carry out planting activities |  | Y7 Q4: • 800 hectares of community and privately owned SRPs established via the provision of TA and seedlings • 4,312 ha from left aside degraded forests and areas supported with restoration via the provision of TA and seedlings
3.3.2.7: Maintain FLR sites |  | Y7 Q4: Maintenance of FLR sites within project activities concluded and handing over of land term maintenance plan
3.3.2.8 Facilitate SFM of plantation sites |  | Y7 Q4: • 24,375 ha of plantations from public corporations under SFM
Activity 3.3.3: In partnership with the Ministry of Agriculture and Waterways, support FLR via agroforestry investments | bar: Y1 Q1 to Y7 Q4
3.3.3.1: Confirm investment sites and investment models |  | Y3 Q4: Investment sites and models confirmed
3.3.3.2: Train stakeholders on introduced practices and technologies |  | Y7 Q4: • 100 professionals from the MOAW and the MOFF trained to replicate models • 50 professionals from CSOs trained to replicate the agroforestry models • 1,750 farmers trained in agroforestry models and supported in introducing knowledge
3.3.3.3: Carry out land preparation |  | Y6 Q4: Land preparation concluded
3.3.3.4: Source and transport of seedlings, inputs, and materials |  | Y7 Q4: Transport of seedlings concluded
3.3.3.5: Carry out planting activities |  | Y7 Q4: •7,000 ha of agroforestry established
3.3.3.6: Implement monitoring across the target districts |  | Y7 Q4: Monitoring within project activities concluded and handing over of long term maintenance plan
Project Monitoring* | Inception Report (within 6 months of EOD) | Y1 Q1: Inception report start up baseline data collection; Y1 Q4: finalization baseline data collection; Y2 Q1: APR; Y3 Q1: APR; Y4 Q1: APR; Y4 Q3: Start Up Interim Evaluation; Y4 Q4: Submission Interim Evaluation Report; Y5 Q1: APR; Y6 Q1: APR; Y7 Q1: APR; Y7 Q4: Start up Final Evaluation; Y8 Q2: Submission Final Evaluation Report Completion Report
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.