## Sheet1
Annex 5: Implementation Timetable
Improving climate resilience of vulnerable communities in Tajikistan and enabling conditions for local action
COMPONENTS/OUTPUTS | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
COMPONENT 1: ENABLING ENVIRONMENT FOR CLIMATE CHANGE ADAPTATION AT THE DISTRICT AND LOCAL LEVELS
Output 1.1. District Adaptation Plans (DAPs) that also promote DRR and anticipatory action
Activity 1.1.1 Develop district-level climate risk profiles to support local adaptation and risk management planning (including DRR and anticipatory action). | bar: 2027 Q3 to 2028 Q4
Activity 1.1.2 Strengthen the capacity of local government agencies and community leaders to plan and implement climate change adaptation and risk management (DRR and anticipatory action) measures. | bar: 2027 Q3 to 2031 Q3
Activity 1.1.3 Co-develop DAPs with relevant stakeholders (including DACs), incorporating risk management (DRR and anticipatory action). | bar: 2027 Q3 to 2029 Q2
Activity 1.1.4 Establish or strengthen District Adaptation Committees (DACs) (comprising CEP district authorities, jamoat representatives, women’s groups, Water User Associations (WUAs), and community-based organisations) to validate DAP priorities and rank investment options. | bar: 2027 Q3 to 2029 Q4
Output 1.2. Tailored climate information sustainably delivered to district governments and local communities to facilitate local-level adaptation, including DRR and anticipatory action
Activity 1.2.1 Strengthen the forecasting capacity of the Agency for Hydrometeorology’s Centre of Climate Change through training and the provision of equipment. | bar: 2027 Q3 to 2031 Q3
Activity 1.2.2 Build the capacity of the Agency for Hydrometeorology to expand SMS-based and AI-powered digital internet-based systems — such as mobile apps, Telegram channels, or other locally appropriate digital tools — for the provision of climate and market information. | bar: 2027 Q3 to 2031 Q3
Activity 1.2.3 Support the Agency for Hydrometeorology to commercialise the provision of climate information to ensure sustainability (including the development of a commercialisation strategy). | bar: 2029 Q1 to 2029 Q4
Activity 1.2.4 Train 42 extension workers (3 per district) and ~1,400 smallholder farmers (~100 per district) (at least 30% women and 30% youth) to understand and apply climate information. | bar: 2028 Q1 to 2031 Q3
COMPONENT 2: LOCAL-LEVEL RESILIENCE BUILDING THROUGH WATER ASSET MANAGEMENT AND LIVELIHOOD DIVERSIFICATION
Output 2.1. Climate-proofed water assets
Activity 2.1.1 Establish 14 climate-resilient water asset demonstration plots (one in each district) to showcase innovative water use, management technologies and nature-based methods for agricultural and domestic use. | bar: 2028 Q1 to 2031 Q3
Activity 2.1.2 Develop and strengthen climate-resilient water saving and green technologies combined with NbS solutions for slope stabilization, pasture recovery to reduce risk of nature hazards and increasing farm production. | bar: 2028 Q3 to 2031 Q3
Activity 2.1.3 Climate proof canals to strengthen their durability to damage from flooding, landslides and mudslides, and to improve their contribution to flood attenuation. | bar: 2028 Q3 to 2031 Q3
Output 2.2. Climate-resilient smallholder production systems
Activity 2.2.1 Establish 14 climate-resilient agricultural production demonstration plots (one in each district) to showcase innovative practices and technologies. | bar: 2028 Q1 to 2031 Q3
Activity 2.2.2 Construct or rehabilitate 200 greenhouses. | bar: 2028 Q1 to 2031 Q3
Activity 2.2.3 Establish 500 ha of mixed orchards using drought/flood-resistant species, including the installation of green fencing using appropriate species to prevent livestock damage to orchards. Seedlings will be provided by local or Forestry Department nurseries. | bar: 2028 Q3 to 2031 Q3
Activity 2.2.4 Train farmers, inclusive of women and young farmers, in climate-resilient practices and technologies using participatory and digital methods. | bar: 2028 Q3 to 2030 Q4
Output 2.3. Capacity of smallholder farmers built for livelihood diversification
Activity 2.3.1 Construct or rehabilitate 140 storage units to support community storage of agricultural produce. In high-lying areas, the units will be naturally cooled, while in low-lying areas (warmer) solar-powered cooling will be used. | bar: 2028 Q3 to 2031 Q3
Activity 2.3.2 Provide training and equipment to 800 women and disabled persons to support processing, preservation, and marketing of agricultural products. This will include the distribution of 800 solar dryers, processing equipment along with training on their safe and efficient use. This will also be supported by the online learning research hub established under Activity 2.2.4. | bar: 2027 Q3 to 2031 Q3
Activity 2.3.3 Provide training to smallholder farmers to improve bulking/aggregation practices, market negotiation and value chain participation. | bar: 2028 Q3 to 2031 Q3
Activity 2.3.4 Establish bulking centres to allow producer groups to aggregate produce and attract wholesale buyers. | bar: 2028 Q3 to 2031 Q3
Activity 2.3.5 Implement market information services, including price alerts and access to local demand data targeted at farmers and producer groups to support informed market participation. | bar: 2028 Q3 to 2031 Q3
COMPONENT 3: KNOWLEDGE MANAGEMENT AND AWARENESS RAISING ON CLIMATE CHANGE ADAPTATION
Output 3.1. Improved awareness of climate change impacts on food security and nutrition, and adaptation and risk management (including DRR and anticipatory action) responses
Activity 3.1.1 Conduct gender-responsive awareness-raising campaigns on climate risks and impacts on local communities using a mix of traditional media and digital platforms. | bar: 2027 Q3 to 2031 Q3
Output 3.2. Knowledge generated to support project sustainability and the evidence-based scaling up and replication of climate change adaptation
Activity 3.2.1 Document information on key lessons and achievements related to the project’s adaptation interventions. | bar: 2027 Q3 to 2031 Q3
Activity 3.2.2 Enhance policy learning by disseminating bi-annual policy-style learning briefs and running 14 policy learning workshops. | bar: 2028 Q1 to 2031 Q3
Activity 3.2.3 Coordinate sharing of knowledge products on a preexisting knowledge management platform and develop an adaptation manual for practitioners and policymakers based on the outputs of Activities 3.2.1 and 3.2.2. | bar: 2028 Q1 to 2031 Q3
Project Monitoring* | 2027 Q2: Inception Report; 2028 Q1: APR; 2029 Q1: APR; 2029 Q3: Interim Evaluation; 2030 Q1: APR; 2031 Q1: Completion Report; 2031 Q4: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.